## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Enabling Works - Footpath, Kerb and channel | itp |  |  |  |  | ITP - Route 377 Bus Stop Extension - Enabling Works - Footpath, Kerb and channel
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers.
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Onsite records/photos
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Kassel Kerb & Channel
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0030 &KC0031
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Kassel kerb and channel including 1m transitions at both ends as per standard.
label | ○ Half channel at 3% cross fall.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2.1 - Bedding
label | VERIFICATION ACTIVITY: QA Form
label | METHODS OR REFERENCE: TDM Technical Standard - KC0002
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: GAP65 subbase in roads (CBR>5)
label | ○ Concrete subbase must be 20MPa
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
label | ONSITE RESPONSIBILITY:
checkpoint | 3 - Channel Level
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - KC0001
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | CIVIL WORKS
checkpoint | 4 - Concrete Footpaths / Pram Crossing
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - FP0001
label | FREQUENCY: 10m Intervals
label | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
label | ○ Clegg CIV > 12
label | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
label | ○ Pram crossing
label | ○ MAX gradient to be 1:12
label | ○ 4kg/m3 blackoxide with broom finish
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Tactile Pavers (1)
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: TDM Technical Standards - FP0006 (Pram Crossing)
label | ○ TDM Technical Standards - FP0010 (Footpath)
label | ○ TDM Technical Standards - IS0002 (Traffic Island Pavers)
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 150mm concrete slab underneath
label | ○ Must comply to TDM standard
label | ○ FP0006 &FP0010
label | ○ Traffic Island pavers must comply to TDM standard - IS0002
label | HOLD POINT: Inprocess Inspection, Measurement
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 5 - Tactile Pavers (2)
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians
label | ○ AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 6 - Grass Berms
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | 6
checkpoint | 7 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Nithin Thomas
label | Approving Delegate: Daniel Tat
checklist | ITP - Traffic Islands | itp |  |  |  |  | ITP - Route 377 Bus Stop Extension - Traffic Islands
section | Materials
checkpoint | 1 - Mountable Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Mountable Kerb to be laid using precast hand-laid and painted with two coats of reflective paint
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet, photos.
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 2 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Setout Kerb Alignment required to construct to design
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: As per Construction Drawings
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (1)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerbs to be haunced with 20MPa Concrete and Sand Cement Mortar
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3 - Concrete Island (2)
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0003
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Basecourse to be 150mm min thickness of GAP65
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infil
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa broom finish unreinforced Concrete with 3 kg/m3 Red oxide
label | ○ Cross Fall of 2% or max rise in centre of 180mm
label | HOLD POINT: Inprocess Inspection
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Nithin Thomas
label | Approving Delegate: Daniel Tat
checklist | ITP - Signage | itp |  |  |  |  | ITP - Route 377 Bus Stop Extension - Signage
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Pole, Impact recovery post and Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Check for underground service before installtion. All poles and post to be looking in excellent conditon with end caps - 3m long. Ground socket to be 60mm dia, 600mm deep with grouted screw or pins. For Black and white pole 76mm dia and 600mm deep
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 3 - Ground Socket
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Socket
label | ACCEPTANCE CRITERIA: The dug out hole to be 300mm wide and 600mm deep. 20Mpa concrete with 50mm cover at bottom to be used for installing socket. The sockets to have 50mm reveal at top and smooth finish of concrete around the socket.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets/Photos with tape measurement
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 4 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | APPROVALS
checkpoint | ITP Approval
label | Prepared By: Nithin Thomas
label | Approving Delegate: Daniel Tat