## Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Resource to use
GIB QA
Tier 2: Wall; Tier 3: level 34; Tier 4: North Grid D-E | template builder
Tier 4: East Grid 2 to 4 | template builder
Tier 4: West Grid 2 to 3 | template builder
Tier 3: level 33; Tier 4: North grid A to D | template builder
Tier 4: North IT wall grid C | template builder
Tier 4: North grid D | template builder
Tier 4: North grid 2 and IT wall | template builder
Tier 4: East grid E to Corner WE33.1 | template builder
Tier 4: East WE33.1 to 33.3 | template builder
Tier 4: South Grid 4 | template builder
Tier 3: level 32; Tier 4: North grid 1 | template builder
Tier 4: West grid B | template builder
Tier 3: level 31; Tier 4: IT wall grid E | template builder
Tier 3: level 30; Tier 4: Grid E | template builder
Tier 2: Soffit; Tier 3: Level 33; Tier 4: South Grid 4 | template builder
Tier 4: North grid F | template builder
Tier 3: Level 32; Tier 4: North grid 3 to D | template builder
Tier 4: South Grid 3 to D | template builder
Tier 3: Level 31; Tier 4: South grid 4 | template builder
Tier 3: Level 30; Tier 4: North grid F | template builder

## Checklist Template Builder
Component | Name | Values
checklist | Precinct Gib/wrap Checklist
checkpoint | Structure handed over by Aspec, Council has inspected and approved
checkpoint | Check framing layout provides adequate fixing points to be able to meet the minium centres (400mm)
checkpoint | Where gib is on vertical wall and meets a concrete header, it stops 10mm short to allow for sealing (1/FC6-002)
checkpoint | Where gib is on vertical wall it stops flush to floor as per drawing 2/FC6-002 and 2/FC6-012
checkpoint | Where gib is on horizontal soffit it stops at the walls as per drawing 2/FC6-025 and 6-012
checkpoint | Fixings installed along entire gib panel periphery, and every 400mm vertical stud
checkpoint | Fixings are located minimum 12mm vertically from bound and min. 18mm from unbound or cut, edges. Screws commence 75mm from sheet corners
checkpoint | Fixings at 100mm centers)
checkpoint | Fixing screws used are 6gx41mm Gib screws ceramic coated and 8gx63mm where double Gib is used
checkpoint | Vertical and horizontal joins shall have gaps no more than 3mm
checkpoint | Gib fixings are flush with the Weatherline. If not flush install a new screw 25mm away.
signoff | APPROVAL MC / Council
checkpoint | Gib Weatherline substrate approved by Aspec and council
checkpoint | Check Weatherline is dry and free of contaminants before applying the Adhero
checkpoint | 75mm Allco tape is applied over the top of hydrotech along the floor, butting up to gib
checkpoint | Adhero wrap is applied as per installation instructions, smooth and without significant bubbling, 150mm overlaps.
checkpoint | Adhero is applied flush to gib periphery at jambs and header, but allows for extoseal below it at the floor
checkpoint | Where gib protrudes from floor as per 2/FC6-002, PEF rod has been applied to base (not required if gib is flush as per 2/FC6-0012)
checkpoint | 150mm Extoseal is applied at floor with 75mm overlap to allco and gib. Adhero applied over the top
checkpoint | 150mm Extoseal is applied at edge of gib to walls, with 75mm overlap to adhero and wall
checkpoint | 150mm Extoseal is applied at edge of gib to soffits, with 75mm overlap to adhero and wall
checkpoint | Extoseal is applied to each window opening header corner, with >150mm overlap inside and >75mm outside
checkpoint | Extoseal has been applied to entire window sill, lining the steel angles, up jambs >150mm, and down 75mm outside sill
checkpoint | All air bubbles and creases flattened in Adhero with rubber scraper. Adhero placed over the top of extoseal at floor and sill tray areas
checkpoint | Adhero placed over the top of saddles

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty