## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
381ec953-0d47-472b-abe3-6dcb6ad83b40 | checklist | Precinct Gib/Wrap Checklist |  | Precinct Gib/Wrap Checklist
b797ed90-7596-41a1-b5d8-0ffebc08daa4 | section | Checklist
1fd71fb0-49f8-4887-b932-cbee1b0215a2 | checkpoint | Structure handed over by Aspec, Council has inspected and approved
a69792f5-e835-4c49-9755-a71230bb49a2 | checkpoint | Check framing layout provides adequate fixing points to be able to meet the minimum centres (400mm)
bcb5c90a-6f61-46a1-8dcb-a21daf594f3f | checkpoint | Where gib is on vertical wall and meets a concrete header, it stops 10mm short to allow for sealing (1/FC6-002)
5547a5e4-b51d-44fd-9f3f-bb960874ff87 | checkpoint | Where gib is on vertical wall it stops flush to floor as per drawing 2/FC6-002 and 2/FC6-012
286e44ab-28c7-48d7-9e1c-f6589dddda1a | checkpoint | Where gib is on horizontal soffit it stops at the walls as per drawing 2/FC6-025 and 6-012
2f4bfd00-68c9-4c34-a294-078c9523ca5a | checkpoint | Fixings installed along entire gib panel periphery, and every 400mm vertical stud
f10e67b2-2196-4464-ab23-f4d984941a59 | checkpoint | Fixings are located minimum 12mm vertically from bound and min. 18mm from unbound or cut, edges. Screws commence 75mm from sheet corners
0cdc83cc-19bb-4110-86bf-8aa808884acf | checkpoint | Fixings at 100mm centers)
b21dcca9-fc0a-477a-99a5-6bf26740db4f | checkpoint | Fixing screws used are 6gx41mm Gib screws ceramic coated and 8gx63mm where double Gib is used
5d31bcac-706f-4d21-ab15-a44d0d40b4c3 | checkpoint | Vertical and horizontal joins shall have gaps no more than 3mm
ca1e591f-779e-4858-92cc-756df2bcc6ba | checkpoint | Gib fixings are flush with the Weatherline. If not flush install a new screw 25mm away.
fb125162-6065-4e2f-ae4b-9d5f6c3541cf | signoff | APPROVAL MC / Council
c376b3b4-b17c-460b-9c44-b16415159408 | checkpoint | Gib Weatherline substrate approved by Aspec and council
fc259adb-194a-41da-aaee-3801641faa63 | checkpoint | Check Weatherline is dry and free of contaminants before applying the Adhero
80d8dd01-537d-4a35-9e74-429f21288d61 | checkpoint | 75mm Allco tape is applied over the top of hydrotech along the floor, butting up to gib
a00ceaa6-18ff-40a0-bdfd-2e77726e5ec6 | checkpoint | Adhero wrap is applied as per installation instructions, smooth and without significant bubbling, 150mm overlaps.
65466e60-d53d-419f-8a5c-828303231228 | checkpoint | Adhero is applied flush to gib periphery at jambs and header, but allows for extoseal below it at the floor
aa83c8d1-4859-4a84-a7f8-63d2461580aa | checkpoint | Where gib protrudes from floor as per 2/FC6-002, PEF rod has been applied to base (not required if gib is flush as per 2/FC6-0012)
ad076be3-7586-4983-8e1c-7dbfdc2cc1e8 | checkpoint | 150mm Extoseal is applied at floor with 75mm overlap to allco and gib. Adhero applied over the top
13b56452-57dc-472c-9be0-4c6c7c67b7a4 | checkpoint | 150mm Extoseal is applied at edge of gib to walls, with 75mm overlap to adhero and wall
e9cc6b65-6b69-4b17-94b3-be807530ce56 | checkpoint | 150mm Extoseal is applied at edge of gib to soffits, with 75mm overlap to adhero and wall
6e360a86-539d-48e2-add0-a805f5e7111c | checkpoint | Extoseal is applied to each window opening header corner, with >150mm overlap inside and >75mm outside
56006d24-c8b8-4547-b647-de5b4d3d9e04 | checkpoint | Extoseal has been applied to entire window sill, lining the steel angles, up jambs >150mm, and down 75mm outside sill
e152f09f-578a-4726-88c2-52aed5cfa31e | checkpoint | All air bubbles and creases flattened in Adhero with rubber scraper. Adhero placed over the top of extoseal at floor and sill tray areas
52ef57cb-bb34-4bb9-b7a1-f7e276fd678d | checkpoint | Adhero placed over the top of saddles