## Sheet1
1.1 | Submit Concrete mix design | 610.07 (a) (b) Design spec drawings | Mix design and associated on going testing results | Strength, quality, colour, shrinkage must be as per the relevant contract specification. Approved mix design code TU604AA62 | Written | Prior to casting | HP | HP | 1.1 - Submit Concrete mix design | Reference(s) - 610.07 (a) (b) Design spec drawings | Supporting Documents - Mix design and associated on going testing results | Acceptance Criteria - Strength, quality, colour, shrinkage must be as per the relevant contract specification. Approved mix design code TU604AA62 | Conformance: Method - Written | Conformance: Frequency - Prior to casting | HCC Sign - HP | TAMS Group Sign - HP | 1.1 - Submit Concrete mix design
1.2 | Submit ACRS certification of reinforcement and certification for the tendons | Current ACRS certificate for all Tendons and reinforcing | Valid certificate provided | Written | Prior to casting | HP | HP |  | 1.2 - Submit ACRS certification of reinforcement and certification for the tendons | Reference(s) - Current ACRS certificate for all Tendons and reinforcing | Supporting Documents - Valid certificate provided | Acceptance Criteria - Written | Conformance: Method - Prior to casting | Conformance: Frequency - HP | HCC Sign - HP | TAMS Group Sign - | Reference(s) - 610.07 (a) (b) Design spec drawings
1.3 | Radiant heat curing with curing compounds | 610.23 (h) (g) | MSDS Complies with AS 3799 | SikaFilm applied during finishing, covers installed after finishing of concrete. Radiant heat curing will occur until the Antisol AC sprayed or rolled over the components within 30 minutes of removing formwork. | Written | Every component | HP | HP | 1.3 - Radiant heat curing with curing compounds | Reference(s) - 610.23 (h) (g) | Supporting Documents - MSDS Complies with AS 3799 | Acceptance Criteria - SikaFilm applied during finishing, covers installed after finishing of concrete. Radiant heat curing will occur until the Antisol AC sprayed or rolled over the components within 30 minutes of removing formwork. | Conformance: Method - Written | Conformance: Frequency - Every component | HCC Sign - HP | TAMS Group Sign - HP | Supporting Documents - Mix design and associated on going testing results
1.4 | Submit curing methodology | 610.23 (a) | Product TDS, SDS CHAR(AMP) NATA Certificate | Curing compound meets or exceeds AS3799. Application rates noted. | Written | Prior to casting | HP | HP | 1.4 - Submit curing methodology | Reference(s) - 610.23 (a) | Supporting Documents - Product TDS, SDS CHAR(AMP) NATA Certificate | Acceptance Criteria - Curing compound meets or exceeds AS3799. Application rates noted. | Conformance: Method - Written | Conformance: Frequency - Prior to casting | HCC Sign - HP | TAMS Group Sign - HP | Acceptance Criteria - Strength, quality, colour, shrinkage must be as per the relevant contract specification. Approved mix design code TU604AA62
1.5 | Submit evaporative retardant (aliphatic alcohol- based) | 610.17 (f) | Product TDS CHAR(AMP) SDS | Application rates noted. | Written | Prior to casting | HP | HP | 1.5 - Submit evaporative retardant (aliphatic alcohol- based) | Reference(s) - 610.17 (f) | Supporting Documents - Product TDS CHAR(AMP) SDS | Acceptance Criteria - Application rates noted. | Conformance: Method - Written | Conformance: Frequency - Prior to casting | HCC Sign - HP | TAMS Group Sign - HP | Conformance: Method - Written
1.6 | Submit ITP for review | 610.18 (a) (i) | This document | Written acceptance to proceed | Written | Prior to casting | HP | HP | 1.6 - Submit ITP for review | Reference(s) - 610.18 (a) (i) | Supporting Documents - This document | Acceptance Criteria - Written acceptance to proceed | Conformance: Method - Written | Conformance: Frequency - Prior to casting | HCC Sign - HP | TAMS Group Sign - HP | Conformance: Frequency - Prior to casting
1.7 | Submit repair procedure for review | 610.24 (b) 689.13 | Repair Procedure/ Methodology | Review and approval by Client | Written | Prior to repairing components | HP | HP | 1.7 - Submit repair procedure for review | Reference(s) - 610.24 (b) 689.13 | Supporting Documents - Repair Procedure/ Methodology | Acceptance Criteria - Review and approval by Client | Conformance: Method - Written | Conformance: Frequency - Prior to repairing components | HCC Sign - HP | TAMS Group Sign - HP | HCC Sign - HP
1.8 | Ensure all shop drawings are IFC before casting the components | HCC QMP | Stamped shop drawing | Shop drawings are to be IFC and numerical revision | Written | Prior to casting | HP | HP | 1.8 - Ensure all shop drawings are IFC before casting the components | Reference(s) - HCC QMP | Supporting Documents - Stamped shop drawing | Acceptance Criteria - Shop drawings are to be IFC and numerical revision | Conformance: Method - Written | Conformance: Frequency - Prior to casting | HCC Sign - HP | TAMS Group Sign - HP | TAMS Group Sign - HP
1.9 | Stressing Calculations have been submitted for review | 622.02 | Stressing Calculations and chart | Stressing calculations are to be reviewed by project consultant | Once before commencement of casting Reviewed if changes occur during the course of the production | HP | HP |  | 1.9 - Stressing Calculations have been submitted for review | Reference(s) - 622.02 | Supporting Documents - Stressing Calculations and chart | Acceptance Criteria - Stressing calculations are to be reviewed by project consultant | Conformance: Method - Once before commencement of casting Reviewed if changes occur during the course of the production | Conformance: Frequency - HP | HCC Sign - HP | TAMS Group Sign - | 1.2 - Submit ACRS certification of reinforcement and certification for the tendons
2.1 | Pre-pour inspection (external) | 610.18 (a) (ii CHAR(AMP) iii) | Nominated authority’s checklist Relevant shop drawings | Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to structural requirements and specifications. Moulds/formwork are clean and free from debris. 7 Day notification given via ACONEX. Any changes to be reported within 24 hours prior to the pour. | Measured / Visual | Each Unit | HP | HP | 2.1 - Pre-pour inspection (external) | Reference(s) - 610.18 (a) (ii CHAR(AMP) iii) | Supporting Documents - Nominated authority’s checklist Relevant shop drawings | Acceptance Criteria - Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to structural requirements and specifications. Moulds/formwork are clean and free from debris. 7 Day notification given via ACONEX. Any changes to be reported within 24 hours prior to the pour. | Conformance: Method - Measured / Visual | Conformance: Frequency - Each Unit | HCC Sign - HP | TAMS Group Sign - HP | Reference(s) - Current ACRS certificate for all Tendons and reinforcing
2.2 | Pre-pour inspection (internal) | 610.18 (a) (ii CHAR(AMP) iii) | HCC QMP Section 3.12 Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to shop drawings. Moulds/formwork are clean and free from debris. | Measured / Visual | Each Unit | HP |  | 2.2 - Pre-pour inspection (internal) | Reference(s) - 610.18 (a) (ii CHAR(AMP) iii) | Supporting Documents - HCC QMP Section 3.12 Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Acceptance Criteria - Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to shop drawings. Moulds/formwork are clean and free from debris. | Conformance: Method - Measured / Visual | Conformance: Frequency - Each Unit | HCC Sign - HP | TAMS Group Sign - | Supporting Documents - Valid certificate provided
2.3 | Check conditions prior to, during and post concrete delivery and placement | 610.17 (a-f) | On-line Weather report and forecast | Ambient temperature not: CHAR(LESS) 5°C or > 35°C Concrete temperature not: CHAR(LESS) 10°C or > 32°C Weather condition: conducive to pour Evaporation Limits for Concreting Operations The Contractor shall be responsible for measuring and recording the air temperature, relative humidity, concrete temperature and wind velocity (measured one metre above the as placed concrete) at the point of concrete placement from commencement of placing the concrete and continue until curing has commenced. This information shall be used in conjunction with Figure 610.171 to determine the rate of evaporation of water from the freshly placed and unprotected surface of the concrete. The rate of evaporation shall be monitored by the Contractor until such time as curing commences. When the value of the rate of evaporation as determined from Figure 610.171 exceeds 0.50 kg/m² per hour the Contractor shall take precautions to minimise evaporative moisture losses such as the application of an aliphatic-alcohol based evaporative retarding compound or controlled fog spray. Application of evaporative retarding compound is required during pouring of concrete. | Measured / Visual | Each Lot | HP |  | 2.3 - Check conditions prior to, during and post concrete delivery and placement | Reference(s) - 610.17 (a-f) | Supporting Documents - On-line Weather report and forecast | Acceptance Criteria - Ambient temperature not: CHAR(LESS) 5°C or > 35°C Concrete temperature not: CHAR(LESS) 10°C or > 32°C Weather condition: conducive to pour Evaporation Limits for Concreting Operations The Contractor shall be responsible for measuring and recording the air temperature, relative humidity, concrete temperature and wind velocity (measured one metre above the as placed concrete) at the point of concrete placement from commencement of placing the concrete and continue until curing has commenced. This information shall be used in conjunction with Figure 610.171 to determine the rate of evaporation of water from the freshly placed and unprotected surface of the concrete. The rate of evaporation shall be monitored by the Contractor until such time as curing commences. When the value of the rate of evaporation as determined from Figure 610.171 exceeds 0.50 kg/m² per hour the Contractor shall take precautions to minimise evaporative moisture losses such as the application of an aliphatic-alcohol based evaporative retarding compound or controlled fog spray. Application of evaporative retarding compound is required during pouring of concrete. | Conformance: Method - Measured / Visual | Conformance: Frequency - Each Lot | HCC Sign - HP | TAMS Group Sign - | Acceptance Criteria - Written
2.4 | Reinforcing placement and inspection | 611 | AS 5100 Component Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Check against relevant shop drawing that all reinforcing bars are installed correctly, at the right centres and in a clean condition. Reinforcing bars spacing to be no less than 1.5 times the size of the largest aggregate. Correct bar laps to be observed. Correct radius in bends. | Visual/ measuring | Each component | HP |  | 2.4 - Reinforcing placement and inspection | Reference(s) - 611 | Supporting Documents - AS 5100 Component Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Acceptance Criteria - Check against relevant shop drawing that all reinforcing bars are installed correctly, at the right centres and in a clean condition. Reinforcing bars spacing to be no less than 1.5 times the size of the largest aggregate. Correct bar laps to be observed. Correct radius in bends. | Conformance: Method - Visual/ measuring | Conformance: Frequency - Each component | HCC Sign - HP | TAMS Group Sign - | Conformance: Method - Prior to casting
2.5 | Cover verification | 610.33 610.26 610.46 611.10 AS 2425 | Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 AS 5100.5 | Requirements of the design documents. all around as per drawings. Ensure bar chairs comply with AS2425. (Higher cover for standard form work. Lower cover for rigid formwork with high intensive vibrators fitted to form work.) Tie wire not to intrude into cover zone. Maintain cover to rebar during concrete placing. Cover to be minimum 25 mm all around , 20mm on top (tolerance of 0 to +5mm). | Measure cover using measuring tape | Ensure 100% compliance of cover requirement Is achieved and witnessed Compliance must be recorded on check sheet drawings | HP |  | 2.5 - Cover verification | Reference(s) - 610.33 610.26 610.46 611.10 AS 2425 | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 AS 5100.5 | Acceptance Criteria - Requirements of the design documents. all around as per drawings. Ensure bar chairs comply with AS2425. (Higher cover for standard form work. Lower cover for rigid formwork with high intensive vibrators fitted to form work.) Tie wire not to intrude into cover zone. Maintain cover to rebar during concrete placing. Cover to be minimum 25 mm all around , 20mm on top (tolerance of 0 to +5mm). | Conformance: Method - Measure cover using measuring tape | Conformance: Frequency - Ensure 100% compliance of cover requirement Is achieved and witnessed Compliance must be recorded on check sheet drawings | HCC Sign - HP | TAMS Group Sign - | Conformance: Frequency - HP
2.6 | Tendons supply and traceability | 622.03 622.02 | AS/NZ 4672, 4672.1.1 Component check sheet | 15.2mm strands used. ACRS supplied, Coil batch certification recorded, stressing design approved and documented by consulting engineer Strands Certificate of Compliance Designs, drawings and De-bond detail plan | Visual | All Components | HP |  | 2.6 - Tendons supply and traceability | Reference(s) - 622.03 622.02 | Supporting Documents - AS/NZ 4672, 4672.1.1 Component check sheet | Acceptance Criteria - 15.2mm strands used. ACRS supplied, Coil batch certification recorded, stressing design approved and documented by consulting engineer Strands Certificate of Compliance Designs, drawings and De-bond detail plan | Conformance: Method - Visual | Conformance: Frequency - All Components | HCC Sign - HP | TAMS Group Sign - | HCC Sign - HP
2.7 | Storage and surface condition of Tendons | 622.2 (d) | AS/NZ 4672 | Coils of wire and strand and assembled tendons shall be stored above ground level and shall be protected from mechanical damage, contamination with harmful substances or other damage until their incorporation into the works. Wires and strands that show any evidence of damage, kinks or bends shall not be used. Wires and strands which are heavily corroded or visibly pitted will not be accepted. Slight surface rusting shall not be a reason for rejection provided that no pitting is visible. Wire and strand shall be kept free from loose rust, oil, grease, tar, paint, soil or any other harmful substances. If the wire or strand become contaminated with any substance, it shall be cleaned with suitable equipment and appropriate detergents and/or clean water until all of the contaminant and any detergent has been removed satisfaction of the Superintendent. Loose rust shall be removed by mechanical or manual methods that do not cause damage to the wire or strand or which impair the bond between the wire or strand and the concrete. | Visual | All Coils | HP |  | 2.7 - Storage and surface condition of Tendons | Reference(s) - 622.2 (d) | Supporting Documents - AS/NZ 4672 | Acceptance Criteria - Coils of wire and strand and assembled tendons shall be stored above ground level and shall be protected from mechanical damage, contamination with harmful substances or other damage until their incorporation into the works. Wires and strands that show any evidence of damage, kinks or bends shall not be used. Wires and strands which are heavily corroded or visibly pitted will not be accepted. Slight surface rusting shall not be a reason for rejection provided that no pitting is visible. Wire and strand shall be kept free from loose rust, oil, grease, tar, paint, soil or any other harmful substances. If the wire or strand become contaminated with any substance, it shall be cleaned with suitable equipment and appropriate detergents and/or clean water until all of the contaminant and any detergent has been removed satisfaction of the Superintendent. Loose rust shall be removed by mechanical or manual methods that do not cause damage to the wire or strand or which impair the bond between the wire or strand and the concrete. | Conformance: Method - Visual | Conformance: Frequency - All Coils | HCC Sign - HP | TAMS Group Sign - | TAMS Group Sign -
2.8 | Placing Tendons | 622.04 | - | Tendons shall be placed in continuous lengths in the positions shown on the drawings and shall be held in the required position by end-blocks of sufficient strength and stiffness to safely maintain the required force in the tendons. Tendons shall be de-bonded in the positions shown on the shop drawings. 19mm paper thin plastic sleeves will be used for de-bonding strands.. Grease or other coatings shall not be used for de-bonding. Tendons shall not be allowed to come into contact with the oiled surface of the formwork. If a tendon is contaminated with oil or other harmful substance it shall be cleaned using an appropriate method in order to ensure that the bond between the tendon and the concrete is unimpaired. Tendons that cannot be cleaned shall be replaced. Tendons shall not be welded or exposed to heat from welding or other sources. Where deflected tendons are shown on the drawings, tendons shall be restrained with devices of sufficient strength to hold the tendons in their proper positions without displacement during the placing and compaction of concrete. | Visual Inspection | For all components | HP |  | 2.8 - Placing Tendons | Reference(s) - 622.04 | Supporting Documents - - | Acceptance Criteria - Tendons shall be placed in continuous lengths in the positions shown on the drawings and shall be held in the required position by end-blocks of sufficient strength and stiffness to safely maintain the required force in the tendons. Tendons shall be de-bonded in the positions shown on the shop drawings. 19mm paper thin plastic sleeves will be used for de-bonding strands.. Grease or other coatings shall not be used for de-bonding. Tendons shall not be allowed to come into contact with the oiled surface of the formwork. If a tendon is contaminated with oil or other harmful substance it shall be cleaned using an appropriate method in order to ensure that the bond between the tendon and the concrete is unimpaired. Tendons that cannot be cleaned shall be replaced. Tendons shall not be welded or exposed to heat from welding or other sources. Where deflected tendons are shown on the drawings, tendons shall be restrained with devices of sufficient strength to hold the tendons in their proper positions without displacement during the placing and compaction of concrete. | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - | 1.3 - Radiant heat curing with curing compounds
2.9 | Tensioning, equipment, anchoring and Tendon force | 622.06 622.02 a, b, c and d | Calibration AS2193 | Equipment Contractor shall maintain current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices. Jacks and pressure gauges and other devices shall be calibrated and used as a single unit. Calibration to AS 2193 shall be carried out by a laboratory that is NATA-accredited for that method, and at the appropriate force range. The power unit shall be adjusted so that the rate of extension of the tendon is within the specified limits. The measuring equipment shall permit measurement of the tendon force prior to lock-off to the degree of accuracy required by AS 2193 Grade B. The measuring equipment used shall permit elongation to be determined to an accuracy of ±2%. The equipment shall prevent unwinding of the strand during tensioning. The sag take-up force in the tendons shall be measured with equipment which complies with the repeatability and accuracy requirements of AS 2193 Grade B, at a scale mark at which the equipment has been calibrated. The readability requirements of AS 2193 Grade B shall be ignored for the purpose of establishing sag take-up. Sag take-up force shall not exceed 20% of the required tendon force, and shall be not less than 10% of the required tendon force or 10% of gauge capacity, whichever is the greater. Anchorages Anchorages shall be of a type that prevents the occurrence of slip during casting and curing operations. Tendon Force Before tensioning commences, the Contractor shall calculate the extension corresponding to the required tendon force shown on the drawings. The calculation shall be based on the measured length of the tendon between the tendon anchorages at the end blocks and the modulus of elasticity determined from the sample tested in accordance with Clause 622.02. The calculations shall include allowances for all losses including slip at anchorages, elastic shortening of the stressing bed, pull-in on transfer of prestress, friction losses and temperature changes. The calculations shall be reviewed by the designer of the pre-tensioned concrete units who shall certify that the calculations meet the requirements of the specification and the drawings. The Contractor shall provide a copy of the designer’s certification to the Superintendent. After all tendons have been anchored to the end-blocks (locked off), the force remaining in the tendons at mid-span of the unit shall be the required tendon force stated on the drawings. The allowable variation of the tendon force shall be ±2%. Under no circumstances shall the maximum tensioning force exceed the lesser of the rated capacity of the jacking equipment or 80% of the tensile strength of the tendon. The tensioning force required to achieve the design tendon force shall be determined from the calibration certificate and the actual elongation of the tendon corresponding to the tensioning force shall be recorded. Alternatively, the Superintendent may approve determination of the tensioning force by measurement of the elongation, provided that the limits of variation of the modulus of elasticity of the tendons are satisfactory. In this case, the jacking force shall be recorded. Should the modulus of elasticity of batches of tendons differ by more than 3%, the required elongation shall be adjusted accordingly. Where the difference between the force determined from the calibration certificate and the tensioning force calculated from the elongation exceeds 4%, the Contractor shall nominate some or all of the following remedial steps subject to review by the Superintendent. The Contractor shall suspend stressing until the completion of the Superintendent’s review: • re-calibration of tensioning equipment; • testing of tendon material to check the modulus of elasticity; • that tendons be released and restressed (with the adoption of a modulus of elasticity applicable to the second stressing); • other steps as agreed by the Superintendent. | Visual Inspection | For Stressing Jack and Guage | HP | HP (If applicable) | 2.9 - Tensioning, equipment, anchoring and Tendon force | Reference(s) - 622.06 622.02 a, b, c and d | Supporting Documents - Calibration AS2193 | Acceptance Criteria - Equipment Contractor shall maintain current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices. Jacks and pressure gauges and other devices shall be calibrated and used as a single unit. Calibration to AS 2193 shall be carried out by a laboratory that is NATA-accredited for that method, and at the appropriate force range. The power unit shall be adjusted so that the rate of extension of the tendon is within the specified limits. The measuring equipment shall permit measurement of the tendon force prior to lock-off to the degree of accuracy required by AS 2193 Grade B. The measuring equipment used shall permit elongation to be determined to an accuracy of ±2%. The equipment shall prevent unwinding of the strand during tensioning. The sag take-up force in the tendons shall be measured with equipment which complies with the repeatability and accuracy requirements of AS 2193 Grade B, at a scale mark at which the equipment has been calibrated. The readability requirements of AS 2193 Grade B shall be ignored for the purpose of establishing sag take-up. Sag take-up force shall not exceed 20% of the required tendon force, and shall be not less than 10% of the required tendon force or 10% of gauge capacity, whichever is the greater. Anchorages Anchorages shall be of a type that prevents the occurrence of slip during casting and curing operations. Tendon Force Before tensioning commences, the Contractor shall calculate the extension corresponding to the required tendon force shown on the drawings. The calculation shall be based on the measured length of the tendon between the tendon anchorages at the end blocks and the modulus of elasticity determined from the sample tested in accordance with Clause 622.02. The calculations shall include allowances for all losses including slip at anchorages, elastic shortening of the stressing bed, pull-in on transfer of prestress, friction losses and temperature changes. The calculations shall be reviewed by the designer of the pre-tensioned concrete units who shall certify that the calculations meet the requirements of the specification and the drawings. The Contractor shall provide a copy of the designer’s certification to the Superintendent. After all tendons have been anchored to the end-blocks (locked off), the force remaining in the tendons at mid-span of the unit shall be the required tendon force stated on the drawings. The allowable variation of the tendon force shall be ±2%. Under no circumstances shall the maximum tensioning force exceed the lesser of the rated capacity of the jacking equipment or 80% of the tensile strength of the tendon. The tensioning force required to achieve the design tendon force shall be determined from the calibration certificate and the actual elongation of the tendon corresponding to the tensioning force shall be recorded. Alternatively, the Superintendent may approve determination of the tensioning force by measurement of the elongation, provided that the limits of variation of the modulus of elasticity of the tendons are satisfactory. In this case, the jacking force shall be recorded. Should the modulus of elasticity of batches of tendons differ by more than 3%, the required elongation shall be adjusted accordingly. Where the difference between the force determined from the calibration certificate and the tensioning force calculated from the elongation exceeds 4%, the Contractor shall nominate some or all of the following remedial steps subject to review by the Superintendent. The Contractor shall suspend stressing until the completion of the Superintendent’s review: • re-calibration of tensioning equipment; • testing of tendon material to check the modulus of elasticity; • that tendons be released and restressed (with the adoption of a modulus of elasticity applicable to the second stressing); • other steps as agreed by the Superintendent. | Conformance: Method - Visual Inspection | Conformance: Frequency - For Stressing Jack and Guage | HCC Sign - HP | TAMS Group Sign - HP (If applicable) | Reference(s) - 610.23 (h) (g)
2.1 | Tensioning Procedure | 622.06 (d) | Refer to HCC tendon tensioning procedure | Tensioning Procedure All stressing operations shall be recorded on the daily stressing sheet Tensioning operations shall be performed by suitably trained and experienced personnel. Tensioning has been carried out in accordance with The Hollow Core Concrete Tensioning procedure document | Visual Inspection | For all components | HP | HP (Refer stress record Sheet for HPR) | 2.1 - Tensioning Procedure | Reference(s) - 622.06 (d) | Supporting Documents - Refer to HCC tendon tensioning procedure | Acceptance Criteria - Tensioning Procedure All stressing operations shall be recorded on the daily stressing sheet Tensioning operations shall be performed by suitably trained and experienced personnel. Tensioning has been carried out in accordance with The Hollow Core Concrete Tensioning procedure document | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - HP (Refer stress record Sheet for HPR) | Supporting Documents - MSDS Complies with AS 3799
2.11 | Transfer of prestress | 622.08 a, b, c | Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings | Transfer of stress will only be permitted after the cylinder testing shows minimum of 40 MPa of compressive strength (as approved by the designer) | Visual Inspection | For all components | HP |  | 2.11 - Transfer of prestress | Reference(s) - 622.08 a, b, c | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings | Acceptance Criteria - Transfer of stress will only be permitted after the cylinder testing shows minimum of 40 MPa of compressive strength (as approved by the designer) | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - | Acceptance Criteria - SikaFilm applied during finishing, covers installed after finishing of concrete. Radiant heat curing will occur until the Antisol AC sprayed or rolled over the components within 30 minutes of removing formwork.
2.12 | Calibration certificates for Jack and Guage | 622.06 | Calibration certificates | Calibration certification will be conduct at six monthly intervals. Current certified equipment is being used. | Visual Inspection | For all components | HP |  | 2.12 - Calibration certificates for Jack and Guage | Reference(s) - 622.06 | Supporting Documents - Calibration certificates | Acceptance Criteria - Calibration certification will be conduct at six monthly intervals. Current certified equipment is being used. | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - | Conformance: Method - Written
2.13 | Data to be recorded | 622.09 | AS/NZ 4672.1 HCC Prestress Check List | Ensure the following data is recorded: • identification number of the unit; • identification number of each dynamometer, gauge, and jack; • calibration certificates for each dynamometer, gauge, and jack; • identification details for each tendon; • sag take-up force (or pressure) when tendons are marked for measurement of elongation; • elongation obtained at intervals during tensioning, together with corresponding force (or pressure gauge reading); • tendon force (or pressure) and elongation obtained on completion of tensioning prior to lock-off; • elongation after release of jack; • pull-in; • compressive strength of concrete at time of transfer of prestress; • steam curing charts; • measurement of hog following transfer of prestress. Completed records shall be forwarded to the Nominated Authority prior to delivery of the pre-stressed units to the site. | Measured / Visual Recorded | Every component | HP |  | 2.13 - Data to be recorded | Reference(s) - 622.09 | Supporting Documents - AS/NZ 4672.1 HCC Prestress Check List | Acceptance Criteria - Ensure the following data is recorded: • identification number of the unit; • identification number of each dynamometer, gauge, and jack; • calibration certificates for each dynamometer, gauge, and jack; • identification details for each tendon; • sag take-up force (or pressure) when tendons are marked for measurement of elongation; • elongation obtained at intervals during tensioning, together with corresponding force (or pressure gauge reading); • tendon force (or pressure) and elongation obtained on completion of tensioning prior to lock-off; • elongation after release of jack; • pull-in; • compressive strength of concrete at time of transfer of prestress; • steam curing charts; • measurement of hog following transfer of prestress. Completed records shall be forwarded to the Nominated Authority prior to delivery of the pre-stressed units to the site. | Conformance: Method - Measured / Visual Recorded | Conformance: Frequency - Every component | HCC Sign - HP | TAMS Group Sign - | Conformance: Frequency - Every component
2.14 | Protection of Exposed ends of Tendons | 622.1 | Mega poxy MSDS | If the ends of tendons are to remain exposed, they shall be wire-brushed to remove rust, loose mortar, grease, dirt and all other harmful material and shall then be coated with a minimum 6 mm thickness of epoxy compound. | Visual Inspection | For all components | HP |  | 2.14 - Protection of Exposed ends of Tendons | Reference(s) - 622.1 | Supporting Documents - Mega poxy MSDS | Acceptance Criteria - If the ends of tendons are to remain exposed, they shall be wire-brushed to remove rust, loose mortar, grease, dirt and all other harmful material and shall then be coated with a minimum 6 mm thickness of epoxy compound. | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - | HCC Sign - HP
2.15 | Concrete delivery | 610.16 | Concrete docket | Correct information on delivery docket | Visual | Each Load | HP |  | 2.15 - Concrete delivery | Reference(s) - 610.16 | Supporting Documents - Concrete docket | Acceptance Criteria - Correct information on delivery docket | Conformance: Method - Visual | Conformance: Frequency - Each Load | HCC Sign - HP | TAMS Group Sign - | TAMS Group Sign - HP
2.16 | Concrete Mix Design | 610 | Hanson concrete mix design letter | TU604AA62 150 Slump | Documented | All Components | HP |  | 2.16 - Concrete Mix Design | Reference(s) - 610 | Supporting Documents - Hanson concrete mix design letter | Acceptance Criteria - TU604AA62 150 Slump | Conformance: Method - Documented | Conformance: Frequency - All Components | HCC Sign - HP | TAMS Group Sign - | 1.4 - Submit curing methodology
2.17 | Concrete slump test | 610.16 | AS1012.3.1 Concrete tester’s field sheet | 150mm slump = ±30mm (120mm to 180mm) | Measured / Visual | Each Load | HP |  | 2.17 - Concrete slump test | Reference(s) - 610.16 | Supporting Documents - AS1012.3.1 Concrete tester’s field sheet | Acceptance Criteria - 150mm slump = ±30mm (120mm to 180mm) | Conformance: Method - Measured / Visual | Conformance: Frequency - Each Load | HCC Sign - HP | TAMS Group Sign - | Reference(s) - 610.23 (a)
2.18 | Concrete compressive strength cylinders made | 610.05 610.16 (L) | AS1012.8 | Sets of 3 cylinders, also one cylinder to be used for early strength verification as required. | Visual | 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets | HP |  | 2.18 - Concrete compressive strength cylinders made | Reference(s) - 610.05 610.16 (L) | Supporting Documents - AS1012.8 | Acceptance Criteria - Sets of 3 cylinders, also one cylinder to be used for early strength verification as required. | Conformance: Method - Visual | Conformance: Frequency - 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets | HCC Sign - HP | TAMS Group Sign - | Supporting Documents - Product TDS, SDS CHAR(AMP) NATA Certificate
2.19 | Concrete placement | 610.18 (a), (d) 610.22 | Daily observation will take place to monitor this process is followed | Time lag between trucks on site not to exceed 25 minutes Air bubbles released to surface without segregation of the mix Ensure segregation of the concrete does not occur by preventing free fall of concrete from anything greater than 2 meters Care shall be taken to fill every part of the forms or excavations, to force the concrete under and around the reinforcement without displacing it, to work coarse aggregate back from the face, and to remove air bubbles and voids. Concrete shall be deposited in horizontal layers not more than 350 mm thick. During and immediately after placing, the concrete shall be effectively compacted by vibrators of adequate size, number and frequency. ll be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs. Where internal vibrators are used, they shall be inserted vertically at at spacings not exceeding 250 mm spacings and shall not be allowed to rest on the steel reinforcement. Curing shall commence immediately following the progressive completion at any location of final finishing operations. Thermo Couples shall be placed Three per Unit as agreed with the super intendent.( One central in the Unit, another 25mm from the exposed face and edge of the unit, the third central in the unit 25 mm deep from the exposed face. Maximum temperature shall not exceed 75 degrees Celsius. Maximum differential temperature to be no greater than 20 degrees Celsius. | Visual | Every Load | HP |  | 2.19 - Concrete placement | Reference(s) - 610.18 (a), (d) 610.22 | Supporting Documents - Daily observation will take place to monitor this process is followed | Acceptance Criteria - Time lag between trucks on site not to exceed 25 minutes Air bubbles released to surface without segregation of the mix Ensure segregation of the concrete does not occur by preventing free fall of concrete from anything greater than 2 meters Care shall be taken to fill every part of the forms or excavations, to force the concrete under and around the reinforcement without displacing it, to work coarse aggregate back from the face, and to remove air bubbles and voids. Concrete shall be deposited in horizontal layers not more than 350 mm thick. During and immediately after placing, the concrete shall be effectively compacted by vibrators of adequate size, number and frequency. ll be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs. Where internal vibrators are used, they shall be inserted vertically at at spacings not exceeding 250 mm spacings and shall not be allowed to rest on the steel reinforcement. Curing shall commence immediately following the progressive completion at any location of final finishing operations. Thermo Couples shall be placed Three per Unit as agreed with the super intendent.( One central in the Unit, another 25mm from the exposed face and edge of the unit, the third central in the unit 25 mm deep from the exposed face. Maximum temperature shall not exceed 75 degrees Celsius. Maximum differential temperature to be no greater than 20 degrees Celsius. | Conformance: Method - Visual | Conformance: Frequency - Every Load | HCC Sign - HP | TAMS Group Sign - | Acceptance Criteria - Curing compound meets or exceeds AS3799. Application rates noted.
2.2 | Placement of the lifting lugs | Certified Shop drawings | Shop drawings for each individual component drawings | Ensure all lifters are cast into position to within 20 mm tolerances from the design locations | Visual | Every unit | HP |  | 2.2 - Placement of the lifting lugs | Reference(s) - Certified Shop drawings | Supporting Documents - Shop drawings for each individual component drawings | Acceptance Criteria - Ensure all lifters are cast into position to within 20 mm tolerances from the design locations | Conformance: Method - Visual | Conformance: Frequency - Every unit | HCC Sign - HP | TAMS Group Sign - | Conformance: Method - Written
2.21 | Evaporation retarding compound | 610.17 | Product MSDS | Apply aliphatic alcohol-based compound, as required, during initial finishing of concrete . | Visual | Every unit | HP |  | 2.21 - Evaporation retarding compound | Reference(s) - 610.17 | Supporting Documents - Product MSDS | Acceptance Criteria - Apply aliphatic alcohol-based compound, as required, during initial finishing of concrete . | Conformance: Method - Visual | Conformance: Frequency - Every unit | HCC Sign - HP | TAMS Group Sign - | Conformance: Frequency - Prior to casting
2.22 | Concrete finish | 610.18 (d) (iii) | - | Requirements of the Project is exposed washed surface on top and off form class 2 finish to the sides and bottoms of the beams | Visual | Every Unit | HP |  | 2.22 - Concrete finish | Reference(s) - 610.18 (d) (iii) | Supporting Documents - - | Acceptance Criteria - Requirements of the Project is exposed washed surface on top and off form class 2 finish to the sides and bottoms of the beams | Conformance: Method - Visual | Conformance: Frequency - Every Unit | HCC Sign - HP | TAMS Group Sign - | HCC Sign - HP
2.23 | Early age thermal cracking | 610.22 | HCC Thermal monitoring record sheet | Measures to be taken if least dimension exceeds 500mm thickness and one or, more faces are restrained. Thermal Couplers used, | Thermal monitoring | First Unit of each type of beam. If risks are identified, further sampling will be carried out | HP |  | 2.23 - Early age thermal cracking | Reference(s) - 610.22 | Supporting Documents - HCC Thermal monitoring record sheet | Acceptance Criteria - Measures to be taken if least dimension exceeds 500mm thickness and one or, more faces are restrained. Thermal Couplers used, | Conformance: Method - Thermal monitoring | Conformance: Frequency - First Unit of each type of beam. If risks are identified, further sampling will be carried out | HCC Sign - HP | TAMS Group Sign - | TAMS Group Sign - HP
3.1 | Concrete compressive strength | 610.05 | AS1012.8 Lifting Certificate HCC drawings | Requirements of the Project/Unit: Stripping strength = 40MPa 7 Day strength = 40MPa 28 Day strength = 50MPa | Schmidt Hammer NATA Laboratory | 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets Note: 3 cyls/ set | HP |  | 3.1 - Concrete compressive strength | Reference(s) - 610.05 | Supporting Documents - AS1012.8 Lifting Certificate HCC drawings | Acceptance Criteria - Requirements of the Project/Unit: Stripping strength = 40MPa 7 Day strength = 40MPa 28 Day strength = 50MPa | Conformance: Method - Schmidt Hammer NATA Laboratory | Conformance: Frequency - 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets Note: 3 cyls/ set | HCC Sign - HP | TAMS Group Sign - | 1.5 - Submit evaporative retardant (aliphatic alcohol- based)
3.2 | Units labelled | 620.06 | Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | The identification number, date of casting, the manufacturer’s name or registered mark and the maximum mass shall be marked on every precast unit. | Visual | Each Unit | HP |  | 3.2 - Units labelled | Reference(s) - 620.06 | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Acceptance Criteria - The identification number, date of casting, the manufacturer’s name or registered mark and the maximum mass shall be marked on every precast unit. | Conformance: Method - Visual | Conformance: Frequency - Each Unit | HCC Sign - HP | TAMS Group Sign - | Reference(s) - 610.17 (f)
3.3 | Curing (apply Sika Antisol AC curing compound) | 610.23 (d), 610.231 AS3799 | Manufacturer’s TDS CHAR(AMP) SDS | 2 coats with a minimum application rate of 0.2 litres/m².Keep record. Record rate of application. 1st coat to be applied within 30 minutes of stripping form work. Allow 3 hours between coats. Check box on label once the second coat is applied. Curing membrane shall be retained and maintained as per Table 610.231 | Measured / Visual | Each Unit | HP |  | 3.3 - Curing (apply Sika Antisol AC curing compound) | Reference(s) - 610.23 (d), 610.231 AS3799 | Supporting Documents - Manufacturer’s TDS CHAR(AMP) SDS | Acceptance Criteria - 2 coats with a minimum application rate of 0.2 litres/m².Keep record. Record rate of application. 1st coat to be applied within 30 minutes of stripping form work. Allow 3 hours between coats. Check box on label once the second coat is applied. Curing membrane shall be retained and maintained as per Table 610.231 | Conformance: Method - Measured / Visual | Conformance: Frequency - Each Unit | HCC Sign - HP | TAMS Group Sign - | Supporting Documents - Product TDS CHAR(AMP) SDS
3.4 | Post-pour Inspection | 610.30 610.46 | Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Surface finish as per Project requirements (Class 3) Dimensions as per table 610.463 and 610.464. | Measured / Visual / Photographic | Each Unit | HP |  | 3.4 - Post-pour Inspection | Reference(s) - 610.30 610.46 | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 | Acceptance Criteria - Surface finish as per Project requirements (Class 3) Dimensions as per table 610.463 and 610.464. | Conformance: Method - Measured / Visual / Photographic | Conformance: Frequency - Each Unit | HCC Sign - HP | TAMS Group Sign - | Acceptance Criteria - Application rates noted.
3.5 | Cracking or any other imperfections to the product | 610.24 (a) (b) Table 610.241 687 | Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings | Refer to Table 610.241 for acceptable maximum crack widths. Cracks assessed by a technical specialist with a minimum of 5 years practical experience. Submit a crack repair procedure prior to any repair works being undertaken. If cracking is witnessed NCR will be raised and repair procedure selected following an inspection by the NA. | Visual Inspection | For all components | HP | HP | 3.5 - Cracking or any other imperfections to the product | Reference(s) - 610.24 (a) (b) Table 610.241 687 | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings | Acceptance Criteria - Refer to Table 610.241 for acceptable maximum crack widths. Cracks assessed by a technical specialist with a minimum of 5 years practical experience. Submit a crack repair procedure prior to any repair works being undertaken. If cracking is witnessed NCR will be raised and repair procedure selected following an inspection by the NA. | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - HP | Conformance: Method - Written
3.6 | Post pour dimensional checks | 610.46 | Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings | Ensure that post pour dimensional checks are carried out. Cast in items checked and noted. Concrete finishes are as per design drawings Curing applied | Measured / Visual | For all components | HP |  | 3.6 - Post pour dimensional checks | Reference(s) - 610.46 | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings | Acceptance Criteria - Ensure that post pour dimensional checks are carried out. Cast in items checked and noted. Concrete finishes are as per design drawings Curing applied | Conformance: Method - Measured / Visual | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - | Conformance: Frequency - Prior to casting
3.7 | Lifting product out of the mould | 620.03 | Refer to shop drawings HCC drawings | Minimum of 40 MPa strength required before lifting the components out of the mould. | Cylinder crack testing. | Each Lot | HP |  | 3.7 - Lifting product out of the mould | Reference(s) - 620.03 | Supporting Documents - Refer to shop drawings HCC drawings | Acceptance Criteria - Minimum of 40 MPa strength required before lifting the components out of the mould. | Conformance: Method - Cylinder crack testing. | Conformance: Frequency - Each Lot | HCC Sign - HP | TAMS Group Sign - | HCC Sign - HP
3.8 | Post pour cover check | 610.34 | Record results on Cover check sheet | Test 3 square meters out of every 25m2 of surface. 10 tests or measurements must be recorder per 3 square meter sample area. | Written record | Each unit | HP |  | 3.8 - Post pour cover check | Reference(s) - 610.34 | Supporting Documents - Record results on Cover check sheet | Acceptance Criteria - Test 3 square meters out of every 25m2 of surface. 10 tests or measurements must be recorder per 3 square meter sample area. | Conformance: Method - Written record | Conformance: Frequency - Each unit | HCC Sign - HP | TAMS Group Sign - | TAMS Group Sign - HP
3.9 | Storage and stacking of the bridge planks | 620.07 622 | Rigging and Stacking Design Doc | Components shall only be lifted by the designated cast- in lifters. Components will be stacked simply supported by a bearer under each end directly under the cast in lifters. Maximum of 3 components to be stacked. Stacking will be in accordance with engineers design Bearers will be positioned in line with the cast in lifters. Bearers will be placed on a level concreted ground surface. | Visual Inspection | For all components | HP |  | 3.9 - Storage and stacking of the bridge planks | Reference(s) - 620.07 622 | Supporting Documents - Rigging and Stacking Design Doc | Acceptance Criteria - Components shall only be lifted by the designated cast- in lifters. Components will be stacked simply supported by a bearer under each end directly under the cast in lifters. Maximum of 3 components to be stacked. Stacking will be in accordance with engineers design Bearers will be positioned in line with the cast in lifters. Bearers will be placed on a level concreted ground surface. | Conformance: Method - Visual Inspection | Conformance: Frequency - For all components | HCC Sign - HP | TAMS Group Sign - | 1.6 - Submit ITP for review
3.1 | Product delivery | 620.08, 610.26 | Delivery Docket(s) Certificates of Compliance | Unit(s) to have achieved minimum 28 day compressive strength and must comply with table 610.261 prior to transporting. Components will be lashed down in accordance with engineers design. Chains will be directly above the bearers under the Beams. Beam edges will be protected using plastic angels to prevent damage from the tie down chains. Compliance certificates will be issued the day before delivery of components to site. | Written | Each Unit | HP |  | 3.1 - Product delivery | Reference(s) - 620.08, 610.26 | Supporting Documents - Delivery Docket(s) Certificates of Compliance | Acceptance Criteria - Unit(s) to have achieved minimum 28 day compressive strength and must comply with table 610.261 prior to transporting. Components will be lashed down in accordance with engineers design. Chains will be directly above the bearers under the Beams. Beam edges will be protected using plastic angels to prevent damage from the tie down chains. Compliance certificates will be issued the day before delivery of components to site. | Conformance: Method - Written | Conformance: Frequency - Each Unit | HCC Sign - HP | TAMS Group Sign - | Reference(s) - 610.18 (a) (i)
Supporting Documents - This document
Acceptance Criteria - Written acceptance to proceed
Conformance: Method - Written
Conformance: Frequency - Prior to casting
HCC Sign - HP
TAMS Group Sign - HP
1.7 - Submit repair procedure for review
Reference(s) - 610.24 (b) 689.13
Supporting Documents - Repair Procedure/ Methodology
Acceptance Criteria - Review and approval by Client
Conformance: Method - Written
Conformance: Frequency - Prior to repairing components
HCC Sign - HP
TAMS Group Sign - HP
1.8 - Ensure all shop drawings are IFC before casting the components
Reference(s) - HCC QMP
Supporting Documents - Stamped shop drawing
Acceptance Criteria - Shop drawings are to be IFC and numerical revision
Conformance: Method - Written
Conformance: Frequency - Prior to casting
HCC Sign - HP
TAMS Group Sign - HP
1.9 - Stressing Calculations have been submitted for review
Reference(s) - 622.02
Supporting Documents - Stressing Calculations and chart
Acceptance Criteria - Stressing calculations are to be reviewed by project consultant
Conformance: Method - Once before commencement of casting Reviewed if changes occur during the course of the production
Conformance: Frequency - HP
HCC Sign - HP
TAMS Group Sign -
2.1 - Pre-pour inspection (external)
Reference(s) - 610.18 (a) (ii CHAR(AMP) iii)
Supporting Documents - Nominated authority’s checklist Relevant shop drawings
Acceptance Criteria - Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to structural requirements and specifications. Moulds/formwork are clean and free from debris. 7 Day notification given via ACONEX. Any changes to be reported within 24 hours prior to the pour.
Conformance: Method - Measured / Visual
Conformance: Frequency - Each Unit
HCC Sign - HP
TAMS Group Sign - HP
2.2 - Pre-pour inspection (internal)
Reference(s) - 610.18 (a) (ii CHAR(AMP) iii)
Supporting Documents - HCC QMP Section 3.12 Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254
Acceptance Criteria - Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to shop drawings. Moulds/formwork are clean and free from debris.
Conformance: Method - Measured / Visual
Conformance: Frequency - Each Unit
HCC Sign - HP
TAMS Group Sign -
2.3 - Check conditions prior to, during and post concrete delivery and placement
Reference(s) - 610.17 (a-f)
Supporting Documents - On-line Weather report and forecast
Acceptance Criteria - Ambient temperature not: CHAR(LESS) 5°C or > 35°C Concrete temperature not: CHAR(LESS) 10°C or > 32°C Weather condition: conducive to pour Evaporation Limits for Concreting Operations The Contractor shall be responsible for measuring and recording the air temperature, relative humidity, concrete temperature and wind velocity (measured one metre above the as placed concrete) at the point of concrete placement from commencement of placing the concrete and continue until curing has commenced. This information shall be used in conjunction with Figure 610.171 to determine the rate of evaporation of water from the freshly placed and unprotected surface of the concrete. The rate of evaporation shall be monitored by the Contractor until such time as curing commences. When the value of the rate of evaporation as determined from Figure 610.171 exceeds 0.50 kg/m² per hour the Contractor shall take precautions to minimise evaporative moisture losses such as the application of an aliphatic-alcohol based evaporative retarding compound or controlled fog spray. Application of evaporative retarding compound is required during pouring of concrete.
Conformance: Method - Measured / Visual
Conformance: Frequency - Each Lot
HCC Sign - HP
TAMS Group Sign -
2.4 - Reinforcing placement and inspection
Reference(s) - 611
Supporting Documents - AS 5100 Component Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254
Acceptance Criteria - Check against relevant shop drawing that all reinforcing bars are installed correctly, at the right centres and in a clean condition. Reinforcing bars spacing to be no less than 1.5 times the size of the largest aggregate. Correct bar laps to be observed. Correct radius in bends.
Conformance: Method - Visual/ measuring
Conformance: Frequency - Each component
HCC Sign - HP
TAMS Group Sign -
2.5 - Cover verification
Reference(s) - 610.33 610.26 610.46 611.10 AS 2425
Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 AS 5100.5
Acceptance Criteria - Requirements of the design documents. all around as per drawings. Ensure bar chairs comply with AS2425. (Higher cover for standard form work. Lower cover for rigid formwork with high intensive vibrators fitted to form work.) Tie wire not to intrude into cover zone. Maintain cover to rebar during concrete placing. Cover to be minimum 25 mm all around , 20mm on top (tolerance of 0 to +5mm).
Conformance: Method - Measure cover using measuring tape
Conformance: Frequency - Ensure 100% compliance of cover requirement Is achieved and witnessed Compliance must be recorded on check sheet drawings
HCC Sign - HP
TAMS Group Sign -
2.6 - Tendons supply and traceability
Reference(s) - 622.03 622.02
Supporting Documents - AS/NZ 4672, 4672.1.1 Component check sheet
Acceptance Criteria - 15.2mm strands used. ACRS supplied, Coil batch certification recorded, stressing design approved and documented by consulting engineer Strands Certificate of Compliance Designs, drawings and De-bond detail plan
Conformance: Method - Visual
Conformance: Frequency - All Components
HCC Sign - HP
TAMS Group Sign -
2.7 - Storage and surface condition of Tendons
Reference(s) - 622.2 (d)
Supporting Documents - AS/NZ 4672
Acceptance Criteria - Coils of wire and strand and assembled tendons shall be stored above ground level and shall be protected from mechanical damage, contamination with harmful substances or other damage until their incorporation into the works. Wires and strands that show any evidence of damage, kinks or bends shall not be used. Wires and strands which are heavily corroded or visibly pitted will not be accepted. Slight surface rusting shall not be a reason for rejection provided that no pitting is visible. Wire and strand shall be kept free from loose rust, oil, grease, tar, paint, soil or any other harmful substances. If the wire or strand become contaminated with any substance, it shall be cleaned with suitable equipment and appropriate detergents and/or clean water until all of the contaminant and any detergent has been removed satisfaction of the Superintendent. Loose rust shall be removed by mechanical or manual methods that do not cause damage to the wire or strand or which impair the bond between the wire or strand and the concrete.
Conformance: Method - Visual
Conformance: Frequency - All Coils
HCC Sign - HP
TAMS Group Sign -
2.8 - Placing Tendons
Reference(s) - 622.04
Supporting Documents - -
Acceptance Criteria - Tendons shall be placed in continuous lengths in the positions shown on the drawings and shall be held in the required position by end-blocks of sufficient strength and stiffness to safely maintain the required force in the tendons. Tendons shall be de-bonded in the positions shown on the shop drawings. 19mm paper thin plastic sleeves will be used for de-bonding strands.. Grease or other coatings shall not be used for de-bonding. Tendons shall not be allowed to come into contact with the oiled surface of the formwork. If a tendon is contaminated with oil or other harmful substance it shall be cleaned using an appropriate method in order to ensure that the bond between the tendon and the concrete is unimpaired. Tendons that cannot be cleaned shall be replaced. Tendons shall not be welded or exposed to heat from welding or other sources. Where deflected tendons are shown on the drawings, tendons shall be restrained with devices of sufficient strength to hold the tendons in their proper positions without displacement during the placing and compaction of concrete.
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign -
2.9 - Tensioning, equipment, anchoring and Tendon force
Reference(s) - 622.06 622.02 a, b, c and d
Supporting Documents - Calibration AS2193
Acceptance Criteria - Equipment Contractor shall maintain current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices. Jacks and pressure gauges and other devices shall be calibrated and used as a single unit. Calibration to AS 2193 shall be carried out by a laboratory that is NATA-accredited for that method, and at the appropriate force range. The power unit shall be adjusted so that the rate of extension of the tendon is within the specified limits. The measuring equipment shall permit measurement of the tendon force prior to lock-off to the degree of accuracy required by AS 2193 Grade B. The measuring equipment used shall permit elongation to be determined to an accuracy of ±2%. The equipment shall prevent unwinding of the strand during tensioning. The sag take-up force in the tendons shall be measured with equipment which complies with the repeatability and accuracy requirements of AS 2193 Grade B, at a scale mark at which the equipment has been calibrated. The readability requirements of AS 2193 Grade B shall be ignored for the purpose of establishing sag take-up. Sag take-up force shall not exceed 20% of the required tendon force, and shall be not less than 10% of the required tendon force or 10% of gauge capacity, whichever is the greater. Anchorages Anchorages shall be of a type that prevents the occurrence of slip during casting and curing operations. Tendon Force Before tensioning commences, the Contractor shall calculate the extension corresponding to the required tendon force shown on the drawings. The calculation shall be based on the measured length of the tendon between the tendon anchorages at the end blocks and the modulus of elasticity determined from the sample tested in accordance with Clause 622.02. The calculations shall include allowances for all losses including slip at anchorages, elastic shortening of the stressing bed, pull-in on transfer of prestress, friction losses and temperature changes. The calculations shall be reviewed by the designer of the pre-tensioned concrete units who shall certify that the calculations meet the requirements of the specification and the drawings. The Contractor shall provide a copy of the designer’s certification to the Superintendent. After all tendons have been anchored to the end-blocks (locked off), the force remaining in the tendons at mid-span of the unit shall be the required tendon force stated on the drawings. The allowable variation of the tendon force shall be ±2%. Under no circumstances shall the maximum tensioning force exceed the lesser of the rated capacity of the jacking equipment or 80% of the tensile strength of the tendon. The tensioning force required to achieve the design tendon force shall be determined from the calibration certificate and the actual elongation of the tendon corresponding to the tensioning force shall be recorded. Alternatively, the Superintendent may approve determination of the tensioning force by measurement of the elongation, provided that the limits of variation of the modulus of elasticity of the tendons are satisfactory. In this case, the jacking force shall be recorded. Should the modulus of elasticity of batches of tendons differ by more than 3%, the required elongation shall be adjusted accordingly. Where the difference between the force determined from the calibration certificate and the tensioning force calculated from the elongation exceeds 4%, the Contractor shall nominate some or all of the following remedial steps subject to review by the Superintendent. The Contractor shall suspend stressing until the completion of the Superintendent’s review: • re-calibration of tensioning equipment; • testing of tendon material to check the modulus of elasticity; • that tendons be released and restressed (with the adoption of a modulus of elasticity applicable to the second stressing); • other steps as agreed by the Superintendent.
Conformance: Method - Visual Inspection
Conformance: Frequency - For Stressing Jack and Guage
HCC Sign - HP
TAMS Group Sign - HP (If applicable)
2.1 - Tensioning Procedure
Reference(s) - 622.06 (d)
Supporting Documents - Refer to HCC tendon tensioning procedure
Acceptance Criteria - Tensioning Procedure All stressing operations shall be recorded on the daily stressing sheet Tensioning operations shall be performed by suitably trained and experienced personnel. Tensioning has been carried out in accordance with The Hollow Core Concrete Tensioning procedure document
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign - HP (Refer stress record Sheet for HPR)
2.11 - Transfer of prestress
Reference(s) - 622.08 a, b, c
Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings
Acceptance Criteria - Transfer of stress will only be permitted after the cylinder testing shows minimum of 40 MPa of compressive strength (as approved by the designer)
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign -
2.12 - Calibration certificates for Jack and Guage
Reference(s) - 622.06
Supporting Documents - Calibration certificates
Acceptance Criteria - Calibration certification will be conduct at six monthly intervals. Current certified equipment is being used.
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign -
2.13 - Data to be recorded
Reference(s) - 622.09
Supporting Documents - AS/NZ 4672.1 HCC Prestress Check List
Acceptance Criteria - Ensure the following data is recorded: • identification number of the unit; • identification number of each dynamometer, gauge, and jack; • calibration certificates for each dynamometer, gauge, and jack; • identification details for each tendon; • sag take-up force (or pressure) when tendons are marked for measurement of elongation; • elongation obtained at intervals during tensioning, together with corresponding force (or pressure gauge reading); • tendon force (or pressure) and elongation obtained on completion of tensioning prior to lock-off; • elongation after release of jack; • pull-in; • compressive strength of concrete at time of transfer of prestress; • steam curing charts; • measurement of hog following transfer of prestress. Completed records shall be forwarded to the Nominated Authority prior to delivery of the pre-stressed units to the site.
Conformance: Method - Measured / Visual Recorded
Conformance: Frequency - Every component
HCC Sign - HP
TAMS Group Sign -
2.14 - Protection of Exposed ends of Tendons
Reference(s) - 622.1
Supporting Documents - Mega poxy MSDS
Acceptance Criteria - If the ends of tendons are to remain exposed, they shall be wire-brushed to remove rust, loose mortar, grease, dirt and all other harmful material and shall then be coated with a minimum 6 mm thickness of epoxy compound.
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign -
2.15 - Concrete delivery
Reference(s) - 610.16
Supporting Documents - Concrete docket
Acceptance Criteria - Correct information on delivery docket
Conformance: Method - Visual
Conformance: Frequency - Each Load
HCC Sign - HP
TAMS Group Sign -
2.16 - Concrete Mix Design
Reference(s) - 610
Supporting Documents - Hanson concrete mix design letter
Acceptance Criteria - TU604AA62 150 Slump
Conformance: Method - Documented
Conformance: Frequency - All Components
HCC Sign - HP
TAMS Group Sign -
2.17 - Concrete slump test
Reference(s) - 610.16
Supporting Documents - AS1012.3.1 Concrete tester’s field sheet
Acceptance Criteria - 150mm slump = ±30mm (120mm to 180mm)
Conformance: Method - Measured / Visual
Conformance: Frequency - Each Load
HCC Sign - HP
TAMS Group Sign -
2.18 - Concrete compressive strength cylinders made
Reference(s) - 610.05 610.16 (L)
Supporting Documents - AS1012.8
Acceptance Criteria - Sets of 3 cylinders, also one cylinder to be used for early strength verification as required.
Conformance: Method - Visual
Conformance: Frequency - 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets
HCC Sign - HP
TAMS Group Sign -
2.19 - Concrete placement
Reference(s) - 610.18 (a), (d) 610.22
Supporting Documents - Daily observation will take place to monitor this process is followed
Acceptance Criteria - Time lag between trucks on site not to exceed 25 minutes Air bubbles released to surface without segregation of the mix Ensure segregation of the concrete does not occur by preventing free fall of concrete from anything greater than 2 meters Care shall be taken to fill every part of the forms or excavations, to force the concrete under and around the reinforcement without displacing it, to work coarse aggregate back from the face, and to remove air bubbles and voids. Concrete shall be deposited in horizontal layers not more than 350 mm thick. During and immediately after placing, the concrete shall be effectively compacted by vibrators of adequate size, number and frequency. ll be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs. Where internal vibrators are used, they shall be inserted vertically at at spacings not exceeding 250 mm spacings and shall not be allowed to rest on the steel reinforcement. Curing shall commence immediately following the progressive completion at any location of final finishing operations. Thermo Couples shall be placed Three per Unit as agreed with the super intendent.( One central in the Unit, another 25mm from the exposed face and edge of the unit, the third central in the unit 25 mm deep from the exposed face. Maximum temperature shall not exceed 75 degrees Celsius. Maximum differential temperature to be no greater than 20 degrees Celsius.
Conformance: Method - Visual
Conformance: Frequency - Every Load
HCC Sign - HP
TAMS Group Sign -
2.2 - Placement of the lifting lugs
Reference(s) - Certified Shop drawings
Supporting Documents - Shop drawings for each individual component drawings
Acceptance Criteria - Ensure all lifters are cast into position to within 20 mm tolerances from the design locations
Conformance: Method - Visual
Conformance: Frequency - Every unit
HCC Sign - HP
TAMS Group Sign -
2.21 - Evaporation retarding compound
Reference(s) - 610.17
Supporting Documents - Product MSDS
Acceptance Criteria - Apply aliphatic alcohol-based compound, as required, during initial finishing of concrete .
Conformance: Method - Visual
Conformance: Frequency - Every unit
HCC Sign - HP
TAMS Group Sign -
2.22 - Concrete finish
Reference(s) - 610.18 (d) (iii)
Supporting Documents - -
Acceptance Criteria - Requirements of the Project is exposed washed surface on top and off form class 2 finish to the sides and bottoms of the beams
Conformance: Method - Visual
Conformance: Frequency - Every Unit
HCC Sign - HP
TAMS Group Sign -
2.23 - Early age thermal cracking
Reference(s) - 610.22
Supporting Documents - HCC Thermal monitoring record sheet
Acceptance Criteria - Measures to be taken if least dimension exceeds 500mm thickness and one or, more faces are restrained. Thermal Couplers used,
Conformance: Method - Thermal monitoring
Conformance: Frequency - First Unit of each type of beam. If risks are identified, further sampling will be carried out
HCC Sign - HP
TAMS Group Sign -
3.1 - Concrete compressive strength
Reference(s) - 610.05
Supporting Documents - AS1012.8 Lifting Certificate HCC drawings
Acceptance Criteria - Requirements of the Project/Unit: Stripping strength = 40MPa 7 Day strength = 40MPa 28 Day strength = 50MPa
Conformance: Method - Schmidt Hammer NATA Laboratory
Conformance: Frequency - 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets Note: 3 cyls/ set
HCC Sign - HP
TAMS Group Sign -
3.2 - Units labelled
Reference(s) - 620.06
Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254
Acceptance Criteria - The identification number, date of casting, the manufacturer’s name or registered mark and the maximum mass shall be marked on every precast unit.
Conformance: Method - Visual
Conformance: Frequency - Each Unit
HCC Sign - HP
TAMS Group Sign -
3.3 - Curing (apply Sika Antisol AC curing compound)
Reference(s) - 610.23 (d), 610.231 AS3799
Supporting Documents - Manufacturer’s TDS CHAR(AMP) SDS
Acceptance Criteria - 2 coats with a minimum application rate of 0.2 litres/m².Keep record. Record rate of application. 1st coat to be applied within 30 minutes of stripping form work. Allow 3 hours between coats. Check box on label once the second coat is applied. Curing membrane shall be retained and maintained as per Table 610.231
Conformance: Method - Measured / Visual
Conformance: Frequency - Each Unit
HCC Sign - HP
TAMS Group Sign -
3.4 - Post-pour Inspection
Reference(s) - 610.30 610.46
Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254
Acceptance Criteria - Surface finish as per Project requirements (Class 3) Dimensions as per table 610.463 and 610.464.
Conformance: Method - Measured / Visual / Photographic
Conformance: Frequency - Each Unit
HCC Sign - HP
TAMS Group Sign -
3.5 - Cracking or any other imperfections to the product
Reference(s) - 610.24 (a) (b) Table 610.241 687
Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings
Acceptance Criteria - Refer to Table 610.241 for acceptable maximum crack widths. Cracks assessed by a technical specialist with a minimum of 5 years practical experience. Submit a crack repair procedure prior to any repair works being undertaken. If cracking is witnessed NCR will be raised and repair procedure selected following an inspection by the NA.
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign - HP
3.6 - Post pour dimensional checks
Reference(s) - 610.46
Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings
Acceptance Criteria - Ensure that post pour dimensional checks are carried out. Cast in items checked and noted. Concrete finishes are as per design drawings Curing applied
Conformance: Method - Measured / Visual
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign -
3.7 - Lifting product out of the mould
Reference(s) - 620.03
Supporting Documents - Refer to shop drawings HCC drawings
Acceptance Criteria - Minimum of 40 MPa strength required before lifting the components out of the mould.
Conformance: Method - Cylinder crack testing.
Conformance: Frequency - Each Lot
HCC Sign - HP
TAMS Group Sign -
3.8 - Post pour cover check
Reference(s) - 610.34
Supporting Documents - Record results on Cover check sheet
Acceptance Criteria - Test 3 square meters out of every 25m2 of surface. 10 tests or measurements must be recorder per 3 square meter sample area.
Conformance: Method - Written record
Conformance: Frequency - Each unit
HCC Sign - HP
TAMS Group Sign -
3.9 - Storage and stacking of the bridge planks
Reference(s) - 620.07 622
Supporting Documents - Rigging and Stacking Design Doc
Acceptance Criteria - Components shall only be lifted by the designated cast- in lifters. Components will be stacked simply supported by a bearer under each end directly under the cast in lifters. Maximum of 3 components to be stacked. Stacking will be in accordance with engineers design Bearers will be positioned in line with the cast in lifters. Bearers will be placed on a level concreted ground surface.
Conformance: Method - Visual Inspection
Conformance: Frequency - For all components
HCC Sign - HP
TAMS Group Sign -
3.1 - Product delivery
Reference(s) - 620.08, 610.26
Supporting Documents - Delivery Docket(s) Certificates of Compliance
Acceptance Criteria - Unit(s) to have achieved minimum 28 day compressive strength and must comply with table 610.261 prior to transporting. Components will be lashed down in accordance with engineers design. Chains will be directly above the bearers under the Beams. Beam edges will be protected using plastic angels to prevent damage from the tie down chains. Compliance certificates will be issued the day before delivery of components to site.
Conformance: Method - Written
Conformance: Frequency - Each Unit
HCC Sign - HP
TAMS Group Sign -