## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Stressed Beams | itp |  |  |  |  | ITP - Stressed Beams Rev10
section | 1.0 - Approvals and reviews
checkpoint | 1.1 - Submit Concrete mix design
label | Reference(s) - 610.07 (a) (b) Design spec drawings
label | Supporting Documents - Mix design and associated on going testing results
label | Acceptance Criteria - Strength, quality, colour, shrinkage must be as per the relevant contract specification.
label | ○ Approved mix design code TU604AA62
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to casting
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Submit ACRS certification of reinforcement and certification for the tendons
label | Reference(s) - Current ACRS certificate for all Tendons and reinforcing
label | Acceptance Criteria - Valid certificate provided
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to casting
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Radiant heat curing with curing compounds
label | Reference(s) - 610.23 (h) (g)
label | Supporting Documents - MSDS Complies with AS 3799
label | Acceptance Criteria - SikaFilm applied during finishing, covers installed after finishing of concrete.
label | ○ Radiant heat curing will occur until the Antisol AC sprayed or rolled over the components within 30 minutes of removing formwork.
label | Conformance: Method - Written
label | Conformance: Frequency - Every component
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Submit curing methodology
label | Reference(s) - 610.23 (a)
label | Supporting Documents - Product TDS, SDS & NATA Certificate
label | Acceptance Criteria - Curing compound meets or exceeds AS3799. Application rates noted.
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to casting
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Submit evaporative retardant (aliphatic alcohol- based)
label | Reference(s) - 610.17 (f)
label | Supporting Documents - Product TDS & SDS
label | Acceptance Criteria - Application rates noted.
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to casting
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Submit ITP for review
label | Reference(s) - 610.18 (a) (i)
label | Supporting Documents - This document
label | Acceptance Criteria - Written acceptance to proceed
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to casting
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Submit repair procedure for review
label | Reference(s) - 610.24 (b), 689.13
label | Supporting Documents - Repair Procedure/Methodology
label | Acceptance Criteria - Review and approval by Client
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to repairing components
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Ensure all shop drawings are IFC before casting the components
label | Reference(s) - HCC QMP
label | Supporting Documents - Stamped shop drawing
label | Acceptance Criteria - Shop drawings are to be IFC and numerical revision
label | Conformance: Method - Written
label | Conformance: Frequency - Prior to casting
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Stressing Calculations have been submitted for review
label | Reference(s) - 622.02
label | Supporting Documents - Stressing Calculations and chart
label | Acceptance Criteria - Stressing calculations are to be reviewed by project consultant
label | Conformance: Frequency - Once before commencement of casting Reviewed if changes occur during the course of the production
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Manufacturing Activities
checkpoint | 2.1 - Pre-pour inspection (external)
label | Reference(s) - 610.18 (a) (ii & iii)
label | Supporting Documents - Nominated authority’s checklist, Relevant shop drawings
label | Acceptance Criteria - Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to structural requirements and specifications.
label | ○ Moulds/formwork are clean and free from debris.
label | ○ 7 Day notification given via ACONEX. Any changes to be reported within 24 hours prior to the pour.
label | Conformance: Method - Measured / Visual
label | Conformance: Frequency - Each Unit
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pre-pour inspection (internal)
label | Reference(s) - 610.18 (a) (ii & iii)
label | Supporting Documents - HCC QMP Section 3.12 Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254
label | Acceptance Criteria - Product dimensions, cast in components, correct reinforcement, cover, lifting anchors etc. conform to shop drawings.
label | ○ Moulds/formwork are clean and free from debris.
label | Conformance: Method - Measured / Visual
label | Conformance: Frequency - Each Unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Check conditions prior to, during and post concrete delivery and placement
label | Reference(s) - 610.17 (a-f)
label | Supporting Documents - On-line Weather report and forecast
label | Acceptance Criteria - Ambient temperature not: < 5°C or > 35°C Concrete temperature not: < 10°C or > 32°C Weather condition: conducive to pour Evaporation Limits for Concreting Operations
label | ○ The Contractor shall be responsible for measuring and recording the air temperature, relative humidity, concrete temperature and wind velocity (measured one metre above the as placed concrete) at the point of concrete placement from commencement of placing the concrete and continue until curing has commenced. This information shall be used in conjunction with Figure 610.171 to determine the rate of evaporation of water from the freshly placed and unprotected surface of the concrete. The rate of evaporation shall be monitored by the Contractor until such time as curing commences.
label | ○ When the value of the rate of evaporation as determined from Figure 610.171 exceeds 0.50 kg/m² per hour the Contractor shall take precautions to minimise evaporative moisture losses such as the application of an aliphatic-alcohol based evaporative retarding compound or controlled fog spray.
label | ○ Application of evaporative retarding compound is required during pouring of concrete.
label | Conformance: Method - Measured / Visual
label | Conformance: Frequency - Each Lot
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Reinforcing placement and inspection
label | Reference(s) - 611
label | Supporting Documents - AS 5100 Component Check Sheets in the form of the product specific shop drawings HCC drawings 0001 TO 0254
label | Acceptance Criteria - Check against relevant shop drawing that all reinforcing bars are installed correctly, at the right centres and in a clean condition.
label | ○ Reinforcing bars spacing to be no less than 1.5 times the size of the largest aggregate. Correct bar laps to be observed.
label | ○ Correct radius in bends.
label | Conformance: Method - Visual/ measuring
label | Conformance: Frequency - Each component
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Cover verification
label | Reference(s) - 610.33, 610.26, 610.46, 611.10, AS 2425
label | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254 AS 5100.5
label | Acceptance Criteria - Requirements of the design documents. all around as per drawings.
label | ○ Ensure bar chairs comply with AS2425. (Higher cover for standard form work. Lower cover for rigid formwork with high intensive vibrators fitted to form work.)
label | ○ Tie wire not to intrude into cover zone. Maintain cover to rebar during concrete placing.
label | ○ Cover to be minimum 25 mm all around , 20mm on top (tolerance of 0 to +5mm).
label | Conformance: Method - Measure cover using measuring tape
label | Conformance: Frequency - Ensure 100% compliance of cover requirement Is achieved and witnessed Compliance must be recorded on check sheet drawings
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Tendons supply and traceability
label | Reference(s) - 622.03, 622.02
label | Supporting Documents - AS/NZ 4672, 4672.1.1 Component check sheet
label | Acceptance Criteria - 15.2mm strands used. ACRS supplied, Coil batch certification recorded, stressing design approved and documented by consulting engineer
label | ○ Strands Certificate of Compliance Designs, drawings and De-bond detail plan
label | Conformance: Method - Visual
label | Conformance: Frequency - All Components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Storage and surface condition of Tendons
label | Reference(s) - 622.2 (d)
label | Supporting Documents - AS/NZ 4672
label | Acceptance Criteria - Coils of wire and strand and assembled tendons shall be stored above ground level and shall be protected from mechanical damage, contamination with harmful substances or other damage until their incorporation into the works.
label | ○ Wires and strands that show any evidence of damage, kinks or bends shall not be used.
label | ○ Wires and strands which are heavily corroded or visibly pitted will not be accepted.
label | ○ Slight surface rusting shall not be a reason for rejection provided that no pitting is visible.
label | ○ Wire and strand shall be kept free from loose rust, oil, grease, tar, paint, soil or any other harmful substances.
label | ○ If the wire or strand become contaminated with any substance, it shall be cleaned with suitable equipment and appropriate detergents and/or clean water until all of the contaminant and any detergent has been removed satisfaction of the Superintendent.
label | ○ Loose rust shall be removed by mechanical or manual methods that do not cause damage to the wire or strand or which impair the bond between the wire or strand and the concrete.
label | Conformance: Method - Visual
label | Conformance: Frequency - All Coils
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Placing Tendons
label | Reference(s) - 622.04
label | Acceptance Criteria - Tendons shall be placed in continuous lengths in the positions shown on the drawings and shall be held in the required position by end-blocks of sufficient strength and stiffness to safely maintain the required force in the tendons.
label | ○ Tendons shall be de-bonded in the positions shown on the shop drawings.
label | ○ 19mm paper thin plastic sleeves will be used for de-bonding strands.. Grease or other coatings shall not be used for de-bonding.
label | ○ Tendons shall not be allowed to come into contact with the oiled surface of the formwork. If a tendon is contaminated with oil or other harmful substance it shall be cleaned using an appropriate method in order to ensure that the bond between the tendon and the concrete is unimpaired. Tendons that cannot be cleaned shall be replaced.
label | ○ Tendons shall not be welded or exposed to heat from welding or other sources.
label | ○ Where deflected tendons are shown on the drawings, tendons shall be restrained with devices of sufficient strength to hold the tendons in their proper positions without displacement during the placing and compaction of concrete.
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Tensioning, equipment, anchoring and Tendon force
label | Reference(s) - 622.06, 622.02 a, b, c and d
label | Supporting Documents - Calibration AS2193
label | Acceptance Criteria - Equipment
label | — Contractor shall maintain current calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devices. Jacks and pressure gauges and other devices shall be calibrated and used as a single unit. Calibration to AS 2193 shall be carried out by a laboratory that is NATA-accredited for that method, and at the appropriate force range.
label | — The power unit shall be adjusted so that the rate of extension of the tendon is within the specified limits. The measuring equipment shall permit measurement of the tendon force prior to lock-off to the degree of accuracy required by AS 2193 Grade B. The measuring equipment used shall permit elongation to be determined to an accuracy of ±2%. The equipment shall prevent unwinding of the strand during tensioning.
label | — The sag take-up force in the tendons shall be measured with equipment which complies with the repeatability and accuracy requirements of AS 2193 Grade B, at a scale mark at which the equipment has been calibrated. The readability requirements of AS 2193 Grade B shall be ignored for the purpose of establishing sag take-up. Sag take-up force shall not exceed 20% of the required tendon force, and shall be not less than 10% of the required tendon force or 10% of gauge capacity, whichever is the greater.
label | ○ Anchorages
label | — Anchorages shall be of a type that prevents the occurrence of slip during casting and curing operations.
label | ○ Tendon Force
label | — Before tensioning commences, the Contractor shall calculate the extension corresponding to the required tendon force shown on the drawings. The calculation shall be based on the measured length of the tendon between the tendon anchorages at the end blocks and the modulus of elasticity determined from the sample tested in accordance with Clause 622.02.
label | — The calculations shall include allowances for all losses including slip at anchorages, elastic shortening of the stressing bed, pull-in on transfer of prestress, friction losses and temperature changes.
label | — The calculations shall be reviewed by the designer of the pre-tensioned concrete units who shall certify that the calculations meet the requirements of the specification and the drawings. The Contractor shall provide a copy of the designer’s certification to the Superintendent.
label | — After all tendons have been anchored to the end-blocks (locked off), the force remaining in the tendons at mid-span of the unit shall be the required tendon force stated on the drawings.
label | — The allowable variation of the tendon force shall be ±2%.
label | — Under no circumstances shall the maximum tensioning force exceed the lesser of the rated capacity of the jacking equipment or 80% of the tensile strength of the tendon.
label | — The tensioning force required to achieve the design tendon force shall be determined from the calibration certificate and the actual elongation of the tendon corresponding to the tensioning force shall be recorded. Alternatively, the Superintendent may approve determination of the tensioning force by measurement of the elongation, provided that the limits of variation of the modulus of elasticity of the tendons are satisfactory. In this case, the jacking force shall be recorded.
label | — Should the modulus of elasticity of batches of tendons differ by more than 3%, the required elongation shall be adjusted accordingly.
label | ○ Where the difference between the force determined from the calibration certificate and the tensioning force calculated from the elongation exceeds 4%, the Contractor shall nominate some or all of the following remedial steps subject to review by the Superintendent. The Contractor shall suspend stressing until the completion of the Superintendent’s review:
label | — re-calibration of tensioning equipment;
label | — testing of tendon material to check the modulus of elasticity;
label | — that tendons be released and restressed (with the adoption of a modulus of elasticity applicable to the second stressing);
label | — other steps as agreed by the Superintendent.
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For Stressing Jack and Guage
label | HCC Sign - HP
label | TAMS Group Sign - HP (If applicable)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Tensioning Procedure
label | Reference(s) - 622.06 (d)
label | Supporting Documents - Refer to HCC tendon tensioning procedure
label | Acceptance Criteria - Tensioning Procedure
label | ○ All stressing operations shall be recorded on the daily stressing sheet
label | ○ Tensioning operations shall be performed by suitably trained and experienced personnel.
label | ○ Tensioning has been carried out in accordance with The Hollow Core Concrete Tensioning procedure document
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
label | TAMS Group Sign - HP (Refer stress record Sheet for HPR)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Transfer of prestress
label | Reference(s) - 622.08 a, b, c
label | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings
label | Acceptance Criteria - Transfer of stress will only be permitted after the cylinder testing shows minimum of 40 MPa of compressive strength (as approved by the designer)
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Calibration certificates for Jack and Guage
label | Reference(s) - 622.06
label | Supporting Documents - Calibration certificates
label | Acceptance Criteria - Calibration certification will be conduct at six monthly intervals. Current certified equipment is being used.
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.13 - Data to be recorded
label | Reference(s) - 622.09
label | Supporting Documents - AS/NZ 4672.1 HCC, Prestress Check List
label | Acceptance Criteria - Ensure the following data is recorded:
label | — identification number of the unit;
label | — identification number of each dynamometer, gauge, and jack;
label | — calibration certificates for each dynamometer, gauge, and jack;
label | — identification details for each tendon;
label | — sag take-up force (or pressure) when tendons are marked for measurement of elongation;
label | — elongation obtained at intervals during tensioning, together with corresponding force (or pressure gauge reading);
label | — tendon force (or pressure) and elongation obtained on completion of tensioning prior to lock-off;
label | — elongation after release of jack;
label | — pull-in;
label | — compressive strength of concrete at time of transfer of prestress;
label | — steam curing charts;
label | — measurement of hog following transfer of prestress.
label | ○ Completed records shall be forwarded to the Nominated Authority prior to delivery of the pre-stressed units to the site.
label | Conformance: Method - Measured / Visual Recorded
label | Conformance: Frequency - Every component
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.14 - Protection of Exposed ends of Tendons
label | Reference(s) - 622.1
label | Supporting Documents - Mega poxy MSDS
label | Acceptance Criteria - If the ends of tendons are to remain exposed, they shall be wire-brushed to remove rust, loose mortar, grease, dirt and all other harmful material and shall then be coated with a minimum 6 mm thickness of epoxy compound.
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.15 - Concrete delivery
label | Reference(s) - 610.16
label | Supporting Documents - Concrete docket
label | Acceptance Criteria - Correct information on delivery docket
label | Conformance: Method - Visual
label | Conformance: Frequency - Each Load
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.16 - Concrete Mix Design
label | Reference(s) - 610
label | Supporting Documents - Hanson concrete mix design letter
label | Acceptance Criteria - TU604AA62 150 Slump
label | Conformance: Method - Documented
label | Conformance: Frequency - All Components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.17 - Concrete slump test
label | Reference(s) - 610.16
label | Supporting Documents - AS1012.3.1 Concrete tester’s field sheet
label | Acceptance Criteria - 150mm slump = ±30mm (120mm to 180mm)
label | Conformance: Method - Measured / Visual
label | Conformance: Frequency - Each Load
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.18 - Concrete compressive strength cylinders made
label | Reference(s) - 610.05, 610.16 (L)
label | Supporting Documents - AS1012.8
label | Acceptance Criteria - Sets of 3 cylinders, also one cylinder to be used for early strength verification as required.
label | Conformance: Method - Visual
label | Conformance: Frequency - 0–10m³ = 1 set
label | ○ 10-25m³ = 2 sets 25-50m³ = 3 sets
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.19 - Concrete placement
label | Reference(s) - 610.18 (a), (d) 610.22
label | Supporting Documents - Daily observation will take place to monitor this process is followed
label | Acceptance Criteria - Time lag between trucks on site not to exceed 25 minutes
label | ○ Air bubbles released to surface without segregation of the mix
label | ○ Ensure segregation of the concrete does not occur by preventing free fall of concrete from anything greater than 2 meters
label | ○ Care shall be taken to fill every part of the forms or excavations, to force the concrete under and around the reinforcement without displacing it, to work coarse aggregate back from the face, and to remove air bubbles and voids.
label | ○ Concrete shall be deposited in horizontal layers not more than 350 mm thick.
label | ○ During and immediately after placing, the concrete shall be effectively compacted by vibrators of adequate size, number and frequency.
label | ○ ll be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
label | ○ Where internal vibrators are used, they shall be inserted vertically at at spacings not exceeding 250 mm spacings and shall not be allowed to rest on the steel reinforcement.
label | ○ Curing shall commence immediately following the progressive completion at any location of final finishing operations.
label | ○ Thermo Couples shall be placed Three per Unit as agreed with the super intendent.( One central in the Unit, another 25mm from the exposed face and edge of the unit, the third central in the unit 25 mm deep from the exposed face.
label | ○ Maximum temperature shall not exceed 75 degrees Celsius.
label | ○ Maximum differential temperature to be no greater than 20 degrees Celsius.
label | Conformance: Method - Visual
label | Conformance: Frequency - Every Load
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.20 - Placement of the lifting lugs
label | Reference(s) - Certified Shop drawings
label | Supporting Documents - Shop drawings for each individual component drawings
label | Acceptance Criteria - Ensure all lifters are cast into position to within 20 mm tolerances from the design locations
label | Conformance: Method - Visual
label | Conformance: Frequency - Every unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.21 - Evaporation retarding compound
label | Reference(s) - 610.17
label | Supporting Documents - Product MSDS
label | Acceptance Criteria - Apply aliphatic alcohol-based compound, as required, during initial finishing of concrete .
label | Conformance: Method - Visual
label | Conformance: Frequency - Every unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.22 - Concrete finish
label | Reference(s) - 610.18 (d) (iii)
label | Acceptance Criteria - Requirements of the Project is exposed washed surface on top and off form class 2 finish to the sides and bottoms of the beams
label | Conformance: Method - Visual
label | Conformance: Frequency - Every Unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.23 - Early age thermal cracking
label | Reference(s) - 610.22
label | Supporting Documents - HCC Thermal monitoring record sheet
label | Acceptance Criteria - Measures to be taken if least dimension exceeds 500mm thickness and one or, more faces are restrained. Thermal Couplers used,
label | Conformance: Method - Thermal monitoring
label | Conformance: Frequency - First Unit of each type of beam. If risks are identified, further sampling will be carried out
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Post-Manufacturing Activities
checkpoint | 3.1 - Concrete compressive strength
label | Reference(s) - 610.05
label | Supporting Documents - AS1012.8 Lifting Certificate HCC drawings
label | Acceptance Criteria - Requirements of the Project/Unit: Stripping strength = 40MPa
label | ○ 7 Day strength = 40MPa
label | ○ 28 Day strength = 50MPa
label | Conformance: Method - Schmidt Hammer NATA Laboratory
label | Conformance: Frequency - 0–10m³ = 1 set 10-25m³ = 2 sets 25-50m³ = 3 sets
label | ○ Note: 3 cyls/ set
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Units labelled
label | Reference(s) - 620.06
label | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254
label | Acceptance Criteria - The identification number, date of casting, the manufacturer’s name or registered mark and the maximum mass shall be marked on every precast unit.
label | Conformance: Method - Visual
label | Conformance: Frequency - Each Unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Curing (apply Sika Antisol AC curing compound)
label | Reference(s) - 610.23 (d), 610.231 AS3799
label | Supporting Documents - Manufacturer’s TDS & SDS
label | Acceptance Criteria - 2 coats with a minimum application rate of 0.2 litres/m². Keep record.
label | ○ Record rate of application.
label | ○ 1st coat to be applied within 30 minutes of stripping form work. Allow 3 hours between coats. Check box on label once the second coat is applied.
label | ○ Curing membrane shall be retained and maintained as per Table 610.231
label | Conformance: Method - Measured / Visual
label | Conformance: Frequency - Each Unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Post-pour Inspection
label | Reference(s) - 610.30, 610.46
label | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings HCC drawings 0001 TO 0254
label | Acceptance Criteria - Surface finish as per Project requirements (Class 3)
label | ○ Dimensions as per table 610.463 and 610.464.
label | Conformance: Method - Measured / Visual / Photographic
label | Conformance: Frequency - Each Unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Cracking or any other imperfections to the product
label | Reference(s) - 610.24 (a) (b) Table 610.241 687
label | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings, HCC drawings
label | Acceptance Criteria - Refer to Table 610.241 for acceptable maximum crack widths. Cracks assessed by a technical specialist with a minimum of 5 years practical experience.
label | ○ Submit a crack repair procedure prior to any repair works being undertaken.
label | ○ If cracking is witnessed NCR will be raised and repair procedure selected following an inspection by the NA.
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
label | TAMS Group Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Post pour dimensional checks
label | Reference(s) - 610.46
label | Supporting Documents - Post-pour Check Sheet in the form of the product specific shop drawings, HCC drawings
label | Acceptance Criteria - Ensure that post pour dimensional checks are carried out.
label | ○ Cast in items checked and noted. Concrete finishes are as per design drawings
label | ○ Curing applied
label | Conformance: Method - Measured / Visual
label | Conformance: Frequency - For all components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Lifting product out of the mould
label | Reference(s) - 620.03
label | Supporting Documents - Refer to shop drawings HCC drawings
label | Acceptance Criteria - Minimum of 40 MPa strength required before lifting the components out of the mould.
label | Conformance: Method - Cylinder crack testing.
label | Conformance: Frequency - Each Lot
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Post pour cover check
label | Reference(s) - 610.34
label | Supporting Documents - Record results on Cover check sheet
label | Acceptance Criteria - Test 3 square meters out of every 25m2 of surface. 10 tests or measurements must be recorder per 3 square meter sample area.
label | Conformance: Method - Written record
label | Conformance: Frequency - Each unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.9 - Storage and stacking of the bridge planks
label | Reference(s) - 620.07, 622
label | Supporting Documents - Rigging and Stacking Design Doc
label | Acceptance Criteria - Components shall only be lifted by the designated cast- in lifters.
label | ○ Components will be stacked simply supported by a bearer under each end directly under the cast in lifters. Maximum of 3 components to be stacked.
label | ○ Stacking will be in accordance with engineers design
label | ○ Bearers will be positioned in line with the cast in lifters. Bearers will be placed on a level concreted ground surface.
label | Conformance: Method - Visual Inspection
label | Conformance: Frequency - For all components
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Product delivery
label | Reference(s) - 620.08, 610.26
label | Supporting Documents - Delivery Docket(s) Certificates of Compliance
label | Acceptance Criteria - Unit(s) to have achieved minimum 28 day compressive strength and must comply with table 610.261 prior to transporting.
label | ○ Components will be lashed down in accordance with engineers design. Chains will be directly above the bearers under the Beams.
label | ○ Beam edges will be protected using plastic angels to prevent damage from the tie down chains.
label | ○ Compliance certificates will be issued the day before delivery of components to site.
label | Conformance: Method - Written
label | Conformance: Frequency - Each Unit
label | HCC Sign - HP
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 - Lot Conformance & Notes
checkpoint | Lot Conformance & Notes
bool | Lot conforms
textbox | Non-conformances raised for this lot:
bool | Non-conformances closed out
label | Hollow Core Representative’s Name:
bool | Aidan Collins
bool | Balint Djeri
bool | Chelsy Grieef
date | Date:
holdpoint | Hollow Core Representative’s Signature: