## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 02.01 - Traffic Management | itp
section | Details
checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
label | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.2
checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
label | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
label | Check Item - Hold Point 1
label | Reference - MRTS02 Cl. 5.3
holdpoint | Hold Point
checkpoint | All traffic control devices inspected and records kept in accordance with the specification
label | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.6.4
checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
label | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.6.5
checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
label | Acceptance Criteria and Frequency (Project Specific) - TMD sign off of TGS and, RPEQ Risk Assessment as required
label | Check Item - Hold Point 2
label | Reference - MRTS02 Cl. 6.2
holdpoint | Hold Point
checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
label | Check Item - Milestone
label | Reference - MRTS02 Cl. 7.5
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs | itp
section | Details
checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.4
checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Kerb excavations shall be backfilled to flush with the surrounding area.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.10 - Supply and Installation of Precast Concrete Culverts | itp
section | Details
checkpoint | Maximum Lot Size - 1 Culvert
label | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.2
checkpoint | Concrete Pipe culvert components comply with MRTS25/26, FRCP with Slotted Drain Insert Complies with MRTS26
label | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | All pipes of diameter 800 mm or less shall have spigot and socket joints with rubber sealing rings. Joints for other sizes shall be as specified on the drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | Component size, wall thickness and class is as specified in the drawings
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS03 Cl11.2
holdpoint | Hold Point
checkpoint | Culvert Construction Procedures to be accepted prior to commencement of Installation
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS03 Cl11.3.1
holdpoint | Hold Point
checkpoint | Load testing of non standard pipes ordered for specific projects shall be a witness point
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - Annexure MRTS26.1 Cl 2
section | Excavation
checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earth works
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl.11.3.1
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL.11.3
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | Hold Point
checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation -RDD Q140A
label | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b), CV 95% minimum (1 tests / 50m2 - min 2 / lot)
label | Check Item - Test results
label | Reference - MRTS04 Table A.2
section | Culvert Installation
checkpoint | Components are assembled as per manufaturers specifications, and if possible, contruction commenced at outlet
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.3, Cl11.3.4
checkpoint | Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | The pipes shall be laid with the lifting hole or "TOP" marking uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | The horizontal alignment of culverts shall not vary from the location specified in the Drawings by more than ± 100 mm
label | Acceptance Criteria and Frequency (Project Specific) - ± 100mm (All points shown on drawings - min 1 per 20m or 2 points)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.8.2
checkpoint | The invert heights of culverts shall not vary from those specified by more than ± 10 mm and nowhere shall the grades of culverts depart from those specified by more than 1%
label | Acceptance Criteria and Frequency (Project Specific) - ± 10mm, ± 1% grade (All points shown on drawings - min 1 per 20m or 2 points)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.8.3
section | FRCP with Slotted Drain Installation
checkpoint | Fibre-reinforced concrete pipes shall be designed for installation in accordance with AS/NZS 3725. Construction load cases shall be considered in accordance with Clause 5.5.1. Designs already completed to AS 5100.2 shall be deemed to comply with these requirements.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS26.1 Cl 2, MRTS26 5.5
checkpoint | FRCP: The maximum angle of deflection of joints for pipes is two degrees
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS26.1 Cl 2, MRTS26 11
checkpoint | For the specified pipe class and size, the contractor shall progressively backfill the pipe using the fill depth and construction equipment permissible in Table B1 of AS/NZS 3725.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS26.1 Cl 2, MRTS26 11
section | Backfill
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS03 11.3.10
holdpoint | Hold Point
checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, etc have been completed and inspected, and any specified curing periods have elapsed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 14
label | Reference - MRTS04 Cl.19.3.3
holdpoint | Hold Point
checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 excep 100% material shall pass 25.0mm test sieve.
label | Acceptance Criteria and Frequency (Project Specific) - Class A1:
label | ○ Class A2:
label | ○ Class B:
label | ○ Except: 100% passing 25mm
label | Check Item - Witness Point
label | Reference - MRTS04 19.3.1, 19.2.2 Table 14.2.2
checkpoint | Compaction - Q142A, Q141B
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(b)
checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria and Frequency (Project Specific) - Class A1/A2: 70-100%
label | ○ Class B: 80-110%
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(c)
section | Completion
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator. Visual inspection may be approved by the Administrator in lieu of CCTV inspection.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS03 Cl11.3.5
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ | itp
section | Details
checkpoint | Maximum Lot Size - 1 Culvert
label | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.2
checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
label | Acceptance Criteria and Frequency (Project Specific) - Administrator Approval - Per Project
label | Check Item - Hold Point 2
label | Reference - MRTS03 Cl 11.3.1
holdpoint | Hold Point
section | Excavation
checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
label | Check Item - Check Item
label | Reference - MRTS03 Cl 12.3.1
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
textbox | Reference Unsuitable Lot No. :
label | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl 9.4
holdpoint | Hold Point
checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation - AS 1289.5.4.1 or AS1289.5.7.1
label | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b)
label | ○ CV 95% minimum (1 tests / 50m2 - min 2 / lot)
label | Check Item - Test results
label | Reference - MRTS04 Table A.2
section | Installation
checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 & MRTS71
label | Acceptance Criteria and Frequency (Project Specific) - MRTS03
label | ○ Cl.15: End Structures
label | ○ Cl.21: Gullies
label | ○ Cl.21: Access Chambers
label | Check Item - Check Item
label | Reference - MRTS03 Cl.6.1
checkpoint | Precast: Installed in accordance with MRTS03 - Components shall be laid on a foundation bedding which provides continuous even support to the structures.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | ○ Cl.19: Precast End Structures
label | ○ Cl.21: Precast Gullies
label | ○ Cl.21.5.1 Precast Access Chamber
label | Check Item - Check Item
label | Reference - MRTS03
label | ○ Cl. 16
label | ○ Cl. 21
label | ○ Cl. 21.5.1
checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 21.3
section | Tolerances
checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
label | Acceptance Criteria and Frequency (Project Specific) - ±50mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
label | Acceptance Criteria and Frequency (Project Specific) - ±10mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
label | Acceptance Criteria and Frequency (Project Specific) - Gullies:
label | ○ ±100mm in road direction
label | ○ ±50mm perpendicular to road
label | Access Chambers:
label | ○ ±100mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.1
checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5, Hold Point 6
label | Reference - MRTS03 Cl.21.3
holdpoint | Hold Point
section | Backfill
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS03 11.3.10
holdpoint | Hold Point
checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
label | Acceptance Criteria and Frequency (Project Specific) - Quarry Material Test Results
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl. 14.2.1
holdpoint | Hold Point
checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
label | Acceptance Criteria and Frequency (Project Specific) - Test Results
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl. 19.3.1
checkpoint | Hold Point 12
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 12
label | Reference - MRTS04 Cl.19.3.3
holdpoint | Hold Point
checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
label | Acceptance Criteria and Frequency (Project Specific) - Class A: WPI < 1200, PI > 7,
label | ○ % passing 0.075mm: 15 - 30
label | ○ Class B: 1200 < WPI < 2200
label | ○ Class A/B: 100% passing 25mm
label | Check Item - Witness Point
label | Reference - MRTS04 19.3.1, 19.2.2
checkpoint | Compaction - Q142A, Q141B
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(b), MRTS03.1 Cl.1
checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria and Frequency (Project Specific) - Class A: 70-100%
label | ○ Class B: 80-110%
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(c)
section | Completion
checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS03 Cl. 21.6.2
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS03 Cl11.3.5
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.22 - Subsoil Drainage | itp
section | Details
checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
checkpoint | Backfill materialshall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 22.3
checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 22.3
checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.2
checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.3 TMR SD 1116
checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.2.7 TMR SD 1116
checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS03 Cl22.3
checkpoint | As Constructed drawings prepared
label | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
label | Check Item - Witness Point
checkpoint | All geometric tolerance requirements met
label | Acceptance Criteria and Frequency (Project Specific) - Survey
label | Check Item - Check Item
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 03.35 - Rock Protection | itp
section | Details
checkpoint | Rock employed as per drawings. If not specified, between 150 - 500mm, with at least 50% larger than twice the minimum size
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Check Item
label | Reference - MRTS03 Cl 35.2
checkpoint | Uniform appearance overall, and shall not have noticeable overall irregularities in horizontal and vertical alignments. The layers of placed rock shall be of even thickness and of even grading
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Check Item
label | Reference - MRTS03 Cl 35.3
checkpoint | Ordering Geotextile - Documentation which demonstrates that the design of the geotextile is in accordance with MRTS27 Cl. 6 submitted to the administrator and accepted prior to ordering.
label | Acceptance Criteria and Frequency (Project Specific) - Written Approval
label | Check Item - Hold Point 1
label | Reference - MRTS27 Cl 8.1
holdpoint | Hold Point
checkpoint | Geotextile - Inspection of product to be incorporated into works. Where Lot sites are greater than 5000m2, a representative sample covering approximately 15 m² of geotextile shall be cut from each sampled roll but not within two metres of the start or end of the roll. Where directed by the Administrator, samples shall also be cut and supplied to the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Witness Point 1
label | Reference - MRTS27 Cl 10.2
checkpoint | Compliance of delivered Geotextile - Geotextile shall not be placed prior to acceptance of the test results by the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual Inspection
label | Check Item - Hold Point 2
label | Reference - MRTS27 Cl 10.4
holdpoint | Hold Point
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.07 - Clear and Grub | itp
section | Details
checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS04 Cl. 7.2.2
holdpoint | Hold Point
checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 1.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS04 Cl. 7.2.3
holdpoint | Hold Point
checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area shall be installed.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | Hold Point
checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.5
checkpoint | Surplus topsoil material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.2
checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2, Cl 1.4
checkpoint | The additional width for clearing (no grubbing) is 3.0m as per Annexure MRTS04.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - Annexure MRTS04.1
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.3
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.09 - Unsuitable Material | itp
section | Details
checkpoint | The identification of unsuitable material shall include items listed in MRTS04 Cl. 9.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 9.2
checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | Hold Point
checkpoint | Excavated as per MRTS04
label | Acceptance Criteria and Frequency (Project Specific) - MRTS04 (General Excavation ITP)
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13
checkpoint | Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 and notice of such Works provided to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Survey Report
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.2
checkpoint | Backfill as per MRTS04. Replacement fill material shall be placed uniformly in layers and compacted using compacted layer method.
label | Acceptance Criteria and Frequency (Project Specific) - MRTS04 (Backfill ITP)
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3, MRTS04 Cl 15.3
checkpoint | After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken.
label | Acceptance Criteria and Frequency (Project Specific) - Survey Report
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.2
checkpoint | All surplus material and/or Unsuitable Material shall be disposed of off the Site
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 11.3
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.12 - Ground Surface Treatment | itp
section | Details
checkpoint | Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the Site which could reasonably be expected to have a possible acid sulfate potential.
label | Acceptance Criteria and Frequency (Project Specific) - Field pH testing As per National Acid Sulfate Soils Guidance
label | Check Item - Hold Point 5
label | Reference - MRTS04 Cl. 10.1.4 Table A2
holdpoint | Hold Point
checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 12.2.1.1
checkpoint | Holes and localised depressions filled with similar material to the surrounding ground surface or material specified and compacted in accordance with Cl. 15
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 12.2.1.2
checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | Hold Point
checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl. 15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a maximum depth of 300mm using appropriate methods. Material below this depth shall be assesed under Clause 9.2.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 12.2.1.3
checkpoint | Relative Compaction - AS 1289.5.4.1 or AS 1289.5.7.1. After any clearing and grubbing, stripping of Topsoil and replacement of Unsuitable Material, the exposed ground surface on which an Embankment is to be placed shall, as a minimum, be scarified and re-compacted to a depth of at least 150 mm
label | Acceptance Criteria and Frequency (Project Specific) - CV 95% minimum - 1 tests per 500 m2 (min 1 per lot)
label | Check Item - Test
label | Reference - MRTS04 Table 15.3(b) App. A
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.13 - General Excavation | itp
section | Details
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | Hold Point
checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl. 13.3.2.1
holdpoint | Hold Point
checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
label | Acceptance Criteria and Frequency (Project Specific) - Survey
label | Check Item - Check Item
label | Reference - MRTS04 Cl.13.3.1, Cl. 6
checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.3.3
checkpoint | Dewatering of excavations shall comply with requirements of EMP
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.8
checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 16.1
checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.4
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.14 - Embankment | itp
section | Details
checkpoint | Earthworks construction procedure shall be sumbitted to the Administrator at least seven days prior to commencing the Works.
label | Acceptance Criteria and Frequency (Project Specific) - Construction Procedure Acceptance
label | Check Item - Hold Point 1
label | Reference - MRTS04 Cl. 5.2
holdpoint | Hold Point
checkpoint | Define lot size.
label | Acceptance Criteria and Frequency (Project Specific) - Normal : Max 2000m2
label | ○ Reduced Level : Max 4000m2
label | Check Item - Check Item
label | Reference - MRTS04 App. A Table A.2
checkpoint | Earth Fill Material stockpile or source material results submitted to Administarator
textbox | Reference Stockpile Lot No. :
label | Acceptance Criteria and Frequency (Project Specific) - Stockpile Lot Acceptance
label | Check Item - Hold Point 10
label | Reference - MRTS04 Cl. 14.2.1
holdpoint | Hold Point
checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported, complies with General fill Class A1, A2 or B and is homogeneous.
label | Acceptance Criteria and Frequency (Project Specific) - Stockpile Lot MRTS04 Table 14.2.2
label | Check Item - Test reports
label | Reference - MRTS04 Cl. 14.3.1
checkpoint | Compacted Layer Method:
label | Fill material placed uniformly in layers. Uncompacted layer thicknesses;
label | – General Fill 150-300m
label | – Fill material in water-retaining embankments 150- 200mm
label | – Backfill except Sand 100-150mm
label | – Sand 150-300mm
label | Fill compacted to required density (by Characteristic Value)
label | Acceptance Criteria and Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
label | ○ Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level≥95%
label | ○ Normal: 1 per 500m2 (per layer), 4 per lot
label | ○ Reduced Level: 1 per 1000m2 (per layer) or 4 per lot
label | Check Item - Test reports
label | Reference - MRTS04 Cl. 15.3 Table 15.3(b)
checkpoint | Compacted Layer Method: Embankment moisture ratio within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria and Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
label | ○ Class A1/A2: 70 - 100
label | ○ Class B: 80 - 110
label | ○ Normal : 1 per 500m2/layer or 4 per lot
label | ○ Reduced Level : 1 per 1000m2/layer or 4 per lot
label | Check Item - Test results
label | Reference - MRTS04 Cl. 15.3 Table 15.3(c)
checkpoint | Testing of Each Layer - Each layer shall be tested to conform the requirements as per Clause 5.6 before placing the subsequent layers.
label | Acceptance Criteria and Frequency (Project Specific) - Testing after compaction on site
label | ○ Gradings: AS1289.3.6.1
label | ○ PI: AS1289.3.3.1 or AS1289.3.3.2
label | ○ WPI: Test Method Q252
label | ○ 1 per 1000m2(per Layer), 2 per Lot
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl. 15.3
checkpoint | Mechanical Interlock Method: Each layer rolled until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
label | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
label | Check Item - Witness Point 6
label | Reference - MRTS04 Cl15.4
checkpoint | Geotextile placed at interchange between compaction methods
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 14.3.2
checkpoint | Within Vertical Geometric Tolerance
label | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25
label | ○ average ± 10
label | ○ 1 test /20m
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 04.181 - Subgrade Level | itp
section | Details
checkpoint | Define Lot
label | Acceptance Criteria and Frequency (Project Specific) - Normal: Max Lot Size : 2000m2
label | ○ Reduced: Max Lot Size : 4000m2
label | Check Item - Lot Records
label | Reference - MRTS04 App A
checkpoint | Reporting Pavement Design Requirements
label | For Contracts where the Principal has supplied the pavement design (that is, Construct Only or similar Contracts), the Contractor shall submit the following information to the Administrator for each existing Subgrade Lot:
label | a) test pit logs
label | b) all test results for each layer encountered within the test pit, including certified test certificates, and
label | c) marked-up drawings accurately showing all test locations within the Lot.
label | The Contractor shall allow a minimum period of 14 days for the Administrator to review the information prior to any Subgrade treatment and the placement of any overlying materials.
label | Acceptance Criteria and Frequency (Project Specific) - Submission to Administrator
label | Check Item - Hold Point 16
label | Reference - MRTS04 App B.6.1
holdpoint | Hold Point
checkpoint | Bottom of Excavation for Cuttings - Where subgrade is reached in cutting works shall cease until subgrade treatment type has been directed by the Administrator in accordance with Clause 13.3.2.1
textbox | Subgrade Treatment Type Directed:
label | Acceptance Criteria and Frequency (Project Specific) - As directed by Administrator
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl13.3.2.1, Cl 18.3.3
holdpoint | Hold Point
checkpoint | Subgrade Treatment Type A - As ordered by the Administrator at subgrade level on all section. The material below Subgrade Level shall be to compacted a density of not less than that stated in Table 15.3(b) and to a depth of 150 mm.
label | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 150mm
label | ○ Compaction Standard: min 97%
label | ○ Normal: 1 per 500m2, 4 per lot
label | ○ Reduced: 1 per 1000m2, 1 per lot
label | Check Item - Test Reports
label | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
checkpoint | Subgrade Treatment Type C - Replace with unbound granular material. As ordered by the Administrator at subgrade in cuttings and embankment. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and a depth of 200mm (or as directed by Administrator).
label | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 200mm
label | ○ Compaction Standard: min 100%
label | ○ Normal: 1 per 500m2, 4 per lot
label | ○ Reduced: 1 per 1000m2, 1 per lot
label | Check Item - Test Reports
label | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
checkpoint | Subgrade Treatment Type E - Replace with plant-mixed stabilised material. As ordered by the Administrator at subgrade in cuttings and embankment. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and a depth of 200mm (or as directed by Administrator).
label | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 200mm
label | ○ 102% standard upper most layer
label | ○ 100% standard lower layers
label | ○ (1/500m2, min 4/lot)
label | ○ (1/1000m2, min 4/lot)
label | Check Item - Test Reports
label | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
checkpoint | Subgrade Treatment Type I - High-permiability drainage layer. Drainage Layer Required. As ordered by the Administrator at subgrade in cuttings and embankment. The material below subgrade level shall be to a depth of 200mm (or as directed by Administrator). The drainage layer shall be wrapped in a non-woven geotextile in accordance with MRTS27.
label | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 300mm
label | ○ 70% (Density Index)
label | ○ Normal: 1 per 2500t, 1000m3
label | ○ Reduced: 1 per 5000tn, 2000m3
label | Check Item - Test Reports
label | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1 Table 15.3(b)
checkpoint | Subgrade Emabankment - Material to be compacted to requirements not less than that specified in Table 15.3(b). Subgrade relative density tested to Q140A.
textbox | Material Source Stockpile Lot Ref:
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below subgrade level -
label | ○ Embankment Fill at subgrade: Class A1, B, Unbound Granular or stabilised material : min 97%
label | ○ Normal: 1 per 500m2, 4 per lot
label | ○ Reduced: 1 per 1000m2, 4 per lot
label | Check Item - Test Reports
label | Reference - MRTS04 Cl15.3(b) App A
checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
label | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
label | – 10,000L water tanker with 600kPa tyre pressure.
label | Acceptance Criteria and Frequency (Project Specific) - Visual. No Deflection. Continuous
label | Check Item - Witness Point 8
label | Reference - MRTS04 Cl18.3.2 Q723
checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
label | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25
label | ○ average ± 10
label | ○ 1 test /20m
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
label | Acceptance Criteria and Frequency (Project Specific) - 1 test per 20m (Left and rigt)
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6.3.2
checkpoint | Subgrade shall not pond water and be free draining.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Clause 6.3.2
checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 12
label | Reference - MRTS04 Cl. 18.3.1
holdpoint | Hold Point
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 05.01 - Unbound Pavement | itp
section | Details
checkpoint | Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
label | Acceptance Criteria and Frequency (Project Specific) - Supply of unbound pavement materials - 5000tn
label | ○ Maximum lot size - A continuous single layer constructed in 1 day's production
label | ○ Road roughness testing: maximum lot size 100m
label | Check Item - Check Item
label | Reference - MRTS05 App. A Table A1
checkpoint | Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Registration Certificate per quarry
label | Check Item - Milestone
label | Reference - MRTS05 Cl.6.2
checkpoint | No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS05 Cl 5.2.1
holdpoint | Hold Point
checkpoint | The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the works.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of production procedure
label | Check Item - Milestone
label | Reference - MRTS05 CL 5.2.2
checkpoint | Submission of Construction Procedure for unbound pavement construction at least 14 days prior to commencement of works.
label | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
label | Check Item - Milestone
label | Reference - MRTS05 Cl 5.2.3
checkpoint | The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works.
label | Acceptance Criteria and Frequency (Project Specific) - Written Permission from Administrator
label | Check Item - Hold Point 2
label | Reference - MRTS05 Cl.6.1
holdpoint | Hold Point
checkpoint | Layer Thickness between 75mm and 250mm for all subtypes excluding Type 1 (HSG).
label | Acceptance Criteria and Frequency (Project Specific) - Visual, Layer Thickness 75mm - 250mm
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.3
checkpoint | Minimum value of Relative Dry Density Requirements - C.V of RDD = 100% MDD for Base course 2.1, 2.2, = 100% SDD for other than base course 2.1, 2.2 and 100% SSD for all layers of 2.3, 2.4 and 2.5.
label | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD
label | ○ Normal: 1 test / 500m2, 4 per lot,
label | ○ Reduced: 1 test / 1000m2, 4 per lot
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.4.3
checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
label | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
label | Check Item - Hold Point 3
label | Reference - MRTS05 Cl. 8.2
holdpoint | Hold Point
checkpoint | Moisture content such that the degree of saturation is less than 70%(modified).
label | Acceptance Criteria and Frequency (Project Specific) - S < 70%
label | ○ Normal: 1 test / 500m2, 4 per lot,
label | ○ Reduced: 1 test / 1000m2, 4 per lot
label | Check Item - Hold Point 4
label | Reference - MRTS05 Table 8.3.4.1
holdpoint | Hold Point
checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
label | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
label | ○ Additional tests as directed by the Administrator
label | Check Item - Check Item
label | Reference - MRTS05 Table A3
checkpoint | Geometric Tolerances in accordance with MRTS05 Cl.8.4.4.3
label | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
label | ○ ±15 mm in all other cases (1 test / 20m)
label | Check Item - Check Item
label | Reference - MRTS05.1 Cl.8.4.4.3
checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
label | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.4.2 Table A4
checkpoint | Deviation from a 3m straight edge shall be less than 5mm for material types 1,2,3 and 4
label | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
label | ○ Less than 5mm
label | ○ 1 test per 20m
label | Check Item - Check Item
label | Reference - MRTS05 Cl. 8.4.5
checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
label | Check Item - Witness Point 2
label | Reference - MRTS05 Cl.9.4.7
checkpoint | Additional Geometrics (final layer only) - The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
label | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.4.4
checkpoint | The contractor shall provide a methodology and calculations to determine the road roughness to the administrator for acceptance. Roughness shall be less than 2.31m/km.
label | Acceptance Criteria and Frequency (Project Specific) - Less than 2.31m/km
label | ○ 1 test per 500m
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.6
checkpoint | The finished surface of any unbound pavement layer shall:
label | – be hard and homogenous in apperance
label | – not have any loose, segregated or contaminated areas
label | – have the coarse particles slightly exposed
label | – not be affected by delamination
label | – not show signs of water pumping, and
label | – not visibly deflect under load when proof rolled in accordance with Cl 9.4.7
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.3.5.1
checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
label | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
label | Check Item - Hold Point 5
label | Reference - MRTS05 Cl.9.1
holdpoint | Hold Point
checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
label | a) all testing has been completed
label | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
label | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
label | d) the layer has been presented to the Administrator for inspection, and
label | e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
label | Check Item - Hold Point 6
label | Reference - MRTS05 Cl.9.5.1
holdpoint | Hold Point
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 10.01 - Plant Mixed Lightly Bound Pavements | itp
section | Details
checkpoint | Construction Procedure: Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator)
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 1, Milestone
label | Reference - Clause 5.2 MRTS10
holdpoint | Hold Point
checkpoint | Material Requirements - Unbound Pavement Material: The Contractor shall not incorporate unbound pavement material into the works unless it has been demonstrated that the unbound pavement material lot conforms fully to the requirements of MRTS10. All conformance results shall be no more than six months old.
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 2
label | Reference - MRTS10 Clause 6.1.1
holdpoint | Hold Point
checkpoint | Mix Design Report: A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 3
label | Reference - MRTS10 Clause 7.1
holdpoint | Hold Point
checkpoint | Moisture Content - The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure:
label | a) there is adequate moisture to achieve the specified compaction standard
label | b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and
label | c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A.
label | Acceptance Criteria and Frequency (Project Specific) - Testing - AS1289.2.1.1
label | ○ 1 per 500m2
label | ○ 4 per lot
label | Check Item - Test Report
label | Reference - MRTS10 Clause 8.2.5, Clause 9.4.8 Table A3
checkpoint | Construction - Trial Pavement
label | ○ Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
label | ○ The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression.
label | ○ The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken.
label | Acceptance Criteria and Frequency (Project Specific) - Visual & Check
label | Check Item - Witness Point 1 /Hold Point 4
label | Reference - MRTS10 Clause 8.1
holdpoint | Hold Point
checkpoint | Material Compliance Testing - Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
textbox | Material Type:
textbox | Material Stockpile Lot Ref:
label | Acceptance Criteria and Frequency (Project Specific) - MRTS05 Cl. 7, Table A1, MRTS10 Cl.6, Table A2
label | Check Item - Check Item
label | Reference - MRTS05 Clause 7
checkpoint | Equipment - Equipment as specified in approved construction procedure
label | Acceptance Criteria and Frequency (Project Specific) - Construction Procedure Approval
label | Check Item - Contract Notice
label | Reference - MRTS10 Cl.8.2.1.4
checkpoint | Weather Conditions - CMB material shall not proceed when:
label | a) air temperature is less than 10°C or greater than 40°C
label | b) during rain or when rain is likely to fall during placement
label | c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.4
checkpoint | Allowable Working Time - Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following:
label | a) Working time determined in accordance with Test Method Q136A
label | b) Four hours
label | Acceptance Criteria and Frequency (Project Specific) - Monitor
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.3
checkpoint | Construction Joints - Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.10
checkpoint | Fresh Joints - Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Cl. 8.2.10.1
checkpoint | Other (Cold) Joints - Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Cl. 8.2.10.2 Cl.6.4
checkpoint | Curing of CMB Layers - The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.9
checkpoint | Trafficking of CMB Layers during Construction - Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10)
label | Acceptance Criteria and Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.11
checkpoint | Compaction Standard - The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard
label | Acceptance Criteria and Frequency (Project Specific) - 102% standard upper most layer
label | ○ 100% standard lower layers
label | ○ (1/500m2, min 4/lot)
label | ○ (1/1000m2, min 4/lot)
label | Check Item - Test Report
label | Reference - MRTS10 Clause 8.3.4
checkpoint | UCS - Unconfined compressive strength between 1 - 2MPa
label | Acceptance Criteria and Frequency (Project Specific) - UCS 1-2MPa (1 per lot)
label | Check Item - Check Item
label | Reference - MRTS10 Clause 9.4.9
checkpoint | Stabilising Agent Content - The actual content of stabilising agent for each lot shall be represented by both the:
label | a) minimum characteristic value of the actual content of stabilising agent, and
label | b) maximum characteristic value of the actual content of stabilising agent.
label | When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content.
label | Acceptance Criteria and Frequency (Project Specific) - Target content minus MPV
label | ○ Min. test 1 per lot
label | Check Item - Check Item
label | Reference - MRTS10 Clause 9.4.6
checkpoint | Geometrics - Horizontal Tolerances
label | Shall not be more than ± 50mm except for the following:
label | a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm
label | b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner
label | Acceptance Criteria and Frequency (Project Specific) - -50mm/+250mm (1 per 20m)
label | Check Item - Survey Report
label | Reference - MRTS10 Clause 8.3.5.2
checkpoint | Geometrics - Primary Vertical Tolerances
label | The vertical tolerances specified in Table 8.3.5.3 shall apply or:
label | – the surface level measured at any point on the surface of any layer.
label | – The average total thickness of the constructed course compared to the specified total thickness.
label | Acceptance Criteria and Frequency (Project Specific) - ±15mm for layers that have been hard cut
label | ○ ±10mm for all other layers
label | ○ Layer thickness -20mm, +unspecified
label | ○ (1 per 20m at shoulders, lane lines & grade changes)
label | Check Item - Survey Report
label | Reference - MRTS10 Clause 8.3.5.3
checkpoint | Geometrics - Deviation from a Straight - Edge: Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m
label | Acceptance Criteria and Frequency (Project Specific) - 5mm over 3m (1 per 20m and at joints)
label | Check Item - Check Sheet
label | Reference - MRTS10 Clause 8.3.6
checkpoint | Geometrics - Crossfall: Shall not differ from the designed crossfall by more than 0.5% absolute.
label | Acceptance Criteria and Frequency (Project Specific) - Check
label | Check Item - Survey Report
label | Reference - MRTS10 Clause 8.3.5.4
checkpoint | Proof Rolling - The perceptible surface deformation test (Q723) shall be undertaken in the presence of the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witnesss Point 2
label | Reference - MRTS10 Clause 9.4.10
checkpoint | Acceptance - No CMB layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed (other than UCS), the surface finish comlies with Clause 8.2.8 and the layer presented to the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 5
label | Reference - MRTS10 Clause 9.5.1
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 14.07 - Demolition of Road Furniture | itp
section | Details
checkpoint | Road furniture to be removed are as listed in MRTS14.1.
label | Acceptance Criteria and Frequency (Project Specific) - Signange/REGP's and Lighting to be removed
label | Check Item - Check Item
label | Reference - MRTS14.1
checkpoint | Existing road furniture demolished and removed in a manner which avoids damaging any adjacent work.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.7.3
checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.7.3
checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be salvaged in accordance with the provisions of the design documentation
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
label | Check Item - Milestone
label | Reference - MRTS14 Cl8.2
checkpoint | Dismantling and removal shall not commence until expiration of the seven day period
label | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
label | Check Item - Hold Point 1
label | Reference - MRTS14 Cl8.2
holdpoint | Hold Point
checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
label | Check Item - Milestone
label | Reference - MRTS14 Cl9.2
checkpoint | Dismantling and removal shall not commence until epiration of the seven day period
label | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
label | Check Item - Hold Point 2
label | Reference - MRTS14 Cl9.2
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 14.13 - Supply and Installation of Road Signs | itp
section | Details
checkpoint | Not less than seven days prior to commencement of dismantling and removal of existing road furniture, the Contractor shall submit a schedule of items of existing road furniture to be disamantled or re-erection in accordance with the provisions of the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
label | Check Item - Milestone
label | Reference - MRTS14 Cl 9.2
checkpoint | Dismantling and removal shall not commence until the experation of the seven day period.
label | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
label | Check Item - Hold Point 2
label | Reference - MRTS14 Cl 9.2
holdpoint | Hold Point
checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 CL 13.2
checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 CL 13.2
checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 13.3
checkpoint | The sign substrate shall be manufactured from aluminium. Other materials may be considered but evidence of the full approval of the department will be provided to the administrator prior to their use.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS14 CL 13.3.1.1
holdpoint | Hold Point
checkpoint | Sign faces are fabricated in accordance with the requirements of Traffic and Road Use Management Manual (TRUM) Volume 3, Part 5.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 13.4
checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.2.3
checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.2.3
checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.3
checkpoint | Erection of Road Signs.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 1
label | Reference - MRTS14 Cl 14.4
checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.4.2
checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl14.4.5
checkpoint | Welded Mesh Fence shall comply with the details shown in the design documentation & Std Dwg. 1604
label | Acceptance Criteria and Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - MRTS14 Cl 11, MRTS14.1 Cl 6.1, Std Dwg. 1604
checkpoint | Install Fencing as per Manufacturer's Guidelines - Fencing shall be constructed in the locations and to the details shown in the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 11 MRTS14 Cl 11.4
checkpoint | Warrenty Statement from sign panel manufacturer shall be provided.
label | Acceptance Criteria and Frequency (Project Specific) - Submission
label | Check Item - Check Item
label | Reference - Annexure MRTS14.1 Cl 7.1
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments | itp
section | Details
checkpoint | Manufacture of steel beam guardrail post, panel components and end treats are maufactured by an approved manufacturer.
label | Acceptance Criteria and Frequency (Project Specific) - Approved Manufacturer
label | Check Item - Check Item
label | Reference - MRTS14 Cl. 20.2
checkpoint | Steel beam guardrail components and end treatments shall only be supplied by an approved supplier.
label | Acceptance Criteria and Frequency (Project Specific) - Approved Supplier
label | Check Item - Check Item
label | Reference - MRTS14 Cl 20.3
checkpoint | Hexagonal head bolts and nuts shall be manufactured to the dimensions shown on Standard Drawings, and tested in accordance with MRTS78. Mushroom head (C) bolts shall be manufactured to the details shown on Standard Drawing 1479 Circular washers shall conform to the requirements of AS 1237.
label | Acceptance Criteria and Frequency (Project Specific) - Test Certificates
label | Check Item - Check Item
label | Reference - MRTS14 Cl 20.4.7
checkpoint | All panels, steel posts and blockouts shall be batch stamped during the manufacturing process with manufacturer's ID, Metal grade and thickness, and batch number. Single batch <2000 items.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.4.2.2, Cl. 20.4.3.2
checkpoint | All steel components shall be hot-dipped galvanised after manufacture in accordance with the requirements of AS/NZS 4680.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.4.1
checkpoint | All the steel manufacturer material test certificates shall be supplied to the Administrator. The test certificates shall show the full chemical composition including the carbon equivalence, and mechanical test results for yield, tensile and elongation
label | Acceptance Criteria and Frequency (Project Specific) - Test Certificates
label | Check Item - Hold Point 7
label | Reference - MRTS14 Cl20.4.5
holdpoint | Hold Point
checkpoint | If required, the Administrator shall randomly select two post and two panels from each batch number for audit testing.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 3
label | Reference - MRTS14 Cl20.4.6.1
checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied for the batch of guardrail components.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS12 Cl20.4.6.3
holdpoint | Hold Point
checkpoint | A list of component parts and fabrication drawings defining the dimensions and weld sizes of the various components and the grade of materials and relevant standards with which the component materials are required to comply shall be provided to the Administrator prior to commencement of installation of the device or system.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 11
label | Reference - MRTS14 Cl21.2
holdpoint | Hold Point
checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS01 Cl.8
holdpoint | Hold Point
checkpoint | Dial before you dig consulted and services located where required prior to excacation or driving of posts
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference -
checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.1
checkpoint | A proprietary road safety barrier system and/or end treatment shall be installed as shown in and required by the design documentation, and in accordance with the requirements of the installation manual
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.21.4.1
checkpoint | Public Domain (Departure Terminal): Soil plate on type 2 departure terminal shall not be ommitted
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.3
checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.5, Cl21.4.5
checkpoint | Installed within Geometric Tolerances
label | Acceptance Criteria and Frequency (Project Specific) - Post Verticality: ± 15mm
label | ○ Post Height: ± 10mm
label | ○ Rail Height: ± 10mm
label | Check Item - Check Item
label | Reference - MRTS14 Cl21.4.6.2
checkpoint | Adminstrator accepts guardrail installation as per the design documentation
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS14 Cl 20.6.7
holdpoint | Hold Point
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 16.01 - Landscape and Revegetation Works | itp
section | Details
checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
label | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
label | Check Item - Hold Point 1
label | Reference - MRTS16 Cl 5.2.1
holdpoint | Hold Point
checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 2
label | Reference - MRTS16 Cl 5.2.2
holdpoint | Hold Point
checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 3
label | Reference - MRTS16 Cl 5.3.1
holdpoint | Hold Point
checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 5
label | Reference - MRTS16 Cl 5.3.3
holdpoint | Hold Point
checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
label | Acceptance Criteria and Frequency (Project Specific) - Plan
label | Check Item - Hold Point 6
label | Reference - MRTS16 Cl 5.3.4
holdpoint | Hold Point
section | Materials
checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7.6.2
checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8
section | Subsoil and Topsoil Amelioration
checkpoint | Site is weed free prior to ground preparation operations
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 2
label | Reference - MRTS16 Cl 8.3
checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents ripping cultivation roughening
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 3, 4, 5
label | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - Cl 8.4.1.1
holdpoint | Hold Point
checkpoint | Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS16 Cl 8.2.1
holdpoint | Hold Point
checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 6
label | Reference - MRTS16 Cl 8.4.2.1
section | Grass seeding, Hydromulching and Turfing
checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by:
label | a) spreading fertiliser over the topsoil and raking the surface smooth
label | b) to the prepared surface that has been moistened with a solution of water and wetting agent
label | c) on the day turf is delivered to site
label | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
label | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.2
checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.2
checkpoint | For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 9
label | Reference - Cl 8.5.1
holdpoint | Hold Point
checkpoint | All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - Cl 8.5.1
holdpoint | Hold Point
checkpoint | Broadcast seeding installed as per Cl 8.5.1.2
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Check Item
label | Reference - Cl 8.5.1.2
checkpoint | Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Check Item
label | Reference - Cl 8.5.1.4
section | Establishment, Monitoring and Finalisation
checkpoint | Commencement of the Establishment Period
label | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.1
checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.1.1
checkpoint | Commencement of the Monitoring Period
label | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2
checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.2.1
checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
label | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2.2
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 28.01 - Contractor's Camp and Site Facilities | itp
section | Details
checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.2
checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.3
checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.5.6
checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl. 6
checkpoint | Contractors camp complies with all requirements of MRTS28 annexure with a proposed site facility layout submitted to the administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 45.01 - Road Surface Delineation | itp
section | Details
checkpoint | All material conforms to requirements set out in Clause 6
label | Acceptance Criteria and Frequency (Project Specific) - Material product sheets
label | Check Item - Check Item
label | Reference - MRTS45 Cl 6
checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.2
checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.3
checkpoint | In addition to the above requirements, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS45 Cl 7.3
holdpoint | Hold Point
checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS45 Cl 7.4.1
holdpoint | Hold Point
checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5
checkpoint | All Markings are of uniform thickness and intensity
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.2.3
section | Waterborne
checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
label | Acceptance Criteria and Frequency (Project Specific) - Visual, Table 7.5.2.4
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
section | Thermoplastic
checkpoint | If required, a primer of type recommended by manufacturer of the thermoplastic material shall be applied to the surface immediantly in advance of, but concurrent with, the application of thermoplastic material
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.3.1
checkpoint | Thermoplastic shall be applied at a temperature between 180C-200C or as per the manufacturers specifications
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.3.2
checkpoint | Thermoplastic applied at a minimum of 2mm thickness
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.3.3
section | Cold Applied Plastic
checkpoint | If required, a primer of the type reccommended shall be applied to the surface immediately in advance of, but concurrent with the application of the Cold Applied Plastic materials
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.4.1
checkpoint | Cold Applied Plastic shall be applied at a temperature as per the manufacturers specifications
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.4.2
checkpoint | Cold applied Plastic shall be applied at the rates specified in Table 7.5.4.2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.4.2
checkpoint | The use of Raised Retroreflective Pavement Markers shall be in accordance with Cl 5.6.2 of the MUTCD Part 2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.6.14
checkpoint | Material complies with luminance and retro-reflectivity requirements.
label | Acceptance Criteria and Frequency (Project Specific) - Test procedure AS 4049.4
label | Check Item - Check Item
label | Reference - MRTS45 Cl 5.3 & Cl 7.7.6
checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.8
checkpoint | Completed Pavement Markings shall be uniform, clean and well-defined edges without deformation and conforms to dimensions as set out in the MUTCD
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.9
checkpoint | Pavement Markings conform to all tolerances
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.9.1
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 51.01 - Environmental Management Systems | itp
section | Details
checkpoint | Environmental Management Plan (Construction) EMP( C) submitted in accordance with General Conditions of Contract.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of EMP
label | Check Item - Milestone
label | Reference - MRTS51 Cl. 6.3
checkpoint | Works under the Contract shall not start until the EMP( C) is assessed for suitability by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - EMP Approved by Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS51 Cl. 6.3
holdpoint | Hold Point
checkpoint | Any amendments to the EMP( C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Hold Point 2
label | Reference - MRTS51 Cl. 6.4
holdpoint | Hold Point
checkpoint | Environmental site inspections to be conducted daily, against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a monthly basis.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 7.1
checkpoint | Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request.
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Hold Point 3
label | Reference - MRTS51 Cl. 7.8
holdpoint | Hold Point
checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.4.1
checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.5.2
checkpoint | Project records shall include all noise monitoring results if required
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.5.3
checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
label | Acceptance Criteria and Frequency (Project Specific) - Visual (Survey Recorded)
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.6.2.3
checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl. 8.6.2
checkpoint | The contractor shall at all times take reasonable and practicable management measures to avoid cuasing environmental nuisance or harm due to air quality. Burning of material shall not be permitted
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.7.2
checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.8
checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.9.1
checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.10.1
checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.13.2
checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.14.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 52.01 - Erosion and Sediment Control | itp
section | Details
checkpoint | Clearing and grubbing (or the use of the area for stockpiles) for that section shall not start until the ESCP for that section is assessed as suitable by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Approval of ESCP by Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS52 Cl. 6.1
holdpoint | Hold Point
checkpoint | Prior to initial earthworks operations, the Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
label | Acceptance Criteria and Frequency (Project Specific) - In accordance with approved ESCP.
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | Hold Point
checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
label | Check Item - Check Item
label | Reference - MRTS52 Cl. 8.1
checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.2.3.2.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist | 70.01 - MRTS70 Concrete | itp
section | Details
checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 9.2
checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 13.1
checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.11.1
checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl15.5
checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. Each trial mix shall be a Witness Point with a notice peroid of 3 days. The minimum volume of trial mix is 25% of the rated capacity of the mixer.
label | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
label | Check Item - Witness Point 1
label | Reference - MRTS70 Cl 15.1.1
checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS70 Cl 15.1
holdpoint | Hold Point
checkpoint | Concrete placed within 75minutes (conc. Temp<=32 degrees) or 1hour (32>conc. temp < 35 degrees) from the time of charging the mixer. These times may be extended at the Administrator's discretion where set-retarding admixtures are used. No concrete may be placed the temperature of the concrete is less than 10°C or exceeds 35°C.
label | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
label | Check Item - Check Item
label | Reference - MRTS70 Cl 13.1
checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.3
checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS70 Cl 15.3
holdpoint | Hold Point
checkpoint | All formwork shall be subject to inspection and approval by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS70 Cl 15.4.1
holdpoint | Hold Point
checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS70 Cl 15.6
holdpoint | Hold Point
checkpoint | No concrete shall be placed in the Works until:
label | a) the formwork and reinforcement have been inspected
label | b) all foreign material has been completely removed from the forms
label | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5
label | Reference - MRTS70 Cl 15.6.1
holdpoint | Hold Point
checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 2
label | Reference - MRTS70 Cl 15.6.1
checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
label | Acceptance Criteria and Frequency (Project Specific) - Slump Test:
label | <60 - ±10
label | ≥60≤80 - ±15
label | >80≤110 - ±20
label | >110≤150 - ±30
label | >150 - ±40
label | (Every Load)
label | Check Item - Check Item
label | Reference - MRTS70 AS 1379 Table 5.1
checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample.
label | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
label | ○ 4-10 Loads - 4 Samples
label | ○ 11-23 Loads - 5 Samples
label | ○ >23 Loads - 1 per 4 loads
label | Check Item - Test Results
label | Reference - MRTS70 Cl 15.2.1 Table 15.2
checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 16.5.2
checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set. If an interruption greater than 45 minutes occurs, without prio approval from the Administrator, or a cold join occurs, the precast member shall be rejected.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl.16.5.1
checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS70 Cl 15.13
holdpoint | Hold Point
checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS70 Cl 15.8
holdpoint | Hold Point
checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 4
label | Reference - MRTS70 Cl 15.8
checkpoint | Following removal of forms
label | ○ Fins and unwanted projections are ground off
label | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
label | ○ Where surface finish is not specified, class 2 finish is required. Where surfaces of concree do not achieve class 2, surface shall be bagged.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 16.8.1
checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, <Specified MRTS70 Cl15.7.3
label | Check Item - Check Item
label | Reference - MRTS70 Cl 15.7.3
checkpoint | Acceptance or Rejection of Hardened Concrete on the Basis of Strength
label | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
label | b) < Fc (Ave 3 consective samples from Lot)
label | c) > 1.4 Fc (Ave 3 consective samples from Lot)
label | In addition
label | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
label | Check Item - Test Results
label | Reference - MRTS70 Cl 12.5 & Cl 12.4
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off