## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 02.01 - Traffic Management | itp
section | Details
checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
note | Acceptance Criteria and Frequency (Project Specific) - Accreditation Supplied to Administrator
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 5.2
checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
note | Acceptance Criteria and Frequency (Project Specific) - Approval via Contract Notice - Per NTO
note | Check Item - Hold Point 1
note | Reference - MRTS02 Cl. 5.3
signoff | HOLD POINT
checkpoint | All traffic control devices inspected and records kept in accordance with the specification
note | Acceptance Criteria and Frequency (Project Specific) - Site Records - Daily
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 5.6.4
checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
note | Acceptance Criteria and Frequency (Project Specific) - Incident Report - Per incident
note | Check Item - Check Item
note | Reference - MRTS02Cl. 5.6.5
checkpoint | The minimum number of lanes to be maintained on midblock sections of road will be determined as per the method (a), (b) or (c): As Mentioned MRTS02.1 Cl .3.2, 3.3, 3.4, 3.5
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02.1 Cl. 5.7.3
checkpoint | Traffic may be altered from its existing route via the following Cl 3.8 MRTS02.1
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02.1 Cl. 5.7.4
checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Hold Point 2
note | Reference - MRTS02 Cl. 6.2
signoff | HOLD POINT
checkpoint | The Contractor shall provide a minimum of two VMS (one in each direction) for the works under construction on Steve Irwin Way. VMSs shall be in place a minimum of 2 weeks prior to the commencement of the works on site to provide advance warning to the road users of the impending works. The requirements of Clause 6.5.2.1 of MRTS02 shall apply with regards to their use
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02.1 Cl. 6.5.2.1
checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
note | Check Item - Milestone
note | Reference - MRTS02 Cl. 7.5
checkpoint | The following requirements for side tracks shall apply as Stated in MRTS02.1 Cl 5.7
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 6.5.3.3
checkpoint | The following additional control measures are required to mitigate end of queue crashes as stated in MRTS02.1 Cl 5.8
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 6.5.7
checkpoint | On asphalt and bituminous surfaced pavements, when permanent linemarking will not be in place outside working hours, temporary raised pavements markers (Stick and Stomps) are to be installed and maintained on centre lines, lane lines and edge lines at spacing of not greater than 25 m (except for side-track tie-ins where spacing shall not exceed 5 m). Temporary pavement markers shall only be in use for a maximum of 48 hrs and shall be replaced by linemarking after such time. If the Contractor is unable to complete line spotting by the end of each day’s work and the road is to be trafficked, the Contractor shall delineate all separation and lane lines as above. Existing longitudinal lines are to be removed by abrasive blasting or approved other method approved in writing by the Administrator when temporary lanes are in place
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 6.5.8
checkpoint | Temporary road lighting shall be installed in accordinance with MRTS02.1 Cl 5.12
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 6.5.13
checkpoint | In addition to the requirements of Clause 7.1, there is a need for an independent review to establish conformance with the approved TMP and TGS and with the performance requirements of MRTS02 – Provision for traffic
note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 7.1
checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 8
note | Acceptance Criteria and Frequency (Project Specific) - Submission of report to Administrator - Per inspection
note | Check Item - Check Item
note | Reference - MRTS02 Cl. 9
checkpoint | Supplementart Requirements completed as per MRTS02.1 Cl 9
note | Acceptance Criteria and Frequency (Project Specific) - TMD and RPEQ sign off of TGS and Risk Assessment - Per TGS
note | Check Item - Check Item
note | Reference - MRTS02.1 Cl. 9
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.01 - Removal of Existing Drainage Structures and Concrete Slabs | itp
section | Details
checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Culvert Removal - Per Culvert
note | Check Item - Check Item
note | Reference - MRTS03 Cl 9.2
checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
note | Check Item - Check Item
note | Reference - MRTS03 Cl 9.2
checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
note | Check Item - Check Item
note | Reference - MRTS03 Cl 9.2
checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Culvert
note | Check Item - Check Item
note | Reference - MRTS03 Cl 9.2
checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per Kerb
note | Check Item - Check Item
note | Reference - MRTS03 Cl 9.4
checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 9.4
checkpoint | Kerb excavations backfilled to flush with the surrounding area.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 9.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.02 - Supply and Installation of Precast Concrete Pipe | itp
section | Details
checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS01 Cl. 8
signoff | HOLD POINT
checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
note | Check Item - Check Item
note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
checkpoint | Component size, wall thickness and class is as specified in the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.2
checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS03 Cl11.2
signoff | HOLD POINT
checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS03 Cl11.3.1
checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Hold Point 2
note | Reference - MRTS03 Cl11.3.1
signoff | HOLD POINT
checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.1
checkpoint | Excavations completed as per MRTS04
note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl12.3.1, MRTS04
checkpoint | Foundation bedding and Haunch zone material placed in Accordance with MRTS04
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.2
checkpoint | Components are assembled as per manufaturers specifications
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.3
checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.4
checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.5
checkpoint | Pipes laid with the word 'TOP', where marked, or lifting hole facing the top. Lifting holes plugged after the pipe is installed.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.5
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 3
note | Reference - MRTS03 Cl11.3.5
signoff | HOLD POINT
checkpoint | Where RCP's are required to be cut, the cut surface shall be given two coats of a surface tolerant epoxy.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 11.3.9
checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 11.3.10
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS03 Cl. 11.3.10
signoff | HOLD POINT
checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl. 1
checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl. 6
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.03 - Culvert Component/End Structure Insitu Cast | itp
section | Details
checkpoint | Concrete Conforms with Cl 6.1 (MRTS 70), Concrete Mortar conforms to Cl6.2, Steel Reinforcing conforms to MRTS71, Rock Masonry conforms to Cl33, Grouted Rock Pitching complies with Cl 34, Steel Wire Matresses comply with Cl 37
note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS70 ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl 14.2, Cl 15.2, Cl16.2
checkpoint | Cast-in-situ end structures such as headwalls, wingwalls, aprons and kerbs to culverts constructed in the locations specified on the project drawings and comply with standard drawings 1304, 1305 for pipe culverts and 1240, 1250 & 1260 for box culverts as applicable
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 15.3
checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl 15.3
checkpoint | Endwalls, wingwalls and concrete aprons constructed without a foundation bedding unless specified otherwise in the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 15.3
checkpoint | Endwalls and wingwalls seperated with an expansion gap unless otherwise specified on the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 15.3
checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl. 6
checkpoint | Construction of culvert base, walls or endwalls shall include the construction of integral nib or cutoff walls where relevant
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 17.3, Cl 18.3
checkpoint | Construction of culvert base, walls or endwalls shall comply with the Geometrics Section stated in Clause 1.5. MRTS03.1. For Each Structural Element, testing requirements must contain: Dimensional, Positional, and Relative Position
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl 1.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.04 - Pre Cast End Structure | itp
section | Details
checkpoint | Precast end structure conforms to Cl6.6, Concrete Mortar conforms to Cl6.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 16.2
checkpoint | Constructed in the locations specified on the project drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 16.3
checkpoint | Where material on or against which end structures are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl 16.3
checkpoint | End Structures laid on foundation bedding which provides continuous even support
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 16.3
checkpoint | Joints between end structure and culvert in addition to any holes and recesses are filled with cement mortar and finished smooth and uniform and cured for 48hrs
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 16.3
checkpoint | Backfilling operations not undertaken during curing period and complies with MRTS04
note | Acceptance Criteria and Frequency (Project Specific) - Visual, ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl 16.3
checkpoint | Geometrics: All points for which levels are shown on the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Horizontal: ±100mm, Vertical Invert: ±10mm
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl. 1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.05 - Supply and Installation of Precast Box Culverts | itp
section | Details
checkpoint | Contractor shall set out installation as shown on the drawings. The Administrator will determine the design appropriateness of the set out with regard to the actual site conditions.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS01 Cl. 8
signoff | HOLD POINT
checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
note | Acceptance Criteria and Frequency (Project Specific) - Manufacture and Test Certificates
note | Check Item - Check Item
note | Reference - MRTS03 Cl10.2, MRTS25, MRTS26, MRTS24
checkpoint | Component size, wall thickness and class is as specified in the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.2
checkpoint | Procedure for excavation, installation and backfill submitted 14 days prior to works.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Milestone
note | Reference - MRTS03 Cl11.3.1
checkpoint | Culvert Construction Procedures accepted prior to commencement of Installation
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Hold Point 2
note | Reference - MRTS03 Cl11.3.1
signoff | HOLD POINT
checkpoint | Components installed in the locations and in accordance with the details as shown on the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.1
checkpoint | Excavations completed as per MRTS04
note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl12.3.1
checkpoint | Where material on or against which culvert bases are to be constructed is other than rock, the material is compacted as per bottom of excavations in accordance with MRTS04 General Earthworks.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl14.3.1
checkpoint | Cast in-situ concrete bases, footings, infill floors and box culverts constructed without a foundation bedding unless specified otherwise in the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl14.3.1
checkpoint | Construction of bases, footings, infill floors and box culverts include the construction of nibs and integral cut-off walls
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl14.3.1
checkpoint | Components are assembled as per manufaturers specifications
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.3
checkpoint | If Possible, Contruction commenced at outlet. Ends of components free from foreign matter.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.4
checkpoint | Box culverts installed in accordance with Standard Drawings 1250 and 1260 or project drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.6
checkpoint | Holding down anchors installed to retain the units, where specified, as per the details on STD DWG 1250 and 1260.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.6
checkpoint | Where spanning slabs are installed, locating dowels installed in the tops of the units and the spanning slabs seated on continuous cement mortar pads on the adjacent unit.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.6
checkpoint | In multiple cell culverts, the gaps between the lines of installed cells shall be a minimum of 40mm wide and filled with 1:10 leanmix with max 10mm aggregate.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.6
checkpoint | Where spanning slabs are installed, the space between the slabs is filled with lean mix concrete.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.6
checkpoint | Lean mix backfill cured for 24 hours before any other backfill material is placed over the culvert.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl11.3.6
checkpoint | Backfilling of culverts shall be carried out in accordance with Clauses 15 and 20 of MRTS04
note | Acceptance Criteria and Frequency (Project Specific) - Visual, MRTS04 ITP
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 11.3.10
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS03 Cl. 11.3.10
signoff | HOLD POINT
checkpoint | Supplementary Requirements Completed as per Clause 52 MRTS03 & MRTS03.1 Cl 6
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl. 6
checkpoint | Survey Requirements: All points (inlets and outlets) shown on the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03.1 Cl. 1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.20 - Kerb - Cast Insitu/Extruded | itp
section | Details
checkpoint | Supplied Concrete complies with MRTS70/71. MRTS70 and MRTS71 ITP completed.
note | Acceptance Criteria and Frequency (Project Specific) - ITP 70.01
note | Check Item - Check Item
note | Reference - MRTS03 Cl 18.2
checkpoint | Cast-in-place concrete kerb / channel constructed in the locations shown on the Drawings and in accordance with the details shown on Standard Drawings (1033)
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.3
checkpoint | Excavations / foundation preparation in accordance with the requirements of MRTS04 General Earthworks. The ground surface moistened just prior to placing concrete.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.3
checkpoint | Exposed surfaces of manually placed concrete to be steel-trowel finished.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.3
checkpoint | Expansion Joints shall be installed at regular intervals not exceeding 20m. The joints shall have a compressible packing with maximum thickness of 6mm covering the full cross section.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.3
checkpoint | Contraction Joints shall be installed at regular intervals not exceeding 5m. They shall be constructed be forming grooves 40mm deep and not more that 6mm wide.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.3
checkpoint | Concrete shall be cured at least 7 days before any other roadworks operations are carried out adjacent to the kerb / channel.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.3
checkpoint | The Horizontal and Vertical alignments shall vary by no more than ±10mm from those specified. Alignments exhibit smooth lines. Overall dimensions are at least equal to that shown on the Drawings.
note | Acceptance Criteria and Frequency (Project Specific) - ±10mm from Drawings, 1 test per 10m (invert levels)
note | Check Item - Check Item
note | Reference - MRTS03 Cl18.4
checkpoint | WATER TEST: (on channels where the longitudinal grade is less than 1%). The test carried out as soon as possible after the concrete in the channel has hardened and water shall not pond to a depth of more than 5mm
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS03 Cl18.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.27 - Subsoil Drains | itp
section | Details
checkpoint | Subsoil Drains constructed to appropriate dimensions, Geotextile surround and Pipe perforated with textile suround (Inspect trench prior to backfill)
note | Acceptance Criteria and Frequency (Project Specific) - Type B: 700x300mm Trench, 100mm Pipe - 50mm off base
note | ○ Type D: 100mm Wide Trench, 40mm Strip Drain
note | Check Item - Check Item
note | Reference - MRTS03 Fig 22.1
checkpoint | Type B subsoil drains backfilled with either 10mm/20mm drainage agregate or 20mm no fines concrete. Type D subsoil drains backfilled with either course sand or 20mm no fines concrete.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.2.5
checkpoint | Minimum cover over strip filter drains comply with Table 22.3.1 of MRTS03 for the relevant compactor size used for construction. Hand Held Unit - 100mm, < 15 tonnes - 200mm, > 15 tonnes - 300mm
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.3
checkpoint | Minimum grades for subsoil drains comply with Table 22.3.2 of MRTS03. Type B - 0.5%, Type D - 1.0%
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.3
checkpoint | Clean outs installed at head of all subsoil drains and at 60m intervals (Type B - pipe drain) / 50m (Type D - strip drain). Clean outs in accordance with standard drawing 1116
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.3, TMR SD 1116
checkpoint | Backfill material dampened when placed in trench. Placed in 200mm layers and tamped.
note | Acceptance Criteria and Frequency (Project Specific) -
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.3
checkpoint | Concrete outlets, surrounds ,chicken wire cones, pest proof flaps, cast iron/PVC caps, rock pitching in accordance with standard drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.3, TMR SD 1116
checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl22.3, TMR SD 1116
checkpoint | Subsoil Drains Flushed when complete until outlet water is clean and flows consistently
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl27.4
checkpoint | As Constructed drawings prepared / All geometric tolerance requirements met
note | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
note | Check Item - Witness Point
checkpoint | Subsoil Drains Flushed when complete until outlet water is clean and flows consistently
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point 4
note | Reference - MRTS03 Cl22.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.28 - Sheet or Strip Filter Drains | itp
section | Details
checkpoint | Sheet filter drains shall be a suitable proprietary product, compromising a plastic core of thickness not less than 18mm, encased by a non-woven geotextile which complies with MRTS27 Geotextiles.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.2
checkpoint | Strip filter drains shall be a suitable proprietary product, compromising a plastic core of thickness not less than 40mm, designed to allow the drainage of water along the drain and encased by a non-woven geotextile which complies with MRTS27 Geotextiles.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.2
checkpoint | The plastic core shall permit the passage of high water flows, and shall have a crush strength not less than 200kPa
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.2
checkpoint | Drainage pipes, fittings, and joining materials/procedures shall comply with the relevant requirements as specified.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.2
checkpoint | Concrete, where required, shall be grade N20/20 in accordance with clause 6.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.2
checkpoint | Materials shall not be exposed to heat or direct sunlight or stored directly on the ground.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.3
checkpoint | Sheet/Strip filter drains shall be constructed in the locations and in accordance with the drawings and manufacturer's recommendations.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.4
checkpoint | Where sheet filter drains are used against structures employing weepholes, the core of the drain shall have cutouts of a size and spacing recommended by the manufacturer.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.4
checkpoint | Collector pipes shall be constructed to the shapes specified in the drawings and jointed in accordance with the manufacturer's recommendations.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.4
checkpoint | Filling around collection pipes shall be general backfill in accordance with Clause 20 of MRTS04. Fill material shall be compacted to a relative compaction not less than 97%.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.4
checkpoint | Concrete outlets, concrete surrounds, galvanised chicken-wire cones and pest-proof flaps shall be provided in accordance with Standard Drawing 1116.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl 23.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 03.41 - Rock Protection | itp
section | Details
checkpoint | Rock complies with size requirements specified on drawings, otherwise shall be not less than 150mm and not greater than 500mm. Rock shall be well graded with not less than 50% larger than a size twice the minimum specified
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.2
checkpoint | Rock shall be clean, hard, dense and durable igneous or metamorphic rocks. It shall be resistant to weathering, free from overburden, spoil, shale and organic matter.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.2
checkpoint | Rock Protection constructed in the locations and in accordance with the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.3
checkpoint | Rock Protection is uniform in appearance and does not have noticeable veritical or horizontal irregularities
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.3
checkpoint | Rock material shall be placed such that larger rocks are uniformly distributed throughout the rockwork layer with smaller rocks filling the voids.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.3
checkpoint | Where constructed on an embankment, rock protection is constructed concurrent with the embankment with no more than 1m vertical height of open embankment above the completed rock protection
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.3
checkpoint | Cement mortar shall consist of one part Type GP cement to three parts fine sand. Materials shall coply with MRTS70
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS03 Cl. 35.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.01 - Clearing & Grubbing | itp
section | Details
checkpoint | Extent of Clearing has been checked and marked according to the Vegetation Removal Notification nu the Project Arborist
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl 7.2.1
checkpoint | Tree Protection Zones installed as per Arborists recommendations
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl 9.1
checkpoint | Clearing operations and other environmental operations to be supervised by Project Arborist, SQP Contaminated Land and environmental representative where required
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl 9.1
checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS04 Cl. 7.2.2
signoff | HOLD POINT
checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 2.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 3
note | Reference - MRTS04 Cl. 7.2.3
signoff | HOLD POINT
checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area is being installed.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS52 Cl. 7.1
signoff | HOLD POINT
checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 7.2.5
checkpoint | Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 5 of Annexure MRTS04.1 to this Technical Specification. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant statutory requirements, including the requirements in MRTS51 Environmental Management. Cl. 7.2.7
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 7.2.7
checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
checkpoint | Trees shall be clasified as a Mature Tree if they have a diameter greater than 100mm diameter. Diameter of trees may be checked by Adminstrator to confirm if Mature.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl13.1
checkpoint | The additional width for clearing and grubbing is 1.0m from toe of embankments as per Annexure MRTS04.1 Cl. 1.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl. 1.1
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 8.4.3
checkpoint | Additional Requirements for Clearing and Grubbing AS Per MRTS04.1 Cl 1.4 have been followed
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl 1.4
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.04 - Ground Surface Treatment | itp
section | Details
checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl12.2.1.1
checkpoint | Holes and local depresions filled with similar material and compacted in accordance with Cl15
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl12.2.1.2
checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a depth of 300mm using appropriate methods.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl12.2.1.3
checkpoint | Construction Testing Requirements: Test Method
note | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
note | Check Item - MRTS04
note | Reference - Table A1
checkpoint | Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: 5000m2
note | ○ 1 per 500m2
note | ○ 1 per lot
note | Check Item - Check Item
note | Reference - Table 15.3b
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.05 - Embankment | itp
section | Details
checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported. Where embankments are zoned (ref Table 14.2.2 / Clause 14.2 - Annexure MRTS04.1), material is suitable for each zone.
textbox | General Fill Class:
note | Acceptance Criteria and Frequency (Project Specific) - General fill material Class A
note | ○ WPI< 1200, PI>= 7,
note | ○ % passing .075mm 15 - 30
note | General fill material Class B
note | ○ 1200 < WP < 2200
note | General fill material Class C
note | ○ 2200 < WP < 3200
note | General fill material Class D
note | ○ 3200 < WP < 4000, PI <=50
note | – CBR as Specified
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.3.1 Table 14.3.1
checkpoint | Rock Fill shall consist of sound igneous, metamorphic or sedimentary rock or combination of these rock groups that will not disintegrate in water or when exposed to the weather. Rock Fill shall be free from overburden, Spoil, shale, clayey materials and organic matter. Rock Fill shall be either sourced from a quarry (or quarries) registered under Transport and Main Road's Quarry Registration System (QRS) or any other suitable source and shall comply with the properties stated in Table 14.2.3. Rock shall be angular in shape and the least dimension of the rock shall not be less than half its greatest dimension
note | Acceptance Criteria and Frequency (Project Specific) - Table 14.2.3
note | Check Item - Check Item
note | Reference - MRTS04 Cl14.2.3
checkpoint | Where embankments are to be constructed on or against any slopes or batter of existing embankments (including batters resulting from the partial construction of Embankment, for example, Core Zone), steps shall be cut as follows:
note | a) where the ground surface has a slope steeper than 1V to 8H and shallower than 1V to 4H, a series of horizontal steps not less than 300 mm high shall be cut into the ground surface to be covered by the Embankment.
note | ○ Such steps shall be constructed both longitudinally and transversely (refer Figure 14.3.3(a))
note | b) where the existing slope or batter has a slope steeper than 1V to 4H, a series of horizontal steps not less than 600 mm high shall be cut into the ground surface to be covered by the Embankment
note | Check Item - Check Item
checkpoint | Compaction methods suitable for material type
textbox | Compaction Method:
note | Acceptance Criteria and Frequency (Project Specific) - Table 15.2
note | Check Item - Check Item
note | Reference - MRTS04 Cl15.2
checkpoint | Compacted Layer Method: Embankment compacted to required density (by characteristic Value). Refer to Table 15.3-B MRTS04 for more information. Fill material placed uniformly in layers. Uncompacted layer thicknesses;
note | – General Fill 150-300mm
note | – Fill in Water Retaining Fill 150-200mm
note | – Subgrade 100- 200mm
note | – Backfill except Sand 100mm-100mm
note | – Sand 150-300mm
note | Acceptance Criteria and Frequency (Project Specific) - RDD%
note | ○ Insitu - >95%
note | ○ Bottom of Excavations - >95%
note | ○ Subgrade (A/B) - >97%
note | ○ Subgrade (C/D)' - 90>96% Subgrade (C/D)* - > 95%
note | ○ Road Embankment(A/B) ->95%
note | ○ Road Embkmnt(C/D)' -90<96%
note | ○ Road Embkmnt(C/D)* ->95%
note | ○ Levee Embkmnt(A/B) - >97%
note | ○ Backfill(Sand) - >70%
note | ○ Backfill(Not Sand) - >95%
note | ' High Rainfall Zone
note | *Low Rainfall Zone
note | Check Item - Check Item
note | Reference - MRTS04 Cl15.3
checkpoint | Compacted Layer Method: Embankment moisture content within ranges specified
textbox | Rainfall Zone:
note | Acceptance Criteria and Frequency (Project Specific) - Table 15.3C
note | Check Item - Check Item
note | Reference - MRTS04 Cl15.3
checkpoint | Where required, each layer rolled with the mechanical interlock method until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
note | Acceptance Criteria and Frequency (Project Specific) - Table 15.4
note | Check Item - Witness Point 4
note | Reference - MRTS04 Cl15.4
checkpoint | Geotextile placed at interchange between compaction methods
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 14.3.2
checkpoint | Within Geometric Tolerance
note | Acceptance Criteria and Frequency (Project Specific) - MRTS04.1 Cl1.2
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl1.2
checkpoint | Construction Testing Requirements: Test Method
note | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
note | Check Item - MRTS04
note | Reference - Table A3
note | Note - Table 15.3A: Layer Thickness, Min: 150mm & Max: 300mm
checkpoint | Relative Moisture: Q250, Rainfall zone: Medium (500mm - 1000mm), Class A1 & B1: 70% - 90%
note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
note | ○ 1 per 500m2/per layer
note | ○ 4 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Relative Compaction: Q140A, Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
note | ○ 1 per 500m2/per layer
note | ○ 4 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Grading: Q103A
note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
note | ○ 1 per 1000m2/per layer
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Plasticity Index: Q105
note | Acceptance Criteria and Frequency (Project Specific) - 2000m2
note | ○ 1 per 1000m2/per layer
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Stockpile Testing Requirements: Test Method
note | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
note | Check Item - MRTS04
note | Reference - Table A3
checkpoint | Grading: Q103A
note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
note | ○ 1 per 1000m3
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Plasticity Index: Q105
note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
note | ○ 1 per 1000m3
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Emerson Class Number: As 1289.3.8.1
note | Acceptance Criteria and Frequency (Project Specific) - 2000m3
note | ○ 1 per 1000m3
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Prior to incorporating any Earth or Rock Fill Material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 8
note | Reference - MRTS04 Cl. 14.2.1
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.06 - General Excavation | itp
section | Details
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS04 Cl. 9.4
signoff | HOLD POINT
checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS04 Clause 13.3.2.1
note | Check Item - Hold Point 6
note | Reference - MRTS04 Cl. 13.3.2.1, Cl. 18.3.3
signoff | HOLD POINT
checkpoint | Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
note | ○ Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate Fill Material as specified on the drawings or in accordance with Clause 18 and Clause 19. Technical Specification, MRTS04 General Earthworks Transport and Main Roads Specifications, November 2022 30.
note | ○ After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Annexure MRTS0 Clause 13.3.2.2
note | Check Item - Hold Point 6
note | Reference - MRTS04 Cl.13.3.2.2
signoff | HOLD POINT
checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
note | Acceptance Criteria and Frequency (Project Specific) - MRTS04 Clause 6
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 13.3.3.3
checkpoint | Dewatering of excavations shall comply with requirements of EMP
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 13.3.8
checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 16.1
checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 13.3.2.4
checkpoint | Trench excavations and excavations for structures shall be carried out to the dimensions shown on the drawings or, where not so shown, to the minimum dimensions necessary to construct the Works accurately and safely under the Contract. Prior to any excavation Works or trench excavations, an assessment is to be undertaken to identify cadastral marks that may need protecting as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 13.3.3.1
checkpoint | Material which is Unsuitable Material in accordance with the provisions of Clause 9.2 shall not be reused in the Works but shall be removed and disposed of in accordance with the provisions of Clause 9.4
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 13.3.3.2
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.07 - Structure Excavation (Unsuitable) | itp
section | Details
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or pottentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL11.3
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS04 Cl9.4
signoff | HOLD POINT
checkpoint | Where material can be reasonably be expected to contain a possible acid sulphate potential, the test results shall be documented and reported to the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS04 Cl10.
signoff | HOLD POINT
checkpoint | Where shown on the drawings or specified elsewhere, a layer of blinding concrete shall be placed over the foundation material as soon as practical. The top surface of the blinding concrete shall be screeded neatly to the shape and levels shown on the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl13.3.4.1
checkpoint | The widths of excavations for culverts shall be the minimum necessary for their construction and placement of backfill against them, provided that nowhere shall such widths be more than those shown on standard drawings 1359.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl13.3.6
checkpoint | The material in the bottom of excavations shall comply with the density requirements of Clause 15 and compacted to a depth of at least 150mm.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl13.3.6
checkpoint | Compaction: Q140A, Bottom of excavations = 95%
note | Acceptance Criteria and Frequency (Project Specific) - Max Lot Size: each culvert or end structure
note | ○ Min. Test Frequency: 1 per 50m2
note | ○ Min. no of Tests: 2 per lot
note | Check Item - Check Item
note | Reference - Table A2 No. 2.6
checkpoint | Supplementary Requirements as per Clause 22 MRTS04. The material used in backfilling unsuitable material excavations, in addition to the requirements specified in Clause 18.3.4.2 of MRTS04, shall satisfy the minimum CBR requirements of Clause 3 of this annexure.
note | Acceptance Criteria and Frequency (Project Specific) - Testing requirements
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl. 13
checkpoint | No areas on Site are available for the disposal of excess and Unsuitable Material. If no areas are indicated, all such material shall be removed from the Site
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl. 5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.08 - Stripping of Topsoil | itp
section | Details
checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 100mm (+/-25mm) depth, or from areas and depths as specified in Clause 2 of Annexure MRTS04.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2
checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
note | Acceptance Criteria and Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
note | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 8.3
checkpoint | No areas are available within the limits of the site for the disposal of excess and unsuitable material, with the exception of excess topsoil. Excess topsoil may be uniformly distributed on cleared and grubbed areas which are outside the road embankment formation.
note | Acceptance Criteria and Frequency (Project Specific) - Check Item
note | Check Item - Check Item
note | Reference - MRTS04.1 Cl. Cl. 5
checkpoint | Stockpile site locations are to be nominated by the Contractor and approved by the Administrator. The Administrator is not obliged to approve any stockpile site location within the road reserve. Stockpile sites shall not be placed within 50 m of a watercourse or within the 20% Annual Exceedance Probability (i.e. Q5) flood zone of a watercourse, unless approved by the Administrator. No native vegetation shall be cleared for stockpile sites located outside the area defined under Clause 7A of Annexure A (Contract Details) to the General Conditions of Contract, unless approved by the Administrator.
note | ○ Stockpile sites shall not be placed within the Tree Protection Zone defined in Clause 9.1.2 of Annexure MRTS51.1.
note | ○ Preference should be given to existing stockpile sites or existing cleared areas. No guarantee will be given as to stockpile site suitability, condition or availability. In the event that the establishment of stockpile sites requires clearing, grubbing or earthworks to be undertaken, a Cultural Heritage risk assessment and environmental survey must be undertaken prior to any works being undertaken. The Contractor shall advise the Administrator of any such requirements HOLD POINT. No clearing or works beyond the defined project extent may proceed without approval from the Administrator and the TMR Environmental Officer.
note | ○ All costs associated with undertaking necessary earthworks activities required for stockpile sites shall be deemed to be included in the Contractor’s schedule unit rates for the corresponding earthworks items.
note | Acceptance Criteria and Frequency (Project Specific) - Check Item
note | Check Item - Hold Point
note | Reference - MRTS04.1 Cl. 2.2
signoff | HOLD POINT
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
note | Acceptance Criteria and Frequency (Project Specific) - Check Item
note | Check Item - Hold Point
note | Reference - MRTS04 Cl. 8.4.3
signoff | HOLD POINT
checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor, as stated in Cl. 2.2 of Annexure MRTS04.1.
note | Topsoil Stockpiles are;
note | ○ Less than 3m High
note | ○ Less than 10m wide
note | ○ Appropriately battered, drained or otherwise protected to prevent erosion and segregation
note | ○ Stockpiled for the minimum duration
note | ○ Stockpile sites shall not be placed within 50m of a watercourse or within the Q5 flood zone of a watercourse.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area prior to earthworks.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS52 Cl. 7.1
signoff | HOLD POINT
checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl 8.4.5
checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - As Constructed Survey
note | Check Item - Survey Report
note | Reference - MRTS04 Cl 8.4.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.10 - Backfill | itp
section | Details
checkpoint | Prior to incorporating any backfill material, stockpile or source test results as specified in Appendix A shall be submitted demonstrating material meets the specified requirements.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Hold Point 11
note | Reference - MRTS04 Cl19.1
signoff | HOLD POINT
checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the Contract. Where not so shown or specified, material shall be earth backfill material complying with the requirements of Clause 19.2.2. Earth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
note | Acceptance Criteria and Frequency (Project Specific) - Grading
note | Check Item - Witness Point 6
note | Reference - MRTS04 Cl19.2.2, Cl19.3.1
checkpoint | Unless specified otherwise in Clause 19.3 or elsewhere in the Contract, backfill shall be compacted using the compacted layer method of construction in accordance with the requirements of Clause 15, except as may be modified by the requirements of Clause 19.
note | Acceptance Criteria and Frequency (Project Specific) - RDD 1/500m2/300mm Lift - min 4/lot
note | Check Item - Check Item
note | Reference - MRTS04 Cl19.3.1
checkpoint | Backfill around In Place units (pipes, culverts, pits and so on) not placed until completed and inspected by Administrator and any curing period has elapsed.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 12
note | Reference - MRTS04 Cl19.3.3
signoff | HOLD POINT
checkpoint | Where material is placed on opposite sides of a culvert, structure, conduit etc. the difference in level of compacted material on opposing sides shall not exceed 150mm, unless shown otherwise on the drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl19.3.3
checkpoint | Foundation bedding, haunch, side and overlay zones for concrete pipe culverts shall be as per standard drawing 1359.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS04 Cl19.3.4
checkpoint | Construction Testing Requirements: Test Method
note | Acceptance Criteria and Frequency (Project Specific) -
textbox | Max. Lot Size
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
note | Check Item - MRTS04
note | Reference - Table A3
checkpoint | Relative Moisture - Rainfall zone: High (>1000mm), Class A1/A2: 70% - 100%, Class B: 80% - 110%
note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
note | ○ 1 per 100m3
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Relative Compaction - Top 300mm below Subgrade = 97%, Greater than 300mm below Subgrade = 95%
note | Acceptance Criteria and Frequency (Project Specific) - Each culvert/structure
note | ○ 1 per 100m3
note | ○ 2 per lot
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Stockpile Testing Requirements: Test Method
note | Acceptance Criteria and Frequency (Project Specific) -
textbox | Min. Testing Frequency:
textbox | Quarry Source
textbox | Other Source
note | Check Item - MRTS04
note | Reference - Table A3
checkpoint | Grading
note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Plasticity Index
note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Linear Shrinkage
note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Emerson Class Number: AS 1289.3.8.1
note | Acceptance Criteria and Frequency (Project Specific) - 5000t, 1000m3
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Soaked CBR and Swell (For earth backfill in subgrade only)
note | Acceptance Criteria and Frequency (Project Specific) - 4000t, 200m3
note | Check Item - Check Item
note | Reference - Table A1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.18 - Subgrade Testing | itp
section | Details
checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point 5
note | Reference - MRTS04 Appendix B.3
checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Testing
note | ○ 1.5m below subgrade in CUT
note | ○ 2.0m below subgrade in EMBANKMENT
note | Check Item - Check Item
note | Reference - MRTS04 Appendix B.3
checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with RMS Test Method T103
note | Acceptance Criteria and Frequency (Project Specific) - Testing
note | Check Item - Check Item
note | Reference - MRTS04 Appendix B.3.1
checkpoint | Fill Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include: – Lab preconditioning, – Field compaction using construction methods propsed for the works. The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5.
note | Acceptance Criteria and Frequency (Project Specific) - Pre-Conditioning
note | Check Item - Check Item
note | Reference - MRTS04 Appendix B.4
checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
note | Acceptance Criteria and Frequency (Project Specific) - Test Reports
note | Check Item - Check Item
note | Reference - MRTS04 Cl. B3.2.2
checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point 6
note | Reference - MRTS04 Appendix B.4
checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
note | Acceptance Criteria and Frequency (Project Specific) - Testing per material type
note | Check Item - Check Item
note | Reference - MRTS04 Cl. B.4 & MRTS04.1 Cl 3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 05.01 - Placement of Unbound Pavement | itp
section | Details
checkpoint | Layer Thickness between 75mm and 250mm in accordance with table 8.3.3
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | ○ Layer Thickness: 75mm - 250mm
note | Check Item - Check Item
note | Reference - MRTS05 Table 8.3.3
checkpoint | Relative Dry Density Requirements: C.V of RDD >= 100% MDD for Type 1 Materials, = 100% SDD for type 2.3, 2.4 and 2.5
note | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD (1 test / 500m2, min 1 / production day, min 4 per lot)
note | Check Item - Check Item
note | Reference - MRTS05 Table 8.4.3
checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
note | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
note | Check Item - HOLD POINT 3
note | Reference - MRTS05 Cl. 8.2
signoff | HOLD POINT
checkpoint | Moisture content such that the degree of saturation is less than 60%(modified). The administrator may accept a higher level of moisture up to a maximum of 70%.
note | Acceptance Criteria and Frequency (Project Specific) - S < 60% (1 test / 500m2, min 4 / lot)
note | Check Item - HOLD POINT 4
note | Reference - MRTS05 Table 8.3.4.1
signoff | HOLD POINT
checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
note | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot
note | ○ Additional tests as directed by the Administrator
note | Check Item - Check Item
note | Reference - MRTS05 Table A3
checkpoint | Geometric Tolerances in accordance with MRTS05.1 Cl.8.4.4.3
note | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC
note | ○ ±15 mm in all other cases (1 test / 20m)
note | Check Item - Check Item
note | Reference - MRTS05.1 Cl.8.4.4.3
checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
note | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
note | Check Item - Check Item
note | Reference - MRTS05 Cl.8.4.4.2 Table A4
checkpoint | Deviation from a 3m straight edge shall be less than 5mm.
note | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test
note | ○ Less than 5mm
note | ○ 1 test per 20m
note | Check Item - Check Item
note | Reference - MRTS05 Cl. 8.4.5
checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
note | Check Item - Witness Point
note | Reference - MRTS05 Cl.9.4.7
checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
note | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
note | Check Item - Check Item
note | Reference - MRTS05 Cl.8.4.4.4
checkpoint | The finished surface of any unbound pavement layer shall: – be hard and homogenous in apperance, – not have any loose, segregated or contaminated areas, – have the coarse particles slightly exposed, – not be affected by delamination, and, – not visibly deflect under load when proof rolled in accordance with Cl 9.4.6
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS05 Cl.8.3.5.1
checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
note | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
note | Check Item - Hold Point 5
note | Reference - MRTS05 Cl.9.1
signoff | HOLD POINT
checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6: a) all testing has been completed, b) the surface finish of the layer complies with the requirements of Clause 8.3.5, c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator, d) the layer has been presented to the Administrator for inspection, and, e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
note | Check Item - Hold Point 6
note | Reference - MRTS05 Cl.9.5.1
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 10.01 - Plant Mixed Lightly Bound (Cemented) Pavements | itp
section | Details
checkpoint | No lightly bound pavement works commenced until all relevant construction procedures have been accepted by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - HOLD POINT 1, Milestone
note | Reference - Clause 5.2 MRTS10
signoff | HOLD POINT
checkpoint | Lightly Bound Pavement Constution Procedure submitted to Administrator at least 14 days prior to commencement of pavement works.
note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
note | Check Item - Milestone
note | Reference - MRTS10 Clause 5.2.1
checkpoint | The unbound pavement material to be used as part of the plant-mixed lightly bound pavement conforms to the requirements of MRTS05.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Hold Point 2
note | Reference - MRTS10 Clause 6.1
signoff | HOLD POINT
checkpoint | Regsitered mix design and terget content of stabilisation agent nominated and submitted to Administrator along with: 1. Stabilised Mix Design Certificate, 2. Quarry Registration Certificate
note | Acceptance Criteria and Frequency (Project Specific) - Submitted 14 Days Prior
note | Check Item - HOLD POINT 3
note | Reference - MRTS10 Clause 7.1
signoff | HOLD POINT
checkpoint | A trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - WITNESS POINT 1
note | Reference - MRTS10 Clause 8.1
checkpoint | Prior to continuing works after completion of the trial, records which demonstrate compliance submitted to the Adminstrator for acceptance.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS10 Clause 8.1
signoff | HOLD POINT
checkpoint | Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS05 Clause 7
checkpoint | Equipment as specified in approved construction procedure.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Cl.8.2.1
checkpoint | The time between the commencement of mixing the stabilisation agent into the unbound material and the completion of compaction of a single layer is less than the allowable working time. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following a) Tested working time shown on the mix desing certificate, b) Four hours
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.3
checkpoint | Lightly bound pavements not constructed when: a) air temperature is less than 10°C or greater than 40°C, b) during rain or when rain is likely to fall during placement, c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the pavement layers
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.4
checkpoint | Individual compacted layer thicknesses in accordance with Table 8.2.7.1. Minimum - 125mm, Maximum - 250mm
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.7.1
checkpoint | Where a lightly bound pavement layer is to be overlaid directly with another lightly bound pavement layer, the finished surface is hardcut to uniformly roughen the surface across the full width of the layer.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.7.2
checkpoint | Unless constructed in the same shift, a cement slurry is applied to the hard-cut surface prior to placing the next lightly bound pavement layer.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.7.2
checkpoint | Each layer of lightly bound pavement cover with the next layer or bituminous surfacing within seven days of placement. Lightly bound layers not covered with a sprayed seal or prime within 48 hours of placement.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.9
checkpoint | Longitudinal joints offset by a min. 150mm from joints in underlying layers, located away from wheel paths and in the final layer coincide with the lane-marking or change in crossfall. Transverse joints offset by a min. 2.0m from joints in underlying layers.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.10
checkpoint | For fresh joints between adjoining or adjacent run, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Cl. 8.2.10.1
checkpoint | Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Cl. 8.2.10.2, Cl.6.4
checkpoint | With the exception of vehicles directly involved with curing, compliance testing, sealing operations and construction of overlaying pavements and subsoil/pavement drains, lightly bound layers not opened to traffic until the lost has been tested and passes proff rolling.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.2.11
checkpoint | Intelligent Construction (IC) rollers shall be used to compact lightly bound pavement material
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10.1 Clause 8.2.1.7
checkpoint | The actual content of stabilising agent for each lot complies with the requirements in Table 8.3.2. Min/Max Value = Target Content +/- MPV (Mixing-Plant-Variability)
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.2
checkpoint | Unconfined compressive strength between 1 - 2MPa
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.3
checkpoint | The characteristic value of relative compaction shall not be less than 100%, except for the upper most layer of lightly bound base which shall not be less than 102% Compaction testing will be conducted at the 4hrs working time after batching.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.4
checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.5.2
checkpoint | The primary tolerance for the Lightly Bound Layer shall be ± 10mm. Further, the total thickness of the constructed Lightly Bound Layer shall be within -20mm, +unspecified of the specified thickness.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.5.3
checkpoint | Deviation of a straight edge placed anywhere on the surface shall not exceed 5mm over 3m
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.6
checkpoint | Crossfall shall not differ from the designed crossfall by more than 0.5% absolute.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.5.4
checkpoint | Horizontal tolerances shall not be more than ± 50mm except for the following: a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm, b) Where alignment of the pavement with an existing structure is necessary
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.5.2
checkpoint | The Maximum Road Roughness shall not be greater than (Rs) "2.31m/km"
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10.1 Clause 8.3.7
checkpoint | For lightly bound layers that are to be covered by a sprayed bituminous surfacing, the maximum ball penetration is less than 3mm
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS10 Clause 8.3.8
checkpoint | The perceptible surface deformation test shall be undertaken in the presence of the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - WITNESS POINT
note | Reference - MRTS10 Clause 9.4.10
checkpoint | No lightly bound layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed, the surface finish comlies with Clause 8.2.7 and the layer presented to the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Written
note | Check Item - HOLD POINT
note | Reference - MRTS10 Clause 9.5.1
signoff | HOLD POINT
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 04.11 - Demolition of Road Furniture | itp
section | Details
checkpoint | Road furniture to be removed are as listed in MRTS14.1.
note | Check Item - Check Item
note | Reference - MRTS14.1
checkpoint | Existing road furniture demolished and removed avoiding damage to any adjacent work.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl.7.3
checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl.7.3
checkpoint | Milestone - Dismantling and removal shall not commence until expiration of the seven day period. Hold Point 2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS14 Cl.7.3
checkpoint | The items of road furniture to be removed and re-erected shall be as listed in Clause 4 of Annexure MRTS14.1. Not less than seven days prior to commencement of dismantling and removal of any road existing furniture, the Contractor shall submit a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS14 Cl.9
signoff | HOLD POINT
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 14.01 - Supply and Installation of Road Signs | itp
section | Details
checkpoint | Dismantling of items to be salvaged
note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
note | Check Item - Hold Point 1
note | Reference - Cl8.2
signoff | HOLD POINT
checkpoint | Dismantling of items to be re-erected
note | Acceptance Criteria and Frequency (Project Specific) - Submission Schedule
note | Check Item - Hold Point 2
note | Reference - Cl9.2
signoff | HOLD POINT
checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 CL 13.2
checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 CL 13.2
checkpoint | Other materials may be considered but evidence of the full approvalof the department will be provided to the administrator prior to their use.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point
note | Reference - MRTS14 CL 13.3.1.1
signoff | HOLD POINT
checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 13.3
checkpoint | Sign faces are fabricated in accordance with the requirements of the Design Guide for Road signs to the size specified in the contract
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 13.4
checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 14.2.3
checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 14.2.3
checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 14.3
checkpoint | Erection of Road Signs
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS14 Cl 14.4
checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl 14.4.2
checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS14 Cl14.4.5
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 16.01 - Landscape and Revegetation Works | itp
section | Details
checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
note | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
note | Check Item - Hold Point 1
note | Reference - MRTS16 Cl 5.2.1
signoff | HOLD POINT
checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Hold Point 2
note | Reference - MRTS16 Cl 5.2.2
signoff | HOLD POINT
checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Hold Point 3
note | Reference - MRTS16 Cl 5.3.1
signoff | HOLD POINT
checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Hold Point 5
note | Reference - MRTS16 Cl 5.3.3
signoff | HOLD POINT
checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
note | Acceptance Criteria and Frequency (Project Specific) - Plan
note | Check Item - Hold Point 6
note | Reference - MRTS16 Cl 5.3.4
signoff | HOLD POINT
checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | Materials are stored to ensure no deterioration or contamination occurs
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7
checkpoint | containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7.6.2
checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8
checkpoint | Ground preparation works carried out within the drip line of retained vegetation, 300mm of paths, kerbs, road furniture or structures and in accordance with TMR Standard Drawings 1644 and 1646
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.4 TMR SD 1644
checkpoint | Site is weed free prior to ground preparation operations
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.3
checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents, ripping, cultivation, roughening
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.1.1, Cl 8.4.1.1, Cl 8.4.1.2, Cl 8.4.1.3, Cl 8.4.1.4
checkpoint | Stockpiled topsoil is in accordance to Form D - Manufactured Site Topsoil Compliance Testing prior to being used
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 7
note | Reference - MRTS16 Cl 8.2.1
signoff | HOLD POINT
checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 8
note | Reference - Cl 8.4.1.1
signoff | HOLD POINT
checkpoint | The contractor shall submit 1kg samples (plus test certificates) of proposed amelioration agents 4 weeks prior to use for direction as to their suitability.
note | Acceptance Criteria and Frequency (Project Specific) - Test Reports, Samples
note | Check Item - HOLD POINT
note | Reference - CTS16 Cl. 3.1.6
signoff | HOLD POINT
checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.4.2.1
checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by spreading fertiliser over the topsoil and raking the surface smooth
note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
note | c) on the day turf is delivered to site
note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.2.
checkpoint | Hydromulch Seeding installed in accordance with Cl 8.5.1.3, with equipment producing a uniformly applied, homogenous slurry that is applied indirectly, and from at least 2 directions with no watering on the day of installation.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.1.3
checkpoint | Single Pass Hydromulch Seeding installed in accordance with Table 8.2.1.4
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.2.1.4
checkpoint | Fertilisers are broadcast evenly over topsoil in accordance to manufacturer's recommendation and the prepared surface has had a water and a wetting agent applied
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.1.3
checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.2
checkpoint | Mulching be manufactured in accordance with Clause 8.2.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7.6.3.1
checkpoint | Matting shall be installed in accordance to 8.5.1.7 and according to manufacturers recommendations and in accordance with TMR Standard Drawing 1648.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.1.7 TMR SD 1648
checkpoint | Plants installed within 5 days of mulch or matting and within 48 hours of delivery with initial watering on the day of installation, as soon as practical after planting and in accordance with Table 8.5.3.1 and 8.5.3.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.3.2
checkpoint | Administrator notified of plant delivery to allow for inspections
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS16 Cl 8.5.3.1 & Cl8.5.3.2
checkpoint | Prior to installing plants, plants shall be set out in accordance with Clause 8.5.3.3 The Contractor shall give two days notice prior to delivery of plants to allow inspection of the plants
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 11
note | Reference - MRTS16 Cl 8.5.3.3
signoff | HOLD POINT
checkpoint | <25L Container Plants installed as per Cl 8.5.3.1 and Table 8.5.3.1 while ≥25L container plants installed as per Cl 8.5.3.2 and Table 8.5.3.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.5.3.2, Cl 8.5.3.1
checkpoint | Plant mats installed in accordance with TMR Standard Drawing 1647, type of organic matting shall be as specified in Clause 3.4.3 of the Annexure MRTS16.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 8.7.6.4 TMR SD 1648
checkpoint | Stakes and guying shall be in accordance with Table 7.6.5 TMR Standard Drawings 1653 and 1655 while Guying shall be installed with containers ≥200L, ex-ground and transplanted trees and in accordance with TMR SD 1656
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 7.6.5 TMR SD 1653, TMR SD 1655, TMR SD 1656
checkpoint | Certificate of commencement of landscape and revegetation works establishment period issued and is a minimum of 90 days
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.1
checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 9.1.1
checkpoint | If a plant failure is determine to relate to the species, a substitute species has been proposed and submitted to the administrator for suitability
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 10
note | Reference - MRTS16 Cl 9.1.1.5, Cl 9.2.1.5
signoff | HOLD POINT
checkpoint | Certificate of commencement of landscape and revegetation works monitoring period issued and is a minimum of 90 days unless otherwise specified in Clause 4.2 of the Annexure MRTS16.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.2
checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS16 Cl 9.2.1
checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS16 Cl 9.2
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 28.01 - Contractor's Camp and Site Facilities | itp
section | Details
checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl. 4.2
checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided. The Contractor shall supply, equip, service and neatly maintain all necessary buildings, workshops, first aid facilities, parking areas and storage areas for the satisfactory completion of the Work.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl. 4.3
checkpoint | If so stated in Clause 3 of Annexure MRTS28.1, the Contractor shall provide a separate room for the Administrator within the Contractor’s site facilities. The office accommodation is for exclusive use of the Administrator during Work Under the Contract and the size and any amenities required to be provided by the Contractor as stated in the Clause 3 of Annexure MRTS28.1. To encourage collaboration between all parties, the room shall be in the same building with the rest of the Contractor's staff and is to enable private meetings as required between the Administrator and the Principal.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl. 4.4.2
checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl. 4.5.7
checkpoint | Contractors camp complies with all requirements of MRTS28 a with a proposed site facility layout submitted to the administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28 Cl.4.5.1
checkpoint | Contractors camp complies with all requirements of MRTS28.1 Annexure
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28.1, C.l 3
checkpoint | Supplementary Requirements completed as per C.L 8.1 & 8.2 & 8.3
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS28.1 Cl. 8, Additional Obbligation Documents
checkpoint | Final Verification
note | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 30.01 - Dense Graded Asphalt | itp
section | Details
checkpoint | Submission of Asphalt Quality Plan (7 days)
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS30 Cl 5.2
signoff | HOLD POINT
checkpoint | Recommencement of production after non conforming Tensile Strength Ratio
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS30 Cl 7.2.5
checkpoint | Submission of Asphalt Mix Design Certificate (7 days)
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS30 Cl 7.3.3
checkpoint | Incorporation of asphalt into the Works
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS30 Cl 7.4.1
signoff | HOLD POINT
checkpoint | Acceptance of a non conforming or nonstandard mix design for incorporation into the Works
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS30 Cl 7.4.1
signoff | HOLD POINT
checkpoint | Approval to place asphalt over weak substrate substrate
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.2.2
signoff | HOLD POINT
checkpoint | Proof rolling of substrate
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.2.2
checkpoint | Mark out of cracks to be filled substrate
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.2.3
checkpoint | Marking out the areas on which strain alleviating fabric strips are to be applied
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.2.4
checkpoint | Approval to place asphalt at a nonconforming layer thickness
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.6.2
signoff | HOLD POINT
checkpoint | Approval to place asphalt at a nonconforming pavement temperature
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.7
note | HOLD POINT
checkpoint | Placing of the nominated mix (after placement trial)
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS30 Cl 8.11
note | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 45.01 - Road Surface Delineation | itp
section | Details
checkpoint | All material conforms to requirements set out in Clause 6 of MRTS45.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 6
checkpoint | Installtion of Pavement Markings conforms to requirements set out in Clause 7.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7
checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.2
checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.3
checkpoint | In addition to Cl. 7.3, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS45 Cl 7.3
signoff | HOLD POINT
checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS45 Cl 7.4
signoff | HOLD POINT
checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.5
checkpoint | All Markings are of uniform thickness and intensity
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.5.2.3
checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
note | Acceptance Criteria and Frequency (Project Specific) - Visual, Table 7.5.2.4
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
checkpoint | A primer was placed just prior to thermoplastic materials as per manufacturers specifications
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.5.3.1
checkpoint | Thermoplastic shall be applied at a temperature as per the manufacturers specifications
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.2, Cl 7.5.3.2
checkpoint | Thermoplastic applied at a minimum of 2mm thickness
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.5.3.3
checkpoint | Raised Pavement Markers installed in accordance with Cl 4.6.3 of the MUTCD
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.6
checkpoint | Material complies with luminance and retro-reflectivity requirements
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.7.6
checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.8
checkpoint | Completed Pavement Markings are uniform, clean and well-defined edges with deformation and conforms to dimensions as set out in the MUTCD
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.9
checkpoint | Pavement Markings conform to all tolerances
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS45 Cl 7.9
checkpoint | Quality Verification Requirements, Test Method
note | Acceptance Criteria and Frequency (Project Specific) -
textbox | Min. Testing Frequency
textbox | Min. No. of Tests
note | Check Item - MRTS45
note | Reference - Annexure
checkpoint | Materials
note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch, 1 test
note | Check Item - Check Item
note | Reference - MRTS45.1
checkpoint | Thickness of Pavement markings: Longtitudinal lines, Transverse markings
note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot/ 1 test
note | ○ 1 per lot/ 1 test
note | Check Item - Check Item
note | Reference - MRTS45.1
checkpoint | Dimensions of Pavement markings: Longtitudinal lines, Transverse markings
note | Acceptance Criteria and Frequency (Project Specific) - 1 per 200m/ 1 test
note | ○ 1 per type/ 1 test
note | Check Item - Check Item
note | Reference - MRTS45.1
checkpoint | Dimensions of raised pavement marker placement
note | Acceptance Criteria and Frequency (Project Specific) - 1 per 50 / 1 test
note | Check Item - Check Item
note | Reference - MRTS45.1
checkpoint | Retroreflectivity
note | Acceptance Criteria and Frequency (Project Specific) - 1 per lot / 1 test
note | Check Item - Check Item
note | Reference - MRTS45.1
checkpoint | Skid Resistance
note | Acceptance Criteria and Frequency (Project Specific) - 1 per batch / 1 test
note | Check Item - Check Item
note | Reference - MRTS45.1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 51.00 - Environmental Management Systems | itp
section | Details
checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with Conditions of Contract.
note | Check Item - Milestone
note | Reference - MRTS51 Cl. 6.3
checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
note | Check Item - Hold Point 1
note | Reference - MRTS51 Cl. 6.3
signoff | HOLD POINT
checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
note | Check Item - Hold Point 2
note | Reference - MRTS51 Cl. 6.4
signoff | HOLD POINT
checkpoint | Environmental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a Weekly basis.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 7.1
checkpoint | The Contractor shall be responsible for the management of the below inline with the requirements outlined within the Additional Obligation Documents and MRTS51.1:
note | ○ Landfill Gas Requirements
note | ○ Contaminated Land Requirements
note | ○ Water Quality Requirements
note | ○ Bio Security Requirements
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - Contract Documents
checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite BCC organised Cultural Heritage Training completed and applicable inspection where required
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.4.1
checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.5.2
checkpoint | Project records shall include all noise monitoring results if required
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.6.3
checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.6.2.3
checkpoint | Where identified in Cl. 4.3 of Annexure MRTS51.1 the contractor shall undertake vibration monitoring at vibration sensitive receptors.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl. 8.6.1
checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl. 8.6.2
checkpoint | The contractor shall ensure that construction activities do not result in air quality impacts that cause environmental nuisance or harm. Burning of material shall not be permitted
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.7.3
checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.8
checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.9.1
checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list. Carry out Dawn and Dusk Frog Calling prior to Clearing works and other requirement Frog management where required inline with additional obligation documents
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.10.1
checkpoint | A pre-clearing and post clearing report must be provided by the koala spotter.
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl. 8.10.3
checkpoint | The contractor shall be responsible for the management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.11.1
checkpoint | All declared pest known to occur within the worksite and associated management requirements are stated in Cl. 9.1 of Annexure MRTS51.1.The contractor shall manage all declared pests (Animals and Plants ) within the worksite by preventing their spread on and off site
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.12.2
checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.13.2
checkpoint | Fire Ant Inspection Carried out with TMR prior to works commencing. Certificates for applicable imported Items where required.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - BCC Supplied Certificate
checkpoint | Monthly reporting requirements up-to-date copies of all monitoring results and tracking registers (including waste registers) within 5 business days of the end of a calendar month and upon request.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51.1 Cl4.2
checkpoint | Maintan a animal tamping register inline with the SMP
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - SMP requirement
checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 8.14.1
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 52.01 - Erosion and Sediment Control | itp
section | Details
checkpoint | No construction work to commence before an Erosion and Sediment Control Plan has been submitted to the Administrator and assessed as suitable.
note | Acceptance Criteria and Frequency (Project Specific) - Check Item
note | Check Item - Hold Point 1
note | Reference - MRTS52 Cl. 6.1
signoff | HOLD POINT
checkpoint | The Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
note | Acceptance Criteria and Frequency (Project Specific) - Check Item
note | Check Item - Hold Point 2
note | Reference - MRTS52 Cl. 7.1
signoff | HOLD POINT
checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Records
note | Reference - MRTS52 Cl. 8.1
checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Records
note | Reference - MRTS51 Cl. 8.2.3.2.1
checkpoint | The Contractor shall maintain all erosion and sediment controls in effective working order including reconfiguring drainage lines as required during the construction process to ensure dirty water is directed into sediment controls at all times. Reuse of the water collected in sediment ponds or basins for dust suppression and roadworks is preferred over release into the environment. Where water is being stored for dust suppression the required design capacity of the basins shall be available.
note | ○ Sediment basins and other sediment controls shall be operated and maintained in a manner that minimises the risk of environmental harm. The design capacity of the upper settling volume shall be made available within 120 hours of the most recent rainfall event which causes runoff.
note | ○ The sediment storage zone shall be maintained at all times with the accumulated sediment removed in a manner that does not allow the sediment to be conveyed into a watercourse or offsite.
note | ○ Where coagulants or flocculants are used to treat stormwater, they must not cause harm to the receiving waters or environment. A jar test or streaming current detector (SCV) must be undertaken to estimate volumes of the coagulant or flocculant required and to reduce the risk of overdosing.
note | ○ Coagulants or flocculants containing aluminium (including alum and PAC) shall not be used when water is being discharged to an acidic environment where natural pH is less than 6.0 (such as wallum stream or wetland).
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 7.2
checkpoint | The Contractor shall remove temporary controls when permanent measures are in place and/or Site stabilisation has occurred. This should occur prior to the end of the Defects Liability Period or the end of the Landscape and Revegetation Works Monitoring Period whichever is the later. The Contractor will not receive a Final Certificate until these temporary controls have been removed from the Site. Any areas used for erosion and sediment control shall be rehabilitated to the satisfaction of Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS51 Cl. 7.3
checkpoint | The Contractor is required to conduct daily visual assessments of erosion and sediment control structures to verify their condition and effectiveness. The Contractor shall also conduct weekly site inspections. Where any defect or damage is identified it is required that they be rectified immediately. This information must be recorded at the time of inspection, and both daily and weekly records submitted in the Contractor’s Weekly Site Inspection Reports (refer Clause 7.1 of MRTS51). The Contractor's ESCP’s and EMP(C) shall document detailed response procedures to address any observed or documented sediment release or erosion.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Records
note | Reference - MRTS51 .1 Cl. 4.1.1
checkpoint | Independent ESC audits shall be undertaken in accordance with Section 9.1 of MRTS52 and includes one audit immediately following clearing and grubbing, one audit during any cut/fill activities and one audit at the end of major earthworks. Reports shall be submitted to the Administrator within three days of the audit.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Records
note | Reference - MRTS51.1 Cl. 4.1.3
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
checklist | 70.01 - Placement of Concrete | itp
section | Details
checkpoint | Concrete placed within 1 hour (conc. Temp<=32 degrees) or 45 mins (32>conc. temp < 35 degrees) from the time of charging the mixer unless a retardant is used and approved by the Administrator. No concrete may be placedthe temperature of the concrete is less than 10°C or exceeds 35°C
note | Acceptance Criteria and Frequency (Project Specific) - 10< Temp <35 Continuous
note | Check Item - Check Item
note | Reference - MRTS70 Cl 13.1
checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 15.3
checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 2
note | Reference - MRTS70 Cl 15.3
signoff | HOLD POINT
checkpoint | No concrete placed until falsework, formwork, reinforcement and stressing materials inspected by administrator, foreign material removed from forms and equipment and placement procedures approved.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 3
note | Reference - MRTS70 Cl 15.4.1
signoff | HOLD POINT
checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS70 Cl 15.6
signoff | HOLD POINT
checkpoint | No concrete shall be placed in the Works until:
note | a) the formwork and reinforcement have been inspected
note | b) all foreign material has been completely removed from the forms
note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS70 Cl 15.6.1
signoff | HOLD POINT
checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 15.6.1
checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
note | Acceptance Criteria and Frequency (Project Specific) -
note | Slump Test: ¦¦ Spread Test:
note | <60 - ±10 ¦¦ 500 - 600(HWC) ±80
note | 60<80 - ±15 ¦¦ 650 - 700(HWC) ±50
note | 80<110 - ±20
note | 110<150 - ±30
note | 150< 200 - ±40
note | Every Load
note | Check Item - Check Item
note | Reference - MRTS70 AS 1379 Table 6
checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample
note | Acceptance Criteria and Frequency (Project Specific) - 1-3 Loads - Every Load
note | ○ 4-10 Loads - 4 Samples
note | ○ 11-23 Loads - 5 Samples
note | ○ >24 Loads - n/4
note | Check Item - Test Results
note | Reference - MRTS70 Cl 15.2
checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 16.5.2
checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set.If an interruption greater than 45 minutes occurs, a construction joint approved by the Administrator shall be placed.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl.16.5.1
checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 7
note | Reference - MRTS70 Cl 15.13
signoff | HOLD POINT
checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 6
note | Reference - MRTS70 Cl 15.8
signoff | HOLD POINT
checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 15.8
checkpoint | Following removal of forms
note | ○ Fins and unwanted projections are ground off
note | ○ Pockets and honeycombed areas repaired using approved methods
note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 16.8.1
checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual < Specified MRTS70 Cl15.7.3
note | Check Item - Check Item
note | Reference - MRTS70 Cl 15.7.3
checkpoint | Acceptance or Rejection of Hardened Concrete
note | Acceptance Criteria and Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
note | b) < Fc (Ave 3 consective samples from Lot)
note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
note | In addition
note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
note | Check Item - Test Results
note | Reference - MRTS70 Cl 12.5
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Details: Concrete Record
checkpoint | 1 - Date
date | Truck 1:
date | Truck 2:
date | Truck 3:
date | Truck 4:
checkpoint | 2 - Docket
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 3 - Time Batched
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 4 - Truck Arrival Time
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 5 - Load Size (m3)
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 6 - Mix
checkpoint | 7 - Slump (mm)
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 8 - Slump Time
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 9 - Concrete Arrival Temperature (˚C)
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 10 - Ambient Temperature at time of slump (˚C)
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 11 - Time Start delivery
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 12 - Time Finish Delivery
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checklist | 70.02 - MRTS70 Normal Class Concrete | itp
section | Details
checkpoint | Concrete class - The strength grade of concrete and maximum nominal aggregate size used shall be as specified on the Drawings.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 17.1
checkpoint | Acceptance and rejection of hardened concrete - Acceptance and rejection of hardened concrete shall be on a production assessment basis in accordance with AS 1379 except as noted below. Concrete for the following applications shall betested on a project assessment basis, where more than 25 m³ of concrete is used:
note | a) signpost footings and plinths with dimension greater than 150 mm
note | b) spill through or rock grouting, and
note | c) manually placed kerb and channel on or alongside concrete base.
note | ○ Production assessment reports in accordance with AS 1379 shall be submitted to the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Test Results
note | Reference - MRTS70 Cl 17.8
checkpoint | Approval of falsework - All formwork shall be subject to inspection and approval by the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS70 Cl 17.10
signoff | HOLD POINT
checkpoint | Approval of formwork - All formwork shall be subject to inspection and approval by the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS70 Cl 17.11
signoff | HOLD POINT
checkpoint | Supports (bar chairs and spacers) - All bar chairs and spacers shall comply with AS/NZS 2425
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 17.11.1
checkpoint | Where concrete work is constructed on ground surfaces or on a foundation bedding, a polythene sheet separator of thickness not less than 100 μm shall be employed between the ground / bedding and the concrete
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Check Item
note | Reference - MRTS70 Cl 17.12.1
checkpoint | Approval to place concrete - No concrete shall be placed in the Works until the formwork and reinforcement have been inspected, and all foreign material has been completely removed from the forms.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS70 Cl 17.12.1
signoff | HOLD POINT
checkpoint | Placing of concrete - The placing operation shall be conducted in the presence of the Administrator and the Contractor shall give at least 24 hours notice to the Administrator of the time that placing shall start.
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 17.12.1
checkpoint | Removal of formwork - For cast-in-situ concrete, forms, falsework and centring shall remain in position until 72 hours has elapsed.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - HOLD POINT
note | Reference - MRTS70 Cl 17.16
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Signature
section | Details: Concrete Record
checkpoint | 1 - Date
date | Truck 1:
date | Truck 2:
date | Truck 3:
date | Truck 4:
checkpoint | 2 - Docket
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 3 - Time Batched
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 4 - Truck Arrival Time
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 5 - Load Size (m3)
textbox | Truck 1: | m3
textbox | Truck 2: | m3
textbox | Truck 3: | m3
textbox | Truck 4: | m3
checkpoint | 6 - Mix
checkpoint | 7 - Slump (mm)
textbox | Truck 1: | mm
textbox | Truck 2: | mm
textbox | Truck 3: | mm
textbox | Truck 4: | mm
checkpoint | 8 - Slump Time
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 9 - Concrete Arrival Temperature (˚C)
textbox | Truck 1: | ˚C
textbox | Truck 2: | ˚C
textbox | Truck 3: | ˚C
textbox | Truck 4: | ˚C
checkpoint | 10 - Ambient Temperature at time of slump (˚C)
textbox | Truck 1: | ˚C
textbox | Truck 2: | ˚C
textbox | Truck 3: | ˚C
textbox | Truck 4: | ˚C
checkpoint | 11 - Time Start delivery
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checkpoint | 12 - Time Finish Delivery
textbox | Truck 1:
textbox | Truck 2:
textbox | Truck 3:
textbox | Truck 4:
checklist | 70.03 - Supply of Concrete | itp
section | Details
checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 9.2
checkpoint | Submission of long distance travel procedure - Where travel times are, by necessity, longer than 90 min as listed in AS 1379, a procedure for longdistance travel or extended placement times shall be submitted to the Administrator
note | Check Item - Milestone
note | Reference - MRTS70 Cl 17.6.1
checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 13.1
checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl 15.11.1
checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS70 Cl15.5
checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. each trial mix shall be a Witness Point with a notice peroid of 3 days.
note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
note | Check Item - Witness Point
note | Reference - MRTS70 Cl 15.1.1
checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 1
note | Reference - MRTS70 Cl 15.1
signoff | HOLD POINT
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP
checklist | 71.01 - Reinforcing Steel | itp
section | Details
checkpoint | Submission of proposed supplier of reinforcement with three days notice prior to supply.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Milestone
note | Reference - MRTS71 Cl 6.1
checkpoint | Acceptance of supplier from Administrator
note | Check Item - Hold Point 1
note | Reference - MRTS71 Cl 6.1
signoff | HOLD POINT
checkpoint | Inspection of steel reinforcement before placement of concrete.
note | Check Item - Hold Point 3
note | Reference - MRTS71 Cl 10
signoff | HOLD POINT
checkpoint | The min. clear distance between parallel bars other than lapped bars shall be the greater of:
label | ○ 1.5 x the diameter of the larger bar
label | ○ 1.5 x max nominal size of aggregate
label | ○ or 40mm
note | Check Item - Witness Point
note | Reference - MRTS71 Cl 10
signoff | WITNESS POINT
checkpoint | Permitted mechanical reinforcing bar splices listed in Clause 1 of MRTS71.1.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 4
note | Reference - MRTS71 Cl 11.3
signoff | HOLD POINT
checkpoint | Installation of mechanical reinforcing bar splices as per provisions in Clause 11.3.2
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Witness Point
note | Reference - MRTS71 Cl 11.3.2
signoff | WITNESS POINT
checkpoint | No substitution of different size, grade or ductility class of steel reinforcement shall be placed unless approved by the Administrator.
note | Acceptance Criteria and Frequency (Project Specific) - Visual
note | Check Item - Hold Point 5
note | Reference - MRTS71 Cl 13
signoff | HOLD POINT
checkpoint | Application for substitution of reinforcement forwarded to Administrator 3 weeks prior to supply
note | Acceptance Criteria and Frequency (Project Specific) - f'c Each Mix
note | Check Item - Milestone
note | Reference - MRTS71 Cl 13
checkpoint | Final Verification
note | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
note | Client Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
signoff | Sign ITP