## Sheet1
Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval | Written Acceptance | Hold Point 1 | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance | Check Item - Hold Point 1 | Reference - MRTS16 Cl 5.2.1 | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
|  | MRTS16 Cl 5.2.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Written Acceptance
Non-Potable Water Plan and permits submitted to the Administrator | Plan | Hold Point 2 | Non-Potable Water Plan and permits submitted to the Administrator | Acceptance Criteria and Frequency (Project Specific) - Plan | Check Item - Hold Point 2 | Reference - MRTS16 Cl 5.2.2 | Check Item - Hold Point 1
|  | MRTS16 Cl 5.2.2 |  |  |  |  | Reference - MRTS16 Cl 5.2.1
Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site | Plan | Hold Point 3 | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site | Acceptance Criteria and Frequency (Project Specific) - Plan | Check Item - Hold Point 3 | Reference - MRTS16 Cl 5.3.1 | Non-Potable Water Plan and permits submitted to the Administrator
|  | MRTS16 Cl 5.3.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Plan
Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site | Plan | Hold Point 5 | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site | Acceptance Criteria and Frequency (Project Specific) - Plan | Check Item - Hold Point 5 | Reference - MRTS16 Cl 5.3.3 | Check Item - Hold Point 2
|  | MRTS16 Cl 5.3.3 |  |  |  |  | Reference - MRTS16 Cl 5.2.2
Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants | Plan | Hold Point 6 | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants | Acceptance Criteria and Frequency (Project Specific) - Plan | Check Item - Hold Point 6 | Reference - MRTS16 Cl 5.3.4 | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
|  | MRTS16 Cl 5.3.4 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Plan
Materials imported to Site shall be free of prohibited or restricted biosecurity matter | Visual | Check Item | Materials imported to Site shall be free of prohibited or restricted biosecurity matter | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 7 | Check Item - Hold Point 3
|  | MRTS16 Cl 7 |  |  |  |  | Reference - MRTS16 Cl 5.3.1
Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm | Visual | Check Item | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 7 | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
|  | MRTS16 Cl 7 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Plan
Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable | Visual | Check Item | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 7 | Check Item - Hold Point 5
|  | MRTS16 Cl 7 |  |  |  |  | Reference - MRTS16 Cl 5.3.3
Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2 | Visual | Check Item | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2 | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 7.6.2 | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
|  | MRTS16 Cl 7.6.2 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Plan
The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings | Visual | Check Item | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 8 | Check Item - Hold Point 6
|  | MRTS16 Cl 8 |  |  |  |  | Reference - MRTS16 Cl 5.3.4
Site is weed free prior to ground preparation operations | Visual | Witness Point 2 | Site is weed free prior to ground preparation operations | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Witness Point 2 | Reference - MRTS16 Cl 8.3 | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
|  | MRTS16 Cl 8.3 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents ripping cultivation roughening | Visual | Witness Point 3, 4, 5 | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents ripping cultivation roughening | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Witness Point 3, 4, 5 | Reference - MRTS16 Cl 8.1.1 Cl 8.4.1.1 Cl 8.4.1.2 Cl 8.4.1.3 Cl 8.4.1.4 | Check Item - Check Item
|  | MRTS16 Cl 8.1.1 Cl 8.4.1.1 Cl 8.4.1.2 Cl 8.4.1.3 Cl 8.4.1.4 |  |  |  |  | Reference - MRTS16 Cl 7
Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations | Visual | Hold Point 8 | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Hold Point 8 | Reference - Cl 8.4.1.1 | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm
|  | Cl 8.4.1.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used. | Visual | Hold Point 7 | Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used. | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Hold Point 7 | Reference - MRTS16 Cl 8.2.1 | Check Item - Check Item
|  | MRTS16 Cl 8.2.1 |  |  |  |  | Reference - MRTS16 Cl 7
The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation. | Visual | Witness Point 6 | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation. | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Witness Point 6 | Reference - MRTS16 Cl 8.4.2.1 | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
|  | MRTS16 Cl 8.4.2.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by: a)spreading fertiliser over the topsoil and raking the surface smooth b) to the prepared surface that has been moistened with a solution of water and wetting agent c) on the day turf is delivered to site d) by laying rolls parallel to the contour, in a staggered brick pattern, and e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur. | Visual | Check Item | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by: a)spreading fertiliser over the topsoil and raking the surface smooth b) to the prepared surface that has been moistened with a solution of water and wetting agent c) on the day turf is delivered to site d) by laying rolls parallel to the contour, in a staggered brick pattern, and e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur. | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 8.5.2 | Check Item - Check Item
|  | MRTS16 Cl 8.5.2 |  |  |  |  | Reference - MRTS16 Cl 7
Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2 | Visual | Check Item | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2 | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 8.5.2 | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
|  | MRTS16 Cl 8.5.2 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1 | Visual | Hold Point 9 | For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1 | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Hold Point 9 | Reference - Cl 8.5.1 | Check Item - Check Item
|  | Cl 8.5.1 |  |  |  |  | Reference - MRTS16 Cl 7.6.2
All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities | Visual | Hold Point 7 | All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Hold Point 7 | Reference - Cl 8.5.1 | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
|  | Cl 8.5.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Broadcast seeding installed as per Cl 8.5.1.2 |  | Check Item | Broadcast seeding installed as per Cl 8.5.1.2 | Acceptance Criteria and Frequency (Project Specific) - | Check Item - Check Item | Reference - Cl 8.5.1.2 | Check Item - Check Item
|  | Cl 8.5.1.2 |  |  |  |  | Reference - MRTS16 Cl 8
Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4 |  | Check Item | Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4 | Acceptance Criteria and Frequency (Project Specific) - | Check Item - Check Item | Reference - Cl 8.5.1.4 | Site is weed free prior to ground preparation operations
|  | Cl 8.5.1.4 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Commencement of the Establishment Period | Issue of Certificate of Commencement of the Establishment Period by the Administrator | Milestone | Commencement of the Establishment Period | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator | Check Item - Milestone | Reference - MRTS16 Cl 9.1 | Check Item - Witness Point 2
|  | MRTS16 Cl 9.1 |  |  |  |  | Reference - MRTS16 Cl 8.3
The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2 | Visual | Check Item | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2 | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 9.1.1 | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents ripping cultivation roughening
|  | MRTS16 Cl 9.1.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Commencement of the Monitoring Period | Issue of Certificate of Commencement of the Moitoring Period by the Administrator | Milestone | Commencement of the Monitoring Period | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator | Check Item - Milestone | Reference - MRTS16 Cl 9.2 | Check Item - Witness Point 3, 4, 5
|  | MRTS16 Cl 9.2 |  |  |  |  | Reference - MRTS16 Cl 8.1.1 Cl 8.4.1.1 Cl 8.4.1.2 Cl 8.4.1.3 Cl 8.4.1.4
All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1 | Visual | Check Item | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1 | Acceptance Criteria and Frequency (Project Specific) - Visual | Check Item - Check Item | Reference - MRTS16 Cl 9.2.1 | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
|  | MRTS16 Cl 9.2.1 |  |  |  |  | Acceptance Criteria and Frequency (Project Specific) - Visual
Certificate of finalisation of landscape and revegetation works monitoring period issued | Issue of Certificate of Completion of the Moitoring Period by the Administrator | Milestone | Certificate of finalisation of landscape and revegetation works monitoring period issued | Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator | Check Item - Milestone | Reference - MRTS16 Cl 9.2.2 | Check Item - Hold Point 8
|  | MRTS16 Cl 9.2.2 |  |  |  |  | Reference - Cl 8.4.1.1
Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used.
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Hold Point 7
Reference - MRTS16 Cl 8.2.1
The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Witness Point 6
Reference - MRTS16 Cl 8.4.2.1
Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by: a)spreading fertiliser over the topsoil and raking the surface smooth b) to the prepared surface that has been moistened with a solution of water and wetting agent c) on the day turf is delivered to site d) by laying rolls parallel to the contour, in a staggered brick pattern, and e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Check Item
Reference - MRTS16 Cl 8.5.2
Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Check Item
Reference - MRTS16 Cl 8.5.2
For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Hold Point 9
Reference - Cl 8.5.1
All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Hold Point 7
Reference - Cl 8.5.1
Broadcast seeding installed as per Cl 8.5.1.2
Acceptance Criteria and Frequency (Project Specific) -
Check Item - Check Item
Reference - Cl 8.5.1.2
Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4
Acceptance Criteria and Frequency (Project Specific) -
Check Item - Check Item
Reference - Cl 8.5.1.4
Commencement of the Establishment Period
Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator
Check Item - Milestone
Reference - MRTS16 Cl 9.1
The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Check Item
Reference - MRTS16 Cl 9.1.1
Commencement of the Monitoring Period
Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator
Check Item - Milestone
Reference - MRTS16 Cl 9.2
All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
Acceptance Criteria and Frequency (Project Specific) - Visual
Check Item - Check Item
Reference - MRTS16 Cl 9.2.1
Certificate of finalisation of landscape and revegetation works monitoring period issued
Acceptance Criteria and Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator
Check Item - Milestone
Reference - MRTS16 Cl 9.2.2