## General
Modify template as required prior to use, e.g. to accommodate project or customer specific requirements, then delete this instructional text when complete.
SECTION 1 – GENERAL DETAILS
Project Name: | Seacliff Wastewater Treatment and Disposal Upgrade |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561469 |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Dunedin City Council |  |  |  |  | B | Report by Breach | CM | Construction Manager
Contract Number: | 9776 |  |  |  |  | C | Check | CR | Cust. Representative
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 11 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Retaining Wall |  |  |  |  | I | Inspection | PM | Project Manager
Discipline: | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor
Specification: | Seacliff Watewater Treatment Plant Upgrade |  |  |  |  | O | Operation | QE | Quality Engineer
[6 empty] | R | Review | QM | QA Manager
Drawings: | [5 empty] | S | Subcontractor | SP | Supervisor
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: (Name) | Calisa Mcleary |  | Date: | 2024-06-11 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Receiving Inspection
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
3.1 | Set Out | Allignment and heights set out by surveyor. Post locations marked out | Levels and positions set out match dimensions specified on drawings privoded | Complience surveys or spot checks | Prior to the commencements of Works | Visual, Instrumental | H | SP,QE,SV,CR
3.2 | Ground bearing capacity | Confirm bearing capacity of founded ground | Bearing capacity not less than 150kpa tested to the pile embedment depth of 2.9m or as agreed by the engineer | Scala records | Prior to the commencements of Works | Instrumental | H | SP,QE,CR
3.3
3.4
3.5

## In Process Inspections
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
4.1 | Post holes | Excavate post holes | Holes are clean and measurement match Drawings | Photos, Site Inspection | During Installation | Visual, Inspection | H | SP,QE,CR
4.2 | Posts | Confirm using H5 poles and check dimensions | Size and length of pole are suitable and match drawings or agreed by the engineer | Photos, Site Inspection | Prior to Installation | Visual, Inspection | H | SP,QE,CR
4.3 | Pour concrete | 20 MPa concrete |  | Photos, dockets | During Installation | Visual | C | SP,QE,CR
4.4 | Subsoil drain | 110mm perforated subsoil drain at base of wall, AP20 washed drainage material filter fabric around subsoil | Installed as specified in drawings or as approved by the engineer | Photos, Site Inspection | During Installation | Visual, Inspection | H | SP,QE,CR
4.5 | Backfill | Backfill behind retaining wall with clean free draining material | Backfill with approved fill material | Photos | During Installation | Visual | C | SP,QE,CR

## Final Inspection and Handover
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key) | Signature
5.1 | Final Inspection |  | Engineer Approval | photos, Engineer signoff |  | On site Inspection | H | SP,QE, CR
5.2
SECTION 6 – COMMENTS
|  |  | Customer Release Granted: | ☐ Yes | ☐ No | Date:
Certificate Number: