## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | 561469-ITP-0001 - Culverts (DG-QA-TP018) | itp | 561469-ITP-0001 - Culverts (DG-QA-TP018) | 559f1b4b-8634-4143-8065-0ea4aa6d1ff3
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
864883f3-956b-5825-a92c-f53b84709d7d | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
bda9b474-ebba-5217-8b61-4fce60a0a49b | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
adec3a1c-825c-52ec-9941-be80928e1d90 | note | Verifying Document - ITP
dc37da69-012d-5ac1-84f7-37354489a537 | note | Frequency - Prior to the commencement of Works
43950bbd-3739-5672-9de3-6e67e1e0cd59 | note | Inspection Type (Visual, other) - Visual
5d4a99e4-4c31-552b-961d-cad316e1b0ab | note | Inspection: Key - R
58acfe65-109c-52b8-aed6-25d5399bad99 | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
6bad99a4-4177-5fb0-8fed-d722cac68acb | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
444e86c0-ef09-5c0e-b64c-d50196839c56 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
6be833b8-c6f1-5adf-b47b-1a38efe3b8bc | note | Verifying Document - Compliance surveys or spot checks
97886708-2f1b-5ee6-987e-12b85b6c0e00 | note | Frequency - Prior to the commencement of Works
78232e15-0fa5-5fbe-bb14-4f1eb701fc7f | note | Inspection Type (Visual, other) - Visual, Instrumental
e972a1aa-b61d-5376-9b2a-8787d68a54f4 | note | Inspection: Key - H
7c5c7c30-42bb-5590-aec1-f4dc384bd2e5 | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.3 - Service location and Hydro Vacumming
77b385e7-04aa-549d-94b3-8da7f3e6e62c | note | Inspection Point: Quality Control Activity - Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1
4ec3b0ff-8cc8-5313-abba-2ed64998d970 | note | Acceptance Criteria - All services identified in B4UDig, plans and mark outs has been physically located
68cc34c3-e5d0-5347-91f0-d242585bad7a | note | Verifying Document - Plans Mark out, photos
5dbe75d6-91f7-5ecc-8789-ff47f91765cb | note | Frequency - Prior to the commencement of Works
54d3434f-72b5-5535-ab66-616ad8abf1b9 | note | Inspection Type (Visual, other) - Visual
4751d4ec-b5b5-5c72-91f9-5cd58a2bdb10 | note | Inspection: Key - H
6ac313d8-3fc1-5a4c-ae73-cf10034c4bbc | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 3.4 - Pipes Delivery
4c4415a7-31f8-55fc-afb2-eb5ccfd61459 | note | Inspection Point: Quality Control Activity - Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C152 - C153
c76d344b-3db6-5180-9f3e-f415dfe520c8 | note | Acceptance Criteria - The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent
933de114-4e4b-5f0c-881e-8c6be4c106be | note | Verifying Document - Delivery docket, Supplier certificate, Photo
ee0c5544-7cb7-533e-b816-8f88e1cd786f | note | Frequency - Prior to the commencement of Works
1c8363b1-a53a-51b0-bd2c-a64d8c4c01f5 | note | Inspection Type (Visual, other) - Visual
d4607d0e-afdf-525f-b50d-2fc910950415 | note | Inspection: Key - C
71b37659-d651-5aea-81cb-e77c92eddef9 | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.5 - Drainage Pipes Delivery
65fe7f60-79c3-5068-b19d-4806616d1969 | note | Inspection Point: Quality Control Activity - Drainage pipes shall be slotted smooth bore PVC or PE pipes, or corrugated polyethylene subsoil drainage pipes in accordance with NZTA F/5 for light duty applications or NZTA F2 for heay-duty applications. Specs 1131: 14.8
2b9067cb-0dbe-5d07-8a38-f02551b644e1 | note | Acceptance Criteria - The charasteritics of the pipes delivered to site match the specifications and the duty requirments or approved equivalent
b3c59bf4-24a8-513f-ad79-6a1028a71578 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
f33b8b35-d0e5-5bfa-a6fc-9a31b2788fa5 | note | Frequency - Prior to the commencement of Works
fa6e683a-ad6f-57c5-b75a-fab9ec7823e7 | note | Inspection Type (Visual, other) - Visual
31da135b-5551-5712-b38a-08188fd8a3cb | note | Inspection: Key - C
e485cc3d-db5c-507c-bcbf-ba14176fbe24 | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.6 - Subsoil drain bedding
f9499bbd-6929-5005-8651-46d8deb873b5 | note | Inspection Point: Quality Control Activity - Material used for bedding, duct surround and haunching shall be selected granular, non cohesive, free draining material with grading between 0.6mm and 19mm. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.8
4324b605-fb51-5c6f-af6c-1e6bdfab1438 | note | Acceptance Criteria - Visual Inspection, Engineer approval
19db612e-828f-5bf9-9bb3-b2a8e0d89479 | note | Verifying Document - Delivery Docket, Laboratory test results
16c0abb0-7489-5eb9-94a4-b465266636ea | note | Frequency - Prior to the commencement of Works
eaae0dd2-2214-5a56-8181-dfbd2a675435 | note | Inspection Type (Visual, other) - Visual, Lab Test
ab0a16fc-a204-5a91-9479-322419b2def1 | note | Inspection: Key - H
2d207e77-e0f3-57e2-9c88-333471ae8afa | note | Inspection: By (Role Key) - QE/SP/MC
| signoff | HOLD POINT
| checkpoint | 3.7 - Pipe Bedding Agregate
c70955be-e306-5e0a-93d0-0956501b8735 | note | Inspection Point: Quality Control Activity - Pipe bedding should be AP20 and in accordance with AS/NZS 2566.2. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.9.1
e044c144-b8a7-5e3b-97e4-b8c3f680c318 | note | Acceptance Criteria - Visual Inspection, Engineer approval
5b84c1ab-d87a-5990-aab6-1404b0980799 | note | Verifying Document - Delivery Docket, Laboratory test results
84f07862-5281-57ca-97b9-984611ddd9b6 | note | Frequency - Prior to the commencement of Works
d88468c4-8555-5118-973b-ea1c0651d38b | note | Inspection Type (Visual, other) - Visual, Lab Test
cae20ed3-5795-5e34-9c9a-9f8f9c442906 | note | Inspection: Key - H
d8ac8ed8-6745-5119-9dac-0ea477707d9c | note | Inspection: By (Role Key) - QE/SP/MC
| signoff | HOLD POINT
| checkpoint | 3.8 - Drainage Aggregate
b8d80dc3-52d6-5595-847d-b96bc666db25 | note | Inspection Point: Quality Control Activity - Drainage aggregate shall be 19 mm uniformly graded, clean, durable aggregate having a crushing resistance of not less than 100 kN when tested in accordance with NZS 4407. Material used for backfilling the trench above any geotextile wrapping shall be free draining granular material. Specs 1131: 14.9.2
c630cade-b500-5102-9074-87b3849a0f45 | note | Acceptance Criteria - Visual Inspection
99343007-246f-51e9-a11d-0c057e5c3fd5 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
45a2e8dc-e939-5b29-bf4e-edb190f29f61 | note | Frequency - Prior to the commencement of Works
5f629e54-8f60-5f11-bdaf-1f59b3ccb7f6 | note | Inspection Type (Visual, other) - Visual
2bdc45fe-bb94-5b67-b868-e8fcb5feede1 | note | Inspection: Key - C
279a852a-4354-5044-9d16-e177a8874d87 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.9 - Backfill Aggregate
8775d160-ae45-5050-8c64-d763ab387de0 | note | Inspection Point: Quality Control Activity - Backfill aggregate should be GAP 65. Samples of backfill material should be tested in accordence of NZS 4402 to determine the MDD at OMC. The solid density of aggregate should be tested in accordance with NZS 4407. Specs 1131: 16.1.1
cbc85375-1611-5dca-9b20-11267794ea80 | note | Acceptance Criteria - Visual Inspection, Engineer approval
d9c77d5b-feaa-50e2-8b56-3847103b0d04 | note | Verifying Document - Delivery Docket, Laboratory test results
cfb9b5a8-726b-5160-9a7b-44f23d38356f | note | Frequency - Prior to the commencement of Works
293e15d1-55a8-512b-a1dd-8ac9ab234590 | note | Inspection Type (Visual, other) - Visual, Lab Test
a8b2971a-3809-5023-a72b-023021a535e2 | note | Inspection: Key - H
193a9c8a-9369-5b3a-83f3-b4d27ac7d2d2 | note | Inspection: By (Role Key) - QE/SP/MC
| signoff | HOLD POINT
| checkpoint | 3.10 - Concrete Manhole
80adacf3-fdd4-5217-84b5-452283238dc5 | note | Inspection Point: Quality Control Activity - Precast concrete manholes shall comply with NZS 3106. Specs 1131: 14.5
b6c54676-0145-5f96-9bfa-c8ee13d766fb | note | Acceptance Criteria - Manhole charasteritics Match NZS 3106
e8e288f4-e9f6-5c38-87f7-2a159bfeed52 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
b0f894ae-7958-5544-97f1-4278ecb81fd0 | note | Frequency - Prior to the commencement of Works
836699cb-39da-5e3d-8669-cb996c19459d | note | Inspection Type (Visual, other) - Visual
eeb4d2b9-5b26-5133-9433-f004a5dce720 | note | Inspection: Key - C
1dd60547-56b8-5b5f-bb30-121c4987977a | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.11 - Wingwalls
f43682e9-80f4-52eb-857e-2cf9f22d63a9 | note | Inspection Point: Quality Control Activity - Precast wingwalls as specified in Drawings or equivalent approved. Drawings C122 - C123
bcc55e0e-162a-508c-a507-89194ed9604f | note | Acceptance Criteria - Procured precast wingwall comply with specifications
748e2836-6152-5614-be53-396b7c614437 | note | Verifying Document - Delivery docket, Photo, Engineer approval
a7340f9f-bb35-574f-b882-2e9807c4133d | note | Frequency - Prior to the commencement of Works
34f91987-fb84-5416-a389-bf92d733a241 | note | Inspection Type (Visual, other) - Visual
a4b7897d-fdcd-54b1-a649-6f7cd2611cca | note | Inspection: Key - C
b5c290e9-72b3-5631-905c-7a57b8f1db87 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.12 - Geotextile
a6a9e88d-58d5-5522-9168-0aa78e5a7284 | note | Inspection Point: Quality Control Activity - Geotextile underlay bidim A37 or similar approved material. Drawings C122 - C123
de099662-e27a-5f67-a173-cfa85bacd0b6 | note | Acceptance Criteria - Procured Geotextile comply with specifications
f8cb3f0e-76d0-5f60-8f58-1f5cc6aa704f | note | Verifying Document - Delivery docket, Photo, Engineer approval
0e6a49f6-b20d-52fd-b7b1-a35f89983679 | note | Frequency - Prior to the commencement of Works
c1bac2f2-dff0-5d45-835b-55a4f5536508 | note | Inspection Type (Visual, other) - Visual
272de0e9-bab3-54b6-9ff2-0fbcbe73d6f5 | note | Inspection: Key - C
279cbc2e-454c-568a-8a98-d4278d612f27 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.13 - Backfill Trail Compaction Testing
12aee127-acc8-51e5-918d-8bf567fb934e | note | Inspection Point: Quality Control Activity - Prior to commencement of fill compaction. Trial compaction plateau test should be conducted under presense of Engineer or principal. Methodology to be confirmed in advance generally in accordance with TNZ B/02 specification. Specs 1131: 16.1.1, 16.1.2, 16.1.4.
1650fc53-63d0-54ac-8082-024650357011 | note | Acceptance Criteria - Compaction Value ≥ Specification Value
01eb9a68-59bc-5b6f-b067-47f8d87543e4 | note | Verifying Document - Nuclear Density Meter (NDM) Results Sheet, or Clegg Hamer test records
837c3747-48d5-55aa-89e5-9cdf3da56f28 | note | Frequency - Prior to the commencement of Works.
5ea468e7-c5c5-530d-a5f4-58270161ac6a | note | Inspection Type (Visual, other) - On site Test
9f891396-7b9e-5a55-a91d-75053a82d2a4 | note | Inspection: Key - H
8a98ce41-72e5-552d-8683-0faff10a5727 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Site Clearance
6fee8f63-1d8a-5a98-aec7-43a234deae99 | note | Inspection Point: Quality Control Activity - The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1
326e9ee6-9689-5601-a884-0df5e9fcb1d1 | note | Acceptance Criteria - Location approved by the Engineer
a6fab7ab-1da4-5160-b72c-a246a1e30bba | note | Verifying Document - Dumping Docket
191dc969-eb1f-5b92-9fb9-829a452ad5a4 | note | Frequency - After site clearance
b5f8c338-f44b-56f3-b368-c80c060b9136 | note | Inspection Type (Visual, other) - Document Check
50bcee70-98e9-58a1-870c-0ed2a265fc48 | note | Inspection: Key - C
3d3ea8bf-38e7-55fd-90a8-a8af26c8cd4c | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.2 - Trees Removal
eae58fc6-066e-50b8-a4d9-0d0c734990a8 | note | Inspection Point: Quality Control Activity - No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2
0b568e32-4886-5ff5-ae2a-94b10a6229e8 | note | Acceptance Criteria - Engineer Approval
ed7152d3-0feb-5cb6-a835-7118680492eb | note | Verifying Document - Engineer Writen Authorisation
59742f61-21cc-5a77-92ac-115d3069000e | note | Frequency - Before remove any tree
d4843d73-2799-5138-9a0d-4f60110bcc87 | note | Inspection Type (Visual, other) - Client Consultation
5559df85-acba-572b-8904-77953858233d | note | Inspection: Key - H
a7942cd2-ebcd-544e-8747-5b01dfeac91a | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 4.3 - Removal of Topsoil
fd03f22a-d56b-5f55-9f0d-5adb6ac8d709 | note | Inspection Point: Quality Control Activity - Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4
ed6f2a6d-333b-5411-ad85-abf79f5052c5 | note | Acceptance Criteria - Engineer Approval
bd4d46e2-5af8-5cc3-ad2b-c183ab5c3a7b | note | Verifying Document - Engineer Writen Authorisation
2e537431-7cf8-5995-9a93-4d99dfe92123 | note | Frequency - Before Topsoil Removal
807325cd-a162-5967-a2f5-bc7581de87d4 | note | Inspection Type (Visual, other) - Client Consultation
b5f8ff1d-b342-52e7-ac47-20baefdd94b0 | note | Inspection: Key - C
fb878761-f078-5767-ac65-addc716af0e5 | note | Inspection: By (Role Key) - CR
| checkpoint | 4.4 - Hazardous Waste and Contaminated soils
d09b1b1b-23c7-5639-a614-feb2427b1b51 | note | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
5dc16231-95e8-5353-aaa2-1219bd9a0d40 | note | Acceptance Criteria - Dumping site approval for contamiantion type
e7949d1b-a031-57b1-a844-17963b893579 | note | Verifying Document - Dumping Docket
f4ced44e-3051-5872-aca0-b2f8080e2ae3 | note | Frequency - If constaminated soils are found
ac48469b-9fd3-57c8-b097-6873df4cf11b | note | Inspection Type (Visual, other) - Document Check
9d86d2b1-67f9-5e05-9661-04ef0ad48d60 | note | Inspection: Key - C
4d88786f-ab33-5d7e-bef4-112f911dbe1b | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.5 - Trench Excavation
1d605149-696d-54ee-9df9-8b2d57e7b14d | note | Inspection Point: Quality Control Activity - Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated.
b227e393-6cc2-55b1-9a97-6e7b08467de5 | note | Acceptance Criteria - Trench width and pipe clearance to walls comply with requirements
98d9e82e-02ab-5b83-87cb-c6f63d20a4f1 | note | Verifying Document - Installation Check Sheet
af1fa435-1a2e-5516-82e8-f0cbb33cbe40 | note | Frequency - During trench excavation
da4dfbba-3efe-5c10-803a-11c8c972dcdb | note | Inspection Type (Visual, other) - Visual, Measurement Check
fcc8d47d-feb4-5486-b8cd-2ee019875745 | note | Inspection: Key - C
51965d56-d947-5012-bcb1-a795d203266b | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.6 - Pipe Bedding and Haunching
67b03906-6b9c-542c-b902-4fbde855ff41 | note | Inspection Point: Quality Control Activity - Bedding and Haunching for flexible pipes should be in accordance with AS/NZS 2556.2 and have minimum embedment zone as shown in tabke from Specs 1131: 15.2.8.2
4e0a9487-f4dd-5d33-8dfa-6ed7c3d38a2a | note | Acceptance Criteria - Bedding and haunching high and with comply width requirements
6e11bd7f-c0ae-5321-92aa-4e117dbd1468 | note | Verifying Document - Installation Check Sheet
9d97bd4b-dadc-594c-8554-3e417ed862ec | note | Frequency - During bedding and haunching installation
97d6b15b-022a-549b-a817-8af78098d1e0 | note | Inspection Type (Visual, other) - Visual, Measurement Check
1fbdac28-2930-5bd5-9c96-063d3d6d4177 | note | Inspection: Key - C
bc288a31-be5b-563b-96f8-1be207a503a1 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.7 - Pipe Line and Level
359b9b24-5740-5385-abbf-b7476bba68fa | note | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line and level within the tolerances specified in Specs 1131: 15.9. Invert levels shall take precedence over depths. Specs 1131: 15.3.12
94f742f2-fd97-506d-bf93-e93999ae9ad0 | note | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
7455f7b7-5b36-533d-b62f-486167b03851 | note | Verifying Document - Grade Check sheet
b3214e29-000a-50ea-bc7e-b37bcc132472 | note | Frequency - During pipe installation
099c7efb-3515-5ceb-b24e-0352d0ab23d1 | note | Inspection Type (Visual, other) - Visual, Instrumental
1aeb7362-d133-538f-aa39-323035f0ee64 | note | Inspection: Key - C
8d2f5998-8abb-506e-aff7-c795134d922a | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.8 - PE Pipe Installation
b1cfafec-a3d7-511f-b4d5-99e61a954238 | note | Inspection Point: Quality Control Activity - Buried PE pipes shall be installed in accordance with AS/NZS 2033 and AS/NZA 2566.2, as applicable. Specs 1131: 15.3.2.2
dc7ca654-bf2a-58a2-91db-c97d9f875880 | note | Acceptance Criteria - PE Pipe Joints and Intallation comply with standard and specifications
0e1b2c9b-d5bf-50fc-878c-a53427b2d65e | note | Verifying Document - Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
182ff691-925d-5ce1-997d-01292207e148 | note | Frequency - Per weld, and during pipe installation
1b7ee44a-0059-56fc-bf0c-b4f0d77fcee3 | note | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
19dde0c4-81c3-55ee-b87b-0a97007c10ad | note | Inspection: Key - C
c0c116e4-2c29-528b-bb84-f3ce92e7086e | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.9 - PVC Pipe Installation
d279cedd-7f47-5036-94dc-ed9f683a2e19 | note | Inspection Point: Quality Control Activity - Buried PVC pipes shall be installed in accordance with AS/NZS 2032 and AS/NZS 2566.2, as applicable. Fusible PVC pipes shall be welded and installed in accordance with the pipe manufacturers recommendations. Specs 1131: 15.3.1.
347f859c-9806-59d4-b630-b676b741a1bf | note | Acceptance Criteria - PVC Pipes Joints and Intallation comply with standard and specifications
a401bf6d-ceeb-5e22-935e-d1ddd79f4463 | note | Verifying Document - Methodology, Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
64fde91e-49b4-51aa-ae06-943dba23b00f | note | Frequency - Per joint or weld, and during pipe installation
bef487ce-4f67-575b-8e5e-9c4fb48ab273 | note | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
3d816812-fdff-5b6e-95cf-776a02ba3ced | note | Inspection: Key - C
83af20f9-d5fa-5722-9b1e-9256ba291a48 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.10 - Precast Concrete Pipe Installation
7ac2ab88-eb46-539e-b726-c2e0d4d2efb1 | note | Inspection Point: Quality Control Activity - Joints between precast pipe units shall be self-centering and shall be sealed with butyl mastic or similar approved to form a watertight joint. Concrete pipes shall be installed in accordance with AS/NZS 3725. Specs 1131: 15.3.6
c9e838f2-97ed-51db-9adb-eaaebcb6e8bc | note | Acceptance Criteria - Precast concrete pipes Joints and Intallation comply with standard and specifications
7e20663c-a52e-5a67-8f02-2f244b324b0c | note | Verifying Document - Methodology. QA records
da3ef1b0-7ca5-5694-ae24-2dcda4bc5354 | note | Frequency - Per joint, and during pipe installation
7ecfe2ad-95f8-5f65-a880-954a538e33de | note | Inspection Type (Visual, other) - Visual
fa9d6014-209f-567b-a7cf-480e063e9348 | note | Inspection: Key - C
9b9059f1-cdc7-53ab-981f-604e8e91403f | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.11 - Aggregate Compaction
4864d079-5026-518a-ac68-a758648de780 | note | Inspection Point: Quality Control Activity - Compaction shall be as stated in Specs 1131: 15.4.4. For concrete pipes the verification testing of compaction shall use a method recommended in table 3 of the CPAA Technical Note on Installing Concrete Pipe and approved by the Engineer. Specs 1131: 15.3.6
e1a450ea-f9b9-5ce5-ad90-031b7d824d3a | note | Acceptance Criteria - Compaction Value ≥ Specification Value
6023f592-9847-5b5f-af8a-b8c3eb400918 | note | Verifying Document - Depending of Pipe material or Aggregate: CBR Checksheet, Nuclear Density Meter (NDM) Results Sheet, Clegg Hamer test records
98ab40f4-f65b-588c-9b7c-ad74f16be20a | note | Frequency - Every 50m of trench (not confirmed) or specified by Engineer
61680b44-4730-56c7-9fa0-5e24b9505127 | note | Inspection Type (Visual, other) - On site Test
62c9302c-6eae-5c85-927f-12e7e22bdab3 | note | Inspection: Key - H
9af443c1-f413-568f-8246-3970bc1a5cff | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 4.12 - Backfill Compaction
f048771d-f2be-5876-99c8-b6991c0da392 | note | Inspection Point: Quality Control Activity - Selected fill within 0.8m depth from finished surface shall be AP 65. Subgrade and subbase shall be compacted in layers no greater than 200 mm thick unless otherwise agreed with the Engineer. Under carriageway basecourse shall be compacted in layers no greater than 150mm thick unless otherwise aggred with the engineer. Specs 1131: 15.4.3.2, 15.4.3.3
63b5a58f-a917-5dd1-b975-219980c6c0bc | note | Acceptance Criteria - Dry Density ≥ 95% MDD (Under Carriageway). Dry Density ≥ 90% MDD (Outside Carriageway)
215dcf72-b6e2-54d3-bf55-01a23c98bb35 | note | Verifying Document - Nuclear Density Meter (NDM) Results Sheet or Clegg Hamer test records
85148599-077e-5628-8e12-5ea7bc5cef4a | note | Frequency - Every 20m of trench, each layer (Under Carriageway). Every 50m of trench, each layer (Outside Carriageway)
91a42034-b4e6-569b-b673-d023f0704c5f | note | Inspection Type (Visual, other) - On site Test
f9670f5c-7242-526a-9e8e-f352b3287b50 | note | Inspection: Key - H
5ed8fa1e-b409-55ec-8ca4-98968dd26265 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 4.13 - Cutting pipes
f31aa27b-bc20-59b7-8aaf-e0d580c45e46 | note | Inspection Point: Quality Control Activity - Where pipes need to be cut to form non-stardard lengths, pipes shall be cut by a method which complies with manufacturers recommendations and provides a clean square profile. Specs 1131: 15.3.7
0815e60d-bb63-5143-a4d0-611ab89b3687 | note | Acceptance Criteria - Pipe cutted up to the specifications
c433e3a9-b498-57c2-ab4b-c04eac8141ba | note | Verifying Document - Methodology, Photos
2a4bc1ba-a5f1-55d9-9737-88fb9cdd951e | note | Frequency - During pipe installation
a49aee2c-dc52-56e0-95f4-9665c6a166cf | note | Inspection Type (Visual, other) - Visual
d268db8b-081c-5854-8cf1-d7fdfb459364 | note | Inspection: Key - C
15cd9be0-a641-589f-b8f4-a56e0b0e8a29 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.14 - Manhole Benching
6f7fd9de-c7f9-5c90-9ef3-8bb4f573e7d0 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days. Semi-circular channels and fittings shall be placed in possition simultaneously with concrete benching and be embedded in true to grade level and line. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar and finished with steel trowel and rounded at corners. Specs 1131: 15.5
1e13d418-9b76-531d-9169-d4e6014a7f71 | note | Acceptance Criteria - Benching built up to the specifications
1e2f9442-6e77-5730-ab3a-bf066da0d03e | note | Verifying Document - Methodology, Delivery Dockey, Photos
00a0e9f8-3ebb-5af2-8d21-29f6787e1e72 | note | Frequency - During benching contruction
e7639a0f-75de-5adb-81a4-3745aa48eb85 | note | Inspection Type (Visual, other) - Visual
7d8bde9b-61c5-557e-81f3-e8133441d7b6 | note | Inspection: Key - C
7b715ddf-3878-522f-95c8-6760ec587e95 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.15 - Subsoil Drains Installation
c7569e0f-249e-543a-b186-741748f8342d | note | Inspection Point: Quality Control Activity - Drains shall be constructed, geotextile layed and backfill carried out in accordance with TNZ Specification F/6. Specs 1131: 15.7
6eb2e92c-6038-534c-a964-69716752f3d2 | note | Acceptance Criteria - Benching built up to the specifications
d5262169-667c-531d-af24-a47922038d89 | note | Verifying Document - Methodology, TNZ Specifications F/6 and F/7, Photos, QA records
cee7f960-3893-59b7-b339-e089dd272d6b | note | Frequency - During Drains Installation
27fa8af5-5910-5f19-b7fb-afcc5be92e7b | note | Inspection Type (Visual, other) - Visual
f23ff5ea-e1ba-561a-92a9-d568fa574752 | note | Inspection: Key - C
23520cce-27e4-502f-8a8c-8a739df024d4 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.16 - Topsoiling and grassing
21188080-ed27-5797-adb6-9216a24285af | note | Inspection Point: Quality Control Activity - Topsoil shall be used to dress areas disturbed by the contrat works to a minimum thickness of 100mm. Grass seed shall be sown evenly over the prepared topsoil area. Specs 1131: 15.8.6
5114b57f-c1ba-5ce7-8458-c9046f6cb149 | note | Acceptance Criteria - Topsoil installed and grass seed spread in the specified rate and mixture.
c5d5e885-1483-5fb7-8a50-ece26a7459ea | note | Verifying Document - QA records, Photos
a94eed66-dbd2-568a-a641-d7216f3391de | note | Frequency - After compaction of final layer of backfill
ee498165-8ce7-5bea-8b03-346cc7d630d0 | note | Inspection Type (Visual, other) - Visual
cc89dfd2-b5d6-58a0-ae4f-5b4cc04a8a18 | note | Inspection: Key - C
e09009b3-0f69-54cd-879e-b11fdcf1d572 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.17 - Rock Riprap Instllation
32c0fe72-7653-538a-8456-fea75de43fb7 | note | Inspection Point: Quality Control Activity - Rock riprap shall comply with the dimensions and specifications shown in drawings. Drawings C123, C 152 - C155
55d02c46-7f30-5dd6-b8f5-e9886faa926d | note | Acceptance Criteria - Rock rip rap intalling according dimensions and specifications shown in cross sections of project drawings
450763c1-94db-5af6-89fe-c53ec091489e | note | Verifying Document - Installation Check Sheet, QA records, Photos
f3c67440-c7b7-58af-bc76-c1cdf0db7cd7 | note | Frequency - During rock riprap installation
3b58600a-7cb7-5fc3-8d51-05444a73aab9 | note | Inspection Type (Visual, other) - Visual, Measurement Check
0ba16921-9514-5471-9ccd-c7f54d3f4b1d | note | Inspection: Key - C
874bed20-b5be-573f-8230-ee98f48d40ff | note | Inspection: By (Role Key) - QE/SP
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
51764796-2c5b-5734-a1de-96d35c073468 | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
811617bb-8250-5c20-a02c-171b8c9e7af1 | note | Acceptance Criteria - Engineer Approval
eae7f5d8-37b2-5824-b195-6c3a5e53c020 | note | Verifying Document - QA records
66f6ecd6-4f93-5286-9f49-2d5df79a4f10 | note | Frequency - At completion
d5ad1179-ea4f-5307-a6f6-40160bb9754e | note | Inspection: Key - H
8814f7f2-8184-58da-a568-15438a3b03ef | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.2 - Gravity Pipes Testing
5048525b-1453-5f42-83d3-9707089242ea | note | Inspection Point: Quality Control Activity - Stormwater pipes shall be by visual inspection for pipe diameters greater than 750mm and by water testing for diameters up to 750mm. Testing shall be in the presence of the engineer. Specs 1131: 16.2.1
38cbaa66-944c-5db3-ae88-366c3bcee1c1 | note | Acceptance Criteria - Engineer Approval
c0d98839-3e82-5db5-9f5e-bd0aed38e066 | note | Verifying Document - Test Records
fa5719ff-d7a4-53fb-9d0c-72764060886a | note | Frequency - For every section of pipe installed (24hr prior notice to the engineer before test)
58f9847e-4bfc-5195-8021-5e3d6e537c3b | note | Inspection Type (Visual, other) - Test
befbfa94-5e59-5df0-a26a-b6676c114d76 | note | Inspection: Key - H
c6cb515b-f6bb-58ec-a08a-69d8b30ac36e | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.3 - Manholes
959af5b8-c51b-52e8-a8e0-b51bf74b07f8 | note | Inspection Point: Quality Control Activity - Manholes should be tested seperately to pipeline for water tightness up to lower rim of manhole cover frame. Testing shall be in the presence of the engineer. Specs 1131: 16.2.2.5
25ec0881-3acd-512c-a03a-ef2f25e88b96 | note | Acceptance Criteria - A maximum drop in water level over 30 min should not exceed 2mL/hr/mm of diameter/meter height of the manhole. Engineer Approval
1275bc35-36d4-54f7-a70f-1da2b05b1956 | note | Verifying Document - Test Records
e23dc39e-4153-5e43-8c6d-151791209a7d | note | Frequency - For every manhole installed (24hr prior notice to the engineer before test)
cff99d11-a617-56fc-8726-562efd1fd790 | note | Inspection Type (Visual, other) - Test
218e19e3-2435-5c9b-b95a-34f9a45fed23 | note | Inspection: Key - H
e04ca2a0-0b9d-589b-b35e-b99de70afeef | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.4 - CCTV Inspection
8a014343-ab94-528a-905a-15450be339a1 | note | Inspection Point: Quality Control Activity - All pipelines shall pass a CCTV instpection. All pipelines shall be free of debris and flushed 24hrs prior to inspection. Specs 1131: 16.2.3
3661c128-07e0-5ee0-a08f-fb4a3d6e9946 | note | Acceptance Criteria - A pipeline will fail its inspection if:
075f33a6-d162-58bd-a554-175181a28fec | note | – The pipe is horizontally misaligned or deformed by more than 5 % of the pipe diameter.
cca51f3e-a93d-5ffc-860d-9052c3004e11 | note | – The pipe has visible dips or ponding of water.
1f873df1-adab-5e99-a296-37b76eb92b72 | note | – The pipe has visible defects, such as open or displaced joints, defective or protruding laterals, cracked barrels or similar defects.
337ec0dd-223a-5c0b-a458-6eda03167699 | note | – There is evidence of infiltration at joints or laterals.
9edb7c29-7a8d-5850-a023-4668d43f5581 | note | Verifying Document - CCTV footage and log sheets
c4c71121-108b-55fd-868b-7fda631a6d3d | note | Frequency - At every section of pipe installed.
3f2eb7f4-7cc9-595b-b114-0e9a027ea3ab | note | Inspection Type (Visual, other) - Visual
bd263d6d-c0f9-5dbf-a01a-77bd21b82812 | note | Inspection: Key - H
a3b118a1-b11a-5d22-b58c-37b76e40a307 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.5 - Surplus Materials and Refuse Disposal
de2fb8bd-224a-5219-b190-b5ce1983cef6 | note | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
7b7c9d6c-2210-5b29-ae58-5c067fe82061 | note | Frequency - At completion
4d4c20cc-9d04-567a-a6b9-26c4f1cb2e74 | note | Inspection Type (Visual, other) - Visual
373fa264-dfa8-5c8c-a65c-783b7345c8d3 | note | Inspection: Key - C
e88cbe01-81bb-549a-84a0-c8b61f512954 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 5.6 - Cleaning
554bea74-5884-5e72-b76f-10dc77234932 | note | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
b8dbc4de-456e-5659-8429-23fabe3d5d34 | note | Frequency - At completion
6f8880a3-f56d-5b58-bc79-4cef610dbce9 | note | Inspection Type (Visual, other) - Visual
1d5e5709-6677-5dc0-8507-fc25ccf2ea88 | note | Inspection: Key - C
7f9a838a-d216-5569-8bf6-98a582ed6cb7 | note | Inspection: By (Role Key) - QE/SP/CR
| checklist | 561469-ITP-0002 - Access Tracks (DG-QA-TP018) | itp | 561469-ITP-0002 - Access Tracks (DG-QA-TP018) | a5d1febd-11e0-460a-8fb6-b22233bcd5b1
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
48fd5a54-0aa5-5c3f-9383-3042c5204757 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
747fdba9-2e81-5dd0-abe0-8f2923eb99b6 | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
612b44c3-f6c6-512b-8f57-021b0930c35c | note | Verifying Document - ITP
223c5ac7-71f8-5872-9a6c-2beeb3ef9374 | note | Frequency - Prior to the commencement of Works
03d7d778-83af-5cae-bb9a-205eeb8cadb0 | note | Inspection Type (Visual, other) - Visual
12988b04-c193-5522-ae82-7fedbf12c578 | note | Inspection: Key - R
c64cd398-7888-5013-b6a7-b43db3bd8e7b | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
f595049f-cc66-5fe7-befc-bdb22d23c3d6 | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
a22724a1-346b-54c2-9fdd-77f9fd26a10f | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
a839ce10-3693-51eb-b6c4-3ea4e5f020a4 | note | Verifying Document - Compliance surveys or spot checks
67593fee-6e84-5eb1-95f4-6848ff7a4178 | note | Frequency - Prior to the commencement of Works
28864450-c7e0-5ab8-ba97-f6e75911a74a | note | Inspection Type (Visual, other) - Visual, Instrumental
db10332d-0267-5693-89c8-682e122f5b2d | note | Inspection: Key - H
48f686b8-a4f2-52f5-9dff-4db75042775c | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.3 - Service location and Hydro Vacumming
f2d6b3ba-9545-5f9c-99e2-44a9ff6d90c7 | note | Inspection Point: Quality Control Activity - Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1
ad30a2c2-10b2-5303-ba79-7896e28ad423 | note | Acceptance Criteria - All services identified in B4UDig, plans and mark outs has been physically located
34b91f01-529c-5b1e-ad48-a091071254ba | note | Verifying Document - Plans Mark out, photos
6da4f772-92c1-5719-8eab-f2acc114fc73 | note | Frequency - Prior to the commencement of Works
9e001c6a-0fb9-56db-bc8a-209523f9ec94 | note | Inspection Type (Visual, other) - Visual
0bc14506-5a48-551d-9771-71c1ba8969a0 | note | Inspection: Key - H
b6c040f8-cd40-5850-aaa7-153a8a7728c2 | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 3.4 - Aggregate Site Delivery
be1fb10a-f391-584c-896e-671fa0767fda | note | Inspection Point: Quality Control Activity - Sourced GAP65 basecourse and AP20 Running course aggregate shall be clean free from clay, all organic matter and other deleterious materials. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1110: 8.5.1, 9.13
db895e71-9738-53ed-aa10-b07f2d1ed8fb | note | Acceptance Criteria - Visual Inspection, Engineer approval
7f9b6563-47d2-5e6a-91ee-f1087bc810a7 | note | Verifying Document - Delivery Docket, Laboratory test results per source material
84203104-df57-5a57-8078-8e478f51e4d1 | note | Frequency - Prior to the commencement of Works
a8480229-77ac-58c3-8a3a-a209ffd8c36c | note | Inspection Type (Visual, other) - Visual, Lab Test
96f6964b-3139-5c04-a7ab-5c49f00fe946 | note | Inspection: Key - H
13c8deb2-b5fd-55d8-b1a3-a9439e807e0b | note | Inspection: By (Role Key) - QE/SP/MC
| signoff | HOLD POINT
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Site Clearance
00410b27-3e24-5b05-af8b-b3533110e3fd | note | Inspection Point: Quality Control Activity - The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1
a272c086-18cf-5050-b252-fabc0b5d8813 | note | Acceptance Criteria - Location approved by the Engineer
fbd81064-6554-5b26-9a56-7d9c402f2497 | note | Verifying Document - Dumping Docket
062ae6e0-d402-5590-87fa-569c9615f8cc | note | Frequency - After site clearance
a80ec52a-4b78-5009-9f9f-67895542abd4 | note | Inspection Type (Visual, other) - Document Check
3af0719c-9460-5ecb-a516-dc9313aac3b6 | note | Inspection: Key - C
0af3b071-dad3-54b0-a036-9fdc3c7dd117 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.2 - Trees Removal
bd61f653-15c2-59a0-884d-6c385bd41e0f | note | Inspection Point: Quality Control Activity - No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2
7988e606-e6fd-5861-8a72-b7bf866a5e5f | note | Acceptance Criteria - Engineer Approval
389ed5bb-a584-5882-91df-716a7a1b19ad | note | Verifying Document - Engineer Writen Authorisation
9fa7ceeb-a406-505a-a5df-e5678bd5bc39 | note | Frequency - Before remove any tree
9981cd63-895d-5f8b-8856-80f52bdbac05 | note | Inspection Type (Visual, other) - Client Consultation
db656e2f-a9dd-50c8-8bc6-54ed05f43006 | note | Inspection: Key - H
c6f840fa-73b9-5949-8b1e-e8af8f5b3120 | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 4.3 - Removal of Topsoil
e429296d-742f-5fb1-9f1f-c0ee4e833312 | note | Inspection Point: Quality Control Activity - Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4
411ccb63-c1a8-52d3-9ba6-8936ac63914d | note | Acceptance Criteria - Engineer Approval
e8d18c02-3b3e-5924-8f28-9586235b5971 | note | Verifying Document - Engineer Writen Authorisation
cd51c84f-4089-579c-be11-325b5001fe8f | note | Frequency - Before Topsoil Removal
923bcdc4-faba-5084-9b7a-01f429610b40 | note | Inspection Type (Visual, other) - Client Consultation
b79c65bd-8064-5e12-9788-3d79dcf4ecf3 | note | Inspection: Key - C
d67ee7d1-6624-561a-a66d-db82a70f740e | note | Inspection: By (Role Key) - CR
| checkpoint | 4.4 - Hazardous Waste and Contaminated soils
0e9b1643-52be-5b1c-b17d-c7d8dcca5897 | note | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
7e607b3a-baaa-585d-9038-f28c8540579e | note | Acceptance Criteria - Dumping site approval for contamiantion type
68edefec-1908-5539-8f38-e3418bfc6ddc | note | Verifying Document - Dumping Docket
ff2360dc-1d9a-54cc-a8d1-4224c28b9478 | note | Frequency - If constaminated soils are found
e4c44dca-81b3-5bf5-bcc6-9adb2e29ced5 | note | Inspection Type (Visual, other) - Document Check
6077b6cc-c9d8-53b3-aa18-93505ee2bd85 | note | Inspection: Key - C
e70bced2-f0fb-54e5-a822-5fdbf65d6e51 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.5 - Checking Levels and Alignment
261ac64f-48c8-54b3-b2ef-14e5d70f25cb | note | Inspection Point: Quality Control Activity - Compliance surveys or, at a minimum, spot checks, shall be provided to confirm that subgrade levels achieve appropriate accuracy particularly beneath road pavement layers. Specs 1000: 3.2.4
6e545d7e-974d-5925-95ea-16b97b9c455e | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
08aaa478-7d54-5b91-a7df-fa514e61a9dd | note | Verifying Document - Compliance surveys or spot checks
f0c12fc8-bbaf-57d4-ab49-52129906276e | note | Frequency - During and at the end of the Excavation
90f97d4b-3fd3-5d0f-8e6c-41a615dd81a6 | note | Inspection Type (Visual, other) - Visual, Instrumental
2abfeeed-b58f-5bc1-a411-843c51a83953 | note | Inspection: Key - C
13693874-b99a-5365-a103-bf96f2a128d8 | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.6 - Subgrade
ba53938b-10bc-5325-87a7-420dde3cca94 | note | Inspection Point: Quality Control Activity - The subgrade CBR must be tested 5 working days prior to construction. Specs 1110: 9.12.1, Drawing C155
33463c7e-ffc5-5735-a755-b393f428253d | note | Acceptance Criteria - CBR ≥ 5
45e9539e-d9c2-5549-9a2d-d205871493fd | note | Verifying Document - CBR Checksheet
8397b714-e75d-5c5d-9fa9-637ed63f2b30 | note | Frequency - Every 50m of track (not confirmed)
7996fab5-a532-5cc0-9a37-528ac92a782a | note | Inspection Type (Visual, other) - On site Test
89d13f1b-5f36-5676-a86e-4a5bd4e84dd4 | note | Inspection: Key - H
996295cb-913e-549f-a125-14095911c20d | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 4.7 - Basecourse
81e3c75a-e30a-5962-8904-971f606c3085 | note | Inspection Point: Quality Control Activity - On completion of all metalling the surface shall be maintained smooth and level, true to grade and cross section. Specs 1110: 9.8, 9.12.2, 1000: 3.2.4, TNZ F/1 Clause 10 and NZTA B/2
7d52855c-375e-556a-b066-a487000f9a34 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
963867be-b692-506e-b37c-553cdfc4ad5e | note | Verifying Document - Compliance surveys or spot checks
0ffac338-6c2f-5455-a4f0-d24db658e5e2 | note | Frequency - During and at the end of the filling and compaction
0eb6c427-a84e-55e5-aa77-4226be485023 | note | Inspection Type (Visual, other) - Visual, Instrumental
de62973d-367e-5dac-aac3-4505fab6cd78 | note | Inspection: Key - C
8f6e9a93-ee3b-567f-b7a0-0325dc38da67 | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.8 - Basecourse Compaction / Consolidation Testing
3168b38a-819d-52b7-a366-cc018a7d4aae | note | Inspection Point: Quality Control Activity - Maximum density of each metal course layer must be determined. Density meter testin shall be carried on the layers. Specs 1110: 9.12.3, NZTA Clause 7.6
bbefca90-6136-5986-a1ff-b8d53ca8f27d | note | Acceptance Criteria - Dry Density ≥ 95% MDD
23d943e5-cc52-5308-b74c-aca828429e7b | note | Verifying Document - Nuclear Density Meter (NDM) Results Sheet
5fefe6b5-d189-5571-9191-4d4588c8fa98 | note | Frequency - Each 300mm lift shall be tested 1 per 100 m2 (square metres) on a nominal 10m by 10m grid pattern.
dfee7910-c428-580a-8490-eaaaead78272 | note | Inspection Type (Visual, other) - On site Test
944aee03-05bc-53c7-b3a2-fb6fe7a0d46b | note | Inspection: Key - H
2977bc88-157f-5992-bdb0-2654fd23ea94 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 4.9 - Earthworks Tolerance
2a6a0451-61d1-5a6a-b9a3-439295c9dac8 | note | Inspection Point: Quality Control Activity - Earthworks shall be constructed to the tolerances table in Specs 1110: 9.11
1d8ba11e-ba88-5d0c-91cb-2a43840ee8b5 | note | Acceptance Criteria - Parameters inside of the permissible deviation
bab2fc9e-0d99-5a90-a5d7-c523631dd742 | note | Verifying Document - Compliance surveys or spot checks
26db5a8b-a789-5237-8917-3fa7fe2303cf | note | Frequency - During and at the end of the earthworks
b3a92ada-0881-5cb5-89d7-5e41630388b7 | note | Inspection Type (Visual, other) - Visual, Instrumental
36051e78-e997-5666-9b53-2188ef36ed74 | note | Inspection: Key - C
5d57d083-0698-5fda-9afe-4506296bde1f | note | Inspection: By (Role Key) - SP/QE/SV
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
dcd24f8d-f6b4-54f6-b94b-d39b1ddcbe0f | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
a188ba38-05d7-5ff0-91ce-9caa5b6929cb | note | Acceptance Criteria - Engineer Approval
b9b88df3-b099-5fe7-98a1-f0bf3d021fb3 | note | Verifying Document - QA records
de2054ef-0592-571d-ab6d-b8211957e559 | note | Frequency - At completion
1880f2e3-dbf0-51b8-9fd8-28aaa82f210a | note | Inspection: Key - H
e8d1c7f3-cf8d-5582-81d2-4c4868163b6e | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.2 - Surplus Materials and Refuse Disposal
72e71b8d-7bf1-5c63-b2f5-1f6b61934161 | note | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
18b4ca52-1908-5228-82cd-01e5389b289f | note | Frequency - At completion
b588dd75-b3e4-52b0-9ae9-f814e7f69ced | note | Inspection Type (Visual, other) - Visual
d948b944-e9aa-5436-8718-85a2a56ab3b2 | note | Inspection: Key - C
2b68caa2-2091-5cc7-82eb-0f6516c328ec | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 5.3 - Cleaning
cbd20a42-529b-5d6a-b688-2a25ef5b4853 | note | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
adf89486-40c4-5ddc-8bd8-ed6cf9919afe | note | Frequency - At completion
3e13b41a-a8d0-52cf-accf-b4cf4d7770f1 | note | Inspection Type (Visual, other) - Visual
4ff55727-0605-5b05-9149-dafbb0e0aa11 | note | Inspection: Key - C
a71bc721-cbd0-536e-a911-4ea97888a0a6 | note | Inspection: By (Role Key) - QE/SP/CR
| checklist | 561469-ITP-0003 - Pipelines (DG-QA-TP018) | itp | 561469-ITP-0003 - Pipelines (DG-QA-TP018) | 1323ce7b-90e7-4f20-9762-096c837a16e1
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
b2a45e51-c4ea-53d1-ad24-574f92de79c2 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
f9cdbbbe-be4f-5d6a-be56-33a321e8e403 | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
6982a395-97a7-5c87-b2c2-518bc4ecae8c | note | Verifying Document - ITP
8fb5f6ec-043b-5c28-b134-66485309f847 | note | Frequency - Prior to the commencement of Works
d8623bf6-d4b1-55dc-9947-686c0ea52117 | note | Inspection Type (Visual, other) - Visual
f362d90a-4c03-5424-93f8-87ead230c841 | note | Inspection: Key - R
a22e4b84-f673-5b6e-b75c-00918622a037 | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
9d04cd8e-4972-5e1b-b017-1c1ba37fe599 | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
6889dd82-c950-5b38-9e04-6eaef6b23752 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
a0c84092-222b-5af7-b3d0-1301343ad759 | note | Verifying Document - Compliance surveys or spot checks
76393302-3fac-5654-9a62-30a26a7f5be9 | note | Frequency - Prior to the commencement of Works
8708d7a9-20cd-53d2-818b-7b323c75256c | note | Inspection Type (Visual, other) - Visual, Instrumental
0ba30744-6db0-517c-8daf-7ecc0452ba1a | note | Inspection: Key - H
1bbc2151-64eb-53e0-8828-1cad747ac887 | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.3 - Service location and Hydro Vacumming
13f0570c-92b5-5d0b-9361-d61c1e94ec2e | note | Inspection Point: Quality Control Activity - Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1
0061bd5b-d133-5c0a-b5cc-a5869cbb42d1 | note | Acceptance Criteria - All services identified in B4UDig, plans and mark outs has been physically located
4c4768e6-b6e5-562b-9f27-506a19561a48 | note | Verifying Document - Plans Mark out, photos
ecae89ab-b03b-58a1-851d-8018d6e4f4ed | note | Frequency - Prior to the commencement of Works
9c0c1c93-6d4f-568e-9414-63e032af34dc | note | Inspection Type (Visual, other) - Visual
7c5cefd2-96c9-5594-8baf-09c695b5e3af | note | Inspection: Key - H
8e637036-7b6c-5ea4-9e47-45398175e013 | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 3.4 - Pipes Delivery
f0b835eb-67f6-588e-9fcd-6f0b8d659926 | note | Inspection Point: Quality Control Activity - Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C152 - C153
aedf4971-7005-5f9a-b274-12783d755499 | note | Acceptance Criteria - The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent
e76b32af-941f-5d37-b4f6-b20b569a7d17 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
a22b2240-8d59-5238-99c0-af0ed83177c8 | note | Frequency - Prior to the commencement of Works
e2034187-3a11-5dfb-8906-0216edfbc295 | note | Inspection Type (Visual, other) - Visual
729332e5-358c-5f5a-b382-3365cfd59fd4 | note | Inspection: Key - C
f73c884d-2be1-5b60-a5f4-9b273532f87b | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.5 - Valves Delivery
bba8dd1f-d610-5b5f-925e-4a30f97aae8a | note | Inspection Point: Quality Control Activity - Gate valves shall comply with AS/NZS 2638. Valves greater than DN50 shall be resilient seated sluice valves. DN50 shall be gate valves. Sluice valves shall be anti-clockwise closing. DN50 gate valves shall be clockwise closing. Valves shall be provided with a surface box according to the asset owner’s engineering standards. Specs 1131: 14.3.1
0c6b75ca-89bb-5645-aadb-82cb47116899 | note | Acceptance Criteria - The charasteritics of the valves delivered to site match the corresponding specifications, drawings details or approved equivalent
b8d9c5d8-2e10-588a-aa55-ee1873f68fb9 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
f4183ad1-e12c-503a-a28e-d06b90991d73 | note | Frequency - Prior to the commencement of Works
9d44e57c-ae13-58b1-907d-2d063c17ec1c | note | Inspection Type (Visual, other) - Visual
581d7dc7-9dee-54f3-8ca7-f6c239311bfa | note | Inspection: Key - C
9b4e84a0-3020-590a-9fe9-a1a06cb6d9ed | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.6 - Joints and Fittings
17eaf234-8e02-595a-aa14-9d1c09c01146 | note | Inspection Point: Quality Control Activity - All joints and fittings must comply with wath is estipulated on Specs 1131: 14.3.2
091f5a80-1915-5ea9-9ac9-0d90c553f45b | note | Acceptance Criteria - The charasteritics of the fittings delivered to site match the corresponding specifications, drawings details or approved equivalent
040d5cbd-4f9d-5998-9454-2307e7ac209a | note | Verifying Document - Delivery docket, Supplier certificate, Photo
24030147-09c6-5e20-a3ba-a75a512a3d3d | note | Frequency - Prior to the commencement of Works
f3769068-32df-579d-85a4-913eb0e9dcba | note | Inspection Type (Visual, other) - Visual
4e5242cd-f2a0-52ca-b82a-24b0e1889678 | note | Inspection: Key - C
b506cc29-1976-5fc9-b3cf-2dda7f9a18b9 | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.7 - Pipe Bedding and Haunching Agregate
473661b2-0be7-5a91-9f9f-9a034b49c284 | note | Inspection Point: Quality Control Activity - Pipe bedding should be AP20 and in accordance with AS/NZS 2566.2 or AS/NZA 3725. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.9.1
8e4c5c28-22cd-54f5-a297-6f1ca9559cc1 | note | Acceptance Criteria - Visual Inspection, Engineer approval
e482b5eb-283d-5ae1-b59b-2693dc0266a4 | note | Verifying Document - Delivery Docket, Laboratory test results
e4fb6576-707d-5665-a495-0009ed0c0851 | note | Frequency - Prior to the commencement of Works
0b81e1d8-5bb0-549c-9794-a4f099846ae4 | note | Inspection Type (Visual, other) - Visual, Lab Test
a29b95dc-18f4-51eb-99ab-5f8437791eda | note | Inspection: Key - H
40dbce8e-635c-555b-85ae-533c33df4f03 | note | Inspection: By (Role Key) - QE/SP/MC
| signoff | HOLD POINT
| checkpoint | 3.8 - Buried Warning Tape
7aa88520-f942-57a8-ae35-379a54790bbc | note | Inspection Point: Quality Control Activity - Metallic detector tape shall be provided to comply with the NZUAG code of practice. Tapes shall comply with AS/NZS 2648.1. Tapes shall incorporate a 316 stainless steel detectable tracer wire where required. Specs 1131: 14.6.1
5159cdb6-00c1-5492-bd3b-5f70a519f17e | note | Acceptance Criteria - Received warning tape comply with specifications and standard
bda38402-1ffd-5653-bd7a-5d5d8f9a3c55 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
f13ee1d8-9d7e-53fb-aa22-71b7eaa48f51 | note | Frequency - Prior to the commencement of Works
ea246aee-be9f-5af2-ac9c-39985e0ff5ab | note | Inspection Type (Visual, other) - Visual
53d601db-a507-5972-ba37-700ec145c853 | note | Inspection: Key - C
0dbb79cc-9c2b-5278-beb0-2acd7a132b17 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.9 - Backfill Aggregate
eedf4cfc-2ea0-5bb4-a0a6-570090bfa06b | note | Inspection Point: Quality Control Activity - Backfill aggregate should be GAP 65. Samples of backfill material should be tested in accordence of NZS 4402 to determine the MDD at OMC. The solid density of aggregate should be tested in accordance with NZS 4407. Specs 1131: 16.1.1
b48494e2-4af9-537f-b78f-583e365d0750 | note | Acceptance Criteria - Visual Inspection, Engineer approval
98e34d7f-308e-595c-90ec-fc4ebf902a74 | note | Verifying Document - Delivery Docket, Laboratory test results
a2bcafd1-43c5-5d17-a2d8-028414bafbd0 | note | Frequency - Prior to the commencement of Works
4f1d1b44-7468-550a-a498-4aa0584e0ea5 | note | Inspection Type (Visual, other) - Visual, Lab Test
ac00a70f-b089-5739-95df-b3f0fa7b8c96 | note | Inspection: Key - H
7f00200f-5c90-55c2-aab4-1424d769085d | note | Inspection: By (Role Key) - QE/SP/MC
| signoff | HOLD POINT
| checkpoint | 3.10 - Concrete Manhole, Catchpits and Access Chambers
a4e97dba-edd8-5401-bde0-2fcc86860c1e | note | Inspection Point: Quality Control Activity - Precast concrete estructures shall comply with NZS 3106. Specs 1131: 14.5
c387df2d-2acb-5fdf-8bc1-0f7669d26b27 | note | Acceptance Criteria - Manhole charasteritics Match NZS 3106
1a1b8658-769e-5bd7-8bf9-b9cdb811be3d | note | Verifying Document - Delivery docket, Supplier certificate, Photo
935bebb3-f274-5260-8867-a0982a771d23 | note | Frequency - Prior to the commencement of Works
764f9ffa-dc79-5623-ab84-7bcfc74fc8a4 | note | Inspection Type (Visual, other) - Visual
285cc4ee-20ef-53c6-b392-2bf1ce90aebb | note | Inspection: Key - C
b8c2bf37-a22d-531b-b203-78320d19e929 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.11 - Route Markers
088d7abd-8f6d-58a0-b956-217d1eb3e78e | note | Inspection Point: Quality Control Activity - Route markers shall be provided where shown on the Drawings or as required by the Principal. Specs 1131: 14.6.3
42f21f9b-0ac7-5e31-ac45-6e762b71e46b | note | Acceptance Criteria - Route marker supplied according to the drawings and requirements
a76b1443-410d-5d42-8c8b-6a2c774626d7 | note | Verifying Document - Delivery docket, Photo
8d6dc8b3-4599-5759-93ad-671f918127dd | note | Frequency - Prior to the commencement of Works
91cad6d5-1bcc-5da3-bf91-6b9a8928da49 | note | Inspection Type (Visual, other) - Visual
218d1a8a-ea12-582f-bc6c-93c0d342ad3e | note | Inspection: Key - C
6d7a4187-2ce7-56c8-99f4-771c30367fa3 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.12 - Material Storage
ef50ea8a-04b8-5ecf-b79f-0720e4afacea | note | Inspection Point: Quality Control Activity - Storage for materiales must be arranged as it is described in: Specs 1131: 14.10
b48bba37-4f94-573e-945f-4718449912a1 | note | Acceptance Criteria - Pipe stored according to specifications
692fff23-c918-5eab-a97a-a5c581674b2b | note | Verifying Document - Photo
d6da66a9-9370-585f-ae52-d4d13182616d | note | Frequency - Prior to the commencement of Works
93f1750f-2875-56c9-b839-7d3cca2fdaf0 | note | Inspection Type (Visual, other) - Visual
86d6e1b7-45a2-5c69-9fca-6e09fdf16387 | note | Inspection: Key - C
5aae3d88-f0d0-5dfb-891f-c3ca796ca686 | note | Inspection: By (Role Key) - QE/SP/MC
| checkpoint | 3.13 - Backfill Trail Compaction Testing
12273e00-b650-5cce-8af1-ed235ab9f591 | note | Inspection Point: Quality Control Activity - Prior to commencement of fill compaction. Trial compaction plateau test should be conducted under presense of Engineer or principal. Methodology to be confirmed in advance generally in accordance with TNZ B/02 specification. Specs 1131: 16.1.1, 16.1.2, 16.1.4.
a9d0143a-318b-5cbd-940d-02c757ffc9f5 | note | Acceptance Criteria - Compaction Value ≥ Specification Value
9ed504e8-c101-5ca3-9d2d-2a593d79da87 | note | Verifying Document - Nuclear Density Meter (NDM) Results Sheet, or Clegg Hamer test records
5b077e37-83b2-5e93-bd27-f960a800de9d | note | Frequency - Prior to the commencement of Works.
c351dfea-e1c3-5b61-a205-25ca99b872fd | note | Inspection Type (Visual, other) - On site Test
3ada94fc-b2fd-563a-9a82-e9da4907639f | note | Inspection: Key - H
09d6559e-143e-5259-96c8-98c978877295 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 3.14 - Defective Materials
52c7f55c-b335-5ade-bd17-a771a022e1fd | note | Inspection Point: Quality Control Activity - Any materials that do not comply with this specification or that have been damaged as a result of the Contractor’s operations shall be removed from site and replaced at the Contractor’s expense. Repairs may be considered at the sole discretion of the Engineer. Specs 1131: 14.12
ad58d22f-2ea7-5ee3-b4f5-8a5e15895341 | note | Acceptance Criteria - Defective material detected and removed from site
ca1c456a-92d6-5430-a46b-128a2d6d4917 | note | Verifying Document - Delivery docket, Photo
6d91c037-64ea-5f45-8e51-658ddf072c9f | note | Frequency - Prior to the commencement of Works
e78792f1-d5c0-5640-af52-a12d4be43ff7 | note | Inspection Type (Visual, other) - Visual
e20d8583-e962-594a-ac91-cd89ab110962 | note | Inspection: Key - C
7979d930-147a-50d5-b289-96da9bc25601 | note | Inspection: By (Role Key) - QE/SP/MC
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Site Clearance
62092e5a-8547-5704-810c-30eb1ac78743 | note | Inspection Point: Quality Control Activity - The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1
ffcd9410-085a-511c-b60f-5028ce0dc0c7 | note | Acceptance Criteria - Location approved by the Engineer
bae194c9-2109-5f26-958e-3ecde0b48d31 | note | Verifying Document - Dumping Docket
610c398a-13a5-5ada-a625-5bca72dc5ffb | note | Frequency - After site clearance
5dd08bbe-2d86-5103-ae24-5102dd332fd6 | note | Inspection Type (Visual, other) - Document Check
b3264880-3e41-5c69-b02c-ee72d0a3f314 | note | Inspection: Key - C
59712163-5081-527e-992b-755fbc313b51 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.2 - Trees Removal
5055035f-5d36-5a38-ac57-4b73cf2d1629 | note | Inspection Point: Quality Control Activity - No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2
e533c4d2-35e5-5df3-9bc8-356fc67f5518 | note | Acceptance Criteria - Engineer Approval
bce9feaa-2ed6-5eea-991f-9df9c17b4f04 | note | Verifying Document - Engineer Writen Authorisation
88aef9ab-512b-5bfd-af85-11f0d3d733b6 | note | Frequency - Before remove any tree
bf4608f0-a46f-5718-95ad-eb09942161b0 | note | Inspection Type (Visual, other) - Client Consultation
09ac6c34-a79e-5b48-8b76-d2403e48c603 | note | Inspection: Key - H
3d3cda40-a27d-5a0d-aa9a-79d58e5e700e | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 4.3 - Removal of Topsoil
48a12f61-0d2e-58d9-ae35-432ad61a060d | note | Inspection Point: Quality Control Activity - Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4
537108c3-d513-54cc-88ef-f344634e94d9 | note | Acceptance Criteria - Engineer Approval
05bb4e1f-51c4-5cd8-abc7-1ec3c53404e1 | note | Verifying Document - Engineer Writen Authorisation
6f9291de-a458-5a31-b09f-5dc131225d7b | note | Frequency - Before Topsoil Removal
c3ada882-c8eb-5a3e-8ca2-044b28f2ee60 | note | Inspection Type (Visual, other) - Client Consultation
9843296f-2e0d-5ce4-852b-3fb34a49e37c | note | Inspection: Key - C
00ecab42-41cc-5dae-ba8a-22381ab2fabf | note | Inspection: By (Role Key) - CR
| checkpoint | 4.4 - Hazardous Waste and Contaminated soils
2e55348f-60e4-5b4a-a7c1-d0b117de7477 | note | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
87cd9a5e-a718-58e1-9730-86d9e3623fa7 | note | Acceptance Criteria - Dumping site approval for contamiantion type
1a4da165-225d-5201-8285-9b79f2be53e0 | note | Verifying Document - Dumping Docket
6d489a49-91db-50a3-b247-6863758b6c6a | note | Frequency - If constaminated soils are found
f8335c87-1b62-5e8e-870f-110617dbe466 | note | Inspection Type (Visual, other) - Document Check
f0f731a2-c0aa-58f0-acca-96030eb9164b | note | Inspection: Key - C
37b50ba1-e926-5d29-8882-41b9ee633951 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.5 - Trench Excavation
a4237699-d785-5d9e-bb97-2deb36d8ca58 | note | Inspection Point: Quality Control Activity - Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated.
ca438cde-fde7-57d8-bc86-065628d174ea | note | Acceptance Criteria - Trench width and pipe clearance to walls comply with requirements
22642189-430f-580b-8274-d27dc02e2ea8 | note | Verifying Document - Installation Check Sheet
a2f8fd3b-4486-5d46-a13a-0ec87528452d | note | Frequency - During trench excavation
0c255540-8245-5d19-8966-6161c5dbae72 | note | Inspection Type (Visual, other) - Visual, Measurement Check
56e0ebd6-75d1-5668-b137-aa71e595776b | note | Inspection: Key - C
4545dc25-a48e-5919-a56c-75a0108efc5c | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.6 - Pipe Bedding and Haunching
cae09c6f-0885-5a1c-a822-66a01a2c8aba | note | Inspection Point: Quality Control Activity - Bedding and Haunching for flexible pipes should be in accordance with AS/NZS 2556.2 and have minimum embedment zone as shown in table from Specs 1131: 15.2.8.2
4c356e83-46a9-5c70-bca7-853171c1972f | note | Acceptance Criteria - Bedding and haunching high and with comply width requirements
9299e126-84d0-5b9b-b241-baa4d1a64747 | note | Verifying Document - Installation Check Sheet
5443f08d-72be-532c-b1f6-54f2f937f368 | note | Frequency - During bedding and haunching installation
15ae1c3f-5bd7-5ba6-98fe-0a4ccd3d9b42 | note | Inspection Type (Visual, other) - Visual, Measurement Check
859ce87f-4f0d-5945-9076-bdaaed0ea756 | note | Inspection: Key - C
953071ae-21a6-5b99-a628-366c69a1dd85 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.7 - Pipe Line and Level
c243b03c-859e-599d-b3da-db2a88fef613 | note | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line and level within the tolerances specified in Specs 1131: 15.9. Invert levels shall take precedence over depths. Specs 1131: 15.3.12
54ac390d-5994-5973-8e4a-baceac44984e | note | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
7f30a853-32ea-5f25-b541-d10ad6fbed03 | note | Verifying Document - Grade Check sheet
4e30dc6f-3102-577a-a26a-69f6014178f7 | note | Frequency - During pipe installation
733284b4-5597-5623-8b7d-2ffc332e244c | note | Inspection Type (Visual, other) - Visual, Instrumental
15cbe18c-6b58-5bf0-96f1-15f4955445e9 | note | Inspection: Key - C
f348896e-46ca-5332-84cc-9380707ade95 | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.8 - PE Pipe Installation
a2043e05-15cc-51f2-ad8d-16d281227a42 | note | Inspection Point: Quality Control Activity - Buried PE pipes shall be installed in accordance with AS/NZS 2033 and AS/NZA 2566.2, as applicable. Specs 1131: 15.3.2.2
8d64a9c7-c1f7-5b78-9d95-c5c04195e7a3 | note | Acceptance Criteria - PE Pipe Joints and Intallation comply with standard and specifications
f2b8d518-5bea-5dcd-b7d8-3376841461a9 | note | Verifying Document - Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
6eef7755-f9b0-5301-aa71-63f14db4a28c | note | Frequency - Per weld, and during pipe installation
5427663a-6ac9-5feb-8928-6dfce17e008e | note | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
0e07f679-ac4d-52e0-a835-5ed203596787 | note | Inspection: Key - C
8be323a3-191b-5aa9-b377-f9568532f574 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.9 - PVC Pipe Installation
7fa7df3a-c0ef-5794-8a5d-fa4e23cd4d2a | note | Inspection Point: Quality Control Activity - Buried PVC pipes shall be installed in accordance with AS/NZS 2032 and AS/NZS 2566.2, as applicable. Fusible PVC pipes shall be welded and installed in accordance with the pipe manufacturers recommendations. Specs 1131: 15.3.1.
5a8efa2f-10f1-567a-b413-d7e775e49663 | note | Acceptance Criteria - PVC Pipes Joints and Intallation comply with standard and specifications
d0c82962-1630-56ba-baed-8181b57beb3f | note | Verifying Document - Methodology, Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
50a6af10-b23b-5d19-beac-8480ec3a3709 | note | Frequency - Per joint or weld, and during pipe installation
6e149a08-1290-564a-b6f9-986fce01c7d7 | note | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
7bcb53b2-3bfd-5e4b-ac53-9bb39f1bd0ea | note | Inspection: Key - C
5ce1343d-7daa-5c8a-a180-c45cfe530ee5 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.10 - Precast Concrete Pipe Installation
4905a516-4c8c-5223-91c3-46d70213f6fc | note | Inspection Point: Quality Control Activity - Joints between precast pipe units shall be self-centering and shall be sealed with butyl mastic or similar approved to form a watertight joint. Concrete pipes shall be installed in accordance with AS/NZS 3725. Specs 1131: 15.3.6
1ffe33b6-c6f1-5b2e-8ec9-91b2776bec6e | note | Acceptance Criteria - Precast concrete pipes Joints and Intallation comply with standard and specifications
5f4b7e31-e93c-5238-9298-548b13208916 | note | Verifying Document - Methodology. QA records
58208f18-1017-5a7c-94a0-fb249aa2c6bb | note | Frequency - Per joint, and during pipe installation
10fac3cd-4781-5549-9205-12e822ea16a3 | note | Inspection Type (Visual, other) - Visual
c8c472a4-e23b-5c4d-8c15-2a77b61716b7 | note | Inspection: Key - C
9137cbd1-da8e-524a-a813-9a0f09c8c8ae | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.11 - Aggregate Compaction
c33e8824-4bc9-5d1c-9555-7503bfc35ec7 | note | Inspection Point: Quality Control Activity - Compaction shall be as stated in Specs 1131: 15.4.4. For concrete pipes the verification testing of compaction shall use a method recommended in table 3 of the CPAA Technical Note on Installing Concrete Pipe and approved by the Engineer. Specs 1131: 15.3.6
90a33c1d-9457-586c-a676-4d8816187ef6 | note | Acceptance Criteria - Compaction Value ≥ Specification Value
bc2517db-98f7-535a-a969-7bdbde9aaeaa | note | Verifying Document - Depending of Pipe material or Aggregate: CBR Checksheet, Nuclear Density Meter (NDM) Results Sheet, Clegg Hamer test records
c56da71c-659c-53e2-aea3-51312970c984 | note | Frequency - Every 50m of trench (not confirmed) or specified by Engineer
6fe0ce8b-5b73-58dc-9915-a06896d2e481 | note | Inspection Type (Visual, other) - On site Test
eaee45e9-711f-5298-8f6e-08237d0c7c9c | note | Inspection: Key - H
d1e9de33-f16f-57d6-9604-341169f0dca9 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 4.12 - Backfill Compaction
f9373ffa-e18e-5daa-987e-e3f2d650ed6a | note | Inspection Point: Quality Control Activity - Selected fill within 0.8m depth from finished surface shall be AP 65. Subgrade and subbase shall be compacted in layers no greater than 200 mm thick unless otherwise agreed with the Engineer. Under carriageway basecourse shall be compacted in layers no greater than 150mm thick unless otherwise aggred with the engineer. Specs 1131: 15.4.3.2, 15.4.3.3
4883f352-e5b6-52bd-be8b-72efd5513e89 | note | Acceptance Criteria - Dry Density ≥ 95% MDD (Under Carriageway). Dry Density ≥ 90% MDD (Outside Carriageway)
a370e4e0-b90a-568f-8814-761a91daa0a4 | note | Verifying Document - Nuclear Density Meter (NDM) Results Sheet or Clegg Hamer test records
bfd6b2fb-8148-5a49-a927-5c61f0fd4097 | note | Frequency - Every 20m of trench, each layer (Under Carriageway). Every 50m of trench, each layer (Outside Carriageway)
3597aadb-12fd-51ed-881d-96328f1d02b1 | note | Inspection Type (Visual, other) - On site Test
1248cd28-a053-5179-aef7-5a711b2975cb | note | Inspection: Key - H
be9b0ccc-beb3-5406-a851-edea5c576cf0 | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 4.13 - Cutting pipes
8f52461b-9513-58b3-b0a1-40563750f103 | note | Inspection Point: Quality Control Activity - Where pipes need to be cut to form non-stardard lengths, pipes shall be cut by a method which complies with manufacturers recommendations and provides a clean square profile. Specs 1131: 15.3.7
77a83f2b-204b-56ed-bd41-dace2813d33f | note | Acceptance Criteria - Pipe cutted up to the specifications
cf50aa46-908e-5366-89a9-0d4c7c7c1dfb | note | Verifying Document - Methodology, Photos
b72e998d-d0ab-530f-a89c-b7d44c0deedd | note | Frequency - During pipe installation
b4499e15-6ffc-5e53-ab66-a5c6c81111a8 | note | Inspection Type (Visual, other) - Visual
0b6af552-b876-55e7-a889-2f77225852ce | note | Inspection: Key - C
88d934bd-48d3-54f0-8848-9298a25d20bc | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.14 - Manhole Benching
810431c6-8782-55c1-a4ca-ec1545e178b4 | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days. Semi-circular channels and fittings shall be placed in possition simultaneously with concrete benching and be embedded in true to grade level and line. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar and finished with steel trowel and rounded at corners. Specs 1131: 15.5
9f0c7d87-bc6b-5121-ac76-50cb3c8057c2 | note | Acceptance Criteria - Benching built up to the specifications
1a6e41be-7652-5af4-9b70-435bbedc4101 | note | Verifying Document - Methodology, Delivery Dockey, Photos
9f9f5ed7-c16d-5a68-bd01-cf102bcf5729 | note | Frequency - During benching contruction
caf64457-25d2-5ece-8b9d-81616b5e0d69 | note | Inspection Type (Visual, other) - Visual
224e9a2d-bc27-5a7a-a9f7-51df69762ef2 | note | Inspection: Key - C
92e6dc36-f48a-58d0-96d1-364e2c485f2e | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.15 - Subsoil Drains Installation
7923625d-c134-5914-8273-f92c90d30bab | note | Inspection Point: Quality Control Activity - Drains shall be constructed, geotextile layed and backfill carried out in accordance with TNZ Specification F/6. Specs 1131: 15.7
e0739a34-03f4-511e-962b-440bff00dd45 | note | Acceptance Criteria - Benching built up to the specifications
9187963d-f255-50b7-87f8-88cc2762a871 | note | Verifying Document - Methodology, TNZ Specifications F/6 and F/7, Photos, QA records
5470e392-f01f-5093-afa3-7e22d312866a | note | Frequency - During Drains Installation
822f98b4-7819-5584-a418-04267ef5c49a | note | Inspection Type (Visual, other) - Visual
fea88992-f98b-5806-aa18-f55a02d7d41e | note | Inspection: Key - C
e31e9692-afeb-55a1-8ad5-7acab19d7e36 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.16 - Topsoiling and grassing
8b54fb6b-d88d-5451-be8e-08a4fd9fa488 | note | Inspection Point: Quality Control Activity - Topsoil shall be used to dress areas disturbed by the contrat works to a minimum thickness of 100mm. Grass seed shall be sown evenly over the prepared topsoil area. Specs 1131: 15.8.6
4aca459d-b7e5-5bf8-9bd4-16f927502f72 | note | Acceptance Criteria - Topsoil installed and grass seed spread in the specified rate and mixture.
ff0cefac-df76-584b-86c2-d70c2a476e1a | note | Verifying Document - QA records, Photos
6786fb59-fc28-594e-b998-38123a2b5fcb | note | Frequency - After compaction of final layer of backfill
c23b2f4c-7bf0-51c4-9c51-0b2773821bdb | note | Inspection Type (Visual, other) - Visual
42e04f56-382b-5c0d-a0f4-29d4033c0e75 | note | Inspection: Key - C
9739a356-6545-547b-b6fe-3575d639d174 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.17 - Tracing Wire
c22b4803-8ed0-54ba-ba0a-69b92e6a3642 | note | Inspection Point: Quality Control Activity - Tracing wire shall be installed and tested according to what is detailed in: Specs 1131: 14.6.2
3683f488-83c8-56f7-a1b8-13352bada0fc | note | Acceptance Criteria - Tracer wire installation complies with the specifications
c42a589a-2bb8-5f3f-8b5d-aa9d6abc387e | note | Verifying Document - QA records, Photos
f152de29-6ab9-54ff-98a9-09203947351b | note | Frequency - Before pipe and fittings installation, testing after the completion of the network section installation
9f09980b-a166-572a-9684-56bf560aa3f9 | note | Inspection Type (Visual, other) - Visual, On site test
41c2795d-0dac-58e2-bccf-69961a616aaf | note | Inspection: Key - C
e8540830-99fb-5e84-b7dc-79500c01b649 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | Welding PE pipes
ca404702-1486-5f48-ba8f-268ed509cc8a | note | Inspection Point: Quality Control Activity - Jointing shall be done in accordance with pipe manufactures specifications. Where unspecified PE butt welding shall be in accordance with PIPA POP003 and PE electrofusion welding in accordance with PIPA POP001. All welds shall be marked with weld number and welder identification. (maybe put here that everything must be in accordance to the specs)
ead2a044-33d9-5348-8004-dfcde4fc1565 | note | Acceptance Criteria - Specification 1131 15.3.2.1
eaa30566-5a40-5080-9006-43def9bfcf0c | note | Verifying Document - Weld records
c0c77f3d-7964-50a4-bfe6-8771aa532e3b | note | Frequency - each weld
| checkpoint | Bulkheads
27c0ce1e-386b-59a7-8730-81dd0875305f | note | Inspection Point: Quality Control Activity - Shall be placed and constructed as per DCC typical detail 10328
f9f55161-3b7f-52bb-b63f-692ee8f838a0 | note | Acceptance Criteria - Drawing C120, C220
aecacecd-687b-5f68-9836-298f81ff4c12 | note | Verifying Document - methodology
9f38c7f9-083b-509b-8a8e-57a33ac28567 | note | Frequency - During installation
| checkpoint | Joint inspections
0c342fa1-9322-51c1-8c6d-19bc155d66bf | note | Inspection Point: Quality Control Activity - Each butt-welded joint will be visually inspected by the engineer
68299a4b-d0af-5002-bf41-135ecf82c9b1 | note | Acceptance Criteria - Specification 1131 16.3.2.1
382caf0b-5c19-51cb-9d01-d63585c24281 | note | Verifying Document - QA records
| checkpoint | Lab Testing
1f962554-8435-5132-a28e-3ad45294c1f3 | note | Inspection Point: Quality Control Activity - Three butt welded joints and one section of virgin pipe shall be tested in accordance with ISO 13953.
86d9d99b-34b6-57d1-9f4c-333554d2cb9e | note | Acceptance Criteria - Specification 1131 16.3.2.2
| checkpoint | Joint inspections
944c83e9-3a69-5342-8ed1-290f593ee0ef | note | Inspection Point: Quality Control Activity - Each electrofusion joint shall be visually inspected by the contractor
3a349cc7-ad99-544f-ba54-64c79deaebd8 | note | Acceptance Criteria - Specification 1131 16.3.1
9da12e10-61bd-56f3-82da-b9a29243210f | note | Verifying Document - QA records
| checkpoint | Lab Testing
e4c12391-d739-5e9a-bd73-61f6ac0c8af9 | note | Inspection Point: Quality Control Activity - pipes with nominal diameters 90mm and larger shall be tested in accordance with ISO 13954
98613695-1fc4-5f10-b10f-ef030f386508 | note | Acceptance Criteria - Specification 1131 16.3.2.3
| checkpoint | Ductile Iron Pipe Installation
37c51f4e-41bd-5af2-82ed-3c3e3845ce1c | note | Inspection Point: Quality Control Activity - a) Ductile iron pipes shall be installed in accordance with AS/NZS 2566.2.
f2af1967-ca44-5566-b44e-320138b23026 | note | b) Ductile Iron Pipes shall be cement mortar lined in accordance with AS 1281 or AS/NZS 1516 and comply with NZS 3122 and be externally painted with a bituminous coating in accordance with AS/NZS 3750.4 for Bitumen Paint.
20dd84c7-a360-5062-8301-2d5acf4ff02d | note | c) When laid underground, DI pipes shall have a loose polyethylene protective sleeve to AS 3680 and applied in accordance with AS 3681. Specs 1131: 15.3.3
| checkpoint | Steel Pipe Installation
6727ddcc-ab3b-51d3-adca-6db8878a1f08 | note | Inspection Point: Quality Control Activity - a) Steel pipes shall be installed in accordance with AS/NZS 2566.2.
de945bfb-77da-5169-834b-debc176e1277 | note | b) Steel pipes shall have spigot and socket joints with rubber rings or shall be plain ended and butt welded as appropriate. Steel pipes shall be flanged where shown on the Drawings.
971a3eca-e414-51d4-8543-f987f86f8971 | note | c) Flanges shall be drilled as specified.
6beac73a-e65f-5e34-bfde-47beb85ba5f5 | note | d) Pipes for welding shall be joined by an automatic arc welding process capable of consistently producing welds complying with the requirements of NZS 4442.
e7c31c82-a15c-511d-9049-b9489a7f93e4 | note | e) Manual arc welding with automatic wire feed and automatic fluxing may only be used for the repair of weld defects. Manual welding shall occupy no more than 2 % of the total weld length in any pipe, and no weld repair shall be longer than 300 mm.
08288b9f-a95c-558c-993b-f1a032920497 | note | f) Full details of the welding procedure and of the edge preparation proposed to be used shall be supplied to the Engineer prior to welding.
53661d07-61f2-51b2-8a9d-c964f0a8278a | note | g) Any faulty welds shall be cut out and rewelded. On no account shall leaks be sealed by caulking.
4e07272a-45ad-5d70-9fca-1f422407a0c7 | note | h) On completion and acceptance of the welding, the external corrosion protection shall be suitably repaired, and both the weld and coating inspected by the Principal or Engineer.
03a37b93-ac35-5478-845c-f7a05aabec84 | note | i) Steel pipes shall be externally protected with one of the following:
d6ccf1ca-c686-5316-802c-7abcaff9af10 | note | i. for buried pipes, a high-density polyethylene sleeve, “black jacket” complying with AS/NZS 1518 or “Polyken Synergy” wrapping, or “Polyken YG111” wrapping.
d26b105b-405a-5e75-b2d7-7f89b489eadc | note | ii. for pipe above ground, a zinc metal spray sealed with vinyl or epoxy coating complying with AS/NZS 2312, or a fusion bonded epoxy coating complying with AS/NZS 3862.
f69d3997-0bf9-582f-bc46-4eb31c6dc446 | note | j) Steel pipes shall be fitted with cathodic protection complying with AS 2239 and AS 2832.1. Specs 1131: 15.3.4
| checkpoint | Stainless Steel Pipe Installation
804fbd91-42a0-5363-ba38-fdbab46d44ae | note | Inspection Point: Quality Control Activity - a) Stainless steel pipes shall be installed in accordance with AS/NZS 2566.2.
7e9e232f-38e1-5821-b70e-e92b5008779e | note | b) All welds between stainless steel components shall be in accordance with AS 4041. Butt welds shall be full penetration. The weld preparation shall be in accordance with AS/NZS 1554.1.
950cbeae-80d8-5651-8edb-58be11c790e5 | note | c) All stainless-steel welding shall be carried out using approved welding techniques and appropriate procedures. Welds shall be chemically cleaned and fully passivated to an approved procedure. Specs 1131: 15.3.5
| checkpoint | Pipes in a Common Trench
59e01d06-71c3-5bc4-8a25-f8e0e7a26454 | note | Inspection Point: Quality Control Activity - a) Parallel pipelines in a common trench shall be laid sufficiently apart to ensure that the required compaction and support of the side support material is achieved.
e3723372-497f-5693-8d0c-b0c35b5d4faa | note | b) Minimum clear distances between pipes can be reduced where flowable fill embedment materials are used, in line with the applicable pipeline installation standards. Specs 1131: 15.3.8
| checkpoint | Clearances to other Services
76eb5898-3741-52c5-ba2c-e73586745f9c | note | Inspection Point: Quality Control Activity - Unless agreed with the Engineer or specified elsewhere herein or on the Drawings:
d0019f47-fdf4-5ac4-857a-4829d7a8e067 | note | • The minimum clearance of sewer to other services is in table 5.6 to other utility services and structures in clause 5.3.7.10 of NZS4404.
ae9e381d-da17-5498-ab1f-830b16b09adc | note | • The minimum clearance of water pipelines is in table 6.4 to other utility services and structures in clause 6.3.9.2 of NZS4404. Specs 1131: 15.3.9
| checkpoint | Pipes Connected to Structures
cdd0bd58-194e-5783-afef-b8f2e5ab85ba | note | Inspection Point: Quality Control Activity - a) Where a pipe is built into an underground structure, a flexible joint shall be provided as close as possible to the outside face of the structure. A short length of rocker pipe shall be connected to the flexible joint. The length of the rocker pipe shall not exceed 8 times the diameter or three (3) metres, whichever is the shorter and shall be a minimum of 1,200 mm.
37fe3c37-4c6f-58fc-829e-ff6815a707e9 | note | b) PE, PVC connections through walls and floors: an annular space of not less than 6 mm shall be left around the pipe or fitting and the clearance shall be sealed with a flexible sealant such as loosely packed felt, a rubber convolute sleeve or other suitable flexible sealing material such as PE foam or neoprene.
d3540ca9-0f0e-56d0-8a7b-613025a1febb | note | c) Water-tightness at penetrations. Unless otherwise specified, for (material A, etc.) penetrations through a chamber or manhole wall shall be secured either with a concrete anchor block extending 1.5 x pipe diameters and puddle flange with rubber ‘O’ ring and hydrophilic sealant strip. For (material X, etc.) penetrations shall be secured with a concrete anchor block extending 1.5 x pipe diameter with hydrophilic sealant strips. Specs 1131: 15.3.10
| checkpoint | Cast in-situ Concrete
2784b728-debc-507e-88d4-1e000ff15f0b | note | Inspection Point: Quality Control Activity - Concrete cast in-situ for bedding, haunching, thrust blocks, anchor blocks and minor structures shall have a minimum strength of 20 Mpa at 28 days
224cb3c2-24e5-52d4-8303-9f0dae35c238 | note | Acceptance Criteria - Specification 1131 14.7
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
25a33df6-9cea-5277-8ad4-69d2bd889871 | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
e81355ae-7f63-5835-b3ab-78ca5e4dbf92 | note | Acceptance Criteria - Engineer Approval
746471ab-791b-5320-a16e-d93cf414aa4b | note | Verifying Document - QA records
8697eee1-ed4a-5677-99aa-8861252bc0f6 | note | Frequency - At completion
ad0d2e6d-58cf-5ef4-83d1-674a6d203073 | note | Inspection: Key - H
2c035c10-8b27-5937-9d67-102e1c73227a | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.2 - Gravity Pipes Testing
839de665-8848-5fa1-8ff8-e87350c9e05f | note | Inspection Point: Quality Control Activity - Stormwater pipes shall be by visual inspection for pipe diameters greater than 750mm and by water testing for diameters up to 750mm. Testing shall be in the presence of the engineer. Specs 1131: 16.2.1
6b895f7e-ac58-5808-8dbf-413c65f22fb9 | note | Acceptance Criteria - Engineer Approval
8fa25b99-a0de-595c-a1d3-c47e03443955 | note | Verifying Document - Test Records
68cb9064-670e-5a0a-a344-969bdc9d8a3a | note | Frequency - For every section of pipe installed (24hr prior notice to the engineer before test)
5313628b-6663-5120-b66f-f2c249359d82 | note | Inspection Type (Visual, other) - Test
2c8e915b-d505-5786-b28a-7615958bd6a1 | note | Inspection: Key - H
5b618382-938b-5329-b62c-232ef1bb413e | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.3 - Manholes
e57d059b-ca64-5c65-8882-094ad7652cab | note | Inspection Point: Quality Control Activity - Manholes should be tested seperately to pipeline for water tightness up to lower rim of manhole cover frame. Testing shall be in the presence of the engineer. Specs 1131: 16.2.2.5
34e39c8d-42fd-563d-9cde-02d8da6aa882 | note | Acceptance Criteria - A maximum drop in water level over 30 min should not exceed 2mL/hr/mm of diameter/meter height of the manhole. Engineer Approval
b736f644-2558-5bce-b429-84dc7af9bcec | note | Verifying Document - Test Records
f1191616-3038-5f79-bec2-0ca92fab112b | note | Frequency - For every manhole installed (24hr prior notice to the engineer before test)
82e3b0b9-98a0-5e12-8bac-8cf347069908 | note | Inspection Type (Visual, other) - Test
94366430-b489-5dfa-afe2-02b8a3823bda | note | Inspection: Key - H
e7cd48ee-76b9-591a-b42c-84e8d3c82ce1 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.4 - CCTV Inspection
36af2215-d74d-57cd-80ec-dc48814fc38a | note | Inspection Point: Quality Control Activity - All pipelines shall pass a CCTV instpection. All pipelines shall be free of debris and flushed 24hrs prior to inspection. Specs 1131: 16.2.3
8ff03a62-81ae-50a7-b749-366d8d9b2db9 | note | Acceptance Criteria - A pipeline will fail its inspection if:
850b29ad-0d43-5c3b-9a32-611bf577daf3 | note | – The pipe is horizontally misaligned or deformed by more than 5 % of the pipe diameter.
b9a472c4-9389-5ef4-bd1b-e89fda16f6e3 | note | – The pipe has visible dips or ponding of water.
77c7e9c2-a258-512d-ab13-3fe83fd12868 | note | – The pipe has visible defects, such as open or displaced joints, defective or protruding laterals, cracked barrels or similar defects.
df52ff5e-d46c-5e93-8e85-900b191855cd | note | – There is evidence of infiltration at joints or laterals.
468c0889-f7bc-5363-baba-84e314585c5c | note | Verifying Document - CCTV footage and log sheets
967ed2dc-39fe-5437-a2c9-9ba1f03f4140 | note | Frequency - At every section of pipe installed.
c070b806-09c8-5fc2-84bd-155b93263e61 | note | Inspection Type (Visual, other) - Visual
6f6a8bde-70ea-509f-acac-147dae33c62e | note | Inspection: Key - H
2f30a238-a3d9-55e0-8ea9-604255b48484 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.5 - Surplus Materials and Refuse Disposal
1bf3b5b1-b383-5017-a0ff-81afa9826ae8 | note | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
da3243fa-9da7-5a23-8d0c-fd9498ac5ee6 | note | Frequency - At completion
7b1516e1-31be-51bd-b29a-4b27f575c020 | note | Inspection Type (Visual, other) - Visual
64b4e241-c190-56d4-b885-2ffcf68b37c9 | note | Inspection: Key - C
37853e97-b14b-5d09-80c7-fc83ea83d738 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 5.6 - Cleaning
d475bab0-648a-5154-b8a0-5773c338f8cd | note | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
baf19bf4-b291-5658-911e-3a17a0193006 | note | Frequency - At completion
27e69d40-73b3-58b8-9715-1d744eb68d1e | note | Inspection Type (Visual, other) - Visual
4f5a8721-3572-5202-99b7-79bd65a29ba4 | note | Inspection: Key - C
c71e024c-02e6-5f4e-a2ca-7226c7dc2322 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | Air testing
6216eb47-6211-5053-9ade-0a1f53199cdb | note | Acceptance Criteria - Specification 1131 16.2.2.1
715e813f-0147-5111-8e54-4a0450571ba8 | note | Verifying Document - Test Records
| checkpoint | Pressure Testing
d8fba0ec-6a47-5b31-a5ef-fd6f3ed462bb | note | Inspection Point: Quality Control Activity - PE pipelines shall be completed in accordance with AS/NZS 2566.2:2002 relevant appendices
d35726a0-ff48-56f2-b000-efc16c45486d | note | Acceptance Criteria - Specification 1131 16.3.1
26434acc-296b-5df1-b8e2-c1c27c5ea60c | note | Verifying Document - Test records
| checkpoint | Corrosin Protection
6f134bf6-a15b-50e0-abd9-2568d06d2032 | note | Inspection Point: Quality Control Activity - a) Metallic connections shall be appropriately protected against galvanic / dissimilar material corrosion.
31373d84-e577-53e3-bcfb-108dad2f33f7 | note | b) Metallic connections in contact with soil, regardless of any factory applied corrosion protection (e.g. HDG, FBE), shall be fully protected with a suitable petrolatum based wrapping tape (e.g. Denso Petrolatum, Polyken tape), including appropriate filler treatment (e.g. Densyl Mastic, Polyken Mastic) as and where required to ensure the tape does not bridge voids.
8746dc85-fc18-5937-a97f-b5a18798c920 | note | c) Corrosion protection systems shall be made available for inspection once they have been installed in situ, unless the Engineer permits otherwise. Specs 1131: 14.4
| checklist | 561469-ITP-0004 - Sub Main (DG-QA-TP018) | itp | 561469-ITP-0004 - Sub Main (DG-QA-TP018) | 522fb364-5bb9-4c9f-94a8-ab779d023ca5
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
4701ccae-bb29-5d18-a062-a21ce72eb93d | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
1bb9d3f1-b414-57da-9602-3b817cd25b1c | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
7930a1a0-0ae7-5b22-89dc-25fdf5cb3e32 | note | Verifying Document - ITP
cf71d67e-e146-5a22-8274-e125d17f2ce3 | note | Frequency - Prior to the commencement of Works
544c5bed-47ce-526e-8a2b-0d0167761c16 | note | Inspection Type (Visual, other) - Visual
29cd153e-f8a1-5c54-9442-78cabc223df1 | note | Inspection: Key - R
39e02007-8b90-508d-882c-e88bdfa4bb8e | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
94a0e89d-c329-5689-af58-818da8007d0e | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
dc883de8-545c-55ad-b12f-7e62a450de72 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
b15b9acd-be18-5c7b-b08c-db5d2791173e | note | Verifying Document - Compliance surveys or spot checks
9c5b19d4-66df-52a9-af2b-55794f0efc03 | note | Frequency - Prior to the commencement of Works
03510c4c-5ee4-5d03-ac16-adb3e216c528 | note | Inspection Type (Visual, other) - Visual, Instrumental
9c785e2f-de86-50b7-ba8e-be0f72f18030 | note | Inspection: Key - H
f371c528-8afc-5f1e-9a0c-b31e5673901f | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.3 - Pipes Delivery
5ed343ac-7ea8-58cb-87e5-a724ee5cec7c | note | Inspection Point: Quality Control Activity - Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C152 - C153
ac9c171b-137f-547f-b97e-8a50c3e7037c | note | Acceptance Criteria - The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent
c2abc789-c831-5fa5-ac3d-12966aa902c7 | note | Verifying Document - Delivery docket, Photo
9df3eebf-1aba-5279-8e83-e02fa936840e | note | Frequency - Prior to the commencement of Works
d88725fe-a0ce-5fc4-a49b-1a9cd682ddf3 | note | Inspection Type (Visual, other) - Visual
25c89ccf-9f04-58ba-b347-5113f9112c6a | note | Inspection: Key - C
95f562e4-21ac-59f2-a0ee-c93f3c1f72bd | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.4 - Valves Delivery
c98c46e5-786e-5785-a7a8-b05e739113a9 | note | Inspection Point: Quality Control Activity - Gate valves shall comply with AS/NZS 2638. Valves greater than DN50 shall be resilient seated sluice valves. DN50 shall be gate valves. Sluice valves shall be anti-clockwise closing. DN50 gate valves shall be clockwise closing. Valves shall be provided with a surface box according to the asset owner’s engineering standards. Specs 1131: 14.3.1
86a6a5b0-e000-5ffe-a507-1762cdbd42c5 | note | Acceptance Criteria - The charasteritics of the valves delivered to site match the corresponding specifications, drawings details or approved equivalent
7f50e653-0d44-5337-9ffb-6a14e76fe3f4 | note | Verifying Document - Delivery docket, Photo
5505cd0e-1d03-5f44-86ec-19452eeadca1 | note | Frequency - Prior to the commencement of Works
cc7523e7-08b5-5884-ada8-1c7fe2d63c93 | note | Inspection Type (Visual, other) - Visual
493dd2e2-83de-5078-a316-98f133887803 | note | Inspection: Key - C
b6eac577-1136-57f6-b020-9f72fad76a2e | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.5 - Joints and Fittings
2723ca1f-6824-5e7b-9501-e74259756daa | note | Inspection Point: Quality Control Activity - All joints and fittings must comply with what is estipulated on Specs 1131: 14.3.2
7bbda82a-452b-533a-9c33-8ea70c5abd85 | note | Acceptance Criteria - The charasteritics of the fittings delivered to site match the corresponding specifications, drawings details or approved equivalent
fa4fe1d8-b353-50e7-903e-73e3d4a701f0 | note | Verifying Document - Delivery docket, Photo
9bb49073-5936-5d99-9fe4-8a5ff28564ed | note | Frequency - Prior to the commencement of Works
842df5dc-4935-5675-bd0b-4212539bc35e | note | Inspection Type (Visual, other) - Visual
393655bd-e982-5811-b7c6-a24d61761809 | note | Inspection: Key - C
e1516f8e-0b65-51e2-960a-bb8c48193886 | note | Inspection: By (Role Key) - QE/CR
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Trench Excavation
e52bcd43-9cfb-5ca9-8b8f-a491922d6d95 | note | Inspection Point: Quality Control Activity - Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated Drawing C115
a32fd7ea-3f0f-5791-916e-e7262ee28c3e | note | Acceptance Criteria - Depth of trench to achieve:
4685a764-3057-5fbc-b0a9-b42730dbd957 | note | ○ Minimum 450 mm cover in Irrigation area
02ec25d7-5150-56ce-9ddf-4736b8101cce | note | ○ Minimum 600 mm cover under access track
3837732b-f027-5528-985c-9b12cfcf5aa3 | note | Verifying Document - Photos
38c0d707-c980-50dd-bfe4-14244160d454 | note | Frequency - During trench excavation
c257e516-0c54-5696-a3aa-38ce4a50546a | note | Inspection Type (Visual, other) - Visual, Measurement Check
f568a2db-0ab5-51df-a065-c4ec2bb006fc | note | Inspection: Key - C
3c17d1e8-6278-5e36-aabe-7f322ca9eab8 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.2 - Pipe Bedding and Haunching
423f43d5-29ce-5ed3-a0b4-4f3bd660295a | note | Inspection Point: Quality Control Activity - Bedding and Haunching for submains should be in accordance with Drawing C115
6930ac1a-4216-5547-840d-30e48488cc15 | note | Acceptance Criteria - Bedding material to have max size of 20mm
221844ed-7248-532f-b704-1586f9ad5a22 | note | Verifying Document - Photos
828192d4-0a6d-5675-8848-4d90acee5642 | note | Frequency - During bedding and haunching installation
a6f55e42-4c46-518b-8fbd-df025f3ffb9e | note | Inspection Type (Visual, other) - Visual
19f2b5db-ada6-52f3-ba39-88a5b32abdcd | note | Inspection: Key - C
e13898d2-ad9f-5a24-b494-aa7610aee483 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.3 - Pipe Line and Level
37188d32-eebd-5ca4-8e71-b72280b9199c | note | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line as in Drawings C100-C104
15997715-f89a-503d-ae61-025608c806ca | note | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
5a5d8fc6-cc0d-555f-a026-8b2849664f84 | note | Verifying Document - Photos
ed77f187-41ba-5d4a-847e-6cef3840efa8 | note | Frequency - During pipe installation
12f9e06f-c9a5-593a-b813-f28453a2d52d | note | Inspection Type (Visual, other) - Visual
227fd449-6e4e-589c-993e-e984d9e092d9 | note | Inspection: Key - C
bcdafdf7-a927-5c85-9cc4-dec7062d55c5 | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.4 - PE Pipe Installation
2de82387-20f5-5c6b-92ec-38cf0606a1cd | note | Inspection Point: Quality Control Activity - Buried PE pipes shall be installed in accordance with AS/NZS 2033 and AS/NZA 2566.2, as applicable. Specs 1131: 15.3.2.2
50bd3ebb-4da7-5486-8ab6-fd7d3d166e26 | note | Acceptance Criteria - PE Pipe Joints and Intallation comply with standard and specifications
e9e8da7e-5f07-516c-bb99-457b450d6674 | note | Verifying Document - Pipe welds QA records (if required)
b0af94f0-eda1-583d-9d7a-a04e13a9214d | note | Frequency - Per weld, and during pipe installation
5d417c30-023e-514d-b842-26b610871178 | note | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
0531a50d-aa83-57fb-9e20-fdfa70d8c9db | note | Inspection: Key - C
109c97b0-03be-51b4-a9e2-ad0d1bede1cc | note | Inspection: By (Role Key) - QE/SP
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
34f99d8c-84ed-58ac-be19-dd39497a3ceb | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
9f2430a5-f502-5ed1-836e-009a4dc6bd6c | note | Acceptance Criteria - Engineer Approval
e7204c14-3c86-5b01-9c7c-b66af783a569 | note | Verifying Document - QA records
82205d12-a2c2-5ad7-8f3b-57e4ab7a43f9 | note | Frequency - At completion
78bcc27d-f711-5a45-be32-fcd8133b2cad | note | Inspection: Key - H
0bfd102e-b22c-5502-a440-6f759642969f | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.2 - Pressure Testing
f0a41165-38e1-531b-ab1b-2e1d1b06b0d4 | note | Inspection Point: Quality Control Activity - Submain testing shall be a visual test of all joints at the maximum woking pressure of 3.5 bar
28392d8f-1b3c-5a27-948c-9c89ec4bf5d6 | note | Acceptance Criteria - No visual evidence of leaking at joints
ba49db20-8aca-5eea-807f-6b126efdbf8f | note | Verifying Document - Test Records, Photos
09c6bd48-2b8d-528e-9bb7-f70657e8039e | note | Frequency - At each dripline connection along submain
2986c424-7655-56f2-a76e-b5dc0d162907 | note | Inspection Type (Visual, other) - Visual
a1606684-4261-5465-8895-943dd618b7a1 | note | Inspection: Key - H
ecb4b76f-2070-503d-bfad-c11e96daeab4 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| section | SECTION 6 - COMMENTS
| checkpoint | Customer Release Granted
8b1c7e18-ab0a-5ce1-9d37-26e27059d5d1 | textbox | Certificate Number:
f9c5c7cf-fe46-5202-9e54-925d8c25e432 | date | Date:
| checklist | 561469-ITP-0005 - Chambers (DG-QA-TP018) | itp | 561469-ITP-0005 - Chambers (DG-QA-TP018) | 54b229ee-75a8-4d32-a198-07954b2aee57
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
a624be2c-0793-5337-98f2-d694ec1b1cb0 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
b39b913f-07b0-586e-91bf-39d231987fe0 | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
5514ba70-a449-5a15-8a55-b9c3b726335c | note | Verifying Document - ITP
025ab3fb-c801-5831-a05e-6d3092b07bed | note | Frequency - Prior to the commencement of Works
c8096d18-cb29-5809-b272-02db2e8e18cd | note | Inspection Type (Visual, other) - Visual
53d5d2bc-a03f-5f39-8d53-5f08307ae249 | note | Inspection: Key - R
2ba08870-e7e6-50cc-b6c1-bd7cf39ae745 | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Setting Out Levels and position
d3b1aa65-3928-59f0-91d8-dfa64aa0bcbb | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
0fc76a41-2318-5432-bb52-3d7a60cd909d | note | Acceptance Criteria - Levels and position Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
a38ac773-3eb0-5c46-9151-82f268c7d0ba | note | Verifying Document - Compliance surveys or spot checks
2528edb1-1160-5c1e-b47a-f6ddd67b1ed6 | note | Frequency - Prior to the commencement of Works
188bf33a-2611-5487-8652-af3544c97815 | note | Inspection Type (Visual, other) - Visual, Instrumental
66b7876d-35fc-52f2-8c6a-a8dc7bcd421b | note | Inspection: Key - H
7ffb625d-f591-5102-909c-1fddf6e5e9ec | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.10 - Concrete Manhole, Catchpits and Access Chambers
86bf6452-4d10-52b5-8e09-528b8ef13945 | note | Inspection Point: Quality Control Activity - Precast concrete estructures shall comply with NZS 3106. Specs 1131: 14.5
46683021-22c2-5e8c-b23b-0e8f3f2dabd1 | note | Acceptance Criteria - Manhole charasteritics Match NZS 3106
39aa00c0-8f92-5508-a5a9-9bdd73a944b4 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
01d1508c-fcf8-5758-a035-b0d7ddd0917a | note | Frequency - Prior to the commencement of Works
7fce068a-49de-5401-b95f-c0ff3ddcee1d | note | Inspection Type (Visual, other) - Visual
d4ac91f2-73e7-543a-8b61-f0d40b732784 | note | Inspection: Key - C
90e18c8d-3808-5799-bd92-40b45d63ee7c | note | Inspection: By (Role Key) - QE/SP/MC
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.5 - Trench Excavation
1cd277d1-a405-5bdc-9acf-b6060a72d423 | note | Inspection Point: Quality Control Activity - Excavate to achieve required depth as per drawings C250, C106
2f4f97ae-dd2f-516d-9c34-4d7b2f3f1d8c | note | ○ Floor of trench to be even across width and length
e76bc752-2b50-5cbc-be48-f5eefdedc88d | note | Acceptance Criteria - Trench width and chamber clearance to walls comply with requirements
ff06cc0d-8934-5072-9b6a-eb9e4656fe91 | note | Verifying Document - Photo
6c905a64-c5d2-57b8-bfd9-da24383328c5 | note | Frequency - During trench excavation
cbbafb04-f7c7-5edf-a372-14af284bca52 | note | Inspection Type (Visual, other) - Visual, Measurement Check
b435d711-0117-57eb-89fe-2245685d7229 | note | Inspection: Key - C
df812ad3-504c-5000-8780-6ceb4c2b9be6 | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.6 - Bedding
58380490-3da4-5bae-ab2c-e853400fc62b | note | Inspection Point: Quality Control Activity - Bedding should be minimum 150mm compacted material
d1add20f-ac1d-5938-93dc-283acde1e29f | note | Acceptance Criteria - Bedding to comply with requirements
02700c1b-81a5-5e34-8be1-5df95ccdf025 | note | ○ Scala test to achieve 2 blows per 50mm
29ef62e9-9123-5aa4-8e85-e256225ef3a7 | note | Verifying Document - Photo
45fb01e9-f295-5eae-8213-0e0e33d81b4b | note | Frequency - During installation
3b45cdf0-a87e-5292-a018-48af4b44e275 | note | Inspection Type (Visual, other) - Visual, Measurement Check
290045a2-97ef-5115-ba8c-4ad696c53d47 | note | Inspection: Key - C
1cd72de3-b76d-5546-b6ea-bb421b2e6abf | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.7 - Chamber installation
51b5ba55-b24f-5b43-96d9-51df0c9c4a60 | note | Inspection Point: Quality Control Activity - Chambers shall be installed true to the design level
cff8b9b1-b4f3-5793-8812-bbe2b5b7296b | note | Acceptance Criteria - levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
268f4984-6d65-5878-9f82-a8399ef78c63 | note | Verifying Document - Photo
2622665f-11d4-538d-840b-c9eb542f10cc | note | Frequency - During pipe installation
6545f40d-15cd-5949-bbae-4bf9f96591db | note | Inspection Type (Visual, other) - Visual, Instrumental
a9506cde-6535-593f-a384-4141e19bf0c0 | note | Inspection: Key - C
d309d254-27f7-5cdc-948a-4e09ef798f0b | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.14 - Benching
9f690070-7825-523f-ba0a-99c4e650a23f | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days. All benching and sloping surfaces on manhole floor shall be rendered in 20mm thick 1:3 mortar
79d066de-4594-5bb4-980b-bcef5adab356 | note | Acceptance Criteria - Benching built up to the specifications
f1754186-21c0-544e-9949-356bb35509d1 | note | Verifying Document - Photos
44f64372-e8e4-5a97-8c27-380d4791ee29 | note | Frequency - During benching contruction
e9bc1618-6b77-5d8c-8bbe-62803fa6ce56 | note | Inspection Type (Visual, other) - Visual
32438469-3cae-52e9-b149-d400f96c6f38 | note | Inspection: Key - C
7e68cb30-22aa-52cd-a8f0-738f70e1af04 | note | Inspection: By (Role Key) - QE/SP
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
f26c9873-f5ee-533b-889c-773c723df63e | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
e3397f3e-daab-5f65-b71f-2c72d55dfb52 | note | Acceptance Criteria - Engineer Approval
495af7bc-316e-5c6e-a1de-169664add6b3 | note | Verifying Document - QA records
62da949b-de58-5196-9d30-300c8549ce07 | note | Frequency - At completion
c4ebe227-7205-5eb5-9810-8dbc06519745 | note | Inspection: Key - H
3daab93e-66c3-5b99-b3b1-a0367ea8289c | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.3 - Leak testing
6bc3bf4e-a7c1-55ca-a472-2328af81cf96 | note | Inspection Point: Quality Control Activity - Manholes should be tested seperately to pipeline for water tightness up to lower rim of manhole cover frame. Specs 1131: 16.2.2.5
ad35ee03-bf1b-56d6-9170-cfd489abc7ef | note | Acceptance Criteria - A maximum drop in water level over 30 min should not exceed 2mL/hr/mm of diameter/meter height of the manhole.
b1210a9b-2d59-5124-bd90-c8f2f6bc4163 | note | Verifying Document - Photos, Test Records
5b54c2fa-952b-53c4-9907-3d56dfa170b0 | note | Frequency - For every manhole installed
e432a717-a7b2-5086-9eca-ddc6edff1a62 | note | Inspection Type (Visual, other) - Test, visual
71b1b87b-7fe0-51a4-a4e9-ff2aefd732aa | note | Inspection: Key - H
0c9c3b78-45de-509d-a217-94118cef18ce | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| section | SECTION 6 - COMMENTS
| checkpoint | Customer Release Granted
458c6691-f90a-54e1-be16-0ce78384c614 | textbox | Certificate Number:
7fe5d36c-5dc2-58be-9fd2-e25f9e6a0db8 | date | Date:
| checklist | 561469-ITP-0006 - Storage Tank (DG-QA-TP018) | itp | 561469-ITP-0006 - Storage Tank (DG-QA-TP018) | 2446e7f9-1e57-452c-835a-951f014c1d50
| section | SECTION 3 - RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
0a8fc9c6-a08f-5a03-9842-1bb51a5c3c12 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
2cb29c7b-ae84-512c-b88a-0b4c8120b89e | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
2cacba94-f527-5852-a2ff-2642d089561c | note | Verifying Document - ITP
4fb13dac-e745-5c69-9d7a-18eadb7b3b93 | note | Frequency - Prior to the commencement of Works
90672128-58e8-5b0f-9c51-a95f0bdf3827 | note | Inspection Type (Visual, other) - Visual
c6b0c3ff-18d9-5ae2-9d90-08faea5ef1f7 | note | Inspection: Key - R
90aacb3d-b7e6-50f0-a16e-72f90fe0a565 | note | Inspection: By - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
7434a12c-1ea9-522d-9d9e-f82c80657de6 | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
5903a7b9-537c-5681-9f22-4808ffcb7888 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
f7ff8361-d65d-541e-8d5e-c5bd1500de93 | note | Verifying Document - Compliance surveys or spot checks
c30fea64-f61c-5b14-aa2e-2d5c8d2566d6 | note | Frequency - Prior to the commencement of Works
a4b78414-35ee-585f-a3ee-06f046959a3f | note | Inspection Type (Visual, other) - Visual, Instrumental
431e4d10-bb58-5cea-9453-593a2cd507f1 | note | Inspection: Key - H
0e63e184-0cda-5035-94df-52b507603393 | note | Inspection: By - SP/QE/SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Valves Delivery
92d78987-8cd7-5119-bae7-24f0ab597ef1 | note | Inspection Point: Quality Control Activity - Gate valves shall comply with AS/NZS 2638. Valves greater than DN50 shall be resilient seated sluice valves. DN50 shall be gate valves. Sluice valves shall be anti-clockwise closing. DN50 gate valves shall be clockwise closing. Valves shall be provided with a surface box according to the asset owner’s engineering standards. Specs 1131: 14.3.1
b1d29978-2610-5cbc-91ee-9b98b444e690 | note | Acceptance Criteria - The charasteritics of the valves delivered to site match the corresponding specifications, drawings details or approved equivalent
a0b1bff2-9c32-59cf-9018-0faf87bbbd0f | note | Verifying Document - Delivery docket, Supplier certificate, Photo
3cbf4ef3-a1b5-534a-9883-91519da4203f | note | Frequency - Prior to the commencement of Works
77a3dad4-39d4-5914-8bbc-47accb3522fb | note | Inspection Type (Visual, other) - Visual
0b313910-7a82-53d2-8d42-4c3b6eb5f728 | note | Inspection: Key - C
b074f5c4-105b-50f7-9dce-3d09d59fcfe6 | note | Inspection: By - QE/CR
| checkpoint | 3.4 - Joints and Fittings
883edc96-bd57-53d6-a90d-20f8f00689d1 | note | Inspection Point: Quality Control Activity - All joints and fittings must comply with wath is estipulated on Specs 1131: 14.3.2
0a5e8bca-e110-5ef6-ad4b-7397418fda4a | note | Acceptance Criteria - The charasteritics of the fittings delivered to site match the corresponding specifications, drawings details or approved equivalent
f62d35c5-be80-5aeb-8720-ec00cca6bd27 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
98af42b4-a767-5b54-a6a2-fcb0720f875f | note | Frequency - Prior to the commencement of Works
d6acad31-15b7-58c6-9ede-299e08bad296 | note | Inspection Type (Visual, other) - Visual
5de33e5a-0528-5066-91b3-9bd586f1840c | note | Inspection: Key - C
988ba8de-c1d2-506e-b3c9-3c88dd9b24d1 | note | Inspection: By - QE/CR
| checkpoint | 3.5 - Pipe Bedding and Haunching Agregate
69cc5d47-e839-5af3-abc8-90cce43013f9 | note | Inspection Point: Quality Control Activity - Pipe bedding should be AP20 and in accordance with AS/NZS 2566.2 or AS/NZA 3725. Maximum Dry Density (MDD) and Optimum Water Content (OWC) of the aggregate must be provided. Specs 1131: 14.9.1
eb8a82a5-132a-5ab6-9cb3-14ea6ca039d6 | note | Acceptance Criteria - Visual Inspection, Engineer approval
daddf413-e392-5419-9726-553b27f82982 | note | Verifying Document - Delivery Docket, Laboratory test results
99f41925-151f-51c2-aa6d-a43cee481703 | note | Frequency - Prior to the commencement of Works
39b83695-44c7-5e7b-b934-b1ef051d9688 | note | Inspection Type (Visual, other) - Visual, Lab Test
88f2ebec-f8b4-5c1e-9133-80cd5e16329c | note | Inspection: Key - H
ec5ca5ab-8e97-5f7f-8b7f-003e2ba13eb5 | note | Inspection: By - QE/SP/MC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Backfill Aggregate
22b3674a-5a5e-5a24-aa13-c809a1f1ad8f | note | Inspection Point: Quality Control Activity - Backfill aggregate should be GAP 65. Samples of backfill material should be tested in accordence of NZS 4402 to determine the MDD at OMC. The solid density of aggregate should be tested in accordance with NZS 4407. Specs 1131: 16.1.1
31ddaf4a-fe1e-5143-8fbf-66b66d52c66a | note | Acceptance Criteria - Visual Inspection, Engineer approval
7f3c4ec4-9064-50b1-ac08-e0083bbde3fa | note | Verifying Document - Delivery Docket, Laboratory test results
83d850ad-1744-5f49-97f3-1cb4d08b2bf6 | note | Frequency - Prior to the commencement of Works
3888dc66-62c2-52c0-8ef7-869ae0d4ae6a | note | Inspection Type (Visual, other) - Visual, Lab Test
2b39b491-0e68-50d2-9fca-cc4138968e02 | note | Inspection: Key - H
acb88c75-db0c-5521-bb1d-803f2f840deb | note | Inspection: By - QE/SP/MC
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Concrete Manhole, Catchpits and Access Chambers
d14b0e8b-a6bd-5c53-9ddd-87291428c79b | note | Inspection Point: Quality Control Activity - Precast concrete estructures shall comply with NZS 3106. Specs 1131: 14.5
97f07452-b73f-5c31-95c3-75970522504c | note | Acceptance Criteria - Manhole charasteritics Match NZS 3106
1f8a134a-3d8f-5a63-b5b7-3941d4d4799d | note | Verifying Document - Delivery docket, Supplier certificate, Photo
81e68c9a-315b-5a05-992d-e934ff0ba255 | note | Frequency - Prior to the commencement of Works
158cdd34-5954-561c-96f4-9b92b5848a11 | note | Inspection Type (Visual, other) - Visual
a01b856b-5acb-5059-905c-e12b9570d396 | note | Inspection: Key - C
a5ed4d07-ffdd-5f22-b47a-91e7ef4138c2 | note | Inspection: By - QE/SP/MC
| checkpoint | 3.8 - Material Storage
510cc38b-b072-50e7-982e-d36a6bf83130 | note | Inspection Point: Quality Control Activity - Storage for materiales must be arranged as it is described in: Specs 1131: 14.10
57bf1a51-a895-5083-84ef-14c1e7dde284 | note | Acceptance Criteria - Pipe stored according to specifications
dd122651-b066-5d43-bb1d-929ccdbcb12d | note | Verifying Document - Photo
602fc5ae-a67b-51ad-a86e-8ad721f48ead | note | Frequency - Prior to the commencement of Works
25e2383b-26a9-55a6-998f-4896a2486c31 | note | Inspection Type (Visual, other) - Visual
d2d86653-8469-58a8-896d-3add2c2c190d | note | Inspection: Key - C
8078e772-0f32-5f2b-813f-66e6ec477cf3 | note | Inspection: By - QE/SP/MC
| checkpoint | 3.9 - Defective Materials
c0547e7e-e274-5515-9f8f-ba29ca744d08 | note | Inspection Point: Quality Control Activity - Any materials that do not comply with this specification or that have been damaged as a result of the Contractor’s operations shall be removed from site and replaced at the Contractor’s expense. Repairs may be considered at the sole discretion of the Engineer. Specs 1131: 14.12
8d8b6871-4508-5802-9be4-a7bb4b29cc66 | note | Acceptance Criteria - Defective material detected and removed from site
0f3acbab-e8a2-5459-a641-4e9179560ae5 | note | Verifying Document - Delivery docket, Photo
81155a3e-e659-5fda-9864-7399ee9afde2 | note | Frequency - Prior to the commencement of Works
596b05e2-7cae-540a-bde9-9eabb81a25ec | note | Inspection Type (Visual, other) - Visual
c8491195-f687-5ca1-8efe-64c6e3aa69a4 | note | Inspection: Key - C
4a24f07a-9aaf-593d-968c-96e11e2395a3 | note | Inspection: By - QE/SP/MC
| section | SECTION 4 - IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Hazardous Waste and Contaminated soils
2659e2a4-c290-5c07-9ec7-b6aad9459985 | note | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
290a62a1-f79b-525d-a762-0e1ac5a9ebdc | note | Acceptance Criteria - Dumping site approval for contamiantion type
acbe3e55-539d-57e3-9608-4cf07481c59c | note | Verifying Document - Dumping Docket
296b13a5-25de-5e00-a12b-e95af0b1854a | note | Frequency - If constaminated soils are found
f79c35f7-3ed0-54c1-9452-30c0019cb09f | note | Inspection Type (Visual, other) - Document Check
b16630d3-bd57-5cf5-a755-e0ae129a6c38 | note | Inspection: Key - C
53aac44d-9558-53f5-b2ca-0b850e44f8d9 | note | Inspection: By - QE/SP/CR
| checkpoint | 4.2 - Trench Excavation
a3e9b7a3-ab32-5161-a422-e40e46ebde5a | note | Inspection Point: Quality Control Activity - Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated.
a8bb900e-11a7-54ed-b490-27c3ee7d09ed | note | Acceptance Criteria - Trench width and pipe clearance to walls comply with requirements
13b6dfe7-ece4-57b2-aca5-8a86322d6118 | note | Verifying Document - Installation Check Sheet
08888a69-6f17-5021-8563-1a174688fba1 | note | Frequency - During trench excavation
42807ba1-2341-5ec7-9a5c-bdf135591306 | note | Inspection Type (Visual, other) - Visual, Measurement Check
bf0584fa-1096-5f1a-a458-5e47d43d29c6 | note | Inspection: Key - C
5b2f9c78-b9ac-520d-b37f-0db106e1def1 | note | Inspection: By - QE/SP
| checkpoint | 4.3 - Pipe Bedding and Haunching
4ccf6de5-2ab3-522a-8a13-778d38223efb | note | Inspection Point: Quality Control Activity - Bedding and Haunching for flexible pipes should be in accordance with AS/NZS 2556.2 and have minimum embedment zone as shown in table from Specs 1131: 15.2.8.2
34c31c4f-4b66-509d-b946-1b0b56651ec1 | note | Acceptance Criteria - Bedding and haunching high and with comply width requirements
be45c9f4-5f17-5b33-8c0f-40625263e371 | note | Verifying Document - Installation Check Sheet
81bd8524-e27a-53eb-8fe5-f1addbea0e72 | note | Frequency - During bedding and haunching installation
6ca9e2b3-e242-5a38-8473-0efe4aaed967 | note | Inspection Type (Visual, other) - Visual, Measurement Check
206af2b0-33bd-5907-93c0-84457e3b0b6d | note | Inspection: Key - C
7a2920f2-1f51-5bc1-b7aa-28e3875f1e03 | note | Inspection: By - QE/SP
| checkpoint | 4.4 - Pipe Line and Level
99a368ad-a59c-535d-ab55-55583444f32a | note | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line and level within the tolerances specified in Specs 1131: 15.9. Invert levels shall take precedence over depths. Specs 1131: 15.3.12
f1ca9c81-2d3a-53bc-b53e-64a72adb90bb | note | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
b098d9f9-db24-5d19-94ea-37d0d21adea8 | note | Verifying Document - Grade Check sheet
7fc32b28-d923-5657-b026-9a55664ef536 | note | Frequency - During pipe installation
3426488d-d6cc-5d8e-9430-6ce71b931e8b | note | Inspection Type (Visual, other) - Visual, Instrumental
16066ab9-7ac6-58e7-800c-8aa4805009dc | note | Inspection: Key - C
c23276cb-4961-5e2b-aab2-c5dce25799fb | note | Inspection: By - SP/QE/SV
| checkpoint | 4.5 - Precast Concrete Pipe Installation
4798ed6e-3dde-5540-8a4a-f38d1ad2b4bb | note | Inspection Point: Quality Control Activity - Joints between precast pipe units shall be self-centering and shall be sealed with butyl mastic or similar approved to form a watertight joint. Concrete pipes shall be installed in accordance with AS/NZS 3725. Specs 1131: 15.3.6
4926f4b4-c7b2-56f5-b228-41010e992d2d | note | Acceptance Criteria - Precast concrete pipes Joints and Intallation comply with standard and specifications
a609db29-ab87-5e08-b6ee-48cf1b385694 | note | Verifying Document - Methodology. QA records
f31a0160-adcb-5af7-8927-85b2ac75c4f2 | note | Frequency - Per joint, and during pipe installation
fc8b85f0-391d-5087-88a4-f66fa7107601 | note | Inspection Type (Visual, other) - Visual
a7b1e976-9cc1-5085-9427-02619d902f94 | note | Inspection: Key - C
2044dfd6-b1d1-5abf-a15d-afc43a711d35 | note | Inspection: By - QE/SP
| checkpoint | 4.6 - Aggregate Compaction
62b44c1b-2e2b-52a2-afeb-e45fcdecc05f | note | Inspection Point: Quality Control Activity - Compaction shall be as stated in Specs 1131: 15.4.4. For concrete pipes the verification testing of compaction shall use a method recommended in table 3 of the CPAA Technical Note on Installing Concrete Pipe and approved by the Engineer. Specs 1131: 15.3.6
9f221887-a7a5-5634-b823-7c6675c2bee8 | note | Acceptance Criteria - Compaction Value ≥ Specification Value
cd262a3a-330a-510d-b344-9495a44709d9 | note | Verifying Document - Depending of Pipe material or Aggregate: CBR Checksheet, Nuclear Density Meter (NDM) Results Sheet, Clegg Hamer test records
9551aade-f8bd-574a-8862-c9a40e75e551 | note | Frequency - each layer
20fb3e34-e2a1-5969-8932-abf209525237 | note | Inspection Type (Visual, other) - On site Test
c1433e85-c713-5e90-a19c-0be8f5d6198e | note | Inspection: Key - H
82a636c1-8d70-5775-884f-534b6852cf06 | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.7 - Backfill Compaction
537bff63-11b5-556f-8b44-dd16741b36bf | note | Inspection Point: Quality Control Activity - Selected fill within 0.8m depth from finished surface shall be AP 65. Subgrade and subbase shall be compacted in layers no greater than 200 mm thick unless otherwise agreed with the Engineer. Under carriageway basecourse shall be compacted in layers no greater than 150mm thick unless otherwise aggred with the engineer. Specs 1131: 15.4.3.2, 15.4.3.3
718c918f-c7d1-58ae-bf0d-dfcb6cca7f45 | note | Acceptance Criteria - Dry Density ≥ 90% MDD
ee94676c-d76f-5bb5-a91c-259e023f870f | note | Verifying Document - Nuclear Density Meter (NDM) Results Sheet or Clegg Hamer test records
53f02884-f597-51ad-8a71-9bc57131fb4f | note | Frequency - each layer
6d2190d1-b1dc-5146-b9f1-e18c18d7b457 | note | Inspection Type (Visual, other) - On site Test
9ba35310-5e0f-54b3-917d-26b3828b4f6f | note | Inspection: Key - H
0c01f3db-065b-5b2f-a77c-3e4e998e18c0 | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.8 - Topsoiling and grassing
69d68f04-98ae-5b44-9873-9fd68957e237 | note | Inspection Point: Quality Control Activity - Topsoil shall be used to dress areas disturbed by the contrat works to a minimum thickness of 100mm. Grass seed shall be sown evenly over the prepared topsoil area. Specs 1131: 15.8.6
8e18d255-9787-5cfa-b710-07a39586ddc4 | note | Acceptance Criteria - Topsoil installed and grass seed spread in the specified rate and mixture.
d9aaeaed-e88e-5311-b9b6-bc87baec93a9 | note | Verifying Document - QA records, Photos
1552120c-8106-5f08-8fe5-37bd69bba6e8 | note | Frequency - After compaction of final layer of backfill
d1b935f9-39e2-5f82-b431-f9e16eda80ed | note | Inspection Type (Visual, other) - Visual
35ba2468-ca37-539f-a449-65711fb80f2a | note | Inspection: Key - C
1430d552-8675-5e27-9274-cc9776eeac2e | note | Inspection: By - QE/SP
| checkpoint | 4.9 - PE pipes Welding
8e4816c0-e638-5d1f-97f3-2a877d388083 | note | Inspection Point: Quality Control Activity - In accordance with manufactures specifications. Where unspecified butt welding in accordance with PIPA POP003 and electrofusion welding in accordance with PIPA POP001. All welds shall be marked with weld number and welder identification. Specs 1131: 15.3.2.1.
7c99070f-0a98-5469-a4a6-e9a4158c5065 | note | Acceptance Criteria - PE Welding ejectuded as specified
3565b2a3-b9af-566b-a11f-ad3ff8cf52d9 | note | Verifying Document - QA records, Weld records
ddbc77ee-ea8d-5ae2-b689-e09c05ff1633 | note | Frequency - Per weld
9b170814-8b2e-5540-900b-108511bb9237 | note | Inspection Type (Visual, other) - Visual
5ca622d9-3964-5a8b-be45-88915bc3061f | note | Inspection: Key - C
9a75296e-d652-54cc-b3b2-fa53afba58a2 | note | Inspection: By - QE/SP/WS
| checkpoint | 4.10 - Welded Joints Inspections
7c9d234f-68f2-5ed5-8688-b1fffc5990e6 | note | Inspection Point: Quality Control Activity - Each butt-welded joint will be visually inspected by the engineer and Each electrofusion joint shall be visually inspected by the contractor according to Specs 1131: 16.3.2.1
5e8671b2-4db0-5890-8a5e-9577aec49b1a | note | Acceptance Criteria - Welded Joints complies with visual inspection specified
001595b1-ba73-5a9c-8868-02e62b402aad | note | Verifying Document - QA records, Weld records, Photo
c3db93ba-0daa-5970-83ba-6028eb91c375 | note | Frequency - After welding each joint
149199ff-5777-5304-91c9-a6aa91980b97 | note | Inspection Type (Visual, other) - Visual, Measurement Check
8a6e4af5-a092-5d3c-a4d0-96221930a9c7 | note | Inspection: Key - C
35c33ee7-e3c9-531d-813e-184877d63ecf | note | Inspection: By - QE/SP/WS
| checkpoint | 4.11 - Pipes Connected to Structures
7fd92f28-acd7-51fc-bd4b-094b6f7f375c | note | Inspection Point: Quality Control Activity - Where a pipe is built into an underground structure, the requirements stipulated in Specs 1131: 15.3.10 must be followed
63162a8d-ccee-53ba-a3b8-c9e0ce99ca21 | note | Acceptance Criteria - Pipe is connected to the structures according to the specifications
5cfc2efb-963a-5656-983b-365c16ae24d0 | note | Verifying Document - Methodology, QA records, Photos
5d308e2d-d940-5839-a082-85b0a24057a9 | note | Frequency - During installation
2efa4c91-5830-58f2-bc84-2fa0ae4a6a4e | note | Inspection Type (Visual, other) - Visual, Measurement Check
d8373d67-40ce-5b3b-9c7f-52d6ee385714 | note | Inspection: Key - C
71f45685-a16e-5107-b683-4f1f1c1c8bc3 | note | Inspection: By - QE/SP
| section | SECTION 5 - FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
2d7ff931-1518-512d-b1bf-d33b7455b9e4 | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
080e1695-f73e-5f0f-b756-0393bb151a79 | note | Acceptance Criteria - Engineer Approval
920afe6f-74c6-5dc4-b2f2-6dafb456fb92 | note | Verifying Document - QA records
975e0757-99ac-52d6-8f25-c0b9888aae44 | note | Frequency - At completion
046b1cb5-bd3a-53cd-bbfd-33c1e2029243 | note | Inspection: Key - H
282ea995-05cf-55c7-9fbe-86a53c1ae7eb | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Manholes
0b7ad952-6e88-5d46-bfcf-c1655b02622b | note | Inspection Point: Quality Control Activity - Manholes should be tested seperately to pipeline for water tightness up to lower rim of manhole cover frame. Testing shall be in the presence of the engineer. Specs 1131: 16.2.2.5
6614bb39-19d7-5171-aa80-6b88fd9043f5 | note | Acceptance Criteria - A maximum drop in water level over 30 min should not exceed 2mL/hr/mm of diameter/meter height of the manhole. Engineer Approval
799bdd09-aa11-5d8d-be80-af7248a0911e | note | Verifying Document - Test Records
f5e879e9-223e-5c71-a254-c0ffe5eaef88 | note | Frequency - For every manhole installed (24hr prior notice to the engineer before test)
842a5b96-4e7d-5e55-90e9-b1d282bb39e5 | note | Inspection Type (Visual, other) - Test
17f7b322-d6a8-5e04-9b25-b7651a8a4a31 | note | Inspection: Key - H
a3d43d22-6121-534d-8711-eed45c7e82b6 | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - CCTV Inspection
a7d3ebe3-191e-5ced-bdb2-cf29bdea035d | note | Inspection Point: Quality Control Activity - All pipelines shall pass a CCTV inspection. All pipelines shall be free of debris and flushed 24hrs prior to inspection. Specs 1131: 16.2.3
4358de50-7302-54cd-bb62-8dad4f1eed06 | note | Acceptance Criteria - A pipeline will fail its inspection if:
c1cbddc3-da69-5ba5-b0c4-c48d112daf50 | note | – The pipe is horizontally misaligned or deformed by more than 5 % of the pipe diameter.
71f80935-2e32-5e03-b74f-52074dc1f078 | note | – The pipe has visible dips or ponding of water.
cd46b0e9-3e69-5e12-a8bc-574e3fd72eac | note | – The pipe has visible defects, such as open or displaced joints, defective or protruding laterals, cracked barrels or similar defects.
d6ab2fa9-9b0b-54c5-b3c7-9759e4f193b4 | note | – There is evidence of infiltration at joints or laterals.
e3259f65-7c75-560a-ad90-5210ac846bb8 | note | Verifying Document - CCTV footage and log sheets
59aad746-181d-52c5-bc51-227aa5291d7a | note | Frequency - At every section of pipe installed.
f34bd7da-0dad-5fec-9986-84bccb5fc483 | note | Inspection Type (Visual, other) - Visual
cd2146fd-72b7-5d2f-b548-f58a819d58f3 | note | Inspection: Key - H
7938cb7c-a237-58ba-b648-d31afb95b987 | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Surplus Materials and Refuse Disposal
580a15e5-4a44-551f-b927-e6986950a3c3 | note | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
df2010ab-f189-55b4-ae49-bd1843edf603 | note | Frequency - At completion
a4261913-8293-5368-b9e3-e2ceccafb0da | note | Inspection Type (Visual, other) - Visual
ab62de5f-b438-5f5e-86cf-065d06f905dd | note | Inspection: Key - C
6715c8fb-bf4d-5f13-967c-4e919172452b | note | Inspection: By - QE/SP/CR
| checkpoint | 5.5 - Cleaning
f6413ac5-28a5-5576-84bd-eeaaf56265db | note | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
e022a4fd-6055-5a1c-be88-3cc45da25ecb | note | Frequency - At completion
e509123e-1a7d-5e1d-998c-4c62e2a8ffa6 | note | Inspection Type (Visual, other) - Visual
d88e9de4-52ce-556e-b4b0-2cb50d707406 | note | Inspection: Key - C
f5df836e-1d7b-525c-952d-d6c8badb76ff | note | Inspection: By - QE/SP/CR
| section | SECTION 6 - COMMENTS
| checkpoint | Customer Release Granted
728764d5-a043-5a08-aff5-ffb95abd930d | textbox | Certificate Number:
17b03a6f-633c-5828-9b65-805f93028f90 | date | Date:
| checklist | 561469-ITP-0007 - Sand Filter (DG-QA-TP018) | itp | 561469-ITP-0007 - Sand Filter (DG-QA-TP018) | 39b1f4dc-6975-4f2c-9498-aae708e647b9
| section | SECTION 3 - RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
446d26da-5dac-55ba-903b-987fb8e9f434 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
aa1cdc61-7ac6-56a8-a047-e05d5510458d | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
6eb42aa0-8e55-5144-9f8a-54c373f6c458 | note | Verifying Document - ITP
29911fb2-5129-500f-a08c-e96db34ecb8e | note | Frequency - Prior to the commencement of Works
62e8dd53-cad1-56a4-9d1d-b6df015a9b73 | note | Inspection Type (Visual, other) - Visual
16877858-42d4-5cf9-ab27-68d9081a1c9c | note | Inspection: Key - R
22d1655c-c2a9-5fd8-be69-4fd7def357da | note | Inspection: By - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
d4a82937-41b1-553d-a9b2-f74551facbf0 | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
4ff47c97-5641-5885-854d-9d1e38703105 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
604a4aac-27a3-57cd-8602-c46a18a4f4fd | note | Verifying Document - Compliance surveys or spot checks
a11b2f1c-d912-5cc4-b76d-023119f90731 | note | Frequency - Prior to the commencement of Works
00f0e337-d9b8-56cc-a436-722f630fb7a5 | note | Inspection Type (Visual, other) - Visual, Instrumental
0eced4da-fb92-5ff8-8dec-fff22318ac65 | note | Inspection: Key - H
e6e3f834-9f93-5935-8922-0890fc677c17 | note | Inspection: By - SP/QE/SV
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Pipes Delivery
72576b32-8f6a-5662-a15a-e2f81bbd268b | note | Inspection Point: Quality Control Activity - Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C260 - C261
651e2c17-ed2a-5119-9961-5957885efbb3 | note | Acceptance Criteria - The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent
a891dad2-d84a-5c50-ab93-df2c8d90f3b1 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
db372088-0f4e-586e-a677-616220be199f | note | Frequency - Prior to the commencement of Works
7353038d-b346-5dc1-89bf-3c876593cc1f | note | Inspection Type (Visual, other) - Visual
1cc93883-5899-58c5-9feb-53484318635c | note | Inspection: Key - C
e9546818-1c34-51e0-a678-83d0fb5646ed | note | Inspection: By - QE/CR
| checkpoint | 3.4 - Joints and Fittings
6363705f-45b5-556c-aae7-f245f1610e0a | note | Inspection Point: Quality Control Activity - All joints and fittings must comply with wath is estipulated on Specs 1131: 14.3.2
7540da8d-5b4d-59c2-b339-d16f8ae230c5 | note | Acceptance Criteria - The charasteritics of the fittings delivered to site match the corresponding specifications, drawings details or approved equivalent
829df3f5-f845-515b-9c55-2910248da7bb | note | Verifying Document - Delivery docket, Supplier certificate, Photo
0aee1b47-499a-5dd0-a2a7-28b6413a20ad | note | Frequency - Prior to the commencement of Works
1c48d54f-bda7-5b10-b2f4-cf2f7fd1c0ad | note | Inspection Type (Visual, other) - Visual
8f920e15-d265-59c6-b377-cebe1816a62d | note | Inspection: Key - C
004b76b2-dfb7-51d7-ab70-0f38f0b8a1e3 | note | Inspection: By - QE/CR
| checkpoint | 3.5 - Drainage Aggregate
0e7a5b6d-0dec-593f-8834-7f1c2e0bd8e8 | note | Inspection Point: Quality Control Activity - Drainage aggregate shall be 19 mm uniformly graded, clean, durable aggregate having a crushing resistance of not less than 100 kN when tested in accordance with NZS 4407. Material used for backfilling the trench above any geotextile wrapping shall be free draining granular material. Specs 1131: 14.9.2
57cdf4da-9858-5ec3-a40f-b0d29d5c101f | note | Acceptance Criteria - Visual Inspection
f130c458-2a73-53ae-b809-0bdc9bd1610e | note | Verifying Document - Delivery docket, Supplier certificate, Photo
c5dfa3c7-0170-5816-ba1a-60f6c1ea7144 | note | Frequency - Prior to the commencement of Works
41aa9420-2edf-5682-9017-05bc9c763689 | note | Inspection Type (Visual, other) - Visual
dd89b794-e7af-5b1e-a5eb-57a0f5d987ba | note | Inspection: Key - C
66412706-69cc-5c17-8f4c-908846f9e1e4 | note | Inspection: By - QE/SP/MC
| checkpoint | 3.6 - Material Storage
e34eadfa-8cde-5a06-bfe4-ecd4bf258d02 | note | Inspection Point: Quality Control Activity - Storage for materiales must be arranged as it is described in: Specs 1131: 14.10
5c4a29d0-2507-53a6-9be2-68cb7bcbd567 | note | Acceptance Criteria - Pipe stored according to specifications
2cef14e7-6947-5131-bb38-270e880344d4 | note | Verifying Document - Photo
c7c43eff-3bf3-5de8-ae24-51176ee24578 | note | Frequency - Prior to the commencement of Works
0ad52d0b-3b89-5b8a-8bfa-f7a9758d7850 | note | Inspection Type (Visual, other) - Visual
f624f87b-95d4-5498-921f-c6b6e878bb1c | note | Inspection: Key - C
4a19d62d-e079-5210-87e6-e2594b56118f | note | Inspection: By - QE/SP/MC
| checkpoint | 3.7 - Defective Materials
17c2ca0a-fb12-5c5c-b3f0-e91fce5046e4 | note | Inspection Point: Quality Control Activity - Any materials that do not comply with this specification or that have been damaged as a result of the Contractor’s operations shall be removed from site and replaced at the Contractor’s expense. Repairs may be considered at the sole discretion of the Engineer. Specs 1131: 14.12
67118aa0-2af6-53fe-9217-9bc4427f2f4c | note | Acceptance Criteria - Defective material detected and removed from site
82ca2f9f-0e0a-544a-8b66-8d077c74be5e | note | Verifying Document - Delivery docket, Photo
3e3d385b-b867-51b2-8bbb-eb7d9f119c83 | note | Frequency - Prior to the commencement of Works
574358a8-6012-53b2-90ad-0e07ef26ad95 | note | Inspection Type (Visual, other) - Visual
991dfcef-9f8f-5582-b27c-bb61df2830e6 | note | Inspection: Key - C
d6ccb478-0d70-582f-ab0e-481b06996d20 | note | Inspection: By - QE/SP/MC
| checkpoint | 3.8 - PVC Pipes
a1dc6caf-03c2-5a1d-bc33-c51dc13eece2 | note | Inspection Point: Quality Control Activity - PVC-U gravity pipes for sewer, drainage, ducting or venting shall comply with AS/NZS 1260. Shall have spigot and socket joints with rubber rings. Specs 1131: 14.2.1 and Drawings C260 - C261
c4a5522f-c5ea-575c-bfb5-cf1345bdadfd | note | Acceptance Criteria - The charasteritics of the PVC pipes delivered to site comply with the standard and specificationsDelivery docket, Supplier certificate, Photo
2ac57e8f-5560-589e-ba71-f0740bf59643 | note | Verifying Document - Delivery docket, Supplier certificate, Photo
eb62cdc5-89a9-5fe3-b91a-5ef4ad4a94fc | note | Frequency - Prior to the commencement of Works
d42f07bf-5872-5a76-9964-2fc6c593a9ee | note | Inspection Type (Visual, other) - Visual
f74abba7-8ce4-51c6-af72-9630ce365e74 | note | Inspection: Key - C
82964d3a-f5e1-588e-874d-eeef1fa7292c | note | Inspection: By - QE/SP/MC
| checkpoint | 3.9 - Geotextile
3920f971-76c6-571a-b400-d99b4f528554 | note | Inspection Point: Quality Control Activity - Geotextile underlay bidim A37 or similar approved material. Drawings C260 - C261
c3522fa4-6c56-5977-924a-5d4117e8319f | note | Acceptance Criteria - Procured Geotextile comply with specifications
b80170a9-dac6-5086-a6f6-85fc2a87391d | note | Verifying Document - Delivery docket, Photo, Engineer approval
6ffcd97f-8619-5e92-ac15-4b693fd7fff7 | note | Frequency - Prior to the commencement of Works
6385ab62-6988-5ba9-bb27-7b9592e2cd5d | note | Inspection Type (Visual, other) - Visual
e1cb3367-9298-5737-84b5-7e1ddad81a61 | note | Inspection: Key - C
0c87d36b-baed-5069-bc06-aaf9620aab33 | note | Inspection: By - QE/SP/MC
| section | SECTION 4 - IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Hazardous Waste and Contaminated soils
20f201f0-dbe1-539f-a172-b54cb658d469 | note | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3, 1131: 13.5.3
d216f4ca-d567-5555-a8bc-01f5b1d40e86 | note | Acceptance Criteria - Dumping site approval for contamiantion type
e8032ebc-061e-58b0-8462-467f162f9fed | note | Verifying Document - Dumping Docket
2a802dc0-1e95-5b1d-a8d9-159941fef098 | note | Frequency - Hazardous material identified is the filter media in the intermittent sand filters that are to be replaced.
43f4f234-87b1-5d1c-b35c-a2bbb0f739a6 | note | Inspection Type (Visual, other) - Document Check
15f40b98-e255-5ba9-8653-85af96cb9cf0 | note | Inspection: Key - C
ca43690e-55a8-583c-b089-2e22b6db9bf8 | note | Inspection: By - QE/SP/CR
| checkpoint | 4.2 - Existing Plastic Liner
fd027581-7752-556c-b57a-23591d4ad39d | note | Inspection Point: Quality Control Activity - To be kept if possible, take care not to damage when removing existing media. Drawing C261
8604002c-4894-5f45-ac67-d84c7d1810ba | note | Acceptance Criteria - Existing filter media removed with minimum damage to the existing plastic liner
fbfa04f2-cb3f-598d-957e-d6c3a480598a | note | Verifying Document - Methodology, QA records, Photos
687369d2-7352-5253-81e8-d29ba592096e | note | Frequency - During ISF media removal
a1fa7c09-0ea6-58ef-9720-32160b182e1a | note | Inspection Type (Visual, other) - Visual
ad8b346d-fc34-5b23-a242-6c97ff9cf5a2 | note | Inspection: Key - C
51c13318-40d2-565f-8d04-a311644347b1 | note | Inspection: By - QE/SP
| checkpoint | 4.3 - Pipe Line and Level
446e51a8-4815-517d-bd74-e95ef120fc26 | note | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line and level within the tolerances specified in Specs 1131: 15.9. Invert levels shall take precedence over depths. Specs 1131: 15.3.12
69964238-ad12-5f31-96d1-c7ec24c0056f | note | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
ecaf9221-0881-54c4-981f-3e6aa0054eaa | note | Verifying Document - Grade Check sheet
2d094dbf-fcec-57e9-bdc8-e2edb2ba2e92 | note | Frequency - During pipe installation
addbf84b-7439-5c71-97ea-389a1a14493c | note | Inspection Type (Visual, other) - Visual, Instrumental
e12fc8f2-2dd4-5ebc-b9a2-90d34667ea6d | note | Inspection: Key - C
624cc773-edb5-509c-b2ab-383378d21e3c | note | Inspection: By - SP/QE/SV
| checkpoint | 4.4 - PVC Pipe Installation
2e11c8c8-c9d3-5355-8e5a-66f796ce5535 | note | Inspection Point: Quality Control Activity - Buried PVC pipes shall be installed in accordance with AS/NZS 2032 and AS/NZS 2566.2, as applicable. Specs 1131: 15.3.1.
4c1b861a-294e-530d-9b9e-d2d27360d653 | note | Acceptance Criteria - PVC Pipes Joints and Intallation comply with standard and specifications
c2111d65-bc7c-588c-a2a5-8b39cbbb306b | note | Verifying Document - Methodology, QA records, Photos
b80b31c3-49d7-52b7-9d3f-d53b33f37d13 | note | Frequency - During pipe installation
87db86f6-89a8-5571-9335-097c6ea84a5d | note | Inspection Type (Visual, other) - Visual
b3724941-f809-58ac-9c36-f3bef4758990 | note | Inspection: Key - C
af991a6a-c283-5d25-a03f-d4cd008f2157 | note | Inspection: By - QE/SP
| checkpoint | 4.5 - PVC Joints
0d441466-c4d0-5e17-8345-8a21472f84c2 | note | Inspection Point: Quality Control Activity - All PVC-U shall be jointed by solvent cement weld. Drawing C260
9d5cebaf-d5f6-542a-80ea-aa5c76be13a2 | note | Acceptance Criteria - Joints are carried out as specified
efaf9db7-aad7-5dd4-8ceb-bb2544604075 | note | Verifying Document - Methodology, QA records, Photos
34308d17-9996-5e7b-9428-c07d9594aa8d | note | Frequency - During pipe installation
05563fe5-8ace-5368-8522-67b6c3f7c43b | note | Inspection Type (Visual, other) - Visual
6cd67dd5-623c-5207-b1b6-979708e3b4ab | note | Inspection: Key - C
afe7d5da-24bc-5545-9f8f-c056448c5911 | note | Inspection: By - QE/SP
| checkpoint | 4.6 - ISF PVC Laterals
82e3b152-b2dd-5ae7-850e-bad56c3d079b | note | Inspection Point: Quality Control Activity - DN40 PVC-U pipe with 6mm holes at 800mm centres facing upwards, positioned inside DN100 PVC-U pipe with 25mm holes in pipe invert at 150mm centers. Laterals to be positioned at 1.0m from centers in the horizontal. Drawing C260
ef2fd69f-88c4-51cb-a17d-f5d42acea161 | note | Acceptance Criteria - Laterals are installed as specified in drawings
3bc2b0d4-9103-5014-a384-e2977ed325dc | note | Verifying Document - Methodology, QA records, Photos
b5fe9b3e-002a-556a-a4f7-38d8b64d0d06 | note | Frequency - During pipe installation
5fb17426-b239-5f42-bfaf-84654b778634 | note | Inspection Type (Visual, other) - Visual
fd56b129-c2bf-5e90-a0ea-85f3d07893fb | note | Inspection: Key - C
7e27bfa2-80fb-5aed-be8d-ccdc61bacc06 | note | Inspection: By - QE/SP
| checkpoint | 4.7 - ISF PE Drains and Vents
52001857-e081-514f-b27a-6407d8ea3354 | note | Inspection Point: Quality Control Activity - 4xDN110 heavy dutty slotted PE drain pipe with air vents, to be positioned at 2.25m from centers in the horizontal. Drawing C261
edb03f78-374e-505b-a34d-2544b4ed023d | note | Acceptance Criteria - Drains are installed as specified in drawings
83082953-0285-5cee-b800-3267e2562a69 | note | Verifying Document - Methodology, QA records, Photos
9ab3757a-6c91-50ec-97c9-7c2dc5fc7293 | note | Frequency - During pipe installation
1d4030d2-bcd6-53f3-ac7b-00bc5620fecf | note | Inspection Type (Visual, other) - Visual
fa5c2dcf-c710-5e0c-907c-fd5da521de50 | note | Inspection: Key - C
ae8fc165-d873-5268-b0a4-90aa85cb335b | note | Inspection: By - QE/SP
| checkpoint | 4.8 - Drainage Chip
b2162d0c-75fe-5b62-a41a-7271aff93129 | note | Inspection Point: Quality Control Activity - Layers of 12mm and 20mm drainage chip as specified in Drawing C261
2f84f859-5000-517a-a616-fe17c0b19d6c | note | Acceptance Criteria - Drainage chip layers installed as specified in drawings
fd9e9214-8de4-591b-869c-a6d3356bbee8 | note | Verifying Document - Methodology, Delivery docket, QA records, Photos
9362a72c-a33e-5b5e-a7d2-89b99b0810c9 | note | Frequency - During drainage chip installation
5f248e87-7d69-5c81-9ef1-f584fbf3458c | note | Inspection Type (Visual, other) - Visual
d89401c1-8272-59a1-9ffc-07d8e3268158 | note | Inspection: Key - C
7517a032-d735-55a5-ba7c-0d46ead39c77 | note | Inspection: By - QE/SP
| checkpoint | 4.9 - Pea gravel
720c3344-5df6-5d19-b182-11c25cffe085 | note | Inspection Point: Quality Control Activity - 4-7mm pea gravel layer above drainage chip layer and above coarse sand layer around drains as specified in Drawing C261
91926cf5-68ef-564a-95b8-3ab7efad8f32 | note | Acceptance Criteria - Pea gravel layer installed as specified in drawings
99c63a00-6a30-5eb9-b020-25f87e94f223 | note | Verifying Document - Methodology, Delivery docket, QA records, Photos
3129e7cc-e0b3-55fc-a20d-f220c9a92ab3 | note | Frequency - During pea gravel installation
dacb3c0e-2eb0-5768-9dc1-9b20dbc1c5cc | note | Inspection Type (Visual, other) - Visual
e4a93d63-37d9-5af0-9efb-3b19368e8189 | note | Inspection: Key - C
38feaacd-8532-5f3f-8299-78dc4950ddab | note | Inspection: By - QE/SP
| checkpoint | 4.10 - Filter sand
43428955-565e-5cfb-bc79-1a4ef38050be | note | Inspection Point: Quality Control Activity - Clean course sand: effective size 0.25 to 0.75mm, uniformity coefficient <4.0. Drawing C261
b142eb97-a617-5e98-bd49-aa851923adcf | note | Acceptance Criteria - Course sand layer installed as specified in drawings
6d30955c-53b9-58bd-a95c-cd9a112c8788 | note | Verifying Document - Methodology, Delivery docket, QA records, Photos, Supplier certificate
d0fd6635-cfec-5939-a615-2aef1407b630 | note | Frequency - During filter sand installation
29f988b9-9f36-5f24-a040-ce92ff7a13b7 | note | Inspection Type (Visual, other) - Visual
495651e7-5d80-5321-8710-4796ec4808d9 | note | Inspection: Key - C
392fa9df-5599-50cb-938c-851e9ec3cbac | note | Inspection: By - QE/SP
| checkpoint | 4.11 - Cutting pipes
8e7204e5-c84b-5410-a906-3fd437c15b0b | note | Inspection Point: Quality Control Activity - Where pipes need to be cut to form non-stardard lengths, pipes shall be cut by a method which complies with manufacturers recommendations and provides a clean square profile. Specs 1131: 15.3.7
dd18c785-789b-51bc-ad16-7ce7364f777b | note | Acceptance Criteria - Pipe cutted up to the specifications
83c2b811-2f07-512d-874f-47d0b9ca7e31 | note | Verifying Document - Methodology, Photos
c669eb15-450b-5b7e-a62d-012ab7e16827 | note | Frequency - During pipe installation
74fc446c-7e84-578c-a1c2-cdd5d1693d38 | note | Inspection Type (Visual, other) - Visual
d66b6ff5-365c-5e42-adae-d0bc7db9a0df | note | Inspection: Key - C
659d551b-6962-5737-acc9-d8ae6c0be9a5 | note | Inspection: By - QE/SP
| section | SECTION 5 - FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
fb6d2f3c-25e7-57b7-bc35-3b3b629af252 | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
165ba32a-bef9-5c0e-8cf4-3bf2c7d0005a | note | Acceptance Criteria - Engineer Approval
69e96988-07fb-5af2-a151-689a31a8ddc7 | note | Verifying Document - QA records
e5426715-33da-5eca-bd04-0e91a76a0bce | note | Frequency - At completion
58151782-0273-5690-b226-ed19c6804b47 | note | Inspection: Key - H
4ab0b270-1fc2-59af-b391-9272260cf46c | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - CCTV Inspection
51322aa8-82e9-5981-b1e1-6ce4016a0b91 | note | Inspection Point: Quality Control Activity - All pipelines shall pass a CCTV inspection. All pipelines shall be free of debris and flushed 24hrs prior to inspection. Specs 1131: 16.2.3
d4e127cf-7382-55cc-89b1-96a2dfbfc895 | note | Acceptance Criteria - A pipeline will fail its inspection if:
cfc23de9-e0da-59a1-8ecc-78c4eaa5aee7 | note | – The pipe is horizontally misaligned or deformed by more than 5 % of the pipe diameter.
cac8e324-c207-5564-8008-d8935f9c2f76 | note | – The pipe has visible dips or ponding of water.
0fe038f0-e54b-55dd-94b4-79f01dbd7832 | note | – The pipe has visible defects, such as open or displaced joints, defective or protruding laterals, cracked barrels or similar defects.
c85b3acb-5776-5262-bc43-004027b89543 | note | – There is evidence of infiltration at joints or laterals.
4d9dc0bc-1b43-5a26-9fb1-18c67de72290 | note | Verifying Document - CCTV footage and log sheets
d571a12b-0905-50c7-b21a-5d665896d6e5 | note | Frequency - At every section of pipe installed.
3957aa4f-46b7-567d-ada2-8391d1e0ac2e | note | Inspection Type (Visual, other) - Visual
a5bb2ea8-f406-5651-9ce7-f0fd0c788067 | note | Inspection: Key - H
d0059af1-09f9-5738-9834-1bebe9e93d6b | note | Inspection: By - QE/CR
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Surplus Materials and Refuse Disposal
31d3fa88-14ba-5143-99ba-b1f73c8bc981 | note | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
b3b60847-942f-5d10-82c7-ad6ec6ed8c46 | note | Frequency - At completion
8f8226d2-8784-5191-8aac-30e9a18cf4ae | note | Inspection Type (Visual, other) - Visual
8d256c51-fad3-5423-b607-9622efd6053f | note | Inspection: Key - C
91c8455e-4d9c-54f5-946f-a39d6d35088c | note | Inspection: By - QE/SP/CR
| checkpoint | 5.4 - Cleaning
49a5e391-a949-58dc-a4ab-ba0c47025bd6 | note | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
076460cc-3522-5b6f-87c6-8957cdc2d0cf | note | Frequency - At completion
1e414306-8a24-5025-b760-f6c697b261e6 | note | Inspection Type (Visual, other) - Visual
32e4bc76-0ab7-5a06-9056-f774e95ab27e | note | Inspection: Key - C
6030bbf8-6efc-5890-8948-32b15fb740b8 | note | Inspection: By - QE/SP/CR
| section | SECTION 6 - COMMENTS
| checkpoint | Customer Release Granted
e28f724f-1b56-5ec1-99fb-ad2a8ffdea35 | textbox | Certificate Number:
b807cad3-18bf-593b-bef8-003a5102b835 | date | Date:
| checklist | 561469-ITP-0008 - Overflow Line (DG-QA-TP018) | itp | 561469-ITP-0008 - Overflow Line (DG-QA-TP018) | a03de567-68fd-413a-a9de-13534c019f82
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
eab09c3c-64a8-5213-8cda-b97822cf32b3 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
1770d8ed-a5c0-5c08-8ff5-55314150a083 | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
c19b3149-40d3-5b51-8ccd-228fc64ea48a | note | Verifying Document - ITP
4da433c9-59c6-58eb-bac2-6258c5277fee | note | Frequency - Prior to the commencement of Works
d1c78f86-2b2b-5199-9703-6cd21a30e95f | note | Inspection Type (Visual, other) - Visual
178b1646-ce57-5cff-8be1-347a789358e6 | note | Inspection: Key - R
b08da57a-aa24-5d3e-abc0-d9d8eaea80bd | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Setting Out Levels and Alignment
fa3d5833-5710-551a-9a4f-27ea4972f5c1 | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
b268d9ba-3266-53ee-9739-89cc25afd8f7 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
d481cc5f-8a37-5ee0-a1db-9056810822fc | note | Verifying Document - Compliance surveys or spot checks
b3855920-281a-5257-8866-4fad21ff4411 | note | Frequency - Prior to the commencement of Works
20719222-1e76-5872-b2f1-8063264927e5 | note | Inspection Type (Visual, other) - Visual, Instrumental
c639d01a-3e62-5768-9cc6-2d3c61407b6e | note | Inspection: Key - H
18b6acbc-d7fe-58c9-b091-394ade784573 | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.3 - Pipes Delivery
a83fcdbe-eb81-50a4-be0a-dc5e70bf9e3c | note | Inspection Point: Quality Control Activity - Pipes and pipe fittings shall be of the material, pipe class and joint type nominated on the Drawings. Specs 1131: 14.1 and Drawings C152 - C153
80f54388-4b82-546a-a1a8-d72dc979e9d5 | note | Acceptance Criteria - The charasteritics of the pipes delivered to site match the corresponding drawings details or approved equivalent
3a76d36c-3da4-533c-8edb-5c5965cca7fe | note | Verifying Document - Delivery docket, Supplier certificate, Photo
71674b78-02b2-5da3-b3ab-ed843020ec98 | note | Frequency - Prior to the commencement of Works
6162f12e-0b31-50bf-a6e0-41e308e6d2ac | note | Inspection Type (Visual, other) - Visual
7b5df8bf-d5db-5fdb-8b20-2c70b4b9fad5 | note | Inspection: Key - C
1d815513-9471-5b54-913a-9ce67e3e4da4 | note | Inspection: By (Role Key) - QE/CR
| checkpoint | 3.4 - Joints and Fittings
c2211599-a0aa-5ecf-9d7f-6afc869f4653 | note | Inspection Point: Quality Control Activity - All joints and fittings must comply with wath is estipulated on Specs 1131: 14.3.2
7f02d04a-ebbf-5149-bb51-b9681013502a | note | Acceptance Criteria - The charasteritics of the fittings delivered to site match the corresponding specifications, drawings details or approved equivalent
4860ecad-8d77-58de-be14-9e049966598f | note | Verifying Document - Delivery docket, Photo
d811f776-d50b-59e7-b043-8bb6cc19fde2 | note | Frequency - Prior to the commencement of Works
d8d60b06-0bd5-5232-8092-d9c7c8151275 | note | Inspection Type (Visual, other) - Visual
fe41bbb3-575e-5e8c-9c8a-9093d69b2873 | note | Inspection: Key - C
4ea1c9d1-af66-5627-9ed8-bb8e67341f70 | note | Inspection: By (Role Key) - QE/CR
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Trench Excavation
0dfb0c4c-82a4-5380-8eb2-8c33a979b15d | note | Inspection Point: Quality Control Activity - Trenches for flexible pipes shall be excavated within tollerances in table from Specs 1131: 15.2.5 unless otherwise stated Drawing C115
9faaa122-e0a8-5ba6-b40c-dde4ba1861a2 | note | Acceptance Criteria - Depth of trench to achieve required minimum 600 mm cover
098ebdcb-c406-5ac1-86ef-1a0a2c07e373 | note | Verifying Document - Photos
da43ac47-2726-5e57-9f9f-19f3f2cd863f | note | Frequency - During trench excavation
526965ad-674e-5862-aba6-de1a703c35d0 | note | Inspection Type (Visual, other) - Visual, Measurement Check
4673db10-1923-5dfa-a3c9-055b7f6fa054 | note | Inspection: Key - C
3abe3dbb-486d-53aa-8e6d-90d2625ddc9e | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.2 - Pipe Bedding and Haunching
3700c49f-70a0-5dcf-a6e9-064f34875958 | note | Inspection Point: Quality Control Activity - Bedding and Haunching for submains should be in accordance with Drawing C115
2eb737d7-42f5-5609-a9ab-2c43964f1b43 | note | Acceptance Criteria - Bedding material to have max size of 20mm
eac3334b-1a65-53ce-be44-931b6322a3e9 | note | Verifying Document - Photos
bdce1045-ddc3-52e6-89ec-ebc78bc2b7c8 | note | Frequency - During bedding and haunching installation
1c1d5008-d985-5f8f-a823-44d3dc1bcf32 | note | Inspection Type (Visual, other) - Visual
7c43a704-a3c2-500e-9e15-9166299fb69f | note | Inspection: Key - C
5b02d811-0957-5f0f-aefe-0269f0388dec | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.3 - Pipe Line and Level
d6fbbbe0-9641-504c-8b87-8527b4f2990d | note | Inspection Point: Quality Control Activity - Pipes shall be laid true to the design line as in Drawings C100-C104
bb9ee4bf-8c5b-5609-91a5-b7c1488c86e9 | note | Acceptance Criteria - Pipe levels are within the tolerance and according to the drawings, 2D data and linework provided or agreed with the Engineer
0e9ff8b9-fa1a-5875-9803-8ade22786066 | note | Verifying Document - Photos
cfcc42c6-e0ce-5166-ab86-292df640d19f | note | Frequency - During pipe installation
9e649492-4c02-500c-ae69-2fe23ec21a5c | note | Inspection Type (Visual, other) - Visual
e37b5b05-8351-5771-b577-3ef042eb28e9 | note | Inspection: Key - C
9e8b9df9-2e48-57ed-bae0-07c0bc1c7f72 | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.4 - PE Pipe Installation
72108c3a-d0cd-5730-87d9-6bd8f3b5e4c4 | note | Inspection Point: Quality Control Activity - Buried PE pipes shall be installed in accordance with AS/NZS 2033 and AS/NZA 2566.2, as applicable. Specs 1131: 15.3.2.2
11f9dac5-c0cb-57b6-b9a8-62305f575aab | note | Acceptance Criteria - PE Pipe Joints and Intallation comply with standard and specifications
cbbfa97e-13f4-5d68-9516-c60a2656eca6 | note | Verifying Document - Pipe welds QA records, welding checksheets and machine printouts, destructive tests results (if required)
74d306d9-7dc2-54f1-9dbc-6bd5c249e9fb | note | Frequency - Per weld, and during pipe installation
3db7ab4b-d52f-5375-917a-8096114ab61f | note | Inspection Type (Visual, other) - Visual, Document Check, Lab test (if required)
67d8d258-8e57-5322-bb71-f99c1d5eae91 | note | Inspection: Key - C
486f51bc-ee87-5cc7-835e-9d5ed8899e3d | note | Inspection: By (Role Key) - QE/SP
| checkpoint | 4.5 - PVC Pipe Installation
685a068c-bb63-570f-bf4d-b03a488299bf | note | Inspection Point: Quality Control Activity - Buried PVC pipes shall be installed in accordance with AS/NZS 2032 and AS/NZS 2566.2, as applicable. . Specs 1131: 15.3.1.
91e95912-c838-5ffc-8d19-cc6d500d6db1 | note | Acceptance Criteria - PVC Pipes Joints and Intallation comply with standard and specifications
8ecf3a5c-2f98-5e9f-a098-bec65db1d0cf | note | Verifying Document - Photos
50437408-f031-505f-b45e-e9f244f04292 | note | Frequency - During installation
26449b92-5ca5-5a7e-8cd3-d15c2d0b12d9 | note | Inspection Type (Visual, other) - Visual
c23be95a-0757-5a98-bf46-46d2d4fdc631 | note | Inspection: Key - C
7c3ae87d-6462-52da-b54c-85747f74eea1 | note | Inspection: By (Role Key) - QE/SP
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
624bc4d1-7429-50c9-8740-965b489b933b | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
405da86e-a2eb-5e7e-89d5-50918f97130f | note | Acceptance Criteria - Engineer Approval
dc3a4361-7758-506c-8075-aa95e9abff0c | note | Verifying Document - QA records
f7a7834e-76c8-5e07-a965-b551703f0a3d | note | Frequency - At completion
3a43c476-86f8-5378-b434-b6fefa6b751f | note | Inspection: Key - H
37ad6108-ab10-5f93-8acf-5a10ca766039 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.2 - Pressure Testing
bde806da-c6bb-51ff-82c6-06f9629bf5d1 | note | Inspection Point: Quality Control Activity - Test for PE pipelines shall be completed in accordance with AS/NZS 2566.2:2002 relevant appendices. Specs 1131: 16.3.1
eb2bab72-2f84-5f5b-8473-0e8cd52088f9 | note | Acceptance Criteria - Test results per pipe size comply with the standard and specifications
2bdd21d1-3656-526c-8478-ee3d3586aee3 | note | Verifying Document - Test Records, Photos
fc3e51a0-506a-54da-a356-372ba40f75ac | note | Frequency - At sections of pipe required
3ee869c0-9b1d-5dbb-a493-97e86744f188 | note | Inspection Type (Visual, other) - Test
cebeb554-965e-50aa-95bb-4bc91a90a07b | note | Inspection: Key - H
ba0db52e-a793-517b-a64b-28b03771307a | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| section | SECTION 6 - COMMENTS
| checkpoint | Customer Release Granted
7e586167-d51a-5db6-8ef8-ac5913dfcffd | textbox | Certificate Number:
e4af0a09-f2cf-5190-9200-6cb238502d99 | date | Date:
| checklist | 561469-ITP-0010 - Footpath (DG-QA-TP018) | itp | 561469-ITP-0010 - Footpath (DG-QA-TP018) | a7b8811e-06a9-4c4e-9adf-c6d2aeb6d1ee
| section | SECTION 3 – RECEIVING INSPECTIONS
| checkpoint | 3.1 - Review all Drawings and Documents
a92929f1-8f04-5d9a-b684-4ff19c594381 | note | Inspection Point: Quality Control Activity - Review all drawings and documentation provided to the Contractor.
19efb358-f791-5c38-80ed-dcf2678df636 | note | Acceptance Criteria - Prior to the commencement of Works it must be ensure that all necessary documentation has been provided.
645e5aa4-2709-5fcc-ab0e-f5a48adab0c3 | note | Verifying Document - ITP
6c866211-3fa4-5bb9-bb16-17b8fab26e84 | note | Frequency - Prior to the commencement of Works
baca3dfc-d8a9-5a7d-bd47-39a6d52b656b | note | Inspection Type (Visual, other) - Visual
ff7175c1-8a77-5df9-ac8b-f83b4ad90b65 | note | Inspection: Key - R
905081b9-1eea-52bd-b676-58bc68468aea | note | Inspection: By (Role Key) - PM/QE
| checkpoint | 3.2 - Design Approval
6c045afd-deb5-5848-8d24-714b5710a0fd | note | Inspection Point: Quality Control Activity - Footpaths and steps are provisional items and shall only be constructed if approved by the Engineer. Specs 1230: 27
32507a10-4f96-5f14-906a-b668d27d46b9 | note | Acceptance Criteria - Engineer's Approval
35a6f1f7-0d31-5bca-bd04-9d481eed83cd | note | Verifying Document - Engineer Writen Approval
ab72317c-a2ca-5b2a-9187-36cbd3e50d2b | note | Frequency - Prior to the commencement of construction of any footpath or steps
f94492b4-4876-5680-9512-de18ec556c42 | note | Inspection: Key - H
644ad601-65e8-5635-90f3-dda4546efd41 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 3.3 - Setting Out Levels and Alignment
2addcf37-e24b-5a7e-8bb3-f1aee88fdd77 | note | Inspection Point: Quality Control Activity - All setting out shall be performed by or under the control of a licensed surveyor, who shall certify the accuracy of key dimensions of the as constructed works. Specs 1000: 3.2.4
4d12982a-d440-5f24-b6ff-e8d0bce03acd | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, 2D data and linework provided or agreed with the Engineer
1774b5ed-7c8f-5a80-ac83-ed07fcee9735 | note | Verifying Document - Compliance surveys or spot checks
9068cca2-aba3-5b59-ac13-ca32fad400e8 | note | Frequency - Prior to the commencement of Works
c7522b07-4bf0-5b55-bc24-b2ff2f3f3697 | note | Inspection Type (Visual, other) - Visual, Instrumental
cb3051eb-8301-5bc7-8ed9-df613975f5ed | note | Inspection: Key - H
41e4c981-01f9-5072-8f6e-ed025f33c493 | note | Inspection: By (Role Key) - SP/QE/SV
| signoff | HOLD POINT
| checkpoint | 3.4 - Service location and Hydro Vacumming
b8f2f7f4-df97-5249-a052-b422e716d241 | note | Inspection Point: Quality Control Activity - Physically locate the services inside and close to the alignment area and levels depth. Specs 1131: 15.2.1
4678b783-4c04-57e8-87a3-bab5c5a72cbf | note | Acceptance Criteria - All services identified in B4UDig, plans and mark outs has been physically located
2faa0b2c-07c9-50d4-83c9-f4f9fa4c788d | note | Verifying Document - Plans Mark out, photos
78cc767b-92ae-5669-baab-d737aa4a647b | note | Frequency - Prior to the commencement of Works
58245893-c81e-51d5-8159-dd3cefcc29bb | note | Inspection Type (Visual, other) - Visual
9460f662-ef81-562a-9801-404c44e8afc2 | note | Inspection: Key - H
f0d736c5-2919-58aa-a75f-7d7bd55ebafa | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 3.5 - Use of Local Material
deda8270-d734-5674-9911-1771370bacad | note | Inspection Point: Quality Control Activity - Borrow pits are generally a hole dug in the ground from which material is removed and used on the track. Dept. of Consevation Track Construction and Maintenance Guidelines: 13.4, 13.7
146c5c39-0c5d-5089-85a5-31521b1fec45 | note | Acceptance Criteria - Local Materail is any of the following:
1c9e44f1-5b99-5b01-aed0-9d2579df9b42 | note | – Firm clay/silt soils
2d07d8cd-d742-58b5-bef0-4e4f7d686d18 | note | – Sands/gravels
7182487c-f088-534b-a3ff-0037c42f6397 | note | – Boulder clay
49badaa7-fdd7-5f15-ad2c-b8d78ad6ef12 | note | – Weathered rock
dc80ac7d-3c10-5dc5-8d23-23cdf825861b | note | If not, import.
0a3e39e3-e72f-5649-91a2-eb67577e8cc0 | note | Verifying Document - Photos, Delivery Docket
8659a614-e379-5c7e-8624-3fdcfc1e6478 | note | Frequency - Prior to the commencement of Works
ee757c24-a4f1-5d43-b9ba-49540da21ec3 | note | Inspection Type (Visual, other) - Visual
6669b241-224b-59e3-9747-0402b8a86b6d | note | Inspection: Key - C
e3d8a76a-a6df-5134-9887-6edf2b60bff0 | note | Inspection: By (Role Key) - SP/QE
| section | SECTION 4 – IN-PROCESS INSPECTIONS
| checkpoint | 4.1 - Site Clearance
751f7b0b-d1de-5f9d-aa3e-da4d33ebcf07 | note | Inspection Point: Quality Control Activity - The material obtained from site celarance must be dumped at an approved location outside the Site. Specs 1100: 5.1
555d4272-1183-5b25-a165-9f0f48e040ff | note | Acceptance Criteria - Location approved by the Engineer
73305ada-ba4a-5f05-881e-b7b54fc629d9 | note | Verifying Document - Dumping Docket
0b5df65d-f7e3-500d-89a7-8738027f869f | note | Frequency - After site clearance
ae2faa6e-5e2b-50be-bbad-451d2917a65b | note | Inspection Type (Visual, other) - Document Check
e33aa845-dda7-5e1b-9f48-498c132b9e82 | note | Inspection: Key - C
bca8926b-e046-5d0e-997d-849251493577 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.2 - Trees Removal
5d2e9468-725b-5a4c-aa10-22b94fe44701 | note | Inspection Point: Quality Control Activity - No tree shall be cut down until the Engineer has given written authorisation for such work to commence. Specs 1100: 6.2
dbd04759-f40c-5523-811b-a6f58fce8f95 | note | Acceptance Criteria - Engineer Approval
98f1d4eb-ea57-5a45-a89a-d2cc3d4c96f1 | note | Verifying Document - Engineer Writen Authorisation
f461747b-0063-5e7b-95bd-b4b9eb7265a7 | note | Frequency - Before remove any tree
3ed65dc3-2bd9-5542-ad46-4a97a875758c | note | Inspection Type (Visual, other) - Client Consultation
2be2faf6-41a6-5a63-a832-02c7aec6d8d0 | note | Inspection: Key - H
ad4a4426-6111-5e9e-b717-2707baf072ff | note | Inspection: By (Role Key) - CR
| signoff | HOLD POINT
| checkpoint | 4.3 - Removal of Topsoil
7e3a7ebe-2ca7-5224-961f-af819713d079 | note | Inspection Point: Quality Control Activity - Topsoil shall be stockpiled in areas approved by the Engineer for this purpose. stockpiling operations must ensure the maximum utilisation of each area. Specs 1110: 9.4, TNZ F/1 Clause 4
07ec8c51-b6bc-53e1-9638-ebdc78d15100 | note | Acceptance Criteria - Engineer Approval
d14bfcf3-0927-5270-8168-c57290865d7c | note | Verifying Document - Engineer Writen Authorisation
4a0393de-246c-50dc-9c42-24b868c4ec18 | note | Frequency - Before Topsoil Removal
c82383f2-fb34-513e-9f43-45460f138c17 | note | Inspection Type (Visual, other) - Client Consultation
3447fc7e-4172-506d-973d-216e1e05892c | note | Inspection: Key - C
da5135be-f497-539d-ba8e-83953e8d4a9b | note | Inspection: By (Role Key) - CR
| checkpoint | 4.4 - Hazardous Waste and Contaminated soils
db4c7c20-4e76-57e7-8dd4-5054b23b9d93 | note | Inspection Point: Quality Control Activity - Contaminated soils (Type H materials) encountered shall be treated and/or disposed off site in accordance with statutory requirements. Specs 1110: 9.3
29a48604-4b2a-5cdb-90bf-444d021c45c3 | note | Acceptance Criteria - Dumping site approval for contamiantion type
6fb08371-d790-55ab-bc80-c8d1312b4ac8 | note | Verifying Document - Dumping Docket
68802c54-843b-5ff2-91fa-d509d447240c | note | Frequency - If constaminated soils are found
3d449f10-dd10-514d-907e-a14a3db212c4 | note | Inspection Type (Visual, other) - Document Check
6b823f31-f141-5e63-9dd9-48514543fd62 | note | Inspection: Key - C
7914d53f-0401-57c7-a982-9c38bfffbd8f | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 4.5 - Checking Levels and Alignment
0c44651e-4e97-562c-b272-8402c685e2b6 | note | Inspection Point: Quality Control Activity - The Contractor shall inspect all set out prior to construction to confirm that the 2D linework has been interpreted appropriately to achieve the line and level of the finished works. Specs 1000: 3.2.4
c99b3063-de92-56ec-a4db-a873b210a814 | note | Acceptance Criteria - Levels and allignment Set Out matches marks shown on the Drawings, Design, 2D data and linework provided or agreed with the Engineer
44bced11-a0c6-5fec-aea1-62a3fe338dd2 | note | Verifying Document - Compliance surveys or spot checks
c7489f86-8d16-585b-9205-fa9856cb4f8f | note | Frequency - During and at the end of the Excavation
4d597e98-7176-5afe-a395-9df94210dfce | note | Inspection Type (Visual, other) - Visual, Instrumental
201b187e-d27d-5e62-ad41-a28dd53bee9d | note | Inspection: Key - C
8ed81a6d-71c3-50eb-8f49-01c0fe9f772f | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.6 - Cut and Fill Foot path Construction
99071828-90e0-5670-be3d-75e1c627926f | note | Inspection Point: Quality Control Activity - Cut and fill construction involves cutting into the uphill sideslope and placing fill on the downhill slope. Depending of the sideslope. Dept. of Consevation Track Construction and Maintenance Guidelines: 13.1, 13.2
7fc77c66-fed5-5c56-844e-c08519d584f6 | note | Acceptance Criteria - Sideslope > 25° (50%), Cut Construction. Sideslope Between 6° - 25° (10% - 47%), Only Cut Construction.
124ceabd-2f70-5d53-b05c-aeda16371bbf | note | Verifying Document - Compliance surveys or spot checks
4ab20cfc-5b2f-5c4c-b7f6-0c1ae47c5aca | note | Frequency - Before Excavation
c1951aba-e94b-5176-a488-2809f3a71506 | note | Inspection Type (Visual, other) - Visual, Instrumental
f275e17f-d2cf-5bec-8d89-fe748e9146f5 | note | Inspection: Key - C
9ad35c2e-efb4-5dee-967d-7d2d9ff42cf5 | note | Inspection: By (Role Key) - SP/QE/SV
| checkpoint | 4.7 - Footpath Fill Compaction
2bc6e1ad-9ee8-56cc-8b97-890ed9dceffe | note | Inspection Point: Quality Control Activity - Compaction may be checked when undertaking fill formation work. All fill material needs to be compacted in layers no greater than 250 mm (prior to compaction). Dept. of Consevation Track Construction and Maintenance Guidelines: 13.2, 13.5
94264b61-df62-5b08-a75f-7358f9794979 | note | Acceptance Criteria - The Dynamic Cone Penetrometre can be used to indicate the compaction of soil and/or fill materials. If a large number of blows is needed to cause the cone to penetrate a short distance the soil/material is well compacted
9a200fe8-3ee6-5ba9-95a7-5c21c0f15f80 | note | Verifying Document - Dynamic Cone Penetrometre Checksheet
b6e74eb1-b3e1-5b38-bbe1-f39ae61ae31b | note | Frequency - After compaction of fill layer
b33d392f-6bc0-59cc-8a16-67ad2598d8c9 | note | Inspection Type (Visual, other) - Visual, Instrumental
e7b5c8a6-6487-57ac-9661-da09fd24bb64 | note | Inspection: Key - C
53381fcd-f0f5-5d0b-a7af-17f9c6e33ad4 | note | Inspection: By (Role Key) - SP/QE
| section | SECTION 5 – FINAL INSPECTION AND HANDOVER
| checkpoint | 5.1 - As-built Drawings
54d283cc-596c-5a83-ad01-ce3c1effe4af | note | Inspection Point: Quality Control Activity - Two hard copies and one electronic copy of As-built drawings shall be prepared in draft and final versions following Schedule 1D in NZS4404:2010. Specs 1000: 3.9.2
3096487c-5155-5c7a-bf4c-4fbaccd62985 | note | Acceptance Criteria - Engineer Approval
0ae1c2cf-31be-5668-9f8e-9d4b7fe16a9f | note | Verifying Document - QA records
c0aba1ff-e938-5be0-a344-ee9d7ce896bf | note | Frequency - At completion
5f1ca390-277c-5727-bd21-e994a4ae0298 | note | Inspection: Key - H
d6769301-df30-580e-9c2d-b164ea434834 | note | Inspection: By (Role Key) - QE/CR
| signoff | HOLD POINT
| checkpoint | 5.2 - Surplus Materials and Refuse Disposal
badf0291-1d43-5ab1-bc27-6d4388f3ff7e | note | Inspection Point: Quality Control Activity - All surplus, redundant and faulty materials must be removed from the Site and dispose of them in a safe and legal manner. Any demolition material or rubbish coming from the execution of the project must be removed as well. Specs 1000: 3.13.2
06a84dc2-73b7-5a0c-a5dd-03d3038d81f4 | note | Frequency - At completion
d3d0330b-6d86-53b0-9c98-e504598fcde2 | note | Inspection Type (Visual, other) - Visual
5f5271e5-6c54-5616-85a4-9ef6f4410d9a | note | Inspection: Key - C
f67542e5-321d-5d15-ae9c-a5ae3f34bdf6 | note | Inspection: By (Role Key) - QE/SP/CR
| checkpoint | 5.3 - Cleaning
684e6cae-f174-5e2d-8011-0448f2c007cd | note | Inspection Point: Quality Control Activity - Completed items of construction about to be placed in service or occupied for their intended use must be properly and thoroughly cleaned of all foreign matter and other debris. Specs 1000: 3.13.3
a7c2bbbf-2569-5e07-a1fa-118f955d9c8f | note | Frequency - At completion
0b0de89e-791b-5387-a8fb-913600d527a5 | note | Inspection Type (Visual, other) - Visual
24c4eaf2-91f3-54d8-97eb-f20b2430b2d9 | note | Inspection: Key - C
40ce4a98-ca4d-5629-b910-6a2eb9737aca | note | Inspection: By (Role Key) - QE/SP/CR