## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 561469-ITP-0011 - Retaining Wall (DG-QA-TP018) | itp |  |  |  |  | 561469-ITP-0011 - Retaining Wall (DG-QA-TP018)
section | SECTION 3 – RECEIVING INSPECTIONS
checkpoint | 3.1 - Set Out
label | Inspection Point: Quality Control Activity - Allignment and heights set out by surveyor. Post locations marked out
label | Acceptance Criteria - Levels and positions set out match dimensions specified on drawings privoded
label | Verifying Document - Complience surveys or spot checks
label | Frequency - Prior to the commencements of Works
label | Inspection Type (Visual, other) - Visual, Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP,QE,SV,CR
holdpoint | HOLD POINT
checkpoint | 3.2 - Ground bearing capacity
label | Inspection Point: Quality Control Activity - Confirm bearing capacity of founded ground
label | Acceptance Criteria - Bearing capacity not less than 150kpa tested to the pile embedment depth of 2.9m or as agreed by the engineer
label | Verifying Document - Scala records
label | Frequency - Prior to the commencements of Works
label | Inspection Type (Visual, other) - Instrumental
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP,QE,CR
holdpoint | HOLD POINT
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Post holes
label | Inspection Point: Quality Control Activity - Excavate post holes
label | Acceptance Criteria - Holes are clean and measurement match Drawings
label | Verifying Document - Photos, Site Inspection
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, Inspection
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP,QE,CR
holdpoint | HOLD POINT
checkpoint | 4.2 - Posts
label | Inspection Point: Quality Control Activity - Confirm using H5 poles and check dimensions
label | Acceptance Criteria - Size and length of pole are suitable and match drawings or agreed by the engineer
label | Verifying Document - Photos, Site Inspection
label | Frequency - Prior to Installation
label | Inspection Type (Visual, other) - Visual, Inspection
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP,QE,CR
holdpoint | HOLD POINT
checkpoint | 4.3 - Pour concrete
label | Inspection Point: Quality Control Activity - 20 MPa concrete
label | Acceptance Criteria -
label | Verifying Document - Photos, dockets
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP,QE,CR
checkpoint | 4.4 - Subsoil drain
label | Inspection Point: Quality Control Activity - 110mm perforated subsoil drain at base of wall, AP20 washed drainage material filter fabric around subsoil
label | Acceptance Criteria - Installed as specified in drawings or as approved by the engineer
label | Verifying Document - Photos, Site Inspection
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual, Inspection
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP,QE,CR
holdpoint | HOLD POINT
checkpoint | 4.5 - Backfill
label | Inspection Point: Quality Control Activity - Backfill behind retaining wall with clean free draining material
label | Acceptance Criteria - Backfill with approved fill material
label | Verifying Document - Photos
label | Frequency - During Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: Key - C
label | Inspection: By (Role Key) - SP,QE,CR
section | SECTION 5 – FINAL INSPECTION AND HANDOVER
checkpoint | 5.1 - Final Inspection
label | Inspection Point: Quality Control Activity -
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - photos, Engineer signoff
label | Frequency -
label | Inspection Type (Visual, other) - On site Inspection
label | Inspection: Key - H
label | Inspection: By (Role Key) - SP,QE, CR
holdpoint | HOLD POINT
section | SECTION 6 - COMMENTS
checkpoint | Customer Release Granted
textbox | Certificate Number:
date | Date: