## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Drainage ITP | itp | Drainage ITP | 3865ea72-b519-4e5e-a984-205ebde57da8
| section | Preliminary
| checkpoint | Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
07cab16a-beb8-5580-8982-400c5d60daab | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
829c7e48-285a-5574-baa1-0306214b6573 | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
9dcc5aa7-ffec-5637-b3e0-61f7c2a80bdc | note | FREQ. - Before work commences
7e8d84ba-fb49-5940-94e9-46208abe2728 | note | ACCEPTANCE CRITERIA - Zero service strikes
04ba3f66-dbff-544d-bcf7-24156f6e9689 | note | TYPE - H
166ad49d-aa03-5bed-8a9b-110a2802c9c5 | note | ASSESSOR - Richard Taare
400ce292-787e-52ae-8a21-e2b3c631ddeb | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
967356b6-8ce9-55ef-bcf4-2adbe2da9e37 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Cultural/Heritage Risk Assessment
473ad032-d4b5-5ec2-8fd1-b9a7fb8960d3 | note | VERIFICATION ACTIVITY - Notification
14367158-227c-5d51-9675-4b33cba21e82 | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
6ec72f7f-e13d-5bcc-bd87-9dad97317f5f | note | FREQ. - Before work commences
3370c5a8-f8df-5c39-a499-352ea21ab570 | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
c7f3036e-40c0-554f-abe5-5928fee2b142 | note | TYPE - H
b62e3dcc-b11e-55d2-bb94-9b59fdd69d76 | note | ASSESSOR - Richard Taare
3f9c2f7a-1feb-5492-888b-233564bb9bbf | note | DESCRIPTION - Where risk of cultural discovery
0a9132c0-d3ff-5ef0-9e41-bfad888535c7 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| section | Set-out / Site preparation
| checkpoint | Notification of intention to start work
51cdd8e8-ba3f-51f7-aa69-bbc3cc42de5a | note | VERIFICATION ACTIVITY - Notification
c02463c2-f43c-5640-ad4a-590ef3c9289f | note | FREQ. - Before work commences
2f88d14a-720f-5776-8035-fbaace6ef27c | note | ACCEPTANCE CRITERIA - Notification to stakeholders minimum 48 hrs before commencement, minimum 2 weeks notice for sensitive site (SWAMP)
f51ba519-6255-5e39-ac63-87fb04562bbd | note | TYPE - H
82d07218-f287-598b-9f9c-5cbc1b782827 | note | ASSESSOR - Richard Taare
d995b9d0-6c05-51c8-bf2f-71890ab0a60e | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
b025dc1b-8993-51a6-9540-19cc96ea31fc | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Archaeological Risk
e6ccabc8-57e9-536c-9e94-4d3263712e1b | note | VERIFICATION ACTIVITY - Toolbox meeting
f178aec8-67c5-581b-bfe6-9bac2f2ba365 | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
09810625-ebc9-5965-911f-4b3520d745f7 | note | FREQ. - Before work commences
6045778c-7f30-510f-9208-7d44b993c686 | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
e6088f80-660c-5e3c-b549-660dc9a0abfb | note | TYPE - H
b59590f5-4f22-5c72-b1bd-24ae4d586809 | note | ASSESSOR - Richard Taare
13316d6c-bc7b-59ae-a16b-fdc88e7a1883 | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
52a57fe1-aae8-557b-b37b-2ee9e3504a78 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Traffic Management - TMP
9615f682-4aee-543c-aa80-36be23692468 | note | VERIFICATION ACTIVITY - Visual check
a5f95205-c4af-542e-8d7e-1c7491d6483e | note | METHODS OR REFERENCE - CoPTTM
97d1a2e9-b1a0-5b8c-adab-f39ca6c3a61b | note | FREQ. - CoPTTM
77589102-b286-5fda-8602-7c629e01ae28 | note | ACCEPTANCE CRITERIA - TMP checked and approved
02627564-f27b-581f-84fe-c79cfe7c1398 | note | ○ Plans approved
00900cc3-0f64-5cda-acdc-7092b324f08f | note | ○ Current CAR
b4b2db55-2fd0-5384-b093-668cea646a33 | note | TYPE - H
117bcf25-d73b-5d33-9e93-7863b3213c08 | note | ASSESSOR - Richard Taare
6955f496-46ca-585e-805a-71f7df701deb | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
f3450db5-ee67-5941-8fa6-23a9fa71ac7a | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Traffic Management - Setup
2651cdf3-494e-5fce-b70f-7b9260a4fa5e | note | VERIFICATION ACTIVITY - Visual check
06984893-d8cd-5041-8b69-4b8fddf6ebde | note | METHODS OR REFERENCE - Traffic Management Plan
74e362f0-6683-564a-9670-6aeaff15de77 | note | FREQ. - Before work commences
cac3672d-7097-5a43-a898-32bed9efa0fc | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
e40e897d-ab4e-54cd-ae21-a27818c96f37 | note | TYPE - H
b3b2d65a-12e7-563f-a2b6-9dfa82986da0 | note | ASSESSOR - Richard Taare
fe8c72c9-53bd-5589-ba5f-04dfde8c9e0e | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
4d628f6e-3bd8-5867-86eb-239fac12739a | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Filter Material
83929ea3-cac8-5a0b-95ad-3222a8fe9d88 | note | VERIFICATION ACTIVITY - Grading Test
4b15436d-e43c-56d1-a02e-d8b6397101ba | note | METHODS OR REFERENCE - NZS 4402: Part 2:1986
96422008-7797-5979-b1d7-8c84016488ab | note | FREQ. - Per stockpile/ Job
0fcd27a4-d06b-5408-87fb-ce2b20263cce | note | ACCEPTANCE CRITERIA - Filter material shall be clean, durable stone having a crushing resistance of not less than 100 kN when tested and comply with Grading limits
1784038b-21f8-583b-a85d-d317ba04592a | note | TYPE - V
37e4e8e6-b64b-5d9c-8da5-38fd7886956e | note | ASSESSOR - Richard Taare
b8708bfb-3151-52db-8b08-d62c3164fed0 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Geotextile
7e59226d-0dff-56b5-b527-b90f629f941a | note | VERIFICATION ACTIVITY - Verification
56c5a3ce-1848-5542-a92a-c958fa6ff1f2 | note | METHODS OR REFERENCE - NZTAF7
13a4a9a2-024a-5ab9-a86e-a4ee0c6e9231 | note | FREQ. - Per installation
2fcb0216-7574-5a68-a370-3f355ed6ff1e | note | ACCEPTANCE CRITERIA - Strength class B and filtration class 1
4ff2b8e3-3a22-5123-b407-0c6b5f692cc8 | note | TYPE - V
1965a1a4-7842-540d-9a5e-fcd95d9086c8 | note | ASSESSOR - Richard Taare
255adacc-a617-5cdd-8155-cee29bb90c2d | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Sediment Control
035b9d99-a13a-5eaf-b321-e8a65afca32d | note | VERIFICATION ACTIVITY - Physical
87325851-0436-58cc-9bc6-2763e80c129b | note | METHODS OR REFERENCE - ESMP
8b9f7c7e-d76f-5969-a1c0-63f58ca87c62 | note | FREQ. - Before Excavation Commences
c6af4390-3a6f-5cde-873c-6357d6f2c1a8 | note | ACCEPTANCE CRITERIA - Place silt fence, earth bund or other sediment contol device around area to protect nearby waterways
f9e27fd1-dded-5382-9a1e-b152afbc9118 | note | TYPE - H
7f9f0b89-7f37-5094-b4ff-2d157422e768 | note | ASSESSOR - Richard Taare
9ea7628c-b3e5-5d8b-ad8b-4294b2d70bb5 | note | DESCRIPTION - Hold point - No physical works are to be commenced until sediment control measure is in palce
80830426-6a3a-5aa8-9ff2-f45eca89b7cf | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| section | Construction
| checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (1)
98aaa442-a51c-52c6-a4d6-3cd6fcc2ca19 | note | VERIFICATION ACTIVITY - Slope Checks
bdfe3c80-d3f0-5bbe-9fd8-ee3f8ab5f765 | note | METHODS OR REFERENCE - TNZ F/2 Section 3
d3117d00-6c6f-5de0-97e9-7ae734554afd | note | FREQ. - Every 20 m of subsoil bedding layer
11c95ba5-8c84-5982-b7f8-859f3d065a67 | note | ACCEPTANCE CRITERIA - Levels to show that a minimum of 1:100 (1%) fall is being achieved using Rotating laser level, theodolite or other surveying device
65b11d84-1297-5cbc-922f-c156b89efc8a | note | TYPE - V
6394a3ca-e7cd-5ec3-ad11-c0c90c3d6dbe | note | ASSESSOR - Richard Taare
28b567db-3641-53b3-b826-bf0096b10a4c | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (2)
c8f3c1b2-7faa-59c5-9e00-34514eabb2c4 | note | VERIFICATION ACTIVITY - Depth Checks
51329dad-d779-5ebb-ba5b-04df09a56e1a | note | METHODS OR REFERENCE - TNZ F/2 Section 3 NZS 2566:1998
9e5f8b99-d746-56ff-bf4e-f473693ddb0f | note | FREQ. - Every 20 m of excavated area
46bd14a8-82dd-5959-b218-c1de5fb260d3 | note | ACCEPTANCE CRITERIA - Minimum cover for flexible pipes - 750 mm unsealed roads, 600 mm sealed roads, 450 mm outside road carriageway
f70e4a5d-8ca5-5d3e-9fb7-e5c71042a6de | note | TYPE - V
e9873191-230d-5954-890c-836331411583 | note | ASSESSOR - Richard Taare
4483f52b-8955-5443-9a43-5266e7eb0ff8 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (3)
04e2367f-67b9-5d3a-aa52-52349fa3420b | note | VERIFICATION ACTIVITY - Depth Checks
cc663e57-2b35-5d73-bdd3-c0b987995a17 | note | FREQ. - Every 20 m of excavated area
9f5c1ad6-8de1-589d-af25-ff7dcc1b4324 | note | ACCEPTANCE CRITERIA - Invert shall not be less than 800 mm below finished road level
918eb2fa-0966-5af4-a586-e3d7f051b10a | note | TYPE - V
0a1d7d1d-d895-570c-a69f-636cd361859b | note | ASSESSOR - Richard Taare
a1bb8a55-982f-50ea-95b6-443205451921 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (4)
bb74f194-ea14-5927-905e-ae1296011484 | note | VERIFICATION ACTIVITY - Depth Checks
ce06071d-b446-518d-a84c-b02e16f8444d | note | METHODS OR REFERENCE - TNZ F/2 Section 3
0a6cccb7-16d5-5c4a-9e2c-a51b6ecb5c74 | note | FREQ. - Every 20 m of excavated area
b72b21e8-9261-5ce8-b723-64d27ef49906 | note | ACCEPTANCE CRITERIA - Trench shall have vertical sides at a minimum of 300 mm above the top of pipe
0c616c8b-9ce9-5720-9b5f-d523c35a86d9 | note | TYPE - V
98f90238-9018-5735-a63c-03c11958edd2 | note | ASSESSOR - Richard Taare
923404e0-2d00-5acb-bf50-ccd2b8278efe | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (5)
7bf365a1-4801-5f40-8280-10a0ae41520c | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
1d8aa261-4a4d-5a89-adf5-1e41e76ccda5 | note | METHODS OR REFERENCE - Take Photos
ae2ed1a7-8348-5b00-9c2c-d15e518cca52 | note | FREQ. - Upon completion of excavation
5cf7cac6-aa95-5538-8439-0cdce02aabe1 | note | ACCEPTANCE CRITERIA - Photograph excavation upon completion of thereof (evidence)
b21bb3b6-fad3-5720-97b0-b4aa09568522 | note | TYPE - H
267ffdb4-44a7-53ee-ab1e-f07cba5d7a9f | note | ASSESSOR - Richard Taare
18db4017-a673-5626-ac53-604270ca9ab8 | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
61c25773-cb6f-59ba-a716-457e65a387a8 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Bedding (1)
4a665623-c179-527d-a458-aacda199c90f | note | VERIFICATION ACTIVITY - Quantity Check
a63ca449-5a76-568e-9997-897cf65890fe | note | FREQ. - Every 20 m of Subsoil drain
44929e34-ef76-545c-9aaf-a2f1e524aeef | note | ACCEPTANCE CRITERIA - Shall have a minimum of 50 mm filter material underneath the pipe
39e73b1a-58a9-567c-bd0e-c771691fe128 | note | TYPE - V
7d13508f-e7ac-52c7-9cd1-1fe231e1f74d | note | ASSESSOR - Richard Taare
f5210541-1898-54a1-862f-af26ba8e829b | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Bedding (2)
450c93a1-66c6-599a-9d83-ee56b61fd255 | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
5c0aa440-75d4-5f78-b9ef-89b4a31712ce | note | METHODS OR REFERENCE - Take Photos
60410e52-9407-535a-b489-f34561aa2f94 | note | FREQ. - Upon completion of bedding
65bafed9-b5ba-573b-98fb-099f4511fce6 | note | ACCEPTANCE CRITERIA - Photograph bedding upon completion of thereof (evidence)
296c171a-f9b9-5177-afc4-09c6ca9357bd | note | TYPE - V
3cec2a62-0f51-5122-8cf8-ef021abebcf0 | note | ASSESSOR - Richard Taare
29d8c5fb-d06b-5784-a594-c37b7bee8122 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Filter Material
7a937e4f-7743-5753-b0fb-9ba9267d9a86 | note | VERIFICATION ACTIVITY - Quantity Check
4deb26a8-2cec-55f5-b7c9-c753a0f7b2d5 | note | METHODS OR REFERENCE - TNZ F/2 Section 6
0dbf6c9f-b362-5581-a1ef-b93d003456fd | note | FREQ. - Every 20 m of Subsoil drain
f1e7e0d7-5f8b-53c1-aad5-733b86c90a10 | note | ACCEPTANCE CRITERIA - Filter material shall be placed to a minimum depth of 150 mm above the top of pipe, filter material shal be compacted in layers not exceeding 150 mm (see design)
83f671dd-2209-5f15-a872-0c7e7bd76358 | note | TYPE - V
141a475f-4539-5aa0-9057-3ea24ef2d6c9 | note | ASSESSOR - Richard Taare
6034c171-3e3b-5005-99b2-bc4f650f9593 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Backfill (1)
08002959-4e8a-5afb-9457-9254f13f28f8 | note | VERIFICATION ACTIVITY - Density
fe2b7751-2149-5b7b-a450-b33c8f573c89 | note | METHODS OR REFERENCE - ASTM D5874-95
47ae833c-0215-58a1-8c53-b2de796b7608 | note | FREQ. - 1 sample per 2m² lot or at least 5 samples
a71ec7fb-69e5-5ade-a831-08478b8fc58f | note | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>35 per 150mm layer
e5e38e4d-188f-5f19-99c8-fe1d111927a8 | note | TYPE - V
1a41e871-674d-5de9-95a0-c933acaa3a7f | note | ASSESSOR - Richard Taare
5c363526-223b-556d-aed4-f24346c386c3 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Backfill (2)
2dacd2ef-69bb-5002-9d4d-0dcd05a111c8 | note | VERIFICATION ACTIVITY - Level Control
a777c578-fba3-50d7-9cec-00784607133e | note | METHODS OR REFERENCE - None
b2bc2b3b-8417-5c16-9e72-944d16cd6b1e | note | FREQ. - None
0a3ef807-5ceb-5730-9b5e-7fe6c2aa409e | note | ACCEPTANCE CRITERIA - Tie-in flush with adjacent road surface +20mm mound in middle of road crossing
79233b82-4e57-5746-8e96-b634c92dfa4d | note | TYPE - V
d36dcf5e-6509-523b-9107-a53052e688d2 | note | ASSESSOR - Richard Taare
3885f538-bbd6-5529-a46a-6b306e328646 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Backfill (3)
51fd5067-4881-5b45-be3b-344ffece252a | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
5b0aad28-1188-5ae0-8db9-c1a8beff5af7 | note | METHODS OR REFERENCE - Take Photos
cce2a090-51d5-5f30-a946-4c7bfa1d479f | note | FREQ. - Take Photos
20d2f145-ded8-5cf4-a446-0884a6cde280 | note | ACCEPTANCE CRITERIA - Photograph basecourse upon completion of thereof (evidence)
e30189a8-da07-53f2-a7f5-08351cc13141 | note | TYPE - H
3be37cb9-b126-5b63-b29f-5b89a973ccfc | note | ASSESSOR - Richard Taare
8dcdda31-df10-52b6-91d2-eaa3eebf4384 | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
9604dbe8-fce9-5cbd-b2c9-ebe768ebd5fa | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Existing Level Control for culvert realignment Culvert No26 & No 27
ab1cee82-29b8-5e4a-aabd-4a0699ecb9ba | note | VERIFICATION ACTIVITY - Level Control
1614c9b5-cf3a-51db-9748-29d03403498f | note | METHODS OR REFERENCE - Physical survey check
dc369677-37f1-5f81-b71b-47055541db53 | note | FREQ. - Before work commences
4650ef9d-6bf7-5e18-9eca-851608f42ac2 | note | ACCEPTANCE CRITERIA - Survey and stake out lift pegs for existing inlet and outlet positions and elevations
2fc205ad-ef94-5947-9b46-2edef1b02fb5 | note | TYPE - H
944b01c1-68c5-5e32-a55c-91a3b12bdf4e | note | ASSESSOR - Richard Taare
c2134f7a-e520-577d-9ad0-f13a92687ed6 | note | DESCRIPTION - Hold point - No physical works are to be commenced until existing pipe inlet and outlet position and elevation is recorded
e6f7e182-17f0-5669-b284-005f4464243c | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Work Space Restrictions
8f88a0f6-6bcd-52c3-b7e2-205f80602e72 | note | VERIFICATION ACTIVITY - Fencing
277ec840-676a-5ed6-890c-dcb02097fa1f | note | METHODS OR REFERENCE - As per existing
a733d768-27d8-502f-b30c-671172ec8ad1 | note | FREQ. - Where required
24e2b51c-1d1a-5206-830a-bd1e44f3cd6e | note | ACCEPTANCE CRITERIA - Open adequate section in existing fencing to allow for required work space where required, documented and signed permission must be received prior
166bc9ab-8fab-506b-b363-53ab39b277a3 | note | TYPE - H
3d026588-2fdc-50d3-a570-f4801a421d3d | note | ASSESSOR - Richard Taare
84c4afe4-b640-5edb-b677-c143a22e3c03 | note | DESCRIPTION - Hold Point - Documented and signed permission received prior
f5fb0880-f039-5f46-896f-b4fdf26747f2 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Pre-construction Photo Diary
4d475452-d948-5e0c-a1a5-a52eebf6a810 | note | VERIFICATION ACTIVITY - Site Diary, Photos
03695c30-29bb-5fbe-bfd7-421f5155dfe1 | note | METHODS OR REFERENCE - Take Photos
fa6e7c07-8fbf-5d79-b9ce-a2e239419edf | note | FREQ. - Before work commences
7f76cecc-a0c5-5ec4-8e5f-8b54db8307c4 | note | ACCEPTANCE CRITERIA - Photographs the full extent of the work area / site
c4e18002-60c6-5716-a94d-fbc3978132c4 | note | TYPE - H
c201fbb7-445a-5d85-8f65-7132ed8fab16 | note | ASSESSOR - Richard Taare
b840e60e-8b59-5c43-8332-7fb18beae5e7 | note | DESCRIPTION - Hold point - No work is to be commenced until site photos are taken
9d8bd152-2313-5b35-806e-8fb058887811 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP65 (1)
c8c2eab5-bb61-5bd9-9233-1463c10fb99c | note | VERIFICATION ACTIVITY - Aggregate Grading
59f06741-8744-5ce5-b21b-e37a9c97bdf7 | note | METHODS OR REFERENCE - NZS 4407 Test 3.8.1
7ac7e31a-09f9-5d21-8b12-10e289c3bfd0 | note | FREQ. - 1 per 400m³
e78f4015-8673-54e8-af25-192ebadcd3e7 | note | ACCEPTANCE CRITERIA - Grading in accordance with WSP Lab Gisborne Standard grading curve
3265608d-b12a-58c3-8b65-b4c6d25dcb57 | note | TYPE - H
241c28ad-2dab-5a49-b14d-0b8cd3f2a051 | note | ASSESSOR - Richard Taare
57652400-2325-5e03-90b5-d79f438cadc8 | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
83ec972d-14ce-5b45-b9e8-13d0a0790f96 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP65 (2)
4c707d1e-1863-5dbb-a00e-02ba20ed8668 | note | VERIFICATION ACTIVITY - Crushing Resistance
244b0f2d-db02-5119-bdca-837bd98143e9 | note | METHODS OR REFERENCE - NZS 4407 test 3.10
36f47465-a7fc-53c8-ad67-1877070f0e4e | note | FREQ. - 1 per 10,000m3 or per visual change
f8b1145d-f100-5570-a2b6-8f1acf7e741e | note | ACCEPTANCE CRITERIA - >130 kN
cc3a7e37-cff8-5d6c-8703-359522306ba2 | note | TYPE - H
bb70aea0-9ae1-584d-b412-1360a2f546c3 | note | ASSESSOR - Richard Taare
5aa02e77-0c4a-58ca-b3a1-8f3b847698ef | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
d2544444-0617-57a8-bee0-83378f95c246 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP65 (3)
1876c88d-7ec1-5cc6-8d10-c6a9d26e378e | note | VERIFICATION ACTIVITY - Linear Shrinkage
6e3a6870-bce9-511d-9577-fd25bbcfa7cc | note | METHODS OR REFERENCE - NZS 4402
e13ce923-9d46-5edd-8a72-e0fc57633129 | note | FREQ. - 1 per 400m³
d9685eda-1a26-5b52-96ea-cf6603ed95ad | note | ACCEPTANCE CRITERIA - Linear Shrinkage to be <6% - Where LS is approaching 6% communicate to quarry staff about changing source rock
6800a83a-8a8a-569f-92cd-2e67e4ead86c | note | TYPE - H
9fce7baa-b2d0-5f7f-a7b2-b85e86444a3c | note | ASSESSOR - Richard Taare
04340a16-72ef-535d-bc95-8d8554267c03 | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
52822971-c30e-5eb2-8a97-1fc384a2eaff | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP40 (1)
9b453e6c-33ab-5803-bcc6-23e5a819e710 | note | VERIFICATION ACTIVITY - Aggregate Grading
61d0ba32-9875-5b8c-a08e-9a96e634b356 | note | METHODS OR REFERENCE - NZS 4407 Test 3.8.1
0e9cc628-8eaa-50ef-8635-21ae3bfed5fd | note | FREQ. - 1 per 400m³
fce9465c-d5e5-5fa1-bc0f-94aeab6d2efd | note | ACCEPTANCE CRITERIA - Max particle size ≤37.5mm. Not more than 57% by mass shall pass the 9.5mm sieve. Not more than 19% by mass shall pass the 0.6mm sieve
91e53d3b-0323-5da2-af7c-4bdaa27c5f54 | note | TYPE - H
1b1d3dd1-deb2-5bb7-bf75-89369ce00a2c | note | ASSESSOR - Richard Taare
93541e55-aabd-52ec-8f11-4f729b4d04d7 | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
bfd2b0d0-fe8e-50f9-8590-9e9aa1a92313 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP40 (2)
861837ca-5d10-5ca5-8452-3b2754e1bbf9 | note | VERIFICATION ACTIVITY - Crushing Resistance
cf58e614-932f-5488-89e3-7c363ff4d6f2 | note | METHODS OR REFERENCE - NZS 4407 test 3.10
d1a56c31-11f9-5414-b147-6a95476f360e | note | FREQ. - 1 per 10,000m3 or per visual change
85609955-c40b-5c45-a718-2f18531b91b3 | note | ACCEPTANCE CRITERIA - under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced.
23bd11ec-1be8-5601-999e-85c54afee99f | note | TYPE - H
1218f2c2-f198-5044-96ed-26bfaefedb87 | note | ASSESSOR - Richard Taare
50a48f37-10ab-580f-84c9-5105f5c5da26 | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
7f6d22d3-c1d5-591a-86aa-13a68edbcffa | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP40 (3)
6a95ebc3-2dd9-5e5d-822f-ab748ef29718 | note | VERIFICATION ACTIVITY - Linear Shrinkage
84723cf6-10fa-5063-be28-e136b9cb56f2 | note | METHODS OR REFERENCE - NZS 4402
f587fb7d-4078-572d-83d1-4881978a345c | note | FREQ. - 1 per 400m³
d7e52c97-f046-50a1-840d-55ba2a7d78fe | note | ACCEPTANCE CRITERIA - Linear Shrinkage to be <6% - Where LS is approaching 6% communicate to quarry staff about changing source rock
f7b05202-240e-524e-8bdd-ce05ef97e37c | note | TYPE - H
ef31469d-0cc8-56bd-ac84-bdba3865a835 | note | ASSESSOR - Richard Taare
ffddfa41-0da9-5763-a837-b521576168a6 | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
c4e0687b-3c5e-5468-b510-5598e0947f4a | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Qarry Aggregate - AP40 (4)
c2454ee7-1912-5efb-8e9c-dd51c650c7f3 | note | VERIFICATION ACTIVITY - Cement Reactivity
6173baf9-17a1-5eb6-b213-214b59e10ce2 | note | METHODS OR REFERENCE - NZS 4407 Test 3.15
5fe07901-b1ab-5668-905a-eb35023cb536 | note | FREQ. - 3 per source, Sampling shall be carried out in accordance with NZS 4407:1991 Part 2
b21e0df1-4197-5ae2-970f-272f2d9a5503 | note | ACCEPTANCE CRITERIA - Set of 3 with all UCS >3 Mpa
72045d11-97be-5c61-a35f-83139a5ef36e | note | TYPE - H
b7a28967-d28f-549e-8a7d-06fa3c81d535 | note | ASSESSOR - Richard Taare
bcc99700-14eb-51d4-8cb8-d9cd30d3513c | note | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
7d22197b-f6a4-5952-8ce0-1fdafde8530f | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Excavation (1)
51420f74-7ed8-55a2-a1fe-c341cbe8d797 | note | VERIFICATION ACTIVITY - Quantity Checks
4ed20135-ccc1-583e-b1a0-ade6a2bda482 | note | FREQ. - Per site
3948cf2b-53b1-5a37-b56c-c0564633f46c | note | ACCEPTANCE CRITERIA - Earth works must not exceed 10 m3
40efa73c-08fa-5025-b48f-1718530026d9 | note | TYPE - H
692f179a-80a6-515f-8058-27a2b9d25f4b | note | ASSESSOR - Richard Taare
a27dfc49-d299-5b6d-a874-a035d1d4a6bc | note | DESCRIPTION - Hold point - Earth works must not exceed 10 m3
33dd5443-e70e-5154-a2ff-a8e5e57c9711 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Excavation (2)
4aa55c9e-b7e5-5d42-93ed-6e67a17b319d | note | VERIFICATION ACTIVITY - Deep Excavation Safety Measures ( >1m)
272618aa-2e06-5aaa-9162-ba7622f19343 | note | METHODS OR REFERENCE - CoPSESF
15f9c780-2d01-5033-bd1e-e3da6f9aeb66 | note | FREQ. - Every excavation >1.0 m in depth
444f8950-f46c-5d9c-8fdd-cda582815cb5 | note | ACCEPTANCE CRITERIA - Excavation checked and approved, Excavations exceeding 1m in depth to be benched
5702795e-705e-50b5-bc9f-674ba038da22 | note | TYPE - H
116b2942-08d5-58c4-aab9-01cbd59b5486 | note | ASSESSOR - Richard Taare
8aea3e36-fdee-5cda-a35a-cec73318c75f | note | DESCRIPTION - Hold point - No persons may enter the trench until it is adequately benched and deemed to be safe as per the Safety in Exccavations and Shafts for Foundatons
765e20de-8816-5811-9802-99bce9c974c6 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Excavation (3)
73376841-35d7-5707-8b59-0f21368de6cc | note | VERIFICATION ACTIVITY - Unsuitable Foundation
748ff877-9c50-5270-9efc-2f42ab8212f5 | note | METHODS OR REFERENCE - TNZ F3 Section 3.5
37e8a1fe-6081-54dc-809d-c9c6c7b50541 | note | FREQ. - Every 5 m of excavated area
e3341f2c-f8c9-5f63-8654-b2971cc5eb44 | note | ACCEPTANCE CRITERIA - Unsuitable foundation material shall be removed to a minimum depth of 600 mm within carriageway and replaced with suitable material and compacted in 150 mm layers.
5a3814f0-2b9a-5645-8cc0-bf9ee162d4a6 | note | TYPE - V
7b61606b-c217-5966-861f-7ca8337c87ed | note | ASSESSOR - Richard Taare
44c041f8-eb0b-5ada-be96-21f326e17793 | note | DESCRIPTION - Unsuitable foundation (very soft = scala < 3 blows/100 mm or expandable clays, irregular or fragmented rock and saturated soils)
9b5bb8eb-6cf9-590c-9de0-953963a6bf1e | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation (4)
54e9559b-6819-5d43-8a04-aaf58fdd8403 | note | VERIFICATION ACTIVITY - Level Control
bb36f104-ce0d-57ae-8477-8a98a899dbbf | note | METHODS OR REFERENCE - None
b0ec9886-bbab-53f6-8fe8-cad417927b22 | note | FREQ. - Every 1m along length of culvert
210b9d7a-da14-5241-b02a-f0f31158c4f1 | note | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -25mm + 5mm
0754159c-832c-5211-9ef0-314efd49c5a9 | note | TYPE - V
4653f525-98a6-5b1a-b59f-0c6f7001fed5 | note | ASSESSOR - Richard Taare
b4459465-036e-5181-b4bd-d1bc8527035c | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation (5)
0322fe2a-ace3-5a8a-a645-7e0dff963878 | note | VERIFICATION ACTIVITY - Level Marks
ba5526ef-b8b4-58aa-9aa6-5a90fab94e71 | note | METHODS OR REFERENCE - None
b443406f-6d57-57e6-8dd2-f18cbc04e7c7 | note | FREQ. - 3 locations along one side of excavated trench
ab405599-85d5-584d-8fdf-56df07eb8d9d | note | ACCEPTANCE CRITERIA - Layer depth markings visible on photo diary.
eea9e4bb-3a9d-5ae6-a9ba-06aeeee3ffc2 | note | TYPE - V
2b0bb3a5-71fb-5841-b2d6-93bccbe3bafe | note | ASSESSOR - Richard Taare
5c1cc376-b73a-5164-a27c-c229c87a8740 | note | DESCRIPTION - Hold point - No physical works are to be commenced until white/yellow spray paint markings indicating backfill material layers are visible on one side of trench for photo record
70105fed-5a17-5f32-a8d1-36c3600e4408 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Excavation (6)
42dc2fed-5d7c-5876-b90a-2103a5065ed2 | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
2a4f522d-b1b4-5c8c-b741-8cf91d699596 | note | METHODS OR REFERENCE - Physical / Visual check
04cb5bc7-1f99-5c53-a107-1e5995dd62ea | note | FREQ. - Before removal of unsuitable material
1f2172eb-3807-53bf-8b3d-5ce80285a02f | note | ACCEPTANCE CRITERIA - Photograph unsuitable foundation material prior to removal of material (evidence)
057d2b46-0409-55c9-a4bf-f04b77360a53 | note | TYPE - H
35102d30-3dc4-53f7-a425-0488f1a82d26 | note | ASSESSOR - Richard Taare
dcc4e768-73fc-59d0-b6fd-a26a19e34e71 | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
bdfaad3b-f51e-5ce9-bdb6-0128cc6f048a | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Bedding (1)
26e3ce38-54ac-59fd-996d-a07dfe8ce27b | note | VERIFICATION ACTIVITY - Bedding Material
ea227ea0-0914-5b09-87c8-9647d13e7512 | note | METHODS OR REFERENCE - TNZ F3 Section 3.6, AS/NZS 3725:2007
b6df397d-e287-5b70-be32-68cefc8e4efe | note | FREQ. - Per Site
5bf40b03-e6c6-536e-bf32-614b6186ab49 | note | ACCEPTANCE CRITERIA - All bedding material shall satisfy the requirements in AS/NZS 3725:2007 and AS/NZS 2566
3e9bee81-d8bd-58b4-be77-c50194431450 | note | TYPE - V
4b0ad11b-47d6-58ab-9902-37917933cc6e | note | ASSESSOR - Richard Taare
ddd1162e-2753-51ad-868c-8d94a0394db7 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Bedding (2)
595a7753-49ef-5bff-b1ef-4f6ae6b9996e | note | VERIFICATION ACTIVITY - Level Control
84350d09-0551-597a-8d5f-6b3f4de93b4b | note | METHODS OR REFERENCE - None
7d5b8186-d1e7-55fd-98ed-c9c83063c6f9 | note | FREQ. - Every 1m along length of culvert
cffba2ed-a0c3-5dc2-b80d-fb326edc086f | note | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm
f75c9589-4127-567f-a5b9-5330c6a01f53 | note | TYPE - V
79234a53-f2f3-59d6-bf79-22e2aa4f120b | note | ASSESSOR - Richard Taare
69195bf7-f70b-5ac7-807d-f886b8a24f7e | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Bedding (3)
ef9e7000-39d3-511a-8de6-f5fb1979dadd | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
33d11332-819d-5c20-8b95-8201633d39ff | note | METHODS OR REFERENCE - Physical / Visual check
a2254f28-70a0-5fa0-9031-7fd66e8bca69 | note | FREQ. - Before pipe installation
9178c009-0204-5c2e-ae4e-1dcef303d097 | note | ACCEPTANCE CRITERIA - Photograph bedding material after placement and compaction (evidence)
e07e154b-3e2f-5658-907b-c86c0b57513c | note | TYPE - H
7c6cca99-ae22-5138-a210-523c733b35b2 | note | ASSESSOR - Richard Taare
a203bd7e-f515-596e-a0a2-14fdfe58b759 | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
7e0ce358-1252-5f9b-8fb9-f1db9139d329 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Pipe Installation
13172c81-29f3-5eb5-aeba-cf00ffd0a285 | note | VERIFICATION ACTIVITY - Inspection
c7ec7e92-0e44-56bc-af22-49826c8145fe | note | METHODS OR REFERENCE - Physical / Visual check
0427d608-c419-53ed-b0db-26e206439ffa | note | FREQ. - Before pipe Jointing
598e24ee-d6ea-59ea-a8ce-6300e59dccbf | note | ACCEPTANCE CRITERIA - Verify culvert alignment (straightness)
c8d43908-1ba2-5980-836c-845a343b7a9e | note | TYPE - V
f021b8bc-ef70-52a6-b33a-20b803be43ba | note | ASSESSOR - Richard Taare
ead3b5eb-e705-50a8-bb8f-32a2a004b0f2 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Jointing (1)
8845411f-3b55-55e2-8ad1-14b3ed936cd3 | note | VERIFICATION ACTIVITY - Visual/Physical
4d8ba116-d744-588e-8526-6607a9348605 | note | METHODS OR REFERENCE - Physical / Visual check
145aa08f-754d-55dd-bff2-4fee197d4ef2 | note | FREQ. - Per Join
05ac3fe3-85c7-54d4-8880-216a4306ef87 | note | ACCEPTANCE CRITERIA - All joins must be watertight and present a smooth invert surface
66cca74c-bca8-5a66-8282-bc2792a3a164 | note | TYPE - V
f53fc34d-3def-5c80-940d-fb2b787b86d9 | note | ASSESSOR - Richard Taare
4b4fc17b-dadc-5d69-84f7-3f88c904e3ff | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Jointing (2)
625669f2-790f-58a2-aa5f-c4ce4e80566f | note | VERIFICATION ACTIVITY - Mortar
b93b9c17-5999-5a3d-9b60-5432e69beb35 | note | METHODS OR REFERENCE - TNZ F3 Section 2.4 NZS 3103: 1990
335e63c6-5d98-5d05-9a20-a80ce2b2f4f4 | note | FREQ. - Per Bag
34c936f0-1ace-5137-ba95-c1fc5d96f5ed | note | ACCEPTANCE CRITERIA - Mortar shall comply with NZS 3103: 1990
745371b0-2944-52d1-9d45-80adbd5aebb3 | note | TYPE - V
6f083c1b-1a92-52f4-a159-dae8c4abac0e | note | ASSESSOR - Richard Taare
0c126d97-2d6d-5b99-ad89-13a83cff3c6f | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Jointing (3)
8cfc5596-8c17-589d-8319-700525c0f72e | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
885217b1-6dfc-5f8e-a022-689d789203d8 | note | METHODS OR REFERENCE - Physical / Visual check
d9a8ea53-8397-57c8-8f82-1b2fd60d06ea | note | FREQ. - Before Backfilling
3ec6fa35-f6aa-5dcf-819a-3c485c01755d | note | ACCEPTANCE CRITERIA - Photograph pipe and joins after installation (evidence)
4e40932d-d454-5ca1-b999-9b1982be7d4d | note | TYPE - H
a5d328d7-4153-5bce-8909-daea1ed542ac | note | ASSESSOR - Richard Taare
23a13648-6750-542b-8340-d3fd34228f2a | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
1b4b2469-2f7d-51cb-8a96-3dc54d98b491 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Backfilling (Layers of 150mm) (1)
ce5c6c00-360a-5bb5-9950-72e38365e327 | note | VERIFICATION ACTIVITY - Fill Material
3107c31a-8b44-5498-b53b-fc3f3314d263 | note | METHODS OR REFERENCE - TNZ F3 section 6.3
f11aacfb-65f2-553f-933e-99d475783168 | note | FREQ. - Per Stockpile
96dfb836-7626-5555-a475-1fa73a222b6a | note | ACCEPTANCE CRITERIA - Any material that is not type W or type U defined in TNZ F1:1997
7b5442bd-d69d-5b3a-987c-113a4d624dbc | note | TYPE - V
91b1e86d-6ffd-5d64-bb52-07306326df3b | note | ASSESSOR - Richard Taare
ed6e990a-ca97-5245-a480-1cfe1af7321a | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Backfilling (Layers of 150mm) (2)
81320cfd-e25b-51df-a9bf-c4020a4f2601 | note | VERIFICATION ACTIVITY - Density
54ca3f47-be72-5d47-9321-bde67a0c14d7 | note | METHODS OR REFERENCE - ASTM D5874-95
c08e1348-a617-5bb2-813c-6fc5319632de | note | FREQ. - 1 sample per 5m² lot or at least 5 samples
be1bcd3b-1a58-5400-9c88-77856e0e38c5 | note | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>25 per 150mm layer
01b92976-55dd-5194-8acc-6e0273254da5 | note | TYPE - V
1cb556fd-e21e-5349-b36e-0cc072ae0ccb | note | ASSESSOR - Richard Taare
bafe82f4-1320-5fb9-a94f-4a43e95bd4c6 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Backfilling (Layers of 150mm) (3)
16ad7261-e435-52c6-9de1-a485e577640f | note | VERIFICATION ACTIVITY - Level Control
2e8c3da0-9352-515c-8230-560f86005556 | note | METHODS OR REFERENCE - None
0b9f6521-f3c3-58fc-bef4-a1121a614c9f | note | FREQ. - Every 1m along length of culvert
19beb765-37ef-543a-a271-4af5f71c784c | note | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm
e1e37859-309a-51af-ab38-9c0eab0401e2 | note | TYPE - V
55ea6459-c194-5c05-9cbf-9c2fc2409c35 | note | ASSESSOR - Richard Taare
ad220de3-ebee-5f70-bf08-85038d4964e4 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Backfilling (Layers of 150mm) (4)
40c076c3-d6d6-561c-b331-0ec17df9fa54 | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
14e20d2e-84c1-5a49-817f-7ce3de2e10c5 | note | METHODS OR REFERENCE - Take Photos
f3aa503f-5eda-5972-af7e-0d56af355bc3 | note | FREQ. - Before placing sub base
1991bb9d-c0fa-56f2-98f0-b5a728996c53 | note | ACCEPTANCE CRITERIA - Photograph backfilling after installation of each 150mm layer (evidence)
9b6ff87b-66c2-5c25-a0cc-5b3935864f82 | note | TYPE - H
5f3768ff-86c2-5fa9-a8dd-06d858c25804 | note | ASSESSOR - Richard Taare
2da72a0e-0cea-5eb2-9bca-1304b5a1c939 | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
b121e357-6854-5b4a-833a-faed471f9245 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Sub base - AP65 (1)
2711a2bb-b72c-5c70-8c52-53ca060bc729 | note | VERIFICATION ACTIVITY - Density
303c7e20-c0ef-5549-a26d-d0cc9cde1136 | note | METHODS OR REFERENCE - ASTM D5874-95
779c6163-df6e-51c4-8148-9a359a99702b | note | FREQ. - 1 sample per 5m² lot or at least 5 samples
acfb9ebd-e909-5862-a086-19a842f5fd48 | note | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>32 per 150mm layer
ef96ec1a-b95f-542c-bd35-6e4b902af31d | note | TYPE - V
d7ff6108-f08b-53c9-a836-12faac516ea6 | note | ASSESSOR - Richard Taare
4c2f57f4-d60f-50f7-a265-25b2ceae7e09 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Sub base - AP65 (2)
997a5e14-5f5a-5e2c-b625-476eaa8640e1 | note | VERIFICATION ACTIVITY - Level Control
b6060687-890a-5e8f-89c2-473f961003f0 | note | METHODS OR REFERENCE - None
30903844-d457-511a-8686-dbb90f0c50b1 | note | FREQ. - Every 1m along length of culvert
39602ae5-3d81-5e5c-b6fb-b736f1389c49 | note | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm
825017af-e9c9-5c8f-a417-a76e0722efe5 | note | TYPE - V
be2f2caa-11a2-5bfb-8c51-480c0f2b1de6 | note | ASSESSOR - Richard Taare
9e97000e-9a6a-591f-9925-f7691abde6db | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Sub base - AP65 (3)
0ceee1ea-36ad-5fbf-9735-9ae8a98a86ca | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
975912e1-cdd1-5e27-a0b5-9768f1db5dfc | note | METHODS OR REFERENCE - Take Photos
43ca5a06-4204-51e2-b6ea-97fde4ba1bbd | note | FREQ. - Before placing base
68d308ea-ed9c-5076-8325-506ce7ef59c0 | note | ACCEPTANCE CRITERIA - Photograph sub base after installation of each layer (evidence)
4e89e8ee-6ef3-5273-b237-2b10bf94e54a | note | TYPE - H
ffa86e29-caf7-56e3-bc5a-0d5c0c43ffcd | note | ASSESSOR - Richard Taare
abeb6d8e-0218-58a7-a6eb-d2619e417e57 | note | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
ea299d1a-02a0-5909-bcea-64b76a97179b | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Basecourse - AP40 (1)
010058be-14dd-59d3-a5a2-7c9a0c6dc71d | note | VERIFICATION ACTIVITY - Density
2bf61169-cec9-503b-b0ef-3622cd3105fa | note | METHODS OR REFERENCE - ASTM D5874-95
f9cbf04c-d418-5f53-9945-7ba250cea545 | note | FREQ. - 1 sample per 2m² lot or at least 5 samples
59d04e45-a62b-58a4-a2ee-7b511d287d31 | note | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>35 per 150mm layer
08520acb-a167-5e0f-80b7-0b1fa66e5ba0 | note | TYPE - V
78a5820a-57b3-5cea-8b72-a39cd9936e7b | note | ASSESSOR - Richard Taare
2f751733-e602-509a-8686-2fbdc5d8f731 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Basecourse - AP40 (2)
30b09c8b-0bc9-5151-b001-401eaad0ae68 | note | VERIFICATION ACTIVITY - Level Control
9c795108-e694-5f56-a605-22f263c03fd4 | note | METHODS OR REFERENCE - None
01033508-a9a8-570e-93f5-41e0283d6411 | note | FREQ. - None
a2591d6e-4e38-5ed1-bdf2-d81ed01fc9b8 | note | ACCEPTANCE CRITERIA - Tie-in flush with adjacent road surface +20mm mound in middle of road crossing
f1191ea3-0b3b-560f-b8b7-c1b399ba2c0a | note | TYPE - V
2eda753a-6fe2-5a0e-9279-63631a88acf7 | note | ASSESSOR - Richard Taare
e102452d-3ffa-53b1-850b-3913b153c856 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Basecourse - AP40 (3)
f54f5817-0475-54f9-bf28-ca9564bf4080 | note | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
d48ecd36-b423-5e50-896f-96caa935a003 | note | METHODS OR REFERENCE - Take Photos
22f182c5-ec38-54bf-a783-743b8dcf6ed8 | note | FREQ. - Upon completion of basecoarse
baf305c5-468f-5039-954b-10681aa60d2e | note | ACCEPTANCE CRITERIA - Photograph basecourse upon completion of thereof (evidence)
a37a0d63-da77-529a-ba0f-ee5ff4d8fd17 | note | TYPE - V
49ae4b7c-8ae1-5ea5-92f7-9790c2913fa9 | note | ASSESSOR - Richard Taare
a06923c3-ac42-5ae1-b469-ffd8f7bf6f64 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Ancillary Concrete - Head/wing wall
ae5bd854-1f9c-572e-9f94-f772eac1c8e2 | note | VERIFICATION ACTIVITY - Visual/Physical
3c2e6cb2-4779-553a-a372-856f75642d59 | note | METHODS OR REFERENCE - NZS 3114:1987
183d8e1a-3f1b-52a6-8b93-a48b4c08f162 | note | FREQ. - Per Structure
6c050420-26c8-58c6-8158-c00004f8d3c1 | note | ACCEPTANCE CRITERIA - All concrete faces should comply with NZS 3114:1987 and NZS 3101: Part 1: 2006
bf10cb78-f5ab-5bcd-ad8a-3b08f63bd650 | note | TYPE - V
16ae41da-0554-5346-bede-262f333054c7 | note | ASSESSOR - Richard Taare
683ac4c0-98ee-5715-8c2e-05705a54b34c | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Ancillary Concrete - Concrete cover
9fabc29e-4d16-5e7b-8722-171e8b791091 | note | VERIFICATION ACTIVITY - Visual/Physical
0f039d6b-3804-596a-8278-6dae5b61a4da | note | METHODS OR REFERENCE - NZS 3114:1987
b91cc4ed-1afc-5a6c-9dc7-5c9d3d2b3323 | note | FREQ. - Per Structure
8bc6df43-13eb-57e0-ac76-46331f4bb6da | note | ACCEPTANCE CRITERIA - All reinforcing bar/mesh shall have a minimum of 40 mm cover
577f477f-444c-5057-a154-f8a531e64736 | note | TYPE - V
1c1cc8ae-dc9e-56a6-a76d-fa479a4e98f0 | note | ASSESSOR - Richard Taare
be9aac2f-3d82-5b38-bc52-732281a53b99 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Rip Rap
2809dc7d-e774-5505-bf08-ff78c67317f2 | note | VERIFICATION ACTIVITY - Visual/Physical
6b8e09b2-83c0-5654-ab67-49827a829959 | note | FREQ. - Per structure
e962da21-5e14-57b6-b10c-c8194386346f | note | ACCEPTANCE CRITERIA - 200 mm Rip Rap located to provide scour protection at Inlet (1 m wide x 2 m long x 0.4 m deep) with A19 Geotextile
7f65e385-dedf-5712-ae73-fc7585a6aef1 | note | TYPE - V
01fbcb47-d1e5-5523-ba02-5f28f0927bf1 | note | ASSESSOR - Richard Taare
0f416bda-6421-504b-a8f4-f315e587f4af | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Sandbag Structure, At culvert 26
a3001714-be1a-53d7-988e-f5df2dc6e831 | note | VERIFICATION ACTIVITY - Headwall/wingwall
7fc0f43a-a79e-5e7d-b9e3-ca69ee1a590b | note | METHODS OR REFERENCE - Visual/Physical
f698bc0d-90cd-5714-8ab5-8192acf2d9b0 | note | ACCEPTANCE CRITERIA - Per Structure
4badb228-652b-563e-a02e-1ef14a2f27dc | note | TYPE - Install sandbag headwall at inlet
0427e8e8-ab25-53cf-b5fa-b82d1c0e0c46 | note | ASSESSOR - Richard Taare
5e1e4b59-97af-538e-a786-3eb5f40e45ef | note | RESPONSIBLE PERSON - Pat Thompson
| section | Site Reinstatement / Clearance
| checkpoint | Clean Culvert No26 & No27
3ce2d07e-07a1-5ba4-8fb9-91c5b5ae5ed2 | note | VERIFICATION ACTIVITY - Visual check
af1eeeea-8248-51f2-8e98-e8f866a2b8a8 | note | FREQ. - Along openned sections
99a00425-1123-5bf2-a263-b03964f24c6d | note | ACCEPTANCE CRITERIA - Remove all debris from within culvert
7279d092-27d2-5b03-867d-6adbd2d8f98f | note | TYPE - V
0368842e-07bc-577f-95ae-1f664134f187 | note | ASSESSOR - Richard Taare
e8345d1a-0a41-5a9c-8996-19088ebb9217 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Drainage, if applicabe
e30170b3-3b79-5dbb-8fa9-49e497c3cd64 | note | VERIFICATION ACTIVITY - Table Drains
a2b1bb10-d599-5980-9d61-0875fcabce63 | note | METHODS OR REFERENCE - As per existing
2173c322-22c7-5058-9791-21295ccd8a56 | note | FREQ. - Where required
bf9027fb-e24b-5555-8e3b-21ebc1890b82 | note | ACCEPTANCE CRITERIA - Clean andgrade table drains as required upstream of culvert inlets
20f9093c-4ad0-5889-9663-30351257fac2 | note | TYPE - V
1933e1d0-ba3a-50b3-96ac-f58e98c4b418 | note | ASSESSOR - Richard Taare
5e3a8816-bbb4-5ac0-a5b9-a78a5b07a86e | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Traffic Services - Marker pegs/Signs/Markings/RRPMs Replaced
44c54e9e-28f4-5dea-85ad-69dde6e1ab38 | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
75cddc6d-9182-5ff5-82e7-450cbf3339b6 | note | METHODS OR REFERENCE - Visual inspection
3fabb2d1-d747-51d7-8e7f-c315688e7444 | note | FREQ. - All
e5259c02-4f0a-5858-b4cd-ac908db098de | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc
4e654146-ea73-5201-8be9-e36f1cc9d48e | note | TYPE - V
5b3b3a4d-cad0-568f-a2c2-6b800a0c2ac8 | note | ASSESSOR - Richard Taare
527872c2-ca7e-513d-9af0-7699946d82b5 | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
89d4ea4e-b1f1-5c41-88b2-99b19d5b9854 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Grassing
f6ca6179-46ef-5288-95d5-e06517a9bf2f | note | VERIFICATION ACTIVITY - Visual check
f5bccff5-4f14-507d-b72d-3e6cb11b7053 | note | FREQ. - All areas requiring grassing
ce107040-f4af-5946-9ed3-3cedff372e78 | note | ACCEPTANCE CRITERIA - Grassing has been done where required
9d92c4d4-7c33-5bb8-9bec-c0e04b30a672 | note | TYPE - W
9847028e-a671-5c7b-ab76-f9535d8d986f | note | ASSESSOR - Richard Taare
f34503f1-93ca-5897-a0a8-8bf26d346436 | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Drainage
f3f39579-1feb-5d69-9970-eba2c6ea6824 | note | VERIFICATION ACTIVITY - Table Drains
ca4408b7-c389-5274-8157-643a758773e1 | note | METHODS OR REFERENCE - As per existing
f036de1e-08f6-564c-a1f0-cb45f8a1ba92 | note | FREQ. - Where required
baf00efc-2276-530d-86ac-b200e4ec0d58 | note | ACCEPTANCE CRITERIA - Regrade table drains as required upstream of culvert inlets (minimum 30 m either side)
a6f24877-082e-5439-9de6-2d9ea25b9f11 | note | TYPE - V
eb99873b-e1e5-5d48-b425-9e9e6d60c851 | note | ASSESSOR - Richard Taare
| checkpoint | Reinstate seal
55007306-2b31-5a63-817e-1bfdafc0de90 | note | VERIFICATION ACTIVITY - Visual check
fe78bdbe-2d18-5a79-bbcb-c1f2e39728e8 | note | FREQ. - Per worksite
13cd5b30-0f8c-559f-8426-a643a636d466 | note | ACCEPTANCE CRITERIA - Seal reapired where it has been damged or removed
6a6ac39e-04bb-5dfd-ad8d-3146ab36ce7f | note | TYPE - H
2302d076-14af-58dc-be56-c311c5bb22d2 | note | ASSESSOR - Richard Taare
5c833516-9ef9-571f-85e7-6d8f84f4d2f4 | note | DESCRIPTION - Hold Point - TM to remain until surface has been sealed
18855418-c4ac-5f26-8486-32ff2db17623 | note | RESPONSIBLE PERSON - Pat Thompson
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Traffic Management Removed
b7b3de99-f09f-51b0-923d-0579f809cb23 | note | VERIFICATION ACTIVITY - Visual check
3ef443a8-bb5f-5385-920d-5dc562f3e158 | note | FREQ. - When safe, after all physical works completed
523f37d5-4cbf-52ba-8fef-f702b364363e | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
9f8cbbeb-8906-53b6-a4e2-b4dfc6a9e35a | note | TYPE - W
1f39f525-4ac8-566a-bc35-907c9cef8984 | note | DESCRIPTION - Richard Taare
353a7ecb-621b-5074-bc9a-51ee80e77ecb | note | RESPONSIBLE PERSON - Pat Thompson
| checkpoint | Site left clean & tidy
b3ce0a1c-f02b-5d59-b7f4-fc7dadf01c44 | note | VERIFICATION ACTIVITY - Visual check
880ee7b9-699f-555f-adaa-33d42d2cbfea | note | FREQ. - After vacating site
4444a604-b505-5b65-86ae-d8ff0b6d2389 | note | ACCEPTANCE CRITERIA - Plant removed, Litter cleared from site
76c6fdfc-9dad-5640-9d6b-eb29118be7fb | note | TYPE - V
cde09d50-c720-504b-8b5f-a440e06bf635 | note | ASSESSOR - Richard Taare
da221c03-4935-50a8-b646-be8801070a94 | note | RESPONSIBLE PERSON - Pat Thompson
| checklist | Sealing ITP | itp | Sealing ITP | 9897bfb7-703a-4276-b0d5-b8fbe279f304
| section | Seal Design
| checkpoint | Surfacing design
34bb251c-3cf4-5cb5-8afb-f54c6079c21f | note | VERIFICATION ACTIVITY - Request for surfacing
f0b8e9f0-b15f-5e29-983c-b45d6f75147e | note | METHODS OR REFERENCE - Appendix 15 of contract specific MMP
e05dc4df-089c-5f2c-a43b-4b05d003a7cb | note | FREQ. - Each surfacing establishment
a96ddef9-ac07-50f6-b095-c4f566190261 | note | ACCEPTANCE CRITERIA - Quantity, location, bitumen grade, diluents', target application rate, chip grade, asphalt type, asphalt depth.
0b1531a6-ba0c-5cfc-afc3-b17ff66ef225 | note | TYPE - H
df5b6a26-e985-5a70-b1c7-d15aa5fd25c8 | note | DESCRIPTION - Hold point - No work is to commence until designs have been provided
332a5202-2a36-5be5-bcb2-589d51f4c4a0 | note | RESPONSIBLE PERSON - Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Preparation for surfacing
64981a7b-71b5-51d2-b67f-57950ed3e335 | note | VERIFICATION ACTIVITY - Visual check
ac3d1e2b-dce3-5f9d-a8c6-305e86ed56af | note | METHODS OR REFERENCE - Inspection/ Downer Survey
128930c1-ffbd-5eb8-b93f-346a3367dcdc | note | FREQ. - Each surfacing establishment
c9a01005-0b00-5a14-9204-b5a004691b97 | note | ACCEPTANCE CRITERIA - Shape, ride, surface, saturation, (Client, Foreman and Site Engineer must sign QA form provided)
2cafa904-c24e-51b0-8ba2-ca80b50d3eb9 | note | TYPE - H
dc621440-d0ea-5658-9df3-e160bf2f9da4 | note | ASSESSOR - Mark Joblin / Nikhil Mishra
a6107da8-ba7c-5358-b7e0-fe12fcadc7ac | note | DESCRIPTION - Hold point - No work is to commence until inspection of pavement base layer has been inspected and logged via Downer Survey
6841c7a4-e291-5f7a-94aa-14684cecee47 | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| section | Chip Sealing
| checkpoint | Plant
f9dec97c-b04a-56ec-a0eb-80f4e16856b4 | note | VERIFICATION ACTIVITY - Visual
f1fecef4-2d36-5044-a3b7-83987960f2e6 | note | METHODS OR REFERENCE - Documentation
3a2c6a08-1b27-5e0b-b4c8-802f443d4efb | note | FREQ. - Each Site
ee2083f9-148a-5ec4-88aa-75af293dd7b8 | note | ACCEPTANCE CRITERIA - Each vehicle to produce - Warrant of Fitness, Driver eligibility and calibration of machinery
6dc07bc5-e500-5c16-b69b-9c3755a1aa64 | note | TYPE - H
71c9142a-bd58-5a81-844b-1c0af9ebd3fd | note | ASSESSOR - Nikhil Mishra
2a5e1205-30a1-5132-89ce-592b4a4df89a | note | DESCRIPTION - Hold point - No sealing is to commence until weather has been confirmed safe to seal
78807f5d-74de-53e9-a757-cf9ff64d5390 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Weather
31bd81f4-bdd6-59b2-b391-2c47e39a1374 | note | VERIFICATION ACTIVITY - Visual
bf5b5b3b-77cd-53d6-a162-e6f6ce106e87 | note | METHODS OR REFERENCE - SIS
77f25177-1e37-5edc-b669-63fa931bde4f | note | FREQ. - Each Site
93798897-2844-5ab8-94af-80c720365266 | note | ACCEPTANCE CRITERIA - Check SIS prior to sealing
7708b71c-9451-58ec-97d3-de4307236f54 | note | TYPE - H
2812a7cf-fd24-58f1-a349-477b80a0010a | note | ASSESSOR - Nikhil Mishra
fc3eeb55-2531-51c3-bc19-2e4c465b82fa | note | DESCRIPTION - Hold point - No sealing is to commence until weather has been confirmed safe to seal
9a616006-d150-567e-bb3f-17b2cc5818f0 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Spray Bar Check
93c3da76-95b0-5e8f-aab5-92285576381a | note | VERIFICATION ACTIVITY - Overlap Test
a68a5378-85c1-52e3-bd1e-2b32ff0754b2 | note | METHODS OR REFERENCE - RQP 17.3
cdabe4c9-fe3d-5fbe-8589-cb1174075d94 | note | FREQ. - Each Site
ac017064-72b8-5ad8-9da0-fe42d5713bbf | note | ACCEPTANCE CRITERIA - Ensure no overlap or gaps between bitumen from sprayers
56b3c6e4-cbec-5f6f-89ae-c4d4520c0b7b | note | TYPE - H
5ff5eae4-4a85-5b0a-a0d1-8608e9a35034 | note | ASSESSOR - Nikhil Mishra
ed66945e-a145-56e5-bba2-8504980eea71 | note | DESCRIPTION - Hold point - No sealing is to commence until weather has been confirmed safe to seal
5f1cf97d-6306-566e-a0be-33bd98ed8698 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Application rate of binder
7d97a1f2-4d05-59dc-87c0-ae539dfef35e | note | VERIFICATION ACTIVITY - Insitu
19c9af7a-a420-5775-a392-106cf411f1e4 | note | METHODS OR REFERENCE - NZTA P/17 or Chipsealing in New Zealand NZTA (NZTA 2005)
97d36e13-2578-57ac-80d4-dbb4ba272018 | note | FREQ. - As required by the design
c22b2e88-787e-58a9-8887-48b833286de6 | note | ACCEPTANCE CRITERIA - Application rate within tolerance of the seal design spray rate. Longitudinal overlap of spray runs as per design.
49df9a98-e78d-584a-af32-1f635f695eb9 | note | TYPE - W
aec0985d-c474-5ddb-bdd6-4e37381e577b | note | ASSESSOR - Nikhil Mishra
e915f0f9-9342-5203-af80-8fe8bee45afb | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Aggregate - Quality
9b10a10e-c2c6-51ef-9025-0b38982cae5c | note | VERIFICATION ACTIVITY - Lab Test
382b8cd2-07b2-5e70-9bd9-93ff36e67d7f | note | METHODS OR REFERENCE - NZTA M/6
69242ba6-9509-5f6b-9a98-5e0f8e01abeb | note | FREQ. - 1 / 500m³
9d2af738-5bb2-52b7-9bf0-98d4e5ba61b9 | note | ACCEPTANCE CRITERIA - Shape, size, cleanliness
fee58ad3-5878-5c5e-9fb9-0ce5108e1ce1 | note | TYPE - V
9bdca8f2-e41d-5491-ae83-ae76ad04f7a4 | note | ASSESSOR - Nikhil Mishra
7af12fc4-4e94-5c99-86f6-3bd5110c9a82 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Aggregate - Skid Resistance
8b02576b-18b8-5a72-b9d7-74d7eac61658 | note | VERIFICATION ACTIVITY - Lab Test
83b5e444-50d3-54b8-9aa8-6c8bd7834082 | note | METHODS OR REFERENCE - NZTA M/6, NZTA T10
e8e5c382-c140-51de-ac7e-1a73322b6a8e | note | FREQ. - 1 / 1000m³
d60b469f-77cb-5df4-932d-1f13b6f218f7 | note | ACCEPTANCE CRITERIA - Refer to NZTA T10 requirements
57fe7335-dc54-5bac-b0a5-1d74786320d9 | note | TYPE - V
123ee978-469b-5f4d-8e1e-3e688c1ff7ce | note | ASSESSOR - Nikhil Mishra
5081436d-3035-594b-a9bb-119312271fb6 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Aggregate - Crushing Resistance
57d3ab42-d457-5b95-bbd8-933880514ff6 | note | VERIFICATION ACTIVITY - Lab Test
e052485c-2e3f-5d58-a82d-1bf943355194 | note | METHODS OR REFERENCE - NZTA M/6, NZS 4407 Test 3.10
b5953c32-4974-5c7e-8f2c-785af41ea6b1 | note | FREQ. - 1 / 1000m³
f815a2a6-37fe-5599-b30f-de4820a92872 | note | ACCEPTANCE CRITERIA - 10% fines under 230 kN load
c7300913-2b24-57b5-962a-7e781e173ca2 | note | TYPE - V
722fd18a-8626-5b59-b7c5-6f62279a45fe | note | ASSESSOR - Nikhil Mishra
1994e27a-00c5-5940-bd64-91a39fcb1087 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Aggregate - Weathering Resistance
afb5da26-0af6-5bce-8d72-660e4a1d2da8 | note | VERIFICATION ACTIVITY - Lab Test
33816489-eb6d-56ce-9621-8dcae719fcde | note | METHODS OR REFERENCE - NZTA M/6, NZS 4407 Test 3.11
f6edaead-b8f0-5393-911a-b38db5fbd614 | note | FREQ. - 1 / 1000m³
ac948660-a391-5b72-a4b1-e65d25ebf4ab | note | ACCEPTANCE CRITERIA - Shall have a quality index of AA or BA
c96ab99a-324f-5dad-973b-28670d810aef | note | TYPE - V
6bc41652-e198-5d45-8b56-871114c9b71b | note | ASSESSOR - Nikhil Mishra
58bfd892-23d5-5537-a541-63c1bb18dd09 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Rolling (1)
a6976661-8af0-519e-ba1f-48ddb864c062 | note | VERIFICATION ACTIVITY - Visual
f88eb71a-ebb8-5c41-9ac5-2b9238131c14 | note | METHODS OR REFERENCE - NZTA P/3
289a332d-5d4e-571e-8116-285b252cdcf0 | note | FREQ. - Each Site
b3a643e8-3813-5bba-bb03-ecb87256dcf3 | note | ACCEPTANCE CRITERIA - Ensure chip has good contact with binder in all areas not just in wheel path
1dc267ca-79be-5c5d-8fa6-5c606019fac2 | note | TYPE - W
272c3585-4c32-526f-9101-09a315a093c7 | note | ASSESSOR - Nikhil Mishra
c2ee5e41-3a00-533d-86ee-8dcdf92f0f6c | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Rolling (2)
34c0baaf-7a6c-5144-9ca9-2813c7dff437 | note | VERIFICATION ACTIVITY - Plant
49ba3215-e162-5cf9-8c9e-64b8293b1a8d | note | METHODS OR REFERENCE - RQP
19fff4df-818b-5b7b-aaf1-75066b82f4a6 | note | FREQ. - Each Site
ff153d7c-dfb8-5012-84f2-b34ea6e33b23 | note | ACCEPTANCE CRITERIA - Pneumatic Tyre Roller (PTR) is to be used to roll sealed surface
fcb0649e-7aa1-5c1b-9a77-9afc189d3019 | note | TYPE - W
046c29e9-7c51-587c-9195-7720c79a2c62 | note | ASSESSOR - Nikhil Mishra
7cd564df-b2e7-5529-a94f-f7bddb922bcf | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Rolling (3)
0c7485ba-05f9-5081-8300-f2dab6269465 | note | VERIFICATION ACTIVITY - Time
537096f0-9df8-5808-a9e4-123657248b41 | note | METHODS OR REFERENCE - NZTA P/3 Section 22
b075d221-23ec-515a-ac85-37a1c2f79b06 | note | FREQ. - Each Site
f1669272-1bf2-588e-8ab9-093a96ff90c2 | note | ACCEPTANCE CRITERIA - Calculate required rolling time as per equation in section 22
d293849e-2e9c-5a5b-8e18-66a247f32884 | note | TYPE - W
611350e1-bb01-530e-b53e-330113d2686e | note | ASSESSOR - Nikhil Mishra
a10aecbd-8697-5d5f-bd1e-14e1b55c8e17 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Post construction seal protection / Seal life
c44e4bb6-cd8f-5794-be90-51993460abe3 | note | VERIFICATION ACTIVITY - Physical
f20570f3-9cde-5b08-ab9c-ce9e3153b372 | note | METHODS OR REFERENCE - Chipsealing in New Zealand NZTA (NZTA 2005)
c8008ffb-2269-5475-aeb4-aa733595c96f | note | FREQ. - Each site
f8468d10-aac9-5dae-a77c-2845776d1fe7 | note | ACCEPTANCE CRITERIA - Extended rolling time and/or provide positive traffic management to assist compaction, chip embedment and to avoid early stripping
604c3be4-5f41-5955-9389-d0d2f2f2082c | note | TYPE - W
81fa6622-9fed-51f5-adb0-1b8e1a4097ba | note | ASSESSOR - Nikhil Mishra
3bd19102-4ea2-5e2b-8105-f8559eafa8da | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| section | Disestablishment
| checkpoint | Removal of surplus chip
aeb44ae6-8a37-5425-855a-9fe50c98ed07 | note | VERIFICATION ACTIVITY - Visual
7c41885c-3ba3-5c3b-ad40-cbb00f075e1b | note | FREQ. - Within 48 hours of rolling the site
2dcb5802-30d3-56c4-a309-2bf7157314f1 | note | ACCEPTANCE CRITERIA - Not more than 20 loose chip within any 2m2
6bea1500-e33f-5485-9bbd-25f77ac88344 | note | TYPE - V
a66a2e43-b183-5071-9685-8f4bfe1ec4ac | note | ASSESSOR - Nikhil Mishra
b774d261-490e-53d7-a0c1-065eb3583faf | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Pavement marking (1)
09968f7d-1ff6-5853-990b-5a6d112bb14b | note | VERIFICATION ACTIVITY - Request for roadmarking
7a2ca98d-8d99-56e1-b3ce-ca44e7e7aca2 | note | FREQ. - Within 48 hours of rolling the site
5e823620-ed1c-59ff-b028-3f2e96a5b72e | note | ACCEPTANCE CRITERIA - Request made when item programmed
f2134062-dc7e-50d4-949c-e65f07371978 | note | TYPE - V
b5c56b60-d6d3-5802-878e-ff8e06785830 | note | ASSESSOR - Nikhil Mishra
8940ad94-db3b-5bf6-8372-7db65c25261c | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | Pavement marking (2)
0ee5666b-99dd-542a-81f2-10d7bd87bd7f | note | VERIFICATION ACTIVITY - Visual
ec187604-751b-581d-aeec-7c81d95b668d | note | FREQ. - Within 48 hours of rolling the site
c74c7199-799c-5e53-b134-910cd0b2ed32 | note | ACCEPTANCE CRITERIA - Markings follow tabs or new markings installed according to MOTSAM
7e368585-44dd-53a0-a4c0-6fb7a1aba4ea | note | TYPE - W
d15db3e9-ab1b-5426-884c-f235860326a9 | note | ASSESSOR - Nikhil Mishra
77683395-3b2c-5c97-8b20-3de1dcdb26a1 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| checkpoint | TMP
c9aee1bd-3de3-589b-9268-128c5daae124 | note | VERIFICATION ACTIVITY - Visual
0f56d19b-9d04-552e-a06d-36a38e3e3dff | note | METHODS OR REFERENCE - CoPTTM
76fd3b44-9e76-5c06-8745-0b30dd23e995 | note | FREQ. - Within 48 hours of rolling the site
53d19280-cfb2-5859-b818-54a571bb4cfa | note | ACCEPTANCE CRITERIA - Traffic control in place to protect new surface and removed following sweeping and pavement marking
5ed0d16f-57cc-59aa-a500-844a4573af06 | note | TYPE - H
9203af13-9df0-57d3-9189-73e9f6a68607 | note | ASSESSOR - Nikhil Mishra
dadbda40-0206-50ab-aae0-aeb8624cce3e | note | DESCRIPTION - Hold point - No TM is to be removed until linemarking has been completed
14d9bda4-f11d-5fcd-ba16-bc9faa0e1d73 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| section | Quality Assurance
| checkpoint | Site Recording
82d13607-80ca-54b8-8423-1f2c9041620d | note | VERIFICATION ACTIVITY - Visual
f61ad0cf-843b-5c38-8577-3fcbfe3bbf2d | note | FREQ. - Each Site
fb429411-c85b-5ceb-89c7-057103e7ccd5 | note | ACCEPTANCE CRITERIA - Video evidence of site (seal finish) once it has been swept
ba582f40-7e9b-5a79-9e97-b08607ddfb71 | note | TYPE - H
e28da85c-f63f-58d5-921a-a19a3b671c36 | note | ASSESSOR - Nikhil Mishra
43b51a55-2021-5ed1-a0ce-0fab8573bbd6 | note | DESCRIPTION - Hold point - Failures within seal surface must be rectified before site can be confirmed complete
553f1108-ea20-509e-b9f3-056e20f3cef0 | note | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Post seal Inspection
3760fafa-730d-5a97-bccc-71ce4a2c22ec | note | VERIFICATION ACTIVITY - Inspection
0ef3d8bd-349f-5621-9ba0-ae6b025dd9bc | note | METHODS OR REFERENCE - Downer Survey
1e94ce73-2106-5b48-9565-ebae2aae13ad | note | FREQ. - Each Site
98a11c23-89fe-5a46-ba8a-4c0383341897 | note | ACCEPTANCE CRITERIA - NZTA representative is satisfied with finished pavement surface, photograhic evidence shall be supplied if client is unable to attend. Inspection to be logged via Downer Survey
7fddd6b5-f3b1-5b5b-8785-c7e480ee3de4 | note | TYPE - H
93935850-cd27-58bb-b576-ebd2e40d09d0 | note | ASSESSOR - Mark Joblin / Nikhil Mishra
a2e4a52b-4041-5629-a780-b5f81250c6db | note | DESCRIPTION - Hold point - Client must have opportunity to be present on site to complete inspection of finished surface.
a5642019-b9f7-5ece-b4ff-41d7078dabeb | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Measurement check
7fdb1f0a-7278-5273-9960-4367cabccc13 | note | VERIFICATION ACTIVITY - Physical
bc814bf2-7f9f-51fc-8ffc-fcf406ca3128 | note | METHODS OR REFERENCE - Check and measure site and confirm on as-built
11560387-12ff-548e-9f7e-ddbebaa58094 | note | FREQ. - Each site
f26afe77-d5c7-5e04-af3b-f4b541d57bf6 | note | ACCEPTANCE CRITERIA - Once site has been completed and checked as as-built will be uploaded into RAMM Contractor
a07663fa-9150-58cb-8e0c-827bf1970e96 | note | TYPE - W
73aa7006-5e8f-50ed-91e8-5641b4e98482 | note | ASSESSOR - Nikhil Mishra
a24faf21-f6af-5a10-a029-23e52c29e174 | note | RESPONSIBLE PERSON - Akhil Mohan
| checklist | Stabilisation ITP | itp | Stabilisation ITP | 3d23341f-6b37-4123-8d6a-7322adbec242
| section | Preliminary & General
| checkpoint | Approved RQP
a5b2dc66-c3f6-507e-af64-34362994f487 | note | VERIFICATION ACTIVITY - Confirmation
c3a319be-bd3f-5244-a1d7-96dde14ce967 | note | METHODS OR REFERENCE - Contract Specification
c761f5e8-1cae-57a0-b253-922fc960b716 | note | FREQ. - Before work commences
4e8514cf-d470-563a-ba91-48249ca10a13 | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3 TRWNOC
8c67247f-0235-505f-8b28-f4e283adb3a8 | note | TYPE - H
1591bb95-c40e-56dc-91ad-c986e7052f3b | note | ASSESSOR - Mark Joblin
c1716635-4287-5310-bf57-ae843225737c | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
cb762f99-1100-5fc1-8d07-9d1c5a5782d9 | note | RESPONSIBLE PERSON - Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Design Acceptance
79748872-20bf-58d1-813e-71cb4cd53dfc | note | VERIFICATION ACTIVITY - Confirmation
c5dab8af-68fb-5eb9-be4e-cc5b6dc027b8 | note | METHODS OR REFERENCE - Contract Specification
2ca15a73-943f-5197-9a45-f42adc50eaba | note | FREQ. - Before work commences
f49ec8cd-2a0a-54fa-870f-44baddc06765 | note | ACCEPTANCE CRITERIA - Principal Acceptance according to guidelines in appendix 6.3 TRWNOC
e7cff874-33fb-582f-88e2-45a327fef506 | note | TYPE - H
b02b6923-5a21-59d7-8cff-bc2c4574e83e | note | ASSESSOR - Mark Joblin
003d8ee8-6661-5f92-b770-9c865b6c617d | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
42c0bc5b-af9c-5a19-903d-0a30008f5608 | note | RESPONSIBLE PERSON - Nikhil Mishra
| signoff | AUTHORITY HOLDPOINT
| section | Set-out / Site preparation
| checkpoint | Setout
0f93ced8-14c5-5b87-bc13-f92ebeab20dc | note | METHODS OR REFERENCE - Best Practice
8d36f636-b161-5cca-9752-3ac9683f1fd6 | note | FREQ. - Per installation
53b37a0d-bf47-5e59-a1fa-6d9a93bd83f7 | note | ACCEPTANCE CRITERIA - According to existing road profile and alignment
3a45ae5a-3a15-5b39-8dfd-e8e6c8e001c8 | note | TYPE - V
c284bb55-953a-5473-b884-756a897023ef | note | ASSESSOR - Nikhil Mishra
fc72176f-d3b3-5158-8c1e-0434b8b6cb47 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
5b5d32fa-1995-5cfd-acc3-f27127c00e8f | note | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
cbd62e38-3f29-564a-beba-79b49264318b | note | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
03e9947c-9211-5e2e-887e-0175ccb4befa | note | FREQ. - Before work commences
f116725d-eca6-505e-816e-9a13a3097e66 | note | ACCEPTANCE CRITERIA - Zero service strikes
0a664f8a-9ce1-56c4-aca9-0107924a7fd1 | note | TYPE - H
c7689bcf-2c75-5b15-b05c-7651996e6614 | note | ASSESSOR - Nikhil Mishra
8ed8b6d2-2251-58ef-a801-ca6378696b2c | note | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
144b039a-9d6f-541a-adce-ccf4bd34baef | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Cultural/Heritage Risk Assessment
0e65e21e-1912-5d1e-a1c9-e7b36d078cf8 | note | VERIFICATION ACTIVITY - Notification
2bab549b-cbc7-5620-a4a8-9ca43345d12b | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
64624096-c93c-50cc-b3b2-0a1b2f5120ec | note | FREQ. - Before work commences
be7df93b-cec3-5355-bcf7-2ad929302c3c | note | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
d8e56b66-c510-541e-85aa-f7f0b69c3bca | note | TYPE - H
f4ef8bb3-50c1-536c-8397-422dcfcf20cf | note | ASSESSOR - Nikhil Mishra
3f09f4b5-3c57-5bb9-ba8d-6b6092667d93 | note | DESCRIPTION - Where risk of cultural discovery
fe73eb0a-9c00-5ce4-88d5-7f8074cb16c3 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Notification of intention to start work
edac4675-746e-5f71-a9ee-51cf7844f5df | note | VERIFICATION ACTIVITY - Notification
3e150934-3b70-574a-ae65-2878ecf60b88 | note | FREQ. - Before work commences
ff60b18d-07bc-51e1-abf0-ab8ec9b1000f | note | ACCEPTANCE CRITERIA - Letter drop to local residents
77697b38-a447-59b5-a9c4-1b74b1bba26a | note | TYPE - H
5d879856-eb2e-5e33-872e-d593869abefc | note | ASSESSOR - Nikhil Mishra
82fbeebb-6bb1-5bb0-ad7f-7fe36e0ffa6e | note | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 48 hours of establishing on site.
0cfde065-a7ed-56c6-a550-28d520c810d7 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Archaeological Risk
e806438c-ec74-5991-bcab-e86305cc050a | note | VERIFICATION ACTIVITY - Toolbox meeting
b8f3468f-63aa-5204-8ab9-8ccd36a56bd1 | note | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
8ea8970c-9d83-5807-8381-c8cf50020b77 | note | FREQ. - Before work commences
3abbb65b-1725-55e4-a509-a1d472b9dcf7 | note | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
14f77073-0981-5316-ab2a-b4f44f667916 | note | TYPE - H
d9021527-369d-5a45-b80d-6118adaf95d6 | note | ASSESSOR - Nikhil Mishra
e3b60fb0-a730-5c7b-9b89-f545c0b0691a | note | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
0a46f37e-ff8d-5c32-9cf0-13beac60f3cd | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Traffic Management - TMP
c8d0bdbe-108d-55a4-b0d4-803c9389582f | note | VERIFICATION ACTIVITY - Visual check
b23e9596-f762-5759-99b0-6e72bfadb862 | note | METHODS OR REFERENCE - CoPTTM
a35a508c-84b1-512a-80c5-513452709d9f | note | FREQ. - Before traffic management set up
5cd1971a-1572-5984-b59d-d1f785ee1d1c | note | ACCEPTANCE CRITERIA - TMP checked and approved - Plans approved
f7034bb3-86e9-5219-8771-9bf4eff59c67 | note | TYPE - H
53a346e7-2e23-5e3d-aa00-f0421636f205 | note | ASSESSOR - Nikhil Mishra
bd1e36b7-c8e7-5a1d-b0c5-7a907211f4cd | note | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
5ad6eb4e-59c3-5e85-b5b4-291ed4198224 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Traffic Management - Setup
56dbe4fe-14d8-5fba-8a08-b5b154e6e472 | note | VERIFICATION ACTIVITY - Visual check
a030c097-e1d9-51b2-9e1d-62393a945cb8 | note | METHODS OR REFERENCE - Traffic Management Plan
2a03d7b1-c23e-5d74-a5f9-febc6c720908 | note | FREQ. - Before work commences
556644e7-23f5-5bce-9db6-4c6a789c8409 | note | ACCEPTANCE CRITERIA - Traffic management complies with TMP
1fd07b9a-40d9-5586-a99b-a0a38eb79f79 | note | TYPE - H
79fb5786-18a8-5d24-8cf2-d5d812b1ac52 | note | ASSESSOR - Nikhil Mishra
c7691cbf-dcf9-5122-8619-eec1878bb5ca | note | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
1bf46b6c-19f1-5340-b3d7-bb845d2a01e4 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Sediment Control
901f7a47-b9d1-5f49-b1c0-e644ec422339 | note | VERIFICATION ACTIVITY - Physical
39d8369e-d5a9-50c9-a22e-bdb4011c96e7 | note | METHODS OR REFERENCE - ESMP DN-ZH-GU074.1
2f8a4caa-7582-5172-a2b2-fbab405593d4 | note | FREQ. - Before Excavation Commences
35118b45-d9f2-5820-8af1-550affa1bbdf | note | ACCEPTANCE CRITERIA - Sediment and erosion control measures aligning with DN-ZH-GU074.1 and ESMP
0813647c-5137-5918-8a38-ef43b06ba1a8 | note | TYPE - H
3c5478a7-d53b-5027-9693-97a1c156fba4 | note | ASSESSOR - Nikhil Mishra
eabab953-8cb5-52f3-a570-6fb7a5a7243d | note | DESCRIPTION - Hold point - No physical works are to be commenced until sediment control measure is in place
e9fb1f81-3448-527c-895c-9f614b88e269 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Dust Control
48a4e507-2386-5369-b2aa-a6700bd6918e | note | VERIFICATION ACTIVITY - Physical
59412a97-8632-5cc1-9b6f-8f2e463240e1 | note | METHODS OR REFERENCE - ESMP
35d48b75-8a0c-5068-9c2f-e9e11280b3c2 | note | FREQ. - During Execution
4482ac0c-9cbe-5288-ba10-eb7e389bf810 | note | ACCEPTANCE CRITERIA - Complies with ESMP
2fa5db6b-1281-58b6-9e65-7022ae0d9095 | note | TYPE - H
5e414349-e6be-5212-be69-790c91d96b55 | note | ASSESSOR - Nikhil Mishra
9d961c66-511c-5bc0-91e0-3b5abcf20c8f | note | DESCRIPTION - Hold point - No physical works are to be commenced until dust control practices are implemented
537b5994-d902-5c4c-8c65-5f992903d362 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Noise Control
dbc273c1-a049-519c-b11a-157046a09f58 | note | VERIFICATION ACTIVITY - Physical
d8f30dc1-23d6-5a6e-a242-9a237482179b | note | METHODS OR REFERENCE - ESMP
e328123a-ca71-5b06-be17-45e26b00ef49 | note | FREQ. - During Execution
a231d8e6-b7eb-51e6-9282-5a70cdcd2761 | note | ACCEPTANCE CRITERIA - Complies with ESMP
8d541688-975f-570f-9a23-f38e6e9e529b | note | TYPE - H
fa10c7aa-b226-5781-8cc0-2c9f2f3cf44a | note | ASSESSOR - Nikhil Mishra
d02a6e6d-e959-5dbc-9cd9-5992f06eb7c7 | note | DESCRIPTION - Hold point - No physical works are to be commenced until noise control practices are implemented
3771db3f-92f2-5a16-b7b7-ccca48f5e18e | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| section | Preliminary Works
| checkpoint | Shoulder Stripping
a63a7069-3a18-5102-b9c9-f0de56d3e999 | note | VERIFICATION ACTIVITY - Visual check
3856dc09-fef7-521a-9ce0-d6e1c01fa097 | note | METHODS OR REFERENCE - On site
9700b704-51c6-5bb0-ae50-ed1dd8e75c95 | note | ACCEPTANCE CRITERIA - Shoulder stripping completed
d07239e5-c4b4-56b9-9e52-bc409e5621ff | note | TYPE - W
a395e290-3a6d-51ad-aca9-0b6743d57c61 | note | ASSESSOR - Nikhil Mishra
161717ee-1682-5453-b1b3-bc34dd44b6cd | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Compaction Equipment
1a5efda1-97a1-5bd7-8adc-192a8b94fd96 | note | VERIFICATION ACTIVITY - Inspection
94d4a4fe-52c6-588c-b9d4-7296d51b1c5e | note | METHODS OR REFERENCE - RQP 17.1.2
0a00503a-eeb4-59cd-a59a-2e93accd987c | note | FREQ. - Prior to commencement
ba0f0ade-977a-524d-a8a2-669d59e7ef75 | note | ACCEPTANCE CRITERIA - Compaction equipment is sufficient to achieve compaction
901fad10-2bc0-5255-8aa1-d34e82141502 | note | TYPE - V
2ab7e818-976b-5bd4-b7e3-f75976a0a7af | note | ASSESSOR - Nikhil Mishra
69d51875-36b8-58d9-8124-8301b0a67191 | note | DESCRIPTION - Required by appendix 6.3
72991816-8db1-57ae-911b-01573ee5dd69 | note | RESPONSIBLE PERSON - Akhil Mohan
| section | Digout Repairs
| checkpoint | Material
13bfc029-3241-5bbd-9e61-949a57335ecd | note | VERIFICATION ACTIVITY - Lab Test
d6d9fb12-de30-5c8d-ab94-264b0cecc355 | note | METHODS OR REFERENCE - NZTA M/4 - Grading, broken faces, fines properties
5b9d3649-0b97-547d-ab7f-5b6967eec6b2 | note | FREQ. - Most frequent - Every 500m³ or 2 months
1ce54988-7f30-5c82-a4d9-17fd98b08655 | note | ACCEPTANCE CRITERIA - Confirming Lab report AP50
9b188099-f174-5ff3-ba6e-a0592cb54db5 | note | TYPE - H
1988b297-5e58-5d6a-bca8-17545ca505b9 | note | ASSESSOR - Nikhil Mishra
52ccdac2-8d7d-5575-a72b-6abac24d531e | note | DESCRIPTION - Lab Report
1bcb2fbc-7085-54ce-9bd2-e3673eccdb6d | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Depth
fee90eee-233e-5bd7-9c39-ec89d3561a77 | note | VERIFICATION ACTIVITY - Visual
60ba0c28-bdcb-5283-85ce-1a72e00a5269 | note | METHODS OR REFERENCE - According QMP
e0490579-d6de-5b18-84fe-1efd5ade38d8 | note | FREQ. - every 10 m
71ec184b-40ba-5450-b7c8-bd19e8dd1595 | note | ACCEPTANCE CRITERIA - Depth within +25 mm -5 mm
8a655465-a8b3-527e-8493-9bd2a639151a | note | TYPE - H
fa0e8475-8f04-5e7e-8e92-e22eb1ac6f3e | note | ASSESSOR - Nikhil Mishra
cd111cba-6ba0-5862-8366-add2ceb16305 | note | DESCRIPTION - QC Form
904ee35e-abd5-50bf-9b09-7ba3bfa6dbfe | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Compaction
aa175744-b886-5fe0-b6d9-72982a375fe7 | note | VERIFICATION ACTIVITY - Visual
c59038cf-85d1-5256-b823-5746d74bbef1 | note | METHODS OR REFERENCE - Measurement
b36e2d9b-f050-5b24-b91f-2b7fc72e9796 | note | FREQ. - every 10 m
730c7525-9841-579a-8334-029269bdf341 | note | ACCEPTANCE CRITERIA - Compact in layers not exceeding 150 mm (compacted height)
14a4dd80-c8f9-5fef-a137-379591863287 | note | TYPE - I
4ee2e379-db43-548f-9fb9-eb841d928a34 | note | ASSESSOR - Nikhil Mishra
7e99e5d1-6e67-583f-b510-3c4b3637d4e8 | note | DESCRIPTION - QC Form
a54de63f-e0e7-511c-9544-893f65f6889a | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| checkpoint | Density (as required)
5acc9508-a5f7-52d5-9d5c-55fb84672cc7 | note | VERIFICATION ACTIVITY - Site Test
0d5bbb68-f827-543d-9aac-724401c7795a | note | METHODS OR REFERENCE - Nuclear Densometer - Maximum Dry Density
788711ff-ca51-5197-9180-13be6f908bb7 | note | FREQ. - Each Programme
b83ca007-b6eb-59db-ad0e-77d3b68e41cb | note | ACCEPTANCE CRITERIA - Subbase: Average ≥ 95% MDD
c62be603-9669-5288-982b-06aa72959cbc | note | ○ Minimum ≥ 92% MDD
fb3426e9-690a-5f6d-a703-2906dc04f967 | note | TYPE - H
945441f2-93cc-5652-9198-fae7d0e3a1ee | note | ASSESSOR - Nikhil Mishra
bf985c3d-5f55-529c-851d-dcab6c0f00d6 | note | DESCRIPTION - QC Form
76343732-acca-552f-8013-917b23574f02 | note | RESPONSIBLE PERSON - Akhil Mohan
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Surface
44445d58-edb7-571c-b5ef-6e064ab39d5d | note | VERIFICATION ACTIVITY - Visual
69c85504-9526-5fb9-965e-0f02c88d871b | note | METHODS OR REFERENCE - Straight Edge
d780e37c-9db9-5b28-b787-12a5ddeecf12 | note | FREQ. - Each Site
f71e1a1a-c038-5dc7-89c1-efb908cd33cb | note | ACCEPTANCE CRITERIA - Repair edge - Max 50mm in 1m
a9aa21fa-2bbc-594f-9d3b-8c65143da6df | note | ○ Depressions - Max 6mm in 2m straight edge
38a73450-c220-588d-bd7c-46185a1f86e5 | note | ○ Swept, tight surface - no dust
71ba033d-e245-5e81-9f10-c1ba9cac25ec | note | TYPE - I
ae71c087-3aa1-5750-b551-d11235868bef | note | ASSESSOR - Nikhil Mishra
23919000-e307-5203-8982-d75c93a5fda4 | note | DESCRIPTION - QC Form
9740404b-7429-519e-a5cc-64c18ae2d4dd | note | RESPONSIBLE PERSON - Akhil Mohan
| section | Pavement
| checkpoint | Water
127342b3-8149-5ace-a443-ccb98793ab59 | note | VERIFICATION ACTIVITY - Visual Inspection
bf58d5d5-fd36-5f54-8319-fb98981e7f4f | note | METHODS OR REFERENCE - TNZ B/5
92da8383-be90-53a6-89dd-ee757d96e57d | note | FREQ. - ongoing
0471bd35-2bda-5b0f-88e7-3a876854acee | note | ACCEPTANCE CRITERIA - Water for stabilisation, construction and curing is free from impurities, 10 m3 allowed per day from natural source if resource consent obtained
f48beeb7-0df8-543e-bc71-723b6a636dc4 | note | TYPE - W
0d65ee9a-50b5-5e1e-af09-813fdd006660 | note | ASSESSOR - Nikhil Mishra
09787576-c812-500b-8c63-12ddec6dc490 | note | DESCRIPTION - Water quality should be continually observed as clean, when impurities are observed a new source may be required
c53f1f06-c238-50b0-bc37-045e7428ab0a | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| checkpoint | Weather Limitations - Temperature
373fdff1-9c8e-5ba3-a28f-96f7d211b315 | note | VERIFICATION ACTIVITY - Measure Temperature
b1995252-1ddb-5c45-a570-3694b89c31ea | note | METHODS OR REFERENCE - TNZ B/5
f821ec2d-94f9-56b3-887c-02d300d86bef | note | FREQ. - Daily
6065356a-c9f1-5d58-891d-9d2671747e2f | note | ACCEPTANCE CRITERIA - Minimum ambient air temp. Use weather report as evidence
3c2a5f8e-ac0f-585c-958d-165e37fa4199 | note | ○ Cement 5°C
e7241d07-10d2-5d5b-8bc6-3c07074e6107 | note | ○ Lime 10°C
cdd0e46f-6c95-5eac-a178-1ec45769db00 | note | TYPE - W
69dc1eef-fdf0-504d-836d-f88d7ea573ba | note | ASSESSOR - Nikhil Mishra
2b8f8040-eb0d-547c-ae3d-cc5416ee7cbb | note | DESCRIPTION - Work shall not be started if temperature is below the respective minimums.
6344441d-da3c-5d32-aa64-5dc555e8a648 | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| checkpoint | Weather Limitations - Wind
0553258e-1899-5205-a9bb-1f75a2bcb02f | note | VERIFICATION ACTIVITY - Assessment
df1c16a0-2f95-5d04-9d63-abeeabbb290d | note | METHODS OR REFERENCE - TNZ B/5
edee5ebc-028f-5503-8fa9-c99eb0d14e41 | note | FREQ. - Daily
178cf2c4-2159-5c37-9b19-769cd8d7b303 | note | ACCEPTANCE CRITERIA - Maximum wind speed of 25km/hr. Use weather report as evidence
e6f91247-68c8-503d-9e1f-debc32bc3da9 | note | TYPE - W
d52aaaa4-8634-5e5c-86f8-30931a72ebd5 | note | ASSESSOR - Nikhil Mishra
e453b90f-c5b1-5758-8096-556d81a97d50 | note | DESCRIPTION - Work shall not be started if wind speed exceeds the maximum
a67eabc5-0e43-5d58-8284-017ee5550b91 | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| checkpoint | Imported Basecourse Materials Testing (1)
b10a2225-c10b-57b6-bba6-74c6241c3ec5 | note | VERIFICATION ACTIVITY - Comply with project specification
1632ce0b-e76c-5922-a6b4-1dcaffa1d31e | note | METHODS OR REFERENCE - Refer project specification
860b640f-bb5e-5e99-b1ee-a41712190d0a | note | FREQ. - Refer project specification
7366fd99-7414-58e4-8272-2c323faf199b | note | ACCEPTANCE CRITERIA - Refer project specification in pavement report
7ebcb58c-64aa-5530-9a71-16f3592f8b7a | note | TYPE - V
038c270a-ecfc-580f-9c33-894fb5fe6cc6 | note | ASSESSOR - Nikhil Mishra
12a2a67c-9c06-51b0-8d6d-6bb7612e9bc5 | note | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source
b03d4653-9fb2-5e82-9876-953c6a81ef16 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Imported Basecourse Materials Testing (2)
be4bb729-7656-5bd8-83be-8be9cbe0e72c | note | VERIFICATION ACTIVITY - Comply with project specification
e8c9e196-da02-5347-9c3e-e683bcb5f9c3 | note | METHODS OR REFERENCE - Refer project specification
866aadb3-2005-535c-b599-ea4e90ab8ad0 | note | FREQ. - Refer project specification
dd9d0a70-daca-510d-9f2b-1cdfbbb2c839 | note | ACCEPTANCE CRITERIA - Refer project specification in pavement report
4b31344c-4482-534c-af16-0856da38522d | note | TYPE - H
4e680159-eeb3-50d5-81aa-b1e5c2ade6aa | note | ASSESSOR - Nikhil Mishra
381756bd-464a-5918-915a-e1a32e22785a | note | DESCRIPTION - Hold Point – All production and source testing results to be provided prior to placement of material on road for a source
ec6bff1b-4616-5f1b-8803-e5c2a83c7947 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Imported Basecourse Materials Testing - Particle Size Distribution
9c18570c-2ae1-58e7-b54d-370537c270a8 | note | VERIFICATION ACTIVITY - Sieving Test
42023f32-6d4c-59ae-b1f3-88de76f06c9f | note | METHODS OR REFERENCE - TNZ M/4: 2006, NZS 4407 :1991 Test 3.8.1
cc105884-08fa-5bc7-abbc-7cbf17f37609 | note | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
e67448a2-0d77-59a4-84c5-bf0a7cb1fd35 | note | ACCEPTANCE CRITERIA - Particle size distribution fits within the AP50 envelope upper and lower limits
834fcd68-d724-532a-8ddc-6abd7deda042 | note | TYPE - V
68bb0a20-a002-5a00-958a-3d64507eab49 | note | ASSESSOR - Nikhil Mishra
610c7529-0ab3-550a-9891-ba677d329388 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Imported Basecourse Materials Testing - California Bearing Ratio
85ec08e8-162e-5a6c-984f-f1b78c69da68 | note | VERIFICATION ACTIVITY - CBR Test
9d7ffb36-78ee-5dc7-a7bf-6a1089b2152b | note | METHODS OR REFERENCE - NZS 4407:1991 Test 3.15, TNZ M/4:2006
d8f200fd-9709-5877-adea-639307c0c3d1 | note | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
6ef5025d-b6f2-591a-b2c3-7533f28e04fd | note | ACCEPTANCE CRITERIA - The soaked CBR of the basecourse aggregate shall not be less than 80%
a8067120-0bfb-5279-9d5a-c7e7e5bd1ab1 | note | TYPE - v
bc01c385-12cd-5aaa-9cf5-fe70697e0d0e | note | ASSESSOR - Nikhil Mishra
80e5c3e2-758b-54f9-a12b-c29e34150d9e | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Imported Basecourse Materials Testing - MDD
9469cac2-c92f-5586-9b6e-88c8786c41a5 | note | VERIFICATION ACTIVITY - Test
78d4b481-cac0-5e09-b04c-84e62b9163ad | note | FREQ. - 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock
11122d21-d7e7-5a61-a48c-ee379c489f80 | note | ACCEPTANCE CRITERIA - According to Design
01d74492-780d-5220-9ed8-4471d2110cc8 | note | TYPE - V
7508d328-f6ff-53ce-91bc-9f8abb06164a | note | ASSESSOR - Nikhil Mishra
e878946b-070c-5cac-966c-15cfa476e282 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Stabilisation agents - Cement (1)
7c86c538-dfc6-53c1-942c-622a8e8b1278 | note | VERIFICATION ACTIVITY - See NZS 3122
e36fa51a-e05d-5a85-9b63-1d0a00e56fbe | note | METHODS OR REFERENCE - NZS 3122
91d30039-f2d0-554c-a947-c5efe890a808 | note | FREQ. - per batch produced by supplier
5e4fd257-d160-5800-bb02-4a425148355d | note | ACCEPTANCE CRITERIA - Cement must comply with NZS 3122
1cdcf41f-6d5c-54c1-9ad0-5e032acfd511 | note | TYPE - V
b83abfaa-425c-522a-909f-f87edec36535 | note | ASSESSOR - Nikhil Mishra
cfb463d5-0b92-561f-a14c-716ff923ee8f | note | DESCRIPTION - Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier
c3fab2b0-2480-5efe-b74c-2544e559b93d | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Stabilisation agents - Cement (2)
9abe2c2d-216b-5ec0-844a-146a49c7bae6 | note | VERIFICATION ACTIVITY - See NZS 3122
b0c71de5-0b82-516d-aa14-40ba256bc657 | note | METHODS OR REFERENCE - NZS 3122
ba8daa40-a3b4-50f9-835a-5864ac1cbfa0 | note | FREQ. - per batch produced by supplier
d4c9941b-adff-50bc-a2da-1e4678324625 | note | ACCEPTANCE CRITERIA - Cement must comply with NZS 3122
8ea28e0b-1df0-5f79-8a0f-fd09e10b75c3 | note | TYPE - H
3f366a57-f4e2-5d77-afc3-afe3dd6776e6 | note | ASSESSOR - Nikhil Mishra
c9667530-8e4a-5ee6-b195-5c818b18491f | note | DESCRIPTION - Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier
6ce35e33-2624-537c-9095-77d00647d36d | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Stabilisation agents - Delivery
24e4d4ec-d2d3-5d95-a058-3a30e25ffb5a | note | VERIFICATION ACTIVITY - Visual Inspection
9805529a-1fce-5334-852b-596c83f90ef7 | note | METHODS OR REFERENCE - TNZ B/5
44c1ec38-9068-576e-9ad7-37c289984bef | note | FREQ. - Upon delivery
9a87258d-0205-5fd1-9cfc-0027e4848d1c | note | ACCEPTANCE CRITERIA - Stabilising agents to be delivered in tanks or trucks with Certificate of Loading
1ea5cad1-9db7-5503-90a4-51007730e82b | note | TYPE - W
54e6ec25-65ee-5ab7-b99e-c53d4bb42aaf | note | ASSESSOR - Nikhil Mishra
f6698f68-f34a-5be9-a37f-1489283026fc | note | DESCRIPTION - Certificate of loading to be checked on site
c5e4e76c-465c-58ca-8478-cd9c8df7b192 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Weather Limitations - Wind
f1fb6622-dc79-5459-b7c6-10d2d3ec8af0 | note | VERIFICATION ACTIVITY - Assessment
76be750c-bbea-57b9-8652-23c1238acb2e | note | METHODS OR REFERENCE - TNZ B/5
d98867ad-f0cd-53fc-bd50-b32110abf68d | note | FREQ. - Daily
509ff424-0834-58d7-ab25-e8f459291e95 | note | ACCEPTANCE CRITERIA - Maximum wind speed of 25km/hr. Use weather report as evidence
876aea99-5444-53ee-b410-7e7e5ddcfcca | note | TYPE - W
43c40cc2-d1eb-5dbc-a0ae-e614173158f2 | note | ASSESSOR - Nikhil Mishra
61cff501-1bba-54c3-8720-be74489e79ac | note | DESCRIPTION - Work shall not be started if wind speed exceeds the maximum
6444b8e3-6f08-5c2b-af8c-5289254a7088 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Weather Limitations - Rain
c0f07ec0-2242-5d52-b408-032be5cb9dce | note | VERIFICATION ACTIVITY - Check forecast
a1f6fb6c-6d74-5976-8800-7de15443a490 | note | METHODS OR REFERENCE - TNZ B/5
58ffe733-ab9e-5e7a-8a41-4d6351b5b4f4 | note | FREQ. - Daily
1ecf0fb8-0606-5764-94ef-0acebc356ad5 | note | ACCEPTANCE CRITERIA - Zero likelihood of rain. Use weather report as evidence
7fc825f9-ec0e-560a-ae73-f0605ee52fd9 | note | TYPE - W
7d8e5671-3877-5840-96a2-95f70823db28 | note | ASSESSOR - Nikhil Mishra
13e9979f-8d99-55d8-9eb6-3f218db6b10c | note | DESCRIPTION - Spreading shall not commence if rain is forecast
e6bbffbe-2975-5b69-b2f3-792400fa3186 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Spreading - Cement/lime
05a79bbb-eb08-5a33-a21e-958f341841a9 | note | VERIFICATION ACTIVITY - Mat Test, 1m² canvas
5b5e3934-2620-596e-a78d-d6a8412dc493 | note | METHODS OR REFERENCE - TNZ B/5
2ebe3af1-10c7-5eb6-badc-4c5c3a6999bc | note | FREQ. - Every 400m²
62bf6eb5-5b94-580d-84ad-b53dee299fa6 | note | ACCEPTANCE CRITERIA - Within ±0.5 kg/m² of the specified rate
840dd5e8-ff08-51dd-be9b-e60147a76cbf | note | TYPE - V
b4d119d8-0dd8-5d43-adbc-cfe332fdcb63 | note | ASSESSOR - Nikhil Mishra
52188c8a-3d7c-536b-bb0e-61349873496b | note | DESCRIPTION - Tonnage/m² records shall be kept, including mat results
d3cf77f2-814d-5bbe-91f8-32617e2e6f5e | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Time Limitations - Cement/lime
934a8226-ce10-599b-b93a-831e56d80e01 | note | VERIFICATION ACTIVITY - The maximum time period from mixing to primary compaction
749ab376-b0f4-5b33-a7de-1eb97c399a37 | note | METHODS OR REFERENCE - TNZ B/5
cfaa3225-dfc9-56b0-870b-b668c68bc513 | note | FREQ. - post stabilisation
c76be441-e9e9-5426-b673-7a5057221bc2 | note | ACCEPTANCE CRITERIA - 2 Hours
db98f290-335a-5343-afc3-fef0171efa75 | note | TYPE - H
33932655-8e22-5417-b4d8-ae3dd781f1e8 | note | ASSESSOR - Nikhil Mishra
a3d26eab-c584-56eb-a733-39fdd92c84bf | note | DESCRIPTION - Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances
860f8db4-d4f7-5b11-93f6-5818d7c21995 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | In-Situ Mixing - Cut Depth
ee738f00-565d-5473-ab90-e6605fd68e08 | note | VERIFICATION ACTIVITY - Depth measurement
4bedc9e1-d80d-5902-b3ae-5fcb922df666 | note | FREQ. - at both ends of cut and every 100m
0c977c3f-3ad5-5ff3-a199-9fbbecf98524 | note | ACCEPTANCE CRITERIA - +- 20 mm of design depth
a96fd529-2c70-53ce-8d94-31658b1ed6b4 | note | TYPE - W
16b43a4f-70bd-58aa-a2e2-2e88c3217b5d | note | ASSESSOR - Nikhil Mishra
79d85090-facf-58a5-bcb5-a9909336f24b | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | In-Situ Mixing - Depth of STAB
c898456b-303a-57b5-8037-34d05e2567fb | note | VERIFICATION ACTIVITY - Depth measurement
141bf1f1-3abf-5bca-bfec-924b04569fdd | note | FREQ. - Random locations
eed9a08a-c957-514f-868b-c727ee9f2b3c | note | ACCEPTANCE CRITERIA - Meet desgn depths
51338c93-eed4-54e3-8d13-e2b3b075c134 | note | TYPE - V
c0f165a3-0aea-5f18-bbb7-dd7cf3f728df | note | ASSESSOR - Nikhil Mishra
1e6812cc-9394-56bb-aa9a-2ab04ac8c7cc | note | RESPONSIBLE PERSON - Akhil Mohan/Richard Taare
| checkpoint | In-Situ Mixing - Join Overlap
22b9a841-4c36-57de-afe2-ade9fa701535 | note | VERIFICATION ACTIVITY - Inspection
648a4532-19e3-594d-a8cf-054b6f8c78e5 | note | METHODS OR REFERENCE - TNZ B/5
84ad2674-1fe5-557d-b442-e8ccd3e8b52c | note | FREQ. - Continuous
63e6024c-c6d4-573a-8da6-ea49e6472ce2 | note | ACCEPTANCE CRITERIA - 100mm overlap
b87af284-9e2d-53dc-a514-84b40566919d | note | TYPE - W
075d71e9-1716-5f6a-ab39-dca2c2ed260b | note | ASSESSOR - Nikhil Mishra
e7733c87-1d14-5d80-986c-97babdfccd4b | note | DESCRIPTION - All cuts shall overlap by the minimum acceptance criteria
656789be-4823-5446-915a-69410921cb83 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | In-Situ Mixing - Particle breakdown
8ea47e9a-177d-5448-8a66-113a0d717015 | note | VERIFICATION ACTIVITY - Visual Inspection
926dbc5d-79f5-5a66-a904-d788bba0592a | note | METHODS OR REFERENCE - TNZ B/5
433bed55-cf1d-5163-9c71-bef41c691d8f | note | FREQ. - within the first 20m of each run, and where ever material changes
ed14d787-e300-51b2-aa86-9664202c6c2b | note | ACCEPTANCE CRITERIA - Well mixed material with acceptable particle size distribution
d98c5478-dd80-5698-b63a-0c9c19343045 | note | TYPE - W
35a1876d-520f-5f6b-8fc9-bf2d6f54b327 | note | ASSESSOR - Nikhil Mishra
800e60fd-b437-506b-8209-7fcfa5ff98b0 | note | DESCRIPTION - Where breakdown is excessive, method of milling should be altered to avoid such breakdown
0ca02889-5033-5ffa-a77a-197f719ba748 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | In-Situ Mixing - Client Acceptance
dc204af2-b1b0-5ef7-b7a4-f8af9fd11e78 | note | VERIFICATION ACTIVITY - Inspection
a73ea7a5-c09c-5fcc-9c8d-d64af87c6dd9 | note | FREQ. - Per Site
eecafba1-3294-54dd-ba97-c16767f35a7b | note | ACCEPTANCE CRITERIA - Client to be present during stabilisation, photographic evidence shall be provided if the client is unable to attend
c26018b7-0b4b-59a3-958c-cf73e2ae4b84 | note | TYPE - H
8f7c1b16-a2c6-5d91-97cf-c9c6c9527d0f | note | ASSESSOR - Mark Joblin / Nikhil Mishra
dfe2c3fd-cc82-5001-84f8-a990f2c65c21 | note | DESCRIPTION - Hold Point - Client shall be notified prior to stabilisation so they have the opportunity to be present upon commencement of stabilisation
001cd9aa-b32f-5841-98d7-3c80d9359e39 | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Akhil Mohan
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Construction STAB OLAY - Compaction
207c4e9b-b69a-5895-8d6a-471d1c4860a4 | note | VERIFICATION ACTIVITY - NDM – maximum dry density
01212870-e169-5625-a087-36dd8da11700 | note | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
68922af0-7085-5d06-b546-9c73ed02e5f1 | note | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
1bd495a6-036f-5646-b8f6-027db7060b27 | note | ACCEPTANCE CRITERIA - Base: Average ≥ 98% MDD, Minimum ≥ 95% MDD
d558118b-293b-5186-be42-105c13246b63 | note | TYPE - V
253b1e1d-e09d-5ccb-8bc2-b94743dd8328 | note | ASSESSOR - Mark Joblin / Nikhil Mishra
5606f513-65d1-5de2-b112-f5b725cf9411 | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (i.e. average & minimum MDD)
1efba472-a8d1-5986-b826-e5bfe4fd0f78 | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
| checkpoint | Construction STAB OLAY - Compaction
d7745610-1e1f-5935-bac3-8cbeba97b71c | note | VERIFICATION ACTIVITY - NDM – maximum dry density
74aac0af-a7b9-598a-b77e-1cd9111e27f6 | note | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
ec97c9ce-7d45-5bde-a013-683964858dd8 | note | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
26575a95-6804-5967-a4a8-594e00fb4eb6 | note | ACCEPTANCE CRITERIA - Subbase: Average ≥ 95% MDD, Minimum ≥ 92% MDD
10168371-1613-5452-a35d-b67419332b7a | note | TYPE - H
fe654f7e-d323-554d-9a18-5177e844570f | note | ASSESSOR - Mark Joblin / Nikhil Mishra
32834801-b38b-5cab-b34e-85729db997eb | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved (i.e. average & minimum MDD)
b920c100-0fc7-5d6d-a397-73859ae4771e | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Construction STAB OLAY - Degree of Saturation (DOS) (1)
dcad5471-ee8a-5b8d-8cbf-2d035dbe5112 | note | VERIFICATION ACTIVITY - DOS
abaea5de-6e81-5265-a24d-c607d88120b0 | note | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
ee2ec5f9-4893-5e13-b89b-cd0fd7ee4e80 | note | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
564ee3fd-9798-54a1-803d-6b38631f6f67 | note | ACCEPTANCE CRITERIA - DOS ≤ 80% from Solid Density and %W
f7f8d366-cfae-51b5-83cd-061375a1a14a | note | TYPE - V
87dc3934-d4c6-5990-a7ea-8be31e920d9e | note | ASSESSOR - Jack Lewis/Ian Symons/ Akhil Mohan
41bb503b-f604-5a54-8b03-f8f6ab443a2a | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
2a91c7d9-619d-5428-94ec-e0d15663aaf9 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Construction STAB OLAY - Degree of Saturation (DOS) (2)
6d485d2b-285e-51d2-a9fb-832bd2bda8f2 | note | VERIFICATION ACTIVITY - DOS
ab8777ff-64cb-5c54-89ff-90480f471ecc | note | METHODS OR REFERENCE - NZS 4407: 1991, Test 4.2.2. TNZ B/2: 2005
c408e497-3e4f-5f96-abcd-7d79849a2dfc | note | FREQ. - 5 tests per homogeneous lot of up to 1000m2 of laid pavement
dec3c6b0-9b08-5e33-8ecf-f701c5eca35d | note | ACCEPTANCE CRITERIA - DOS ≤ 80% from Solid Density and %W
44b32fea-174b-54f7-afe4-02f2c7fced7d | note | TYPE - H
766f1647-1675-57a5-a00d-c54dda5bb2b8 | note | ASSESSOR - Nikhil Mishraa
59704f6b-5d57-5750-a6e1-7ccd834dbf15 | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
9cf3c9e6-fe8f-56aa-b0a1-a9254e77a757 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Construction STAB OLAY - Particle Size Distribution
1f966cc1-515b-58c9-a7ef-bb76a701dede | note | VERIFICATION ACTIVITY - PSD
ba3a5e6f-1124-5fc0-a49c-059ae7b28ec6 | note | METHODS OR REFERENCE - NZS 4407:2015, Test 3.8.1
590a308c-e17e-557c-9e4f-93ba287960c4 | note | FREQ. - 1 tests per homogeneous lot of up to 1000m2 of laid pavement
ff4d78f2-75fc-5426-9498-def4f109e607 | note | ACCEPTANCE CRITERIA - comparison to the upper and lower limits of M/4 Specification
075db834-ceef-5d07-94ae-425d8d6d6855 | note | TYPE - H
13f56e88-aa74-5171-8857-a717121e6c50 | note | ASSESSOR - Jack Lewis/Ian Symons/Akhil Mohan
0a18bec4-a95f-51aa-a821-89776733a1d7 | note | RESPONSIBLE PERSON - Richard Taare
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Construction STAB OLAY - Unconfined Compressive Strength (UCS)
5ac849cf-e0d2-5aaa-8049-158dc90da596 | note | VERIFICATION ACTIVITY - UCS
0f8bdf9e-97e0-59ce-a940-25177b47741b | note | METHODS OR REFERENCE - NZS 4407:2015, Test 2.4.8.2a
798ee4b7-87d5-5116-a159-0f3677b1e215 | note | FREQ. - 1 tests per homogeneous lot of up to 1000m2 of laid pavement
ed6c8e05-ebd4-50ab-9a10-52ba8957a6fe | note | ACCEPTANCE CRITERIA - Test to confirm compressive strength obatined relative to pavement design
5577e47f-59f4-5890-882b-033cfebbddcd | note | TYPE - V
84b6c1e7-779b-50bf-9e9b-01335c768221 | note | ASSESSOR - Nikhil Mishra
27649546-2f73-5c30-a8ef-0b6e2b3250e6 | note | DESCRIPTION - UCS 1 - 2 lightly bound pavement, > 2 bound pavements
ae6bf880-2d3c-5169-9dd0-946628889594 | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Construction STAB OLAY - Surface shape/profile Layer thickness (1)
a612d0be-e5e1-5b6a-9756-ffbb7edcd793 | note | VERIFICATION ACTIVITY - TNZ B/2
a78daf89-96a6-591c-abc2-551f19501ee1 | note | METHODS OR REFERENCE - Visual inspection
0ce5e064-1bcb-54e6-8ec2-622fe94d2f2a | note | ○ Cut/fill tolerance check
2fbea148-5cfd-57e4-87aa-bb9f9cb61923 | note | ○ String records
1e6201c2-8056-5719-ba12-6b0b431cbeaa | note | ○ Straight edge
0a4cf94a-db55-582b-84f5-d7c2f0a85659 | note | FREQ. - 1 test per 20m
1b0cf3d6-8eb4-5233-9182-0a78e8c82c12 | note | ACCEPTANCE CRITERIA - ≤10mm variance from 3m straight edge.
ddcd8577-0b53-5a42-85dc-7426cccd371d | note | ○ Gradual deviations
90b00b5e-9f53-5e5b-8206-f7791bcbc615 | note | ○ No ponding if crossfall < 1%
35bd87ec-34f5-505d-a8af-263273fa2316 | note | TYPE - V
bd355384-e7e2-588a-83e1-0efabdc19a16 | note | ASSESSOR - Mark Joblin / Nikhil Mishra
e0a2853e-e0f2-5c9a-9427-d291ba0c7983 | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
| checkpoint | Construction STAB OLAY - Surface shape/profile Layer thickness (2)
4f6cddda-9c92-5411-9fb1-807eb5ea1575 | note | VERIFICATION ACTIVITY - TNZ B/2
cbac3f1f-7502-5c20-8902-d52f4210c888 | note | METHODS OR REFERENCE - Visual inspection
8ad833d8-f7fd-5e1b-bef8-bb4fb47451f3 | note | ○ Cut/fill tolerance check
e7a39996-d2c6-5401-9076-3803689fadfd | note | ○ String records
98c896ac-fdd5-5483-b3f3-5daba5026a8f | note | ○ Straight edge
c1e1ccfa-53d4-500c-9507-bc2c0e2bc7bf | note | FREQ. - 1 test per 20m
529c4c19-15a9-572f-be4f-63a80f37d270 | note | ACCEPTANCE CRITERIA - -5mm +15mm or ±5mm at lip of concrete channel
f16fb184-ce58-5502-997f-2a8cbca641de | note | TYPE - V
d5a2881f-1eba-5687-8ed9-9593f2c06b1d | note | ASSESSOR - Mark Joblin / Nikhil Mishra
cc0cf237-bf2f-52d9-b1ba-a959ed8321b0 | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
| checkpoint | Construction STAB OLAY - Tolerances: width unconstrained (1)
a0ff237e-8b69-5b26-b8e8-c51153ffbc73 | note | VERIFICATION ACTIVITY - TNZ B/2
13a80b74-08a5-5dc7-a914-b0235a33ecdb | note | METHODS OR REFERENCE - Confirm offset from lift pegs
ac22490e-8ac5-5426-9ef1-d0097e5de74c | note | FREQ. - 1 at every lift peg or per 180 m2
0042d77a-1e64-59e1-a29f-de96d65206ce | note | ACCEPTANCE CRITERIA - -20mm
ba050ec3-a94d-5a8d-996c-d052de5d0091 | note | TYPE - V
4612e31d-84e9-5d03-b878-9ea423e14cbd | note | ASSESSOR - Nikhil Mishra
54e74d42-5696-5b6a-8801-0990d1d75c43 | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Construction STAB OLAY - Tolerances: width unconstrained (2)
afaaf251-69fe-5f0f-ae09-25aacbba202a | note | VERIFICATION ACTIVITY - TNZ B/2
9e280de9-3827-5d74-ae6b-b59b2ee0f708 | note | METHODS OR REFERENCE - Confirm offset from lift pegs
7f7d7819-7103-508a-ab28-3a6b7990393c | note | FREQ. - 1 at every lift peg or per 180 m2
714ba7c4-c4a6-5c81-bcec-5f9b56e4f00d | note | ACCEPTANCE CRITERIA - +100mm
ee986690-7f94-5c5d-89aa-cbb72a01390d | note | TYPE - V
5d0f727c-1647-5c43-817a-ded085bd261a | note | ASSESSOR - Nikhil Mishra
f4ec9d89-e894-5021-a77b-b74c7dd925f6 | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Construction STAB OLAY - Tolerances: width constrained
ef1390c5-05f1-5cd5-9562-a06ac6ab1890 | note | VERIFICATION ACTIVITY - TNZ B/2
cb2d6548-687e-5e6f-a1a7-198ae94b4eb4 | note | METHODS OR REFERENCE - Stringline/lift pegs
30c1c461-b4dd-5c10-a383-7bd56fe61d9c | note | FREQ. - 1 at every lift peg or per 180 m2
bf5ed549-fe96-5329-ae64-e6023689312a | note | ACCEPTANCE CRITERIA - Zero
91eea469-abec-579e-827b-13119fc9b83e | note | TYPE - V
0d657151-6de8-57b2-a9f3-66f62787923c | note | ASSESSOR - Nikhil Mishra
29748a1e-a4df-5249-8b12-f02b7aa9d203 | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Construction STAB OLAY - Visual appearance
b08c8166-5453-5e23-ada5-7e50f1f91ec6 | note | VERIFICATION ACTIVITY - TNZ B/2
ad219005-bbe0-5ab8-bb56-e17ac40d140a | note | METHODS OR REFERENCE - Visual inspection after sweeping
d7aee1e8-0072-5d95-935c-e73934183238 | note | FREQ. - Immediately prior to sealing
3e74e5d2-e329-543b-9c54-55ba10b0cb22 | note | ACCEPTANCE CRITERIA - No loose material remaining, Photo as evidence
24f00321-970a-5bbb-b4b0-523be4bde01f | note | TYPE - H
59c76f3e-5ea2-5694-80d4-3ed4d60d3f3c | note | ASSESSOR - Nikhil Mishra
db4b958e-97ec-5428-95fc-0fbea1a65bd8 | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until passing results are achieved
1d750217-e979-5384-8446-85c34ec43c01 | note | RESPONSIBLE PERSON - Akhil Mohan
| signoff | AUTHORITY HOLDPOINT
| section | Shoulders
| checkpoint | Slope (1)
d204e538-db9d-5ee0-b695-705d6d06f1c1 | note | VERIFICATION ACTIVITY - Visual check
4e2a50d1-5e70-5e0f-bc31-f4b379e71ec7 | note | METHODS OR REFERENCE - Visual inspection with smart level
7fdc3631-cfb9-5b53-9a33-da51b89e74a1 | note | ACCEPTANCE CRITERIA - Slopes consistent
32053238-fe9d-5b4f-8600-f9412d55c7ef | note | TYPE - V
1fe7a9be-51fc-5b4e-97a3-fb134a2a12e5 | note | ASSESSOR - Nikhil Mishra
57dc3a1b-5b4d-53be-b65c-b954b83269a2 | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
115a71c2-02cf-5de0-a822-1d760536c304 | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Slope (2)
86756db4-366e-5901-80a6-70cac06f7b23 | note | VERIFICATION ACTIVITY - Visual check
61adc57a-2171-5b82-96f0-6c2b0738a152 | note | METHODS OR REFERENCE - Visual inspection with smart level
8be19fa4-c891-5e9b-94ed-d06376bb64d1 | note | ACCEPTANCE CRITERIA - Slopes consistent
31809dc0-1c02-56cc-bf1e-ca823dd0a585 | note | TYPE - H
84d68c4b-cef2-5a4e-956c-6721bdafb4c6 | note | ASSESSOR - Nikhil Mishra
dbc9281a-1c45-5ad1-8495-97e54be408fc | note | DESCRIPTION - Hold Point – no surfacing layer is to be applied until all necessary results are achieved
ed0dfa98-ee1c-5db6-943f-1d7e9a2b40ab | note | RESPONSIBLE PERSON - Akhil Mohan
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Compaction (1)
5bdd2cee-919f-598c-9a5c-4c70c7ca219b | note | VERIFICATION ACTIVITY - Visual check
817a0f01-b28c-512e-ad47-d0ee85144832 | note | METHODS OR REFERENCE - Drive over 4T, check wheel tracks
866a5713-07c2-5b01-8235-2c9ee44f5427 | note | FREQ. - All shoulders
7f29d627-efa8-5d4c-98a5-2848fd399cba | note | ACCEPTANCE CRITERIA - Vehicles can drive on shoulders without becoming stuck
fae7c429-b29e-5b5d-8ce5-5be1691a7d47 | note | TYPE - V
274954ce-50b3-5540-a684-0f63ebbdb180 | note | ASSESSOR - Nikhil Mishra
aa9abf60-53ee-5a1c-a4fa-ade124e24940 | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
4ca1ba4e-7f57-5ee1-8a3b-1ef20dac66be | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Compaction (2)
c0c9bd02-c56c-5089-a192-6175cf31839d | note | VERIFICATION ACTIVITY - Visual check
91b84a03-d067-59cd-b847-f3e5164525f9 | note | METHODS OR REFERENCE - Drive over 4T, check wheel tracks
21f6b32b-e4e7-5d2f-992e-a9619b0ed00d | note | FREQ. - All shoulders
471d1c43-bf58-550f-9ef5-da72c5472e7a | note | ACCEPTANCE CRITERIA - Driver operated rollers must not come within 1 m of the sloped shoulder > 1:5 slope
9fae68e3-fe15-54d1-b803-c4cd1de9f11f | note | TYPE - V
6d529b11-e95d-55e5-bfeb-2bb1ee44efae | note | ASSESSOR - Nikhil Mishra
ff6896ce-1777-59f3-925e-aae15c84f838 | note | DESCRIPTION - Hold Point – physical works cannot be completed until all necessary results are achieved
19b1c702-609b-572a-af6c-0bff9a4d42fd | note | RESPONSIBLE PERSON - Akhil Mohan
| section | Site Reinstatement / Clearance
| checkpoint | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (1)
1311239d-dbaa-5cd3-9a5a-66908f6a237f | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
741e721f-ad31-54bd-a4c3-d235c93258d0 | note | METHODS OR REFERENCE - Visual inspection
2fdc4815-9489-5f8a-890f-628fce926bf3 | note | FREQ. - All signs/markers
8640d971-0774-5506-84ea-8d21609c6aea | note | ACCEPTANCE CRITERIA - Replaced in same position, height etc.
ea1bb424-6e83-5278-8013-b6770201b05f | note | TYPE - V
90fdfeb7-7fa4-5866-98bd-8e690762401a | note | ASSESSOR - Nikhil Mishra
59a27f3c-7c89-5dc7-89d8-a1a03dd5ea6c | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
0beede57-9f5b-56e0-9879-f265037a8f6f | note | RESPONSIBLE PERSON - Akhil Mohan
| checkpoint | Traffic Services - Marker pegs/ Signs/Markings/RRPMs Replaced (2)
ca9cc2db-448c-5361-a1ff-d8235f431f4d | note | VERIFICATION ACTIVITY - TNZ C/20: 2003
d3ebdd92-a475-5d6a-8d77-d95ee2716c46 | note | METHODS OR REFERENCE - Visual inspection
2a52d951-449f-5a61-a761-4f22456c0f9a | note | FREQ. - All signs/markers
284d2bef-54e1-5cb5-8c41-35c7008ea321 | note | TYPE - H
2ba0af1e-059e-5acc-ae64-b9ea227d1b0c | note | ASSESSOR - Nikhil Mishra
28a6a59e-ff63-5dfb-9bff-8bb437b0d3ca | note | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
790cc0b0-93b2-55bb-a1c3-1fbf2933ba83 | note | RESPONSIBLE PERSON - Akhil Mohan
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Traffic Management Removed
445d740d-7403-519c-bc07-1568c52a2b39 | note | VERIFICATION ACTIVITY - Visual check
067f97c1-2cd9-5a37-8990-439739097873 | note | FREQ. - When safe, after all physical works completed
ab432493-36b5-578a-aea6-dd3eab4eb480 | note | ACCEPTANCE CRITERIA - All traffic management removed from site safely
78c7551b-bec0-5233-a7ab-8526877e514f | note | TYPE - W
59c28519-e03e-5012-9c28-7c5c1f5782eb | note | ASSESSOR - Nikhil Mishra
91ec3ac4-a996-5384-85f2-39982cda9d4b | note | DESCRIPTION - Hold Point – TMP cannot be removed until site Audited
02aa50e3-6d41-5ea6-a52b-6270b35fed3d | note | RESPONSIBLE PERSON - Richard Taare
| checkpoint | Site left clean & tidy
119ab9f0-7e53-558c-b266-59f6e2807c8e | note | VERIFICATION ACTIVITY - Visual check
93b0050a-3102-5070-b3c1-320ba335578e | note | FREQ. - After vacating site
8e96528a-867e-5e60-a129-0f3c31f47a1e | note | ACCEPTANCE CRITERIA - Stockpiles removed, EMP installed, Plant removed, clear litter
acb66779-76bb-50f3-b03f-525190da3375 | note | TYPE - H
bd3895f0-949e-50d3-a848-a4b1642ed198 | note | ASSESSOR - Mark Joblin / Nikhil Mishra
173ddec5-ab89-52ba-8b8a-f4b6e2a903ed | note | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra/ Richard Taare
| signoff | AUTHORITY HOLDPOINT
| section | As Built Records
| checkpoint | Collect asset data
d58559d8-76bd-56f0-8248-9f54b225ae18 | note | VERIFICATION ACTIVITY - SHDOM (SM050)
89eee573-510f-5788-aea3-b949ef0e4f66 | note | FREQ. - During construction
72fe0e0c-85a8-53b8-9d5d-ee3426c5685e | note | ACCEPTANCE CRITERIA - All relevant as built information collected.
0126f9d4-c392-5198-9388-39907cf87515 | note | TYPE - V
829a00dd-ed19-513f-add1-1d9e47a3cee0 | note | ASSESSOR - Nikhil Mishra
af825277-66ba-5471-9cd8-0ae3b70a48d0 | note | RESPONSIBLE PERSON - Nikhil Mishra
| checkpoint | Enter asset data into RAMM and/or register(s)
0b38db9e-a9be-518e-a462-48dc2b9c249f | note | VERIFICATION ACTIVITY - SHDOM (SM050)
9d3a7af0-9c2a-5783-8ad9-f5fb371e0b04 | note | METHODS OR REFERENCE - RAMM
b7c1579a-c086-5ebb-a002-f73fb54bf39a | note | FREQ. - At completion of work.
d661213e-fcee-531d-96a7-5b93044e25ce | note | ACCEPTANCE CRITERIA - All data entered into RAMM and/or register(s). Design Report & Drawings attached to RAMM site record as a media file.
3d6f71e6-cf81-5f2d-9884-afc1efaca473 | note | TYPE - H
4c2c933c-edaa-5434-bc08-2fa51804ec17 | note | DESCRIPTION - Hold Point – project cannot be closed until data entered.
3e88478e-605b-5048-b667-3f721f364537 | note | RESPONSIBLE PERSON - Paul Grant
| signoff | AUTHORITY HOLDPOINT