## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Drainage ITP | itp |  |  |  |  | Drainage ITP
section | Preliminary
checkpoint | Services (includes Traffic Count Loops and Traffic Signal Detector Loops)
label | VERIFICATION ACTIVITY - Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth)
label | METHODS OR REFERENCE - NZAUAG Guide to Working on the Road
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Zero service strikes
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No excavation is to be commenced until services are located and accounted for
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Cultural/Heritage Risk Assessment
label | VERIFICATION ACTIVITY - Notification
label | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Local iwi has been notified of intent to start work
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Where risk of cultural discovery
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
section | Set-out / Site preparation
checkpoint | Notification of intention to start work
label | VERIFICATION ACTIVITY - Notification
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Notification to stakeholders minimum 48 hrs before commencement, minimum 2 weeks notice for sensitive site (SWAMP)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Archaeological Risk
label | VERIFICATION ACTIVITY - Toolbox meeting
label | METHODS OR REFERENCE - NZTA Cultural & Heritage Risk Model
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Toolbox meeting held covering accidental discovery protocol
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No excavation is to be commenced until toolbox meeting is held
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Traffic Management - TMP
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - CoPTTM
label | FREQ. - CoPTTM
label | ACCEPTANCE CRITERIA - TMP checked and approved
label | ○ Plans approved
label | ○ Current CAR
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Traffic Management - Setup
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Traffic Management Plan
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Traffic management complies with TMP
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until necessary traffic management is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Filter Material
label | VERIFICATION ACTIVITY - Grading Test
label | METHODS OR REFERENCE - NZS 4402: Part 2:1986
label | FREQ. - Per stockpile/ Job
label | ACCEPTANCE CRITERIA - Filter material shall be clean, durable stone having a crushing resistance of not less than 100 kN when tested and comply with Grading limits
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Geotextile
label | VERIFICATION ACTIVITY - Verification
label | METHODS OR REFERENCE - NZTAF7
label | FREQ. - Per installation
label | ACCEPTANCE CRITERIA - Strength class B and filtration class 1
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Sediment Control
label | VERIFICATION ACTIVITY - Physical
label | METHODS OR REFERENCE - ESMP
label | FREQ. - Before Excavation Commences
label | ACCEPTANCE CRITERIA - Place silt fence, earth bund or other sediment contol device around area to protect nearby waterways
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until sediment control measure is in palce
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
section | Construction
checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (1)
label | VERIFICATION ACTIVITY - Slope Checks
label | METHODS OR REFERENCE - TNZ F/2 Section 3
label | FREQ. - Every 20 m of subsoil bedding layer
label | ACCEPTANCE CRITERIA - Levels to show that a minimum of 1:100 (1%) fall is being achieved using Rotating laser level, theodolite or other surveying device
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (2)
label | VERIFICATION ACTIVITY - Depth Checks
label | METHODS OR REFERENCE - TNZ F/2 Section 3 NZS 2566:1998
label | FREQ. - Every 20 m of excavated area
label | ACCEPTANCE CRITERIA - Minimum cover for flexible pipes - 750 mm unsealed roads, 600 mm sealed roads, 450 mm outside road carriageway
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (3)
label | VERIFICATION ACTIVITY - Depth Checks
label | FREQ. - Every 20 m of excavated area
label | ACCEPTANCE CRITERIA - Invert shall not be less than 800 mm below finished road level
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (4)
label | VERIFICATION ACTIVITY - Depth Checks
label | METHODS OR REFERENCE - TNZ F/2 Section 3
label | FREQ. - Every 20 m of excavated area
label | ACCEPTANCE CRITERIA - Trench shall have vertical sides at a minimum of 300 mm above the top of pipe
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation for culvert realignment Culvert No26 & No 27 (5)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Upon completion of excavation
label | ACCEPTANCE CRITERIA - Photograph excavation upon completion of thereof (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Bedding (1)
label | VERIFICATION ACTIVITY - Quantity Check
label | FREQ. - Every 20 m of Subsoil drain
label | ACCEPTANCE CRITERIA - Shall have a minimum of 50 mm filter material underneath the pipe
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Bedding (2)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Upon completion of bedding
label | ACCEPTANCE CRITERIA - Photograph bedding upon completion of thereof (evidence)
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Filter Material
label | VERIFICATION ACTIVITY - Quantity Check
label | METHODS OR REFERENCE - TNZ F/2 Section 6
label | FREQ. - Every 20 m of Subsoil drain
label | ACCEPTANCE CRITERIA - Filter material shall be placed to a minimum depth of 150 mm above the top of pipe, filter material shal be compacted in layers not exceeding 150 mm (see design)
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Backfill (1)
label | VERIFICATION ACTIVITY - Density
label | METHODS OR REFERENCE - ASTM D5874-95
label | FREQ. - 1 sample per 2m² lot or at least 5 samples
label | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>35 per 150mm layer
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Backfill (2)
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - None
label | FREQ. - None
label | ACCEPTANCE CRITERIA - Tie-in flush with adjacent road surface +20mm mound in middle of road crossing
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Backfill (3)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Take Photos
label | ACCEPTANCE CRITERIA - Photograph basecourse upon completion of thereof (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Existing Level Control for culvert realignment Culvert No26 & No 27
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - Physical survey check
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Survey and stake out lift pegs for existing inlet and outlet positions and elevations
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until existing pipe inlet and outlet position and elevation is recorded
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Work Space Restrictions
label | VERIFICATION ACTIVITY - Fencing
label | METHODS OR REFERENCE - As per existing
label | FREQ. - Where required
label | ACCEPTANCE CRITERIA - Open adequate section in existing fencing to allow for required work space where required, documented and signed permission must be received prior
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold Point - Documented and signed permission received prior
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pre-construction Photo Diary
label | VERIFICATION ACTIVITY - Site Diary, Photos
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Before work commences
label | ACCEPTANCE CRITERIA - Photographs the full extent of the work area / site
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No work is to be commenced until site photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP65 (1)
label | VERIFICATION ACTIVITY - Aggregate Grading
label | METHODS OR REFERENCE - NZS 4407 Test 3.8.1
label | FREQ. - 1 per 400m³
label | ACCEPTANCE CRITERIA - Grading in accordance with WSP Lab Gisborne Standard grading curve
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP65 (2)
label | VERIFICATION ACTIVITY - Crushing Resistance
label | METHODS OR REFERENCE - NZS 4407 test 3.10
label | FREQ. - 1 per 10,000m3 or per visual change
label | ACCEPTANCE CRITERIA - >130 kN
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP65 (3)
label | VERIFICATION ACTIVITY - Linear Shrinkage
label | METHODS OR REFERENCE - NZS 4402
label | FREQ. - 1 per 400m³
label | ACCEPTANCE CRITERIA - Linear Shrinkage to be <6% - Where LS is approaching 6% communicate to quarry staff about changing source rock
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP40 (1)
label | VERIFICATION ACTIVITY - Aggregate Grading
label | METHODS OR REFERENCE - NZS 4407 Test 3.8.1
label | FREQ. - 1 per 400m³
label | ACCEPTANCE CRITERIA - Max particle size ≤37.5mm. Not more than 57% by mass shall pass the 9.5mm sieve. Not more than 19% by mass shall pass the 0.6mm sieve
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP40 (2)
label | VERIFICATION ACTIVITY - Crushing Resistance
label | METHODS OR REFERENCE - NZS 4407 test 3.10
label | FREQ. - 1 per 10,000m3 or per visual change
label | ACCEPTANCE CRITERIA - under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced.
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP40 (3)
label | VERIFICATION ACTIVITY - Linear Shrinkage
label | METHODS OR REFERENCE - NZS 4402
label | FREQ. - 1 per 400m³
label | ACCEPTANCE CRITERIA - Linear Shrinkage to be <6% - Where LS is approaching 6% communicate to quarry staff about changing source rock
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Qarry Aggregate - AP40 (4)
label | VERIFICATION ACTIVITY - Cement Reactivity
label | METHODS OR REFERENCE - NZS 4407 Test 3.15
label | FREQ. - 3 per source, Sampling shall be carried out in accordance with NZS 4407:1991 Part 2
label | ACCEPTANCE CRITERIA - Set of 3 with all UCS >3 Mpa
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until proof of compliance is in place
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Excavation (1)
label | VERIFICATION ACTIVITY - Quantity Checks
label | FREQ. - Per site
label | ACCEPTANCE CRITERIA - Earth works must not exceed 10 m3
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - Earth works must not exceed 10 m3
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Excavation (2)
label | VERIFICATION ACTIVITY - Deep Excavation Safety Measures ( >1m)
label | METHODS OR REFERENCE - CoPSESF
label | FREQ. - Every excavation >1.0 m in depth
label | ACCEPTANCE CRITERIA - Excavation checked and approved, Excavations exceeding 1m in depth to be benched
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No persons may enter the trench until it is adequately benched and deemed to be safe as per the Safety in Exccavations and Shafts for Foundatons
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Excavation (3)
label | VERIFICATION ACTIVITY - Unsuitable Foundation
label | METHODS OR REFERENCE - TNZ F3 Section 3.5
label | FREQ. - Every 5 m of excavated area
label | ACCEPTANCE CRITERIA - Unsuitable foundation material shall be removed to a minimum depth of 600 mm within carriageway and replaced with suitable material and compacted in 150 mm layers.
label | TYPE - V
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Unsuitable foundation (very soft = scala < 3 blows/100 mm or expandable clays, irregular or fragmented rock and saturated soils)
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation (4)
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - None
label | FREQ. - Every 1m along length of culvert
label | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -25mm + 5mm
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation (5)
label | VERIFICATION ACTIVITY - Level Marks
label | METHODS OR REFERENCE - None
label | FREQ. - 3 locations along one side of excavated trench
label | ACCEPTANCE CRITERIA - Layer depth markings visible on photo diary.
label | TYPE - V
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until white/yellow spray paint markings indicating backfill material layers are visible on one side of trench for photo record
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Excavation (6)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Physical / Visual check
label | FREQ. - Before removal of unsuitable material
label | ACCEPTANCE CRITERIA - Photograph unsuitable foundation material prior to removal of material (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Bedding (1)
label | VERIFICATION ACTIVITY - Bedding Material
label | METHODS OR REFERENCE - TNZ F3 Section 3.6, AS/NZS 3725:2007
label | FREQ. - Per Site
label | ACCEPTANCE CRITERIA - All bedding material shall satisfy the requirements in AS/NZS 3725:2007 and AS/NZS 2566
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Bedding (2)
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - None
label | FREQ. - Every 1m along length of culvert
label | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Bedding (3)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Physical / Visual check
label | FREQ. - Before pipe installation
label | ACCEPTANCE CRITERIA - Photograph bedding material after placement and compaction (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Pipe Installation
label | VERIFICATION ACTIVITY - Inspection
label | METHODS OR REFERENCE - Physical / Visual check
label | FREQ. - Before pipe Jointing
label | ACCEPTANCE CRITERIA - Verify culvert alignment (straightness)
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Jointing (1)
label | VERIFICATION ACTIVITY - Visual/Physical
label | METHODS OR REFERENCE - Physical / Visual check
label | FREQ. - Per Join
label | ACCEPTANCE CRITERIA - All joins must be watertight and present a smooth invert surface
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Jointing (2)
label | VERIFICATION ACTIVITY - Mortar
label | METHODS OR REFERENCE - TNZ F3 Section 2.4 NZS 3103: 1990
label | FREQ. - Per Bag
label | ACCEPTANCE CRITERIA - Mortar shall comply with NZS 3103: 1990
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Jointing (3)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Physical / Visual check
label | FREQ. - Before Backfilling
label | ACCEPTANCE CRITERIA - Photograph pipe and joins after installation (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Backfilling (Layers of 150mm) (1)
label | VERIFICATION ACTIVITY - Fill Material
label | METHODS OR REFERENCE - TNZ F3 section 6.3
label | FREQ. - Per Stockpile
label | ACCEPTANCE CRITERIA - Any material that is not type W or type U defined in TNZ F1:1997
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Backfilling (Layers of 150mm) (2)
label | VERIFICATION ACTIVITY - Density
label | METHODS OR REFERENCE - ASTM D5874-95
label | FREQ. - 1 sample per 5m² lot or at least 5 samples
label | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>25 per 150mm layer
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Backfilling (Layers of 150mm) (3)
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - None
label | FREQ. - Every 1m along length of culvert
label | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Backfilling (Layers of 150mm) (4)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Before placing sub base
label | ACCEPTANCE CRITERIA - Photograph backfilling after installation of each 150mm layer (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Sub base - AP65 (1)
label | VERIFICATION ACTIVITY - Density
label | METHODS OR REFERENCE - ASTM D5874-95
label | FREQ. - 1 sample per 5m² lot or at least 5 samples
label | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>32 per 150mm layer
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Sub base - AP65 (2)
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - None
label | FREQ. - Every 1m along length of culvert
label | ACCEPTANCE CRITERIA - String line between existing inlet and outlet invert elevations with tolerance -15mm + 5mm
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Sub base - AP65 (3)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Before placing base
label | ACCEPTANCE CRITERIA - Photograph sub base after installation of each layer (evidence)
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point - No physical works are to be commenced until photos are taken
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Basecourse - AP40 (1)
label | VERIFICATION ACTIVITY - Density
label | METHODS OR REFERENCE - ASTM D5874-95
label | FREQ. - 1 sample per 2m² lot or at least 5 samples
label | ACCEPTANCE CRITERIA - Compaction requirements using the Clegg Impact Hammer tests CIV>35 per 150mm layer
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Basecourse - AP40 (2)
label | VERIFICATION ACTIVITY - Level Control
label | METHODS OR REFERENCE - None
label | FREQ. - None
label | ACCEPTANCE CRITERIA - Tie-in flush with adjacent road surface +20mm mound in middle of road crossing
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Basecourse - AP40 (3)
label | VERIFICATION ACTIVITY - Site Diary, Photos/ inspections
label | METHODS OR REFERENCE - Take Photos
label | FREQ. - Upon completion of basecoarse
label | ACCEPTANCE CRITERIA - Photograph basecourse upon completion of thereof (evidence)
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Ancillary Concrete - Head/wing wall
label | VERIFICATION ACTIVITY - Visual/Physical
label | METHODS OR REFERENCE - NZS 3114:1987
label | FREQ. - Per Structure
label | ACCEPTANCE CRITERIA - All concrete faces should comply with NZS 3114:1987 and NZS 3101: Part 1: 2006
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Ancillary Concrete - Concrete cover
label | VERIFICATION ACTIVITY - Visual/Physical
label | METHODS OR REFERENCE - NZS 3114:1987
label | FREQ. - Per Structure
label | ACCEPTANCE CRITERIA - All reinforcing bar/mesh shall have a minimum of 40 mm cover
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Rip Rap
label | VERIFICATION ACTIVITY - Visual/Physical
label | FREQ. - Per structure
label | ACCEPTANCE CRITERIA - 200 mm Rip Rap located to provide scour protection at Inlet (1 m wide x 2 m long x 0.4 m deep) with A19 Geotextile
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Sandbag Structure, At culvert 26
label | VERIFICATION ACTIVITY - Headwall/wingwall
label | METHODS OR REFERENCE - Visual/Physical
label | ACCEPTANCE CRITERIA - Per Structure
label | TYPE - Install sandbag headwall at inlet
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
section | Site Reinstatement / Clearance
checkpoint | Clean Culvert No26 & No27
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - Along openned sections
label | ACCEPTANCE CRITERIA - Remove all debris from within culvert
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Drainage, if applicabe
label | VERIFICATION ACTIVITY - Table Drains
label | METHODS OR REFERENCE - As per existing
label | FREQ. - Where required
label | ACCEPTANCE CRITERIA - Clean andgrade table drains as required upstream of culvert inlets
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Traffic Services - Marker pegs/Signs/Markings/RRPMs Replaced
label | VERIFICATION ACTIVITY - TNZ C/20: 2003
label | METHODS OR REFERENCE - Visual inspection
label | FREQ. - All
label | ACCEPTANCE CRITERIA - Replaced in same position, height etc
label | TYPE - V
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Grassing
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - All areas requiring grassing
label | ACCEPTANCE CRITERIA - Grassing has been done where required
label | TYPE - W
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Drainage
label | VERIFICATION ACTIVITY - Table Drains
label | METHODS OR REFERENCE - As per existing
label | FREQ. - Where required
label | ACCEPTANCE CRITERIA - Regrade table drains as required upstream of culvert inlets (minimum 30 m either side)
label | TYPE - V
label | ASSESSOR - Richard Taare
checkpoint | Reinstate seal
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - Per worksite
label | ACCEPTANCE CRITERIA - Seal reapired where it has been damged or removed
label | TYPE - H
label | ASSESSOR - Richard Taare
label | DESCRIPTION - Hold Point - TM to remain until surface has been sealed
label | RESPONSIBLE PERSON - Pat Thompson
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Traffic Management Removed
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - When safe, after all physical works completed
label | ACCEPTANCE CRITERIA - All traffic management removed from site safely
label | TYPE - W
label | DESCRIPTION - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson
checkpoint | Site left clean & tidy
label | VERIFICATION ACTIVITY - Visual check
label | FREQ. - After vacating site
label | ACCEPTANCE CRITERIA - Plant removed, Litter cleared from site
label | TYPE - V
label | ASSESSOR - Richard Taare
label | RESPONSIBLE PERSON - Pat Thompson