## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Sealing ITP | itp |  |  |  |  | Sealing ITP
section | Seal Design
checkpoint | Surfacing design
label | VERIFICATION ACTIVITY - Request for surfacing
label | METHODS OR REFERENCE - Appendix 15 of contract specific MMP
label | FREQ. - Each surfacing establishment
label | ACCEPTANCE CRITERIA - Quantity, location, bitumen grade, diluents', target application rate, chip grade, asphalt type, asphalt depth.
label | TYPE - H
label | DESCRIPTION - Hold point - No work is to commence until designs have been provided
label | RESPONSIBLE PERSON - Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Preparation for surfacing
label | VERIFICATION ACTIVITY - Visual check
label | METHODS OR REFERENCE - Inspection/ Downer Survey
label | FREQ. - Each surfacing establishment
label | ACCEPTANCE CRITERIA - Shape, ride, surface, saturation, (Client, Foreman and Site Engineer must sign QA form provided)
label | TYPE - H
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | DESCRIPTION - Hold point - No work is to commence until inspection of pavement base layer has been inspected and logged via Downer Survey
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
section | Chip Sealing
checkpoint | Plant
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - Documentation
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Each vehicle to produce - Warrant of Fitness, Driver eligibility and calibration of machinery
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No sealing is to commence until weather has been confirmed safe to seal
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Weather
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - SIS
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Check SIS prior to sealing
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No sealing is to commence until weather has been confirmed safe to seal
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Spray Bar Check
label | VERIFICATION ACTIVITY - Overlap Test
label | METHODS OR REFERENCE - RQP 17.3
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Ensure no overlap or gaps between bitumen from sprayers
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No sealing is to commence until weather has been confirmed safe to seal
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Application rate of binder
label | VERIFICATION ACTIVITY - Insitu
label | METHODS OR REFERENCE - NZTA P/17 or Chipsealing in New Zealand NZTA (NZTA 2005)
label | FREQ. - As required by the design
label | ACCEPTANCE CRITERIA - Application rate within tolerance of the seal design spray rate. Longitudinal overlap of spray runs as per design.
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Aggregate - Quality
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/6
label | FREQ. - 1 / 500m³
label | ACCEPTANCE CRITERIA - Shape, size, cleanliness
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Aggregate - Skid Resistance
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/6, NZTA T10
label | FREQ. - 1 / 1000m³
label | ACCEPTANCE CRITERIA - Refer to NZTA T10 requirements
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Aggregate - Crushing Resistance
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/6, NZS 4407 Test 3.10
label | FREQ. - 1 / 1000m³
label | ACCEPTANCE CRITERIA - 10% fines under 230 kN load
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Aggregate - Weathering Resistance
label | VERIFICATION ACTIVITY - Lab Test
label | METHODS OR REFERENCE - NZTA M/6, NZS 4407 Test 3.11
label | FREQ. - 1 / 1000m³
label | ACCEPTANCE CRITERIA - Shall have a quality index of AA or BA
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Rolling (1)
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - NZTA P/3
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Ensure chip has good contact with binder in all areas not just in wheel path
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Rolling (2)
label | VERIFICATION ACTIVITY - Plant
label | METHODS OR REFERENCE - RQP
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Pneumatic Tyre Roller (PTR) is to be used to roll sealed surface
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Rolling (3)
label | VERIFICATION ACTIVITY - Time
label | METHODS OR REFERENCE - NZTA P/3 Section 22
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Calculate required rolling time as per equation in section 22
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Post construction seal protection / Seal life
label | VERIFICATION ACTIVITY - Physical
label | METHODS OR REFERENCE - Chipsealing in New Zealand NZTA (NZTA 2005)
label | FREQ. - Each site
label | ACCEPTANCE CRITERIA - Extended rolling time and/or provide positive traffic management to assist compaction, chip embedment and to avoid early stripping
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
section | Disestablishment
checkpoint | Removal of surplus chip
label | VERIFICATION ACTIVITY - Visual
label | FREQ. - Within 48 hours of rolling the site
label | ACCEPTANCE CRITERIA - Not more than 20 loose chip within any 2m2
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Pavement marking (1)
label | VERIFICATION ACTIVITY - Request for roadmarking
label | FREQ. - Within 48 hours of rolling the site
label | ACCEPTANCE CRITERIA - Request made when item programmed
label | TYPE - V
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | Pavement marking (2)
label | VERIFICATION ACTIVITY - Visual
label | FREQ. - Within 48 hours of rolling the site
label | ACCEPTANCE CRITERIA - Markings follow tabs or new markings installed according to MOTSAM
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
checkpoint | TMP
label | VERIFICATION ACTIVITY - Visual
label | METHODS OR REFERENCE - CoPTTM
label | FREQ. - Within 48 hours of rolling the site
label | ACCEPTANCE CRITERIA - Traffic control in place to protect new surface and removed following sweeping and pavement marking
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - No TM is to be removed until linemarking has been completed
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
section | Quality Assurance
checkpoint | Site Recording
label | VERIFICATION ACTIVITY - Visual
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - Video evidence of site (seal finish) once it has been swept
label | TYPE - H
label | ASSESSOR - Nikhil Mishra
label | DESCRIPTION - Hold point - Failures within seal surface must be rectified before site can be confirmed complete
label | RESPONSIBLE PERSON - Akhil Mohan /Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Post seal Inspection
label | VERIFICATION ACTIVITY - Inspection
label | METHODS OR REFERENCE - Downer Survey
label | FREQ. - Each Site
label | ACCEPTANCE CRITERIA - NZTA representative is satisfied with finished pavement surface, photograhic evidence shall be supplied if client is unable to attend. Inspection to be logged via Downer Survey
label | TYPE - H
label | ASSESSOR - Mark Joblin / Nikhil Mishra
label | DESCRIPTION - Hold point - Client must have opportunity to be present on site to complete inspection of finished surface.
label | RESPONSIBLE PERSON - Mark Joblin / Nikhil Mishra
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Measurement check
label | VERIFICATION ACTIVITY - Physical
label | METHODS OR REFERENCE - Check and measure site and confirm on as-built
label | FREQ. - Each site
label | ACCEPTANCE CRITERIA - Once site has been completed and checked as as-built will be uploaded into RAMM Contractor
label | TYPE - W
label | ASSESSOR - Nikhil Mishra
label | RESPONSIBLE PERSON - Akhil Mohan