## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | W25 Wiri RAP Interface ITP | itp |  |  |  |  | W25 Wiri RAP Interface ITP
section | Details
checkpoint | 1 - Issued For Construction Drawings
label | SPECIFICATION REFERENCE: IFC Drawings Issued by Client/Engineer
label | ACCEPTANCE CRITERIA: Issued For Construction Drawings Available
label | DATE/SIGN: Contractor Rep - H
holdpoint | HOLD POINT
checkpoint | 2 - Underground Services Confirmation
label | SPECIFICATION REFERENCE: CTS Permit to Work
label | ACCEPTANCE CRITERIA: Underground Services Drawings to accompany permit and marked out onsite where excavation is to be undertaken
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 3 - Survey & Setout
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Spec
label | ○ CTS Excavation Works Spec
label | ACCEPTANCE CRITERIA: Foundations and embedded items shall be setout following the tolerances, heights and positions shown in each foundations respective drawing.
label | DATE/SIGN: Contractor Rep - P
checkpoint | 4 - Waste Management & Disposal
label | SPECIFICATION REFERENCE: CTS General Civil Construction Spec
label | ○ CTS Excavation Works Spec
label | ○ CTS Contaminated Environmental Ground Soil Managenet Plan RW-231
label | ACCEPTANCE CRITERIA: Waste management plan prepared and followed. Supporting documents available on request
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 5A - Demolition
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Existing pedestal removed at ground level
label | ○ Concrete removed to approved landfill
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 5B - Position of Pump Pedestal Setout
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Setout as per IFC Drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 5C - Pump pedestal location Cleaned & Scabbled
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 5D - Cast in Items - Bolts & Nuts
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ CTS Epoxy Grouting of Anchor Bolts
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
label | ○ Drilled holes for Anchors shall be inspected
label | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 5E - Formwork, Reinforcing & Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ NZS3109/3112
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
label | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
label | ○ All reinforcing and formwork to comply with IFC drawings
label | ○ Concrete to be min 30MPa at 28 days
label | ○ Testing of concrete per CTS Specifications
label | ○ Prepour Inspection Record Filled out Prior to Concrete
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 5F - Grouting of Baseplate
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ Manufacturers Documentation
label | ACCEPTANCE CRITERIA: Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - W
checkpoint | 6A - Demolition
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Existing pedestal removed at ground level
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 6B - Position of Pump Pedestal Setout
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Setout as per drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 6C - Pump Pedestal Location Cleaned & Scabbled
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 6D - Cast in Items - Bolts & Nuts
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ CTS Epoxy Grouting of Anchor Bolts
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
label | ○ Drilled holes for Anchors shall be inspected
label | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 6E - Formwork, Reinforcing & Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ NZS3109/3112
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
label | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
label | ○ All reinforcing and formwork to comply with IFC drawings
label | ○ Concrete to be min 30MPa at 28 days
label | ○ Testing of concrete per CTS Specifications
label | ○ Prepour Inspection Record Filled out Prior to Concrete
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 6F - Grouting of Baseplate
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ Manufacturers Documentation
label | ACCEPTANCE CRITERIA: Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - W
checkpoint | 7A - Setout of Pipe Sleeper
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Comply with setout in drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 7B - Excavation & Foundation Preparation inc Site Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS Excavation Works Specification
label | ○ CTS General Civil Construction Specification
label | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
label | ○ Foundation compaction Inspection Record completed
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - W
checkpoint | 7C - Formwork, Reinforcing & Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ NZS3109/3112
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
label | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
label | ○ All reinforcing and formwork to comply with IFC drawings
label | ○ Concrete to be min 30MPa at 28 days
label | ○ Testing of concrete per CTS Specifications
label | ○ Prepour Inspection Record Filled out Prior to Concrete
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 8A - Position of Pump Pedestal Setout
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Setout as per drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 8B - Excavation & Foundation Preparation inc Site Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS Excavation Works Specification
label | ○ CTS General Civil Construction Specification
label | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
label | ○ Foundation compaction Inspection Record completed
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - W
checkpoint | 8C - Formwork, Reinforcing & Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ NZS3109/3112
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
label | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
label | ○ All reinforcing and formwork to comply with IFC drawings
label | ○ Concrete to be min 30MPa at 28 days
label | ○ Testing of concrete per CTS Specifications
label | ○ Prepour Inspection Record Filled out Prior to Concrete
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 9A - Position of Slab Extension Setout
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Setout as per drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 9B - Excavation & Foundation Preparation inc Site Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS Excavation Works Specification
label | ○ CTS General Civil Construction Specification
label | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
label | ○ Foundation compaction Inspection Record completed
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - W
checkpoint | 9C - Formwork, Reinforcing & Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ NZS3109/3112
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
label | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
label | ○ All reinforcing and formwork to comply with IFC drawings
label | ○ Concrete to be min 30MPa at 28 days
label | ○ Testing of concrete per CTS Specifications
label | ○ Prepour Inspection Record Filled out Prior to Concrete
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 10A - Position of Slab Extension Setout
label | SPECIFICATION REFERENCE: IFC Drawings
label | ACCEPTANCE CRITERIA: Setout as per drawings
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - R
checkpoint | 10B - Excavation & Foundation Preparation inc Site Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS Excavation Works Specification
label | ○ CTS General Civil Construction Specification
label | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
label | ○ Foundation compaction Inspection Record completed
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - W
checkpoint | 10C - Formwork, Reinforcing & Concrete
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ NZS3109/3112
label | ○ Manufacturers Documentation
label | ○ Inspection Records
label | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
label | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
label | ○ All reinforcing and formwork to comply with IFC drawings
label | ○ Concrete to be min 30MPa at 28 days
label | ○ Testing of concrete per CTS Specifications
label | ○ Prepour Inspection Record Filled out Prior to Concrete
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 11 - Complete final Civil Inspection and close off ITP
label | SPECIFICATION REFERENCE: IFC Drawings
label | ○ CTS General Civil Construction Specification
label | ○ Manufacturers Specification
label | ACCEPTANCE CRITERIA: ITP/QC has been completed; all steps & hold points signed byrelevant party.
label | ○ All work completed as per work pack, and any field instructions issued during construction compiled
label | DATE/SIGN: Contractor Rep - P
label | ○ CTS Civil Inspector - H
holdpoint | HOLD POINT
checkpoint | 12 - Non-Conformance Reporting
label | SPECIFICATION REFERENCE: UCC Internal NCR and or Lucidity event NCR
label | ○ QC Requirements for Civil Works
label | ACCEPTANCE CRITERIA: All Non-Conformance reports and Investigations are attached and closed out
label | DATE/SIGN: Contractor Rep - R
checkpoint | 13 - As Built & Final Design Documentation
label | ACCEPTANCE CRITERIA: Confirmation From Engineer on as built records & redline mark ups
label | DATE/SIGN: Contractor Rep - P
checkpoint | 14 - Reference Info, Specifications
label | ACCEPTANCE CRITERIA: All Reference Information and relevant Product Specifications
label | DATE/SIGN:
checkpoint | 15 - Punch Listing
label | SPECIFICATION REFERENCE: CTS QC Requirments for Civil Work
label | ACCEPTANCE CRITERIA: All punch list items are closed out in the relevant timeframe to the required standard
label | DATE/SIGN: Contractor Rep - P
label | ○ Project/Construction Engineer - R
checkpoint | 16 - Compilation of ITP
label | ACCEPTANCE CRITERIA: ITP Completed and Signed off
label | DATE/SIGN: Contractor Rep - H
label | ○ Project/Construction Engineer - H
holdpoint | HOLD POINT