## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ZENT-ITP-7016 - ITP - Civil - Bench | itp |  |  |  |  | ZENT-ITP-7016 - ITP - Civil - Bench
section | SECTION 1 - GENERAL
checkpoint | General
label | ITP Template No.: ZENT-ITP-7016
label | Revision: 0
label | Prepared By: S.Stegic
label | Prepared Date: 17/10/2023
label | Discipline: Civil
label | Component: Benches
section | SECTION 2 - CLOSE OUT SIGNATURE (ZENVIRON ONLY)
checkpoint | Close Out Signature
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature:
section | SECTION 4 - PRELIMINARY
checkpoint | 4.1 - Design drawings, project specifications
note | ACCEPTANCE CRITERIA: Documents controlled through document management system.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 4.2 - Survey and Setout
note | ACCEPTANCE CRITERIA: Control point survey by registered surveyor. Visual inspection of control point/s. Survey equipment spot checked for calibration.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 5 - MATERIAL APPROVALS
checkpoint | 5.1 - Subgrade Material Conformance - Import Fill
note | ACCEPTANCE CRITERIA: ZX118-REP-0201 Earthworks, Roads and Drainage Specification, Section XXXX ;
note | VERIFYING DOCUMENT: NATA Test Reports
note | SUPERVISION TYPE: REVIEW
checkpoint | 5.2 - Pavement Base Course Material Conformance
note | ACCEPTANCE CRITERIA: ZX115-REP-0201 Earthworks, Roads and Drainage Specification;
note | ○ Particle Size Distribution
note | ○ CBR
note | ○ Atterberg Limits
note | ○ Wet/Dry Strength Variation
note | VERIFYING DOCUMENT: NATA Test Reports
note | SUPERVISION TYPE: REVIEW
section | SECTION 6 - CONSTRUCTION PROCESS - BENCH STRIP SOIL
checkpoint | 6.1 - Clear and Grub
note | ACCEPTANCE CRITERIA: Area cleared of all refuse, artificial and deleterious materials. Consult with landowner prior to removing any fencing or gates. Ensure CEMP is adhered to.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 6.2 - Topsoil Stripping
note | ACCEPTANCE CRITERIA: Strip topsoil to a depth required to remove all topsoil from the footprint area. Ensure the area is self draining Ensure CEMP is adhered to.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 7 - CONSTRUCTION PROCESS - BENCH SUBGRADE AND CONDITIONING
checkpoint | 7.1 - Earthworks Foundation
note | ACCEPTANCE CRITERIA: Test results on founding layer compliant to ZX118-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Conforming DCP Results to designer approval
note | VERIFYING DOCUMENT: ZX118-ITR-7103 - ITR
note | ○ DCP Field Data Result - If applicable Include; Location plan of soft, wet or unsuitable materialand the applied replacement methodology.
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Structural Fill/ Rock Fill Embankment (Where Required)
note | ACCEPTANCE CRITERIA: Test results and/ or proof roll records obtained for the fill layers compliant to ZX118-REP-0201 Earthworks, Roads and Drainage Specification, Section XXXX
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report ZX118-ITR-7108 - Proof Roll Inspection per tested layer
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - Rock Subgrade (Where Required)
note | ACCEPTANCE CRITERIA: Proof roll records obtained Inspection by Geotechnical/ Design Engineer
note | VERIFYING DOCUMENT: ZX118-ITR-7108 - Proof Roll Inspection
note | ○ If applicable Include; Location plan of soft, wet or unsuitable material and the applied replacement
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.5 - Finished Subgrade
note | ACCEPTANCE CRITERIA: Test results and proof roll records obtained for the finished layer compliant to ZX118- REP-0201 Earthworks, Roads and Drainage Specification, Section XXXX
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report ZX118-ITR-7108 - Proof Roll Inspection Geotechnical Testing Register - Specifying number of layers and testing compliance to Specification
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 8 - CONSTRUCTION PROCESS - BENCH BASE COURSE PLACEMENT
checkpoint | 8.1 - Base Course Pavement Placement
note | ACCEPTANCE CRITERIA: Material placement compliance test results in accordance with ZX118-REP-0201 Earthworks, Roads and Drainage Specification, Section XXXX
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | ○ Plate Load
note | VERIFYING DOCUMENT: NATA Test Report ZX118-ITR-7108 - Proof Roll Inspection
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 9 - CONSTRUCTION PROCESS - LONGITUDINAL DRAINAGE
checkpoint | 9.1 - Excavation
note | ACCEPTANCE CRITERIA: Finished levels as required in IFC Model
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 9.2 - Erosion Controls
note | ACCEPTANCE CRITERIA: Visual Inspection of scour protection for compliance to Erosion and Sediment Control Drawing ZX118-DWG-1001
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 10 - COMPLETION AND HANDOVER
checkpoint | 10.2 - Redline markup of Construction Drawings
note | ACCEPTANCE CRITERIA: In line with ZX118-REP-0201 Earthworks, Roads and Drainage Specification and BMS- WIN-1024 - Document Red-Line Markup
note | VERIFYING DOCUMENT: Redline Markup in Master Drawing Folder
note | SUPERVISION TYPE: REVIEW
checkpoint | 10.3 - Generate Punch List
note | ACCEPTANCE CRITERIA: Generate specific area/scope Punch List and transfer the open items to the Punch List Master Register
note | VERIFYING DOCUMENT: BMS-TMP-0044 Punch List record
note | SUPERVISION TYPE: REVIEW
checklist | ZENT-ITP-7022 - ITP - Civil - Hardstand Stage 1 (Hardstand and Auxiliary Pads) | itp |  |  |  |  | ZENT-ITP-7022 - ITP - Civil - Hardstand Stage 1 (Hardstand and Auxiliary Pads)
section | SECTION 1 - GENERAL
checkpoint | General
label | ITP Template No.: ZENT-ITP-7022
label | Revision: 0
label | Prepared By: Lachlam A.
label | Prepared Date: 21/11/2023
label | Discipline: Civil
label | Component: ITP - Civil - Hardstand Stage 1
section | SECTION 2 - CLOSE OUT SIGNATURE (ZENVIRON ONLY)
checkpoint | Close Out Signature
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature:
section | SECTION 4 - PRELIMINARY
checkpoint | 4.1 - Design drawings, project specifications.
note | ACCEPTANCE CRITERIA: Documents controlled through document management system.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 4.2 - Survey and Setout
note | ACCEPTANCE CRITERIA: Control point survey by registered surveyor. Visual inspection of control point/s. Survey equipment spot checked for calibration.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 4.3 - Orientation and Layout
note | ACCEPTANCE CRITERIA: Confirm the survey setout aligns with the hardstand typical arrangement proposed for the turbine.
textbox | Hardstand Layout for WTG-
textbox | is
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: REVIEW
section | SECTION 5 - MATERIAL APPROVALS
checkpoint | 5.1 - Pavement Base Course Material Conformance
note | ACCEPTANCE CRITERIA: ZX115-REP-0201 Earthworks, Roads and Drainage Specification;
note | ○ Particle Size Distribution
note | ○ CBR
note | ○ Atterberg Limits
note | ○ Wet/Dry Strength Variation
note | VERIFYING DOCUMENT: NATA Test Reports
note | SUPERVISION TYPE: REVIEW
section | SECTION 6 - CONSTRUCTION PROCESS - HARDSTAND AND AUXILARY STRIP SOIL
checkpoint | 6.1 - Clear and Grub
note | ACCEPTANCE CRITERIA: Area cleared of all refuse, artificial and deleterious materials. Consult with landowner prior to removing any fencing or gates. Ensure CHMP & EMP are adhered to.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 6.2 - Topsoil Stripping
note | ACCEPTANCE CRITERIA: Strip topsoil to a depth required to remove all topsoil from the footprint area. Ensure the area is self draining Ensure CHMP & EMP are adhered too Stockpiles are suitably managed.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 6.3 - Temporary ERSED Controls
note | ACCEPTANCE CRITERIA: Protection measures in line with ZX115-REP- 0201 Earthworks, Roads and Drainage Specification and Typical Drawings. Ensure CHMP & EMP are adhered to.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 7 - CONSTRUCTION PROCESS - HARDSTAND SUBGRADE AND CONDITIONING
checkpoint | 7.1 - Earthworks Foundation
note | ACCEPTANCE CRITERIA: Test results obtained from the founding layer compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ DCP
note | VERIFYING DOCUMENT: DCP Field Results Loctaion plan of soft, wet or unsuitable material including replacement methodology.
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Structural Fill/ Rock Fill Embankment (Where Required)
note | ACCEPTANCE CRITERIA: Test results and/ or proof roll records obtained for the fill layers compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report (Where Required) ZX115-ITR-7108 - Proof Roll
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - Rock Subgrade (Where Required)
note | ACCEPTANCE CRITERIA: Proof roll records obtained Inspection by Geotechnical/ Design Engineer
note | VERIFYING DOCUMENT: ZX115-ITR-7108 - Proof Roll Loctaion plan of rock sungrade material where pavement thickness has been reduced.
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 - Finished Subgrade
note | ACCEPTANCE CRITERIA: Test results and proof roll records obtained for the finished layer compliant to ZX115- REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report ZX115-ITR-7108 - Proof Roll
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 8 - CONSTRUCTION PROCESS - HARDSTAND BASE COURSE PLACEMENT
checkpoint | 8.1 - Base Pavement
note | ACCEPTANCE CRITERIA: Test results and proof roll records obtained for the finished layer compliant to ZX115- REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | ○ Plate Load
note | VERIFYING DOCUMENT: NATA Test Report Plate Load Test Results ZX115-ITR-7108 - Proof Roll Inspection
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 9 - CONSTRUCTION PROCESS - AUXILARY PADS SUBGRADE AND CONDITIONING
checkpoint | 9.1 - Earthworks Foundation
note | ACCEPTANCE CRITERIA: Test results obtained from the founding layer compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ DCP
note | VERIFYING DOCUMENT: DCP Field Results Loctaion plan of soft, wet or unsuitable material including replacement methodology
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.2 - Structural Fill/ Rock Fill Embankment (Where Required)
note | ACCEPTANCE CRITERIA: Test results and/ or proof roll records obtained for the fill layers compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report (Where Required) ZX115-ITR-7108 - Proof Roll
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.3 - Rock Subgrade (Where Required)
note | ACCEPTANCE CRITERIA: Proof roll records obtained Inspection by Geotechnical/ Design Engineer
note | VERIFYING DOCUMENT: ZX115-ITR-7108 - Proof Roll Loctaion plan of rock sungrade material where pavement thickness has been reduced.
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.4 - Finished Subgrade
note | ACCEPTANCE CRITERIA: Test results and proof roll records obtained for the finished layer compliant to ZX115- REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report ZX115-ITR-7108 - Proof Roll
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 10 - CONSTRUCTION PROCESS - AUXILARY PADS BASE COURSE PLACEMENT
checkpoint | 10.1 - Base Pavement
note | ACCEPTANCE CRITERIA: Test results and proof roll records obtained for the finished layer compliant to ZX115- REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | ○ Plate Load
note | VERIFYING DOCUMENT: NATA Test Report Plate Load Test Results ZX115-ITR-7108 - Proof Roll
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 11 - CONSTRUCTION PROCESS - LONGITUDINAL DRAINAGE
checkpoint | 11.1 - Excavation
note | ACCEPTANCE CRITERIA: Levels as required in IFC Model
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 11.2 - Erosion Controls
note | ACCEPTANCE CRITERIA: Turn out drains installed as required in IFC Model. Scour protection in line with ZX115-REP- 0201 Earthworks, Roads and Drainage Specification and Typical Drawings.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 12 - COMPLETION AND HANDOVER
checkpoint | 12.1 - Final Trim
note | ACCEPTANCE CRITERIA: ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ ZX115-REP-0206 - Balance of Plant Works Maintenance Manual Typicals
note | ○ Design Drawings
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 12.2 - Redline markup of Construction Drawings
note | ACCEPTANCE CRITERIA: In line with ZX115-REP-0201 Earthworks, Roads and Drainage Specification and BMS- WIN-1024 - Document Red-Line Markup
note | VERIFYING DOCUMENT: Redline Markup in Master Drawing Folder
note | SUPERVISION TYPE: REVIEW
checkpoint | 12.3 - Generate Punch List
note | ACCEPTANCE CRITERIA: Generate specific area/scope Punch List and transfer the open items to the Punch List Master Register
note | VERIFYING DOCUMENT: BMS-TMP-0044 Punch List record
note | SUPERVISION TYPE: REVIEW
checklist | ZENT-ITP-7023 - ITP - Civil - Hardstand Stage 2 (Backfill and hardstand extention) | itp |  |  |  |  | ZENT-ITP-7023 - ITP - Civil - Hardstand Stage 2 (Backfill and hardstand extention)
section | SECTION 1 - GENERAL
checkpoint | General
label | ITP Template No.: ZENT-ITP-7023
label | Revision: 0
label | Prepared By: Lachlam A.
label | Prepared Date: 22/11/2023
label | Discipline: Civil
label | Component: ITP - Civil - Hardstand Stage 2
section | SECTION 2 - CLOSE OUT SIGNATURE (ZENVIRON ONLY)
checkpoint | Close Out Signature
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature:
section | SECTION 4 - PRELIMINARY
checkpoint | 4.1 - Design drawings, project specifications.
note | ACCEPTANCE CRITERIA: Documents controlled through document management system.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 4.2 - Survey and Setout
note | ACCEPTANCE CRITERIA: Control point survey by registered surveyor. Visual inspection of control point/s. Survey equipment spot checked for calibration.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 5 - MATERIAL APPROVALS
checkpoint | 5.1 - Pavement Base Course Material Conformance
note | ACCEPTANCE CRITERIA: ZX115-REP-0201 Earthworks, Roads and Drainage Specification;
note | ○ Particle Size Distribution
note | ○ CBR
note | ○ Atterberg Limits
note | ○ Wet/Dry Strength Variation
note | VERIFYING DOCUMENT: NATA Test Reports
note | SUPERVISION TYPE: REVIEW
checkpoint | 5.2 - Fencing/ Gates
note | ACCEPTANCE CRITERIA: Schedule 16 - Landholder Agreement Requirements, Approved Property Management Plans
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: REVIEW
section | SECTION 6 - CONSTRUCTION PROCESS - FOUNDATION BACKFILL AND HARDSTAND STAGE 2 SUBGRADE
checkpoint | 6.1 - Earthing Install
note | ACCEPTANCE CRITERIA: Earthing ring installed as per Foundation Drawing ZX115-DWG-1433
note | VERIFYING DOCUMENT: ZX115-ITR-7343 - WTG Earth Grid Installation
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Backfill
note | ACCEPTANCE CRITERIA: Test results obtained for the backfill layers compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Dry Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.3 - Finished Backfill
note | ACCEPTANCE CRITERIA: Test results obtained for theSubgrade layer compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report ZX115-ITR-7108 - Proof Roll Inspection
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 7 - CONSTRUCTION PROCESS - HARDSTAND STAGE 2 BASE COURSE PLACEMENT
checkpoint | 7.1 - Base Pavement
note | ACCEPTANCE CRITERIA: Test results and proof roll records obtained for the finished layer compliant to ZX115- REP-0201 Earthworks, Roads and Drainage Specification
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Report ZX115-ITR-7108 - Proof Roll Inspection
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 8 - COMPLETION AND HANDOVER
checkpoint | 8.1 - Final Trim
note | ACCEPTANCE CRITERIA: ZX115-REP-0201 Earthworks, Roads and Drainage Specification
note | ○ ZX115-REP-0206 - Balance of Plant Works Maintenance Manual
note | ○ Typicals Design Drawings
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 8.2 - Redline markup of Construction Drawings
note | ACCEPTANCE CRITERIA: In line with ZX115-REP-0201 Earthworks, Roads and Drainage Specification and BMS- WIN-1024 - Document Red-Line Markup
note | VERIFYING DOCUMENT: Redline Markup in Master Drawing Folder
note | SUPERVISION TYPE: REVIEW
checkpoint | 8.3 - Generate Punch List
note | ACCEPTANCE CRITERIA: Generate specific area/scope Punch List and transfer the open items to the Punch List Master Register
note | VERIFYING DOCUMENT: BMS-TMP-0044 Punch List record
note | SUPERVISION TYPE: REVIEW
checklist | ZENT-ITP-7024 - ITP - Civil - WTG Excavation | itp |  |  |  |  | ZENT-ITP-7024 - ITP - Civil - WTG Excavation
section | SECTION 1 - GENERAL
checkpoint | General
label | Asset: Civil Area
label | Area: Specific Civil Area
label | ITP Template No.: ZENT-ITP-7024
label | Revision: 0
label | Prepared By: Lachlan A.
label | Prepared Date: 23/11/2023
label | Discipline: Civil
label | Component: ITP - Civil - WTG Excavation
section | SECTION 2 - CLOSE OUT SIGNATURE (ZENVIRON ONLY)
checkpoint | Close Out Signature
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature:
section | SECTION 4 - PRELIMINARY
checkpoint | 4.1 - Design drawings, project specifications
note | INSPECTION FREQUENCY: Design drawing revision status issued for construction, Project specification and current controlled model issued
note | ACCEPTANCE CRITERIA: Documents controlled through document management system
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 4.2 - Survey and Setout
note | INSPECTION FREQUENCY: ZX115-REP-0201 Earthworks, Roads and Drainage Specification Survey and inspection of Control PointS
note | ACCEPTANCE CRITERIA: Control point survey by registered surveyor. Visual inspection of control point/s. Survey equipment spot checked for calibration.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 5 - MATERIAL APPROVALS
checkpoint | 5.1 - Subgrade Replacement Material Conformance (If Required)
note | INSPECTION FREQUENCY: Verify conformance of material to ZX115-REP- 0201 Earthworks, Roads and Drainage Specification
note | ACCEPTANCE CRITERIA: ZX115-REP-0201 Earthworks, Roads and Drainage Specification;
note | ○ Particle Size Distribution
note | ○ CBR
note | ○ Atterberg Limits
note | ○ Wet/Dry Strength Variation
note | VERIFYING DOCUMENT: NATA Test Reports
note | SUPERVISION TYPE: REVIEW
section | SECTION 6 - ACCESS TRACK STRIP SOIL
checkpoint | 6.1 - Foundation Excavation
note | INSPECTION FREQUENCY: Batters to be benched or graded to 1:1 as per WTG Footing Drawings ZX115-DWG-1403
note | ACCEPTANCE CRITERIA: Any temporary drainage and sumps installed as per the drawings to protect foundation excavation from adverse weather conditions
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
checkpoint | 6.2 - Bulk Excavation
note | INSPECTION FREQUENCY: Excavated to 200mm above FSL of the foundation. Excavataion is to be maintained to prevent any damage to the foundation subgrade.
note | ACCEPTANCE CRITERIA: Maintained and dewatered as per Earthworks, Roads and Drainage Specification ZX115-REP-0201
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: REVIEW
checkpoint | 6.3 - Replacement Subgrade (As required)
note | INSPECTION FREQUENCY: Where subgrade replacement is required, verify the following as per Earthworks, Roads and Drainage Specification ZX115-REP- 0201
note | ACCEPTANCE CRITERIA: Inspection of final excavation by design and or geotechnical engineer to confirm if soft or loose areas need to be removed.
note | Test results obtained for layers compliant to ZX115-REP-0201 Earthworks, Roads and Drainage Specification:
note | ○ Compaction
note | ○ Density
note | ○ OMC
note | VERIFYING DOCUMENT: NATA Test Reports Geotechnical Engineer / Design Engineer written approval
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Foundation Release for Blinding
note | INSPECTION FREQUENCY: The base of the foundation should be free of loose material. Foundation excavated to allow minimum 100mm blinding concrete.
note | ACCEPTANCE CRITERIA: The onsite Geotechnical Engineer or Design Engineer must approve the condition of the foundation for cleanliness.
note | ○ Geotech report to verify that the parameters outlined in Earthworks, Roads and Drainage Specification ZX115-REP-0201 have been met.
note | VERIFYING DOCUMENT: Geotechnical Engineer / Design Engineer written approval
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 7 - COMPLETION AND HANDOVER
checkpoint | 7.1 - Redline markup of Construction Drawings
note | INSPECTION FREQUENCY: Redline markup of relevant Construction Drawings in Master Drawing Folder
note | ACCEPTANCE CRITERIA: In line with BMS-WIN-1024 - Document Red- Line Markup
note | VERIFYING DOCUMENT: Redline Markup in Master Drawing Folder
note | SUPERVISION TYPE: REVIEW
checkpoint | 7.2 - Generate Punch List
note | INSPECTION FREQUENCY: Subcontractor walk-down inspection
note | ACCEPTANCE CRITERIA: Generate Subcontractor Punch List
note | VERIFYING DOCUMENT: BMS-TMP-0044 Punch List record
note | SUPERVISION TYPE: REVIEW
checklist | ZENT-ITP-7026 - ITP - Civil - WTG Foundations | itp |  |  |  |  | ZENT-ITP-7026 - ITP - Civil - WTG Foundations
section | SECTION 1 - GENERAL
checkpoint | General
label | Asset: Civil Areas
label | Area: Specific Civil Area
label | ITP Template No.: ZENT-ITP-7026
label | Revision: 0
label | Prepared By: Elwyn Stannard
label | Prepared Date: 24/11/2023
label | Discipline: Civil
label | Component: ITP - Civil - WTG Foundations
section | SECTION 2 - CLOSE OUT SIGNATURE (ZENVIRON ONLY)
checkpoint | Close Out Signature
textbox | Name:
textbox | Position:
date | Date:
holdpoint | Signature:
section | SECTION 4 - PRELIMINARY
checkpoint | 4.1 - Design drawings, project specifications.
note | ACCEPTANCE CRITERIA: Documents controlled through document management system.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: REVIEW
checkpoint | 4.2 - Survey and Setout.
note | ACCEPTANCE CRITERIA: Control point survey by registered surveyor, visual inspection of control point/s.
note | ○ Survey equipment spot checked.
note | ○ No disturbance to survey marks.
note | VERIFYING DOCUMENT: N/A
note | SUPERVISION TYPE: WITNESS
section | SECTION 5 - MATERIAL APPROVALS
checkpoint | 5.1 - Concrete Mix Design(s)
note | ACCEPTANCE CRITERIA: Design Engineer Approval
note | VERIFYING DOCUMENT: Concrete Supplier Mix Designs, Concrete Test/Trial Data
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Steel Reinforcement
note | ACCEPTANCE CRITERIA: Reinforcement Supplier Accreditation
note | VERIFYING DOCUMENT: Supplier ACRS Certificate
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Formwork Approval
note | ACCEPTANCE CRITERIA: AS3610 Project Engineer Review
note | VERIFYING DOCUMENT: Formwork Compliance Certificate
note | SUPERVISION TYPE: REVIEW
checkpoint | 5.4 - Concrete Curing Agent
note | ACCEPTANCE CRITERIA: AS3799 Compliance Certificate
note | VERIFYING DOCUMENT: Manufacturer Compliance Certificates
note | SUPERVISION TYPE: REVIEW
section | SECTION 6 - WTG FOUNDATION PRE-POUR
checkpoint | 6.1 - Foundation Blinding
note | ACCEPTANCE CRITERIA: As per ZX115-REP-0204 Section 1.4.1 & 1.6.2 and ZX115-DWG-1401 Concrete Notes
note | VERIFYING DOCUMENT: ZX115-ITR-7102 Concrete Pour Record, Concrete Dockets
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Survey Setout
note | ACCEPTANCE CRITERIA: Survey Set Out by Licensed Surveyor Dimensional Check
note | VERIFYING DOCUMENT: Survey Report
note | SUPERVISION TYPE: REVIEW
checkpoint | 6.3 - Install Proprietary Formwork (Footing Perimeter)
note | ACCEPTANCE CRITERIA: AS3610 & AS3600 Formwork shall be aligned to a tolerance of mm. Approved release agent applied to form.
note | VERIFYING DOCUMENT: ZX115-ITR-7101 Concrete Pre-Pour Inspection Checklist
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.4 - Install Hold Down Bolts and Assembly
note | ACCEPTANCE CRITERIA: Bolts to be within ±3mm in any direction
note | VERIFYING DOCUMENT: ZX115-ITP-7111 WTG Survey and Setout Report
note | ○ SIF for vertical assembly of 2- and 4-segment anchor cage 0061-5846 V06
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.5 - Install Reinforcement
note | ACCEPTANCE CRITERIA: Design Engineer Inspection Report
note | VERIFYING DOCUMENT: ZX115-ITR-7101 Concrete Pre-Pour Inspection Checklist
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.6 - Install Proprietary Formwork (Pedestal)
note | ACCEPTANCE CRITERIA: AS3610 & AS3600 Formwork shall be aligned to a tolerance of 20mm. Release agent applied to form.
note | VERIFYING DOCUMENT: ZX115-ITR-7101 Concrete Pre-Pour Inspection Checklist
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.7 - Install Embedded / Cast-in Items
note | ACCEPTANCE CRITERIA: Installed as per IFC drawings
note | VERIFYING DOCUMENT: ZX115-ITR-7101 Concrete Pre-Pour Inspection Checklist
note | SUPERVISION TYPE: WITNESS
section | SECTION 7 - WTG FOUNDATION PLACEMENT (CONCRETE)
checkpoint | 7.1 - Place Concrete
note | ACCEPTANCE CRITERIA: As per ZX115-REP-0204 Section 1.5.3 and ZX115-DWG-1401 Concrete Notes
note | VERIFYING DOCUMENT: ZX115-ITR-7102 Concrete Pour Record, Concrete Dockets
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Concrete Testing
note | ACCEPTANCE CRITERIA: As per ZX115-REP-0204 Section 1.6.2 Samples to be taken on first truck and every 50m3
note | VERIFYING DOCUMENT: ZX115-ITR-7102 Concrete Pour Record, NATA Test Records
note | SUPERVISION TYPE: WITNESS
checkpoint | 7.3 - Cure and Protect Concrete
note | ACCEPTANCE CRITERIA: As per ZX115-REP-0204 Section 1.9.2 An approved hydrocarbon based curing agent to be applied
note | VERIFYING DOCUMENT: ZX115-ITR-7104 Concrete Post-Pour Inspection Checklist
note | SUPERVISION TYPE: REVIEW
checkpoint | 7.4 - Strip Formwork & Patch
note | ACCEPTANCE CRITERIA: As per ZX115-REP-0204 Section 1.13
note | VERIFYING DOCUMENT: ZX115-ITR-7104 Concrete Post-Pour Inspection Checklist
note | SUPERVISION TYPE: HOLD POINT
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 8 - COMPLETION AND HANDOVER
checkpoint | 8.1 - Redline markup of Construction Drawings
note | ACCEPTANCE CRITERIA: In line with ZX118-REP-0201 Earthworks, Roads and Drainage Specification and BMS- WIN-1024 - Document Red-Line Markup
note | VERIFYING DOCUMENT: Redline Markup in Master Drawing Folder
note | SUPERVISION TYPE: REVIEW
checkpoint | 8.2 - Generate Punch List
note | ACCEPTANCE CRITERIA: Generate specific area/scope Punch List and transfer the open items to the Punch List Master Register
note | VERIFYING DOCUMENT: BMS-TMP-0044 Punch List record
note | SUPERVISION TYPE: REVIEW