## Table 1
|  |  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-028
[12 empty] | Revision : 01 |  |  | Date: 29/07/25
Client: Yarra Trams |  |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved | by | :
Project: Montague St Northern Crash Beam Contract No: 8B6100 |  |  |  |  | Structural Steel Supply and Install |  | Name: | Leo Watson | Name: | Patrick Fagan |  | Name: Signed : Date : | Shaun Kent 29/07/2025
Specifications: AS4100-2020, AS5131-2016, VicRoads Standard Specification Section 610, 630, 631
[5 empty] | Structure / Component: |  | Signed : |  | Signed :
[5 empty] | Location: |  | Date : | 2025-07-29 | Date : | 2025-07-29
Lot No: Lot Details: Lot Size/ Quantity:
Item |  | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan |  |  | FH's Sub- contractor | Date
1 |  | Design and Submissions
1.1 |  | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  |  |  | N/A
1.2 |  | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, SWMS & WP | PMP, EMP, TMP, SWMS, WP | Visual Inspection | This ITP signed | HP* | Fulton Hogan Engineer | N/A |  |  |  | N/A
1.3 |  | Structural Steel Components |  | Prior to erection | Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component. | P&S IFC | Verify | This ITP signed | IP | Fulton Hogan Engineer | N/A |  |  |  | N/A
2 |  | Preliminaries
2.1 |  | Universal Bearing Structural Grout or Mortar |  | Where applicable, once, for each product, prior to placement of product | Product to be selected based on the following criteria: 1. either a single component, self consolidating and dual shrinkage compensating cementitious grout 2. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum 3. have a consistency appropriate for the required use | P&S IFC 610.33 | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A |  |  |  | N/A
3 |  | Pre Installation Activities
3.1 |  | Materials Inspection Checklist |  | Each component | General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion. Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings. Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues. Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects. | IFC Drawings 630.08 630.09 631.06 631.11 (a) | Inspect | This ITP signed | IP | Fulton Hogan Engineer | N/A |  |  |  | N/A
4 |  | Installation Activities
4.1 |  | Bearing / Mounting Surface Preparation |  | Where applicable, each installation location | Prepare the bearing surface in accordance with the Grout/Mortar Product TDS. As a minimum, ensuring that it is clean and free from loose particles such as rust and laitance. | IFC Drawings Product TDS | Measure Visual | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
4.2 |  | Structural Steel Handling |  | Each component | The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings. | 630.09 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
4.3 |  | Structural Steel Erection |  | Each component | Place steel component into position, ensuring that it is plumb, level, square. Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable). | IFC Drawings | Verify | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
4.4 |  | Fastner Tightening - Snug Tight Condition (8.8/S) |  | Each component | Place bolts, washers and nuts as detailed on the IFC Drawings. Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner. Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm. | IFC Drawings 630.20 (d) | Verify | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
5 | Post-Installation Details
5.1 |  | Survey Conformance |  | Each component | Verify position of steel components. Ensure vertical clearances are met and steel componentary is positioned as per the IFC drawings. | IFC Drawings | Verify | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
5.2 |  | Sampling and Testing of Grout / Mortar |  | Each component | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) | 610.28 610.33 | Verify | This ITP signed | TP | Fulton Hogan | N/A |  |  |  | N/A
5.4 |  | Inspection of Coating |  | Each component | After installation Works are complete, inspect the steel element for damage to the coatings. Where damage exists, it shall be repaired using an approved repair procedure. | IFC Drawings 631.15 | Verify | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
5.5 |  | As Built Drawings |  | Prior to lot closure | Recorded of as-built drawings | Fulton Hogan Procedure | Verify | This ITP signed | IP | Fulton Hogan | N/A |  |  |  | N/A
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Print Name: Position: Signature: Date: / /
Legend
HP | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point |  | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point |  | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point |  | Written or verbal approval given by the Superintendent