## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Vegetation Removal | itp |  |  |  |  | ITP-001 - Vegetation Removal
section | Vegetation Removal
checkpoint | 1. - Establish cultural heritage area
label | FREQUENCY: All Areas
label | ACCEPTANCE CRITERIA: Bunting around the areas
label | REFERENCE DOCUMENTS: Project Drawings
label | INSPECTION / TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | HP
label | RESPONSIBILITY: Supervisor/Surveyor/Environmental Co-ordinator
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2. - Establish track alignment & clearing limit
label | FREQUENCY: Every change of direction of the horizontal alignment
label | ACCEPTANCE CRITERIA: Survey marks
label | REFERENCE DOCUMENTS: Alignment Drawings
label | INSPECTION / TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | WP
label | RESPONSIBILITY: Supervisor/Surveyor
date | Date Completed:
checkpoint | 3. - Identify trees to be removed
label | FREQUENCY: All tress
label | ACCEPTANCE CRITERIA: Removal marks (Blue “R” or Blue mark for small trees) sprayed on the tree following joint inspection with SA Water Superintendent
label | REFERENCE DOCUMENTS: Tree Register
label | INSPECTION / TEST METHOD: Visual
label | RECORD OF CONFORMITY: Completed Tree Register
label | WP
label | RESPONSIBILITY: Supervisor / Environmental Co-ordinator
date | Date Completed:
checkpoint | 4. - Identify branches to be trimmed
label | FREQUENCY: All trees
label | ACCEPTANCE CRITERIA: Trimming mark (Pink ribbon) placed around the branches at the trimming location following joint inspection with SA Water Superintendent
label | REFERENCE DOCUMENTS: Not Required
label | INSPECTION / TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | WP
label | RESPONSIBILITY: Supervisor / Environmental Co-ordinator
date | Date Completed:
checkpoint | 5. - Weed removal
label | FREQUENCY: All areas to be stripped
label | ACCEPTANCE CRITERIA: Removed weeds are deep buried (900mm cover) to reduce the risk of respreading
label | REFERENCE DOCUMENTS: Not Required
label | INSPECTION / TEST METHOD: Visual
label | RECORD OF CONFORMITY: This ITP
label | WP
label | RESPONSIBILITY: Supervisor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP