## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
df6e1544-a2a4-4ba6-a41e-7c3193944586 | checklist | 02.01 - Traffic Management | itp | 02.01 - Traffic Management
9f0fff5a-5057-4c5f-bcb4-a1367b4538b0 | section | Details
e000c404-5e86-463a-9050-a1421712516d | checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
65825c82-4fc4-5f9e-ab13-e9727bc1113a | note | Acceptance Criteria & Frequency (Project Specific) - Accreditation Supplied to Administrator
6f8eb4e1-19ee-576d-b94e-59ea321af5ec | note | Check Item - Check Item
2936c4c5-9077-5ace-9add-57e97cf60884 | note | Reference - MRTS02 Cl. 5.2
572d464c-796e-4f84-bb37-b6cefea7e03d | checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use. TMP REVIEW PERIOD 21 DAYS as per MRTS02.01.
412fd96f-58fa-58c1-a300-08ac61606c58 | note | Acceptance Criteria & Frequency (Project Specific) - Approval via Contract Notice - Per NTO
d681fc5b-7f64-5658-9c74-70d73dfeb92a | note | Check Item - Hold Point 1
c1ab4420-99bc-5296-b0b9-9f2d226eaa18 | note | Reference - MRTS02 Cl. 5.3
4ff0b938-6f97-4a90-8125-b27036bfc4a7 | signoff | HOLD POINT
894dec21-5655-4936-bfad-29adde1dcdb2 | checkpoint | All traffic control devices inspected and records kept in accordance with the specification
8aa4383e-ba0e-57d3-9d59-a8a6e0b445c7 | note | Acceptance Criteria & Frequency (Project Specific) - Site Records - Daily
95a754b7-95c0-55ac-9c69-d015825fcc20 | note | Check Item - Check Item
accba620-330b-5579-b5a2-e7552959e4ef | note | Reference - MRTS02 Cl. 5.6.4
352e89d7-97dc-4eaf-b1c4-470c283bd3d9 | checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
5c5ffccc-a882-589d-9fef-241cbc4f3d4a | note | Acceptance Criteria & Frequency (Project Specific) - Incident Report - Per incident
9c42777f-c4c0-5167-a9d7-d9ccc077d12a | note | Check Item - Check Item
b3b976e0-b06d-57c5-8e1f-805fbe1e58f9 | note | Reference - MRTS02 Cl. 5.6.5
3bd60d38-9ad8-4ab2-acd6-0dcdf4a5b01e | checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ. TGS REVIEW PERIOD 14 DAYS as per MRTS02.01.
31194995-03a1-5108-b3bb-6d5169367905 | note | Acceptance Criteria & Frequency (Project Specific) - TMD sign off of TGS and, RPEQ Risk Assessment as required
c1e66d43-e884-5589-960a-bb81f5ad823b | note | Check Item - Hold Point 2
deae8f38-e981-58c9-a422-90115f1b2bb5 | note | Reference - MRTS02 Cl. 6.2
3811a8d1-6e9a-48e5-b52a-65c81be7daf6 | signoff | HOLD POINT
5b21817c-fd18-4ecb-ba5c-abc9b5db64ac | checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
6ed32486-2877-5274-a991-eec59e2ecdbb | note | Acceptance Criteria & Frequency (Project Specific) - Submission of report to Administrator - Per inspection
476c109c-1412-5364-8167-4fa6769364d9 | note | Check Item - Milestone
32855d79-e4fb-5d5a-8547-8a81656fa32b | note | Reference - MRTS02 Cl. 7.5
8632656c-b2a4-4e0a-b658-6b4c37e51b7f | checkpoint | Final Verification
c7f15403-3e50-5711-8c9d-4e9a92e6e297 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
41a4480f-b41f-5fe3-b78f-77c23bf18977 | textbox | Print Name:
0d0916eb-be88-55c3-abf5-c8ef3a21e176 | date | Date:
fc0d09a7-a7f2-48ab-a298-d53e53b3c789 | section | Final Sign Offs (to be completed at closure of Lot)
bd086058-606f-4320-abaf-814236eca977 | checkpoint | Agreed Quantities
5a460709-2424-40fd-b260-102f041d42a4 | signoff | Agreed Quantities Sign Off
e69fd91d-a62f-445b-9489-ebc7c3b309e0 | checkpoint | Closure of Lot
804104d2-0029-460f-984b-1b76c3b17038 | signoff | Closure of Lot Sign Off
f9ee09fd-8b07-49ed-9457-20b66cb2218f | checklist | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs | itp | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs
26c67593-988d-4972-b671-2796d5ff8132 | section | Details
4489dd3f-953f-457a-92b0-d2be9e09d413 | checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
da915538-48ef-5760-be32-d5a2e8fc1e22 | note | Acceptance Criteria & Frequency (Project Specific) - Culvert Removal - Per Culvert
203604c3-afd7-50d0-b36d-9b1c0b910394 | note | Check Item - Check Item
68439ce2-2236-5893-8c30-4f76f670e38a | note | Reference - MRTS03 Cl 9.2
c379e1d0-e79e-4857-a6ed-d020c0a66793 | checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
040f719a-14b2-5107-bc77-4eddfbef309b | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
26a6922d-1ae8-5184-817e-ce75be9c72f3 | note | Check Item - Check Item
a517134f-cb4d-57f2-ac89-721af1dfd640 | note | Reference - MRTS03 Cl 9.2
c546209a-7f6a-42f5-9845-58069f2b8dc6 | checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
dd8b12b7-728d-567e-a35d-71ff03bfef16 | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
3597ba48-8155-5d14-89fb-72688b246c62 | note | Check Item - Check Item
cec74a08-1b14-510e-83a2-1da7b4aa56bb | note | Reference - MRTS03 Cl 9.2
207eff91-d112-4f5d-80a5-a80ec0c4c1e6 | checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
4afa0569-ce71-5a98-9d65-be9a32f8b821 | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
00070a40-8d58-5f93-bfb0-9137defeb6f3 | note | Check Item - Check Item
c47b8ea3-8cd6-51f4-b5a6-e57a020f481d | note | Reference - MRTS03 Cl 9.2
be964e9d-9a9f-4772-b4e3-73c4079ffb00 | checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
b3243e31-d013-546c-a65d-3dfb04f1addf | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Kerb
31200a46-32fc-518f-8ebe-4db29c30f7fe | note | Check Item - Check Item
3b0bb0b2-d382-58dd-9015-6b6d9bdadb63 | note | Reference - MRTS03 Cl 9.4
3ba93ffb-441c-45d1-848f-8af160494014 | checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
8b610d6d-b521-579f-8ab7-11a6a77fdaa8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b8ff2ba0-8d43-5dde-ae34-6c011ed7efd9 | note | Check Item - Check Item
b778471c-eeb8-5dff-bb38-605a57881ada | note | Reference - MRTS03 Cl. 9.4
95e1abd1-9399-4bd0-824c-ec24f5bb5140 | checkpoint | Kerb excavations shall be backfilled to flush with the surrounding area.
e1b24287-09f1-538c-8c8a-5dabbf7de381 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
58325f00-4945-5052-937a-88bfc11cf4f1 | note | Check Item - Check Item
d01ed717-a9e8-569c-b12e-6523a298d302 | note | Reference - MRTS03 Cl. 9.4
4998fa83-b59d-4326-aadf-6f14e8ef56a4 | checkpoint | Final Verification
3f2f80cd-1ef3-5503-a32e-9af38faa4900 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
6fc23977-e552-5bdc-aa80-f90318e29c68 | textbox | Print Name:
3a69f630-04f9-512b-9f13-d68f8fcf99f5 | date | Date:
72684975-c98d-5164-a1a5-0bd1dd38c03c | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
1103752f-7342-5f80-9c39-ff5223519707 | textbox | Print Name:
6ddd298a-47ab-5e46-afbc-b9340f86ff3d | date | Date:
2a49d354-2ab9-4530-bf31-f9b4bd950fc6 | signoff | Sign ITP
85688c92-f9f8-459a-b9c3-c282c1a6ffac | section | Final Sign Offs (to be completed at closure of Lot)
cdb2c4b7-c3ed-45a8-94fc-28268a10cb36 | checkpoint | Agreed Quantities
bb49375b-95b7-43d6-ba2f-40c046aa590e | signoff | Agreed Quantities Sign Off
6f66acf9-a872-49a7-a9a0-634b700cac65 | checkpoint | Closure of Lot
232d5f7e-320e-4d89-910b-bff56c2319b2 | signoff | Closure of Lot Sign Off
82186883-48d1-401b-997c-7118571e26a1 | checklist | 03.10 - Supply and Installation of Precast Concrete Culverts | itp | 03.10 - Supply and Installation of Precast Concrete Culverts
c9a13a64-2d50-4bb5-9039-9baba4d268d6 | section | Supply and Installation of Precast Concrete Culverts
eb25f00f-5a96-45ff-9b6f-9e4aef43b27c | checkpoint | Maximum Lot Size - 1 Culvert
092ba11a-8d29-5b43-9c60-ef40582554a9 | note | Acceptance Criteria & Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
a22b3acb-dbf9-5d12-9d46-d4ca93c0772b | note | Check Item - Check Item
26488f6a-0609-50a5-9c14-3d9f000f5ce2 | note | Reference - MRTS04 Table A.2
696fa24a-02bb-48be-a0fb-e20018b335b3 | checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
d79b1a0b-0b0e-5550-8ce6-aa7011b0de83 | note | Acceptance Criteria & Frequency (Project Specific) - Manufacture and Test Certificates
a42eaf30-a5f8-53f6-82fb-70e703fc0c18 | note | Check Item - Check Item
9ecb2822-9905-5676-bbf7-5b5ae46ed0b0 | note | Reference - MRTS03 Cl10.2
aee25686-9a93-44bb-bcca-d75f18c6e4b3 | checkpoint | All pipes of diameter 800 mm or less shall have spigot and socket joints with rubber sealing rings. Joints for other sizes shall be as specified on the drawings.
5a0c6352-6732-5311-9775-1a841c0c53c6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1cfe64fe-f0a5-5bbc-863f-32935ec31091 | note | Check Item - Check Item
7a79b53e-0e33-5120-925d-7f7067e2326d | note | Reference - MRTS03 Cl10.2
acfb8db8-0548-4fb9-ad37-9e5fd1c21f3e | checkpoint | Component size, wall thickness and class is as specified in the drawings
d868bf2a-4b55-57d1-a786-2aa1cd9bcce7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e9cf610f-fb3c-5fe8-86a0-922dfef21487 | note | Check Item - Check Item
61eda7bc-238b-519d-9089-91413aebd850 | note | Reference - MRTS03 Cl10.2
324955d6-2814-4a3d-9d2c-ef51331272db | checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by Administrator
08825cbc-37ef-5c11-a5fb-a8b500cfbd75 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b9f416e5-2e83-5aee-84d8-26da2a8fcb4e | note | Check Item - Hold Point 1
d3777613-3a65-57b0-8588-7eb2a17af664 | note | Reference - MRTS03 Cl11.2
70566797-849f-432e-82a4-a54ad16a2e10 | signoff | HOLD POINT
41dad0e8-3e77-40b5-bcbd-53e9c7b31fbd | checkpoint | Culvert Construction Procedures to be accepted prior to commencement of Installation
64988ba1-b556-5f38-9a81-c5ea6f2e11a6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bd2181e2-05ac-5c5e-8510-c30cbba869bc | note | Check Item - Hold Point 2
81554dc3-6606-5cfb-a566-ed57a1283ab0 | note | Reference - MRTS03 Cl11.3.1
d76209d2-8444-474e-a90d-79e7066a7752 | signoff | HOLD POINT
300f7985-9d93-49d7-8870-d2e25c113299 | section | Excavation
8959513c-4d70-4d7c-bea2-ad284ee32929 | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earth works
cf4df604-1d37-5e4a-b501-4fdedb559717 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b19cf8b2-1582-5418-85a3-c5f627dedf8a | note | Check Item - Check Item
a5806ca8-260e-523b-ae2b-e5f0636f4611 | note | Reference - MRTS03 Cl.11.3.1
426fceb4-c0cc-45e1-b701-1538e7aa4ff3 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL.11.3
6866b882-a734-50e0-9f31-6ba1a54f4ca2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a76e5bd8-94b1-5e2d-865a-40f6f61a6986 | note | Check Item - Hold Point 4
6275e4ea-31f9-539a-b54f-cec7f4754a84 | note | Reference - MRTS04 Cl. 9.4
dec54752-07bc-4968-8e90-68016341bf91 | signoff | HOLD POINT
057a414c-de74-4094-8f67-9f68a924fea0 | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation -RDD Q140A
2c56ee60-b5e7-57eb-8999-8478528ea9dc | note | Acceptance Criteria & Frequency (Project Specific) - Cl 15, Table 15.3(b), CV 95% minimum (1 tests / 50m2 - min 2 / lot)
e3c62193-d9de-5319-8e42-66979cd305fa | note | Check Item - Test results
c886e5d9-1128-5e6d-9cf0-639ab4ca7edd | note | Reference - MRTS04 Table A.2
cc120110-9513-42f9-8af4-c446ca431597 | section | Culvert Installation
7a2649ea-0033-4c63-ab2c-43b639862f7d | checkpoint | Components are assembled as per manufaturers specifications, and if possible, contruction commenced at outlet
39af0d8f-edf1-5df6-95ef-f6a462a2d2b0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
991dc694-147f-52d9-923d-3088e9fce764 | note | Check Item - Check Item
fbfcc635-8619-5944-bf6d-7250064cbdea | note | Reference - MRTS03 Cl11.3.3 Cl11.3.4
7b1e86ff-c52d-4d13-b149-e60c79d911c5 | checkpoint | Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet
0185cbc4-cabb-59c5-9cbc-736fce7340f2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e2bd43da-6403-5701-ab98-9e395ce1375b | note | Check Item - Check Item
d5b4ea8c-57b5-51ea-aa9a-8a821029cfa2 | note | Reference - MRTS03 Cl11.3.5
43d5106c-4427-40a8-b11d-c0b6ddb06790 | checkpoint | The pipes shall be laid with the lifting hole or "TOP" marking uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
8c9f47aa-3d91-5b39-9569-b4145ebd4839 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
9f94bd4f-6f09-52ca-b78f-7ada10b1070e | note | Check Item - Check Item
aadcfdc4-43bb-5845-acbc-3a4bc4a629d5 | note | Reference - MRTS03 Cl11.3.5
14f4328a-5779-4a05-9a4e-0e72fd77af45 | checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
76573af9-f7f9-53a1-b1c5-dec0832d22c5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8e1eca3e-696c-5be8-9374-8f0a354d6d34 | note | Check Item - Check Item
3f340735-9d97-54ea-aa6a-3664050a9870 | note | Reference - MRTS03 Cl11.3.5
0b708a85-1efd-4ee5-b408-b84fcc8f8af3 | checkpoint | The horizontal alignment of culverts shall not vary from the location specified in the Drawings by more than ± 100 mm
bb6f05d1-e0c9-58bb-b68e-deabf3a00389 | note | Acceptance Criteria & Frequency (Project Specific) - ± 100mm (All points shown on drawings - min 1 per 20m or 3 points)
066bbb5f-4da7-55bd-8cc9-ac16e9ec0f13 | note | Check Item - Survey Results
bf8c5297-650b-56e6-aa4a-2dc74a2da93d | note | Reference - MRTS03 Cl.8.2
ed1afac4-2257-487f-82e3-d512945af5cd | checkpoint | The invert heights of culverts shall not vary from those specified by more than ± 10 mm and nowhere shall the grades of culverts depart from those specified by more than 1%
a215b9a2-390b-510e-a57d-5afff3ae5e84 | note | Acceptance Criteria & Frequency (Project Specific) - ± 10mm, ± 1% grade (All points shown on drawings - min 1 per 20m or 3 points)
c48ee5d0-7d5a-59f5-af2f-25152fa205c1 | note | Check Item - Survey Results
6ffd5dc9-06c3-5f94-bed1-2bd4e0ae4dc6 | note | Reference - MRTS03 Cl.8.3
b7c6ae60-592b-4bd9-b6ab-28590e9bac91 | section | Backfill
bc54d998-1ba2-4cec-9d37-6430cb8e0f63 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
75f2669e-175f-5e16-934c-330de5dbf8d6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
300ae164-84a1-50ca-848f-9eab4a747ebc | note | Check Item - Hold Point 4
ecc3f622-8105-5ac5-a756-06b4183048b1 | note | Reference - MRTS03 11.3.10
cc5688c2-abc9-40ed-9e0d-fafb35721a1a | signoff | HOLD POINT
47476c57-1ded-4cfb-b127-a7558e153097 | checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, etc have been completed and inspected, and any specified curing periods have elapsed.
c1ecfd48-f9a5-515a-a838-3dd17b6db8ba | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a67ec1b8-9651-55aa-95ff-4179171b6eb5 | note | Check Item - Hold Point 14
8c32f387-bbc7-5be4-a02c-75722a1701d6 | note | Reference - MRTS04 Cl.19.3.3
f9f76280-ad78-48e4-9d2a-e8403d36a12b | signoff | HOLD POINT
f87ca69b-ff87-47e9-9fb5-d73250aa93f4 | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 excep 100% material shall pass 25.0mm test sieve.
a4ca3ae9-bed4-598e-9691-9aac218e63cd | note | Acceptance Criteria & Frequency (Project Specific) -
fe5c4cd0-e0b2-542b-a529-95fd0cf5a4f5 | textbox | Class A1:
5323db93-a170-522b-9505-24ac59a81c48 | textbox | Class A2:
e343d6f8-700e-55bb-9a6b-efd32b4d249f | textbox | Class B:
3eedd92c-1fd4-5208-9682-28cc8f3376e5 | note | Except: 100% passing 25mm
536019f7-4450-5343-93fc-092851bb6e58 | note | Check Item - Witness Point
74910bba-af6c-5176-a065-c802f5d890f6 | note | Reference - MRTS04 19.3.1, 19.2.2 Table 14.2.2
7787aeee-2798-452a-a466-c7044baa3037 | checkpoint | Compaction - Q142A, Q141B
527fe6f3-4fad-5a4d-b5f9-098b686316f8 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
db3d9f96-bbcd-50e8-bb16-e1a6fe538b4c | note | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
d181d0d1-0214-546f-a2ff-284a989d0aa5 | note | Check Item - Test results
53df404f-6136-50bd-85e6-bba95817a6e9 | note | Reference - MRTS04 Table 15.3(b)
a3d8114a-757e-44af-b266-18f8f7ac59d3 | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
d62225c0-4d16-5fed-abba-bc34df8a2cc4 | note | Acceptance Criteria & Frequency (Project Specific) - Class A1/A2: 70-100%
82e87c2e-8f31-56bf-a8c1-4f0dfa1dc3ee | note | ○ Class B: 80-110%
4840586b-008d-5af2-afd9-54b3fa9e9b8e | note | Check Item - Test results
1b2815cb-89ef-58b1-a413-2c57a59d5b56 | note | Reference - MRTS04 Table 15.3(c)
4f35769f-6079-48da-a2ec-86c49a2633fb | section | Completion
65c0121e-3ecd-48c3-9f3c-95c77cf26871 | checkpoint | CCTV inspection undertaken, report submitted and accepted by Administrator.
2d7e7e0c-77d1-50e2-aaa6-d972cb9fcee5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f3d0574a-3877-5f1f-8049-8af492e3d19d | note | Check Item - Hold Point 3
27da4348-0839-5722-8122-196eeb574a5c | note | Reference - MRTS03 Cl11.3.5
1b17d5e5-84b2-4044-a03b-a446fda15067 | signoff | HOLD POINT
576e7c30-d9ce-4727-a65f-33eb35233b0f | checkpoint | Final Verification
d46262cc-299b-55b3-844c-2c7dcc83dc7c | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
7cc3010b-7e56-58f6-9792-fb8503141370 | textbox | Print Name:
8094a9e7-75ba-5f79-bc9b-5b8d122f0679 | date | Date:
b49e0c07-0d2e-5129-941f-5b0c5899e77e | note | Project Manager Verify that the Above has been Constructed according to Specification
282eb26c-4380-5d1c-9d86-70eba0c20f81 | textbox | Print Name:
ee821fd1-7570-5cc3-8ff2-6e842f71795a | date | Date:
02442f14-9f23-45cd-804c-3ee34709e0e9 | signoff | Sign ITP
90249218-9bf5-4ad7-9cae-0e9f5fc5eac6 | section | Final Sign Offs (to be completed at closure of Lot)
d1124182-3087-40e4-b7a1-df4919acce6c | checkpoint | Agreed Quantities
b39b98b8-aa23-4d5f-8cc3-80eb6e3fd41a | signoff | Agreed Quantities Sign Off
624e0f13-09a8-4fb2-9107-8eeab3789f03 | checkpoint | Closure of Lot
8979c3da-d47a-42ad-b661-9325476d2e53 | signoff | Closure of Lot Sign Off
d2aa8be0-6675-41ce-9caf-02efea2dfe6c | checklist | 03.11 - Culvert components and structures Precast or In Situ | itp | 03.11 - Culvert components and structures Precast or In Situ
ceb379e7-3b88-458a-ac6c-65dc85d92aee | section | Culvert components and structures Precast or In Situ
128f2803-0fc4-486e-8f8d-9284c5565424 | checkpoint | Maximum Lot Size - 1 Culvert
e9e8e316-d289-50ff-a844-810f10aa5cf8 | note | Acceptance Criteria & Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
714325f0-154a-55ca-af08-486306453204 | note | Check Item - Check Item
9ba859b2-a090-59cb-99a2-b731efc283e0 | note | Reference - MRTS04 Table A.2
674b5f29-0ba0-41a9-8c99-d9c76ab01b51 | checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
d00994af-279f-576a-9600-5ff4a32e0643 | note | Acceptance Criteria & Frequency (Project Specific) - Administrator Approval - Per Project
881dcb17-7330-5f53-8e0e-fb184ffcd6cc | note | Check Item - Hold Point 2
9feb4af5-c3ff-5fab-bb27-43dcdd237a16 | note | Reference - MRTS03 Cl 11.3.1
68b277bb-2536-406a-a7fb-05969ad74d4d | signoff | HOLD POINT
a0307943-1227-4601-be54-dd5a0a5ca5d9 | section | Excavation
046259a7-0c87-491f-aecc-bd65e1e18553 | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
302b45ef-41fe-5bc2-978f-9a6c4c64cb3e | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per lot
428872c1-b0f3-5514-9230-2bccf9d837d9 | note | Check Item - Check Item
b8653da9-c28b-5e2f-b32a-7036d4c9f70e | note | Reference - MRTS03 Cl 12.3.1
c0f480f2-2e00-4ec5-bc9a-b16a3a776034 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
d2905ac0-b66b-5656-99ac-6ee70bda3156 | textbox | Reference Unsuitable Lot No.:
4bf5fdd6-05ca-5987-81a8-8fcc6d6e3cc2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual - Per lot
44a1f2f1-4a24-50a8-a5af-e5f5316695d1 | note | Check Item - Hold Point 4
fc57f68b-0608-506b-995a-881f3995bf38 | note | Reference - MRTS04 Cl 9.4
69c55402-c80b-4fb6-b43e-5041310fc6c4 | signoff | HOLD POINT
3554cfec-20ee-459a-be3a-1e8af55e68e5 | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation
3b403eae-a1a2-5d83-9ba3-d67ac0dbc4be | note | Acceptance Criteria & Frequency (Project Specific) - Cl 15, Table 15.3(b), CV 95% minimum (1 tests / 50m2 - min 1 / lot)
fa89cbe6-f8f4-5d12-8ccd-6233d9094acb | note | Check Item - Test results
001815ca-6747-537a-a5dd-86d5c40d9b4f | note | Reference - MRTS04 Table A.2
bb522e37-e580-4072-b5c5-060c4f979596 | section | Installation
e278f093-bf9e-44ef-910b-4400911447b3 | checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 & MRTS71
a11bff92-e4e8-5d93-b55e-bc78f90439b9 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS03
e084d0ad-1ad1-5328-a29c-dc89a69f5ae3 | note | ○ Cl.15: End Structures Cl.21: Gullies
dbbc1898-4bed-5885-8f38-c2536df6d7f5 | note | ○ Cl.21: Access Chambers
c220ac1b-80b5-5ef1-9f92-123e46203efc | note | Check Item - Check Item
a22bef22-bfa9-573f-81e8-36406bedf7d8 | note | Reference - MRTS03 Cl.6.1
3f94b8a8-ca55-4b03-b696-880ad5feb1a4 | checkpoint | Precast: Installed in accordance with MRTS03-Components shall be laid on a foundation bedding which provides continuous even support to the structures.
63bf0fca-01a0-59ad-9afc-68798eed8069 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
96c4cc3c-c8b8-5ee1-80cd-558592cd492c | note | ○ Cl.19: Precast End Structures
72267e4f-ff4f-557e-9361-dfaac9ddf826 | note | ○ Cl.21: Precast Gullies
e80c2480-3ae3-571b-94c9-11183bc8ad46 | note | ○ Cl.21.5.1 Precast Access Chamber
a0bfb57c-1cd2-5f9a-9d9c-24ed1b9379fe | note | Check Item - Check Item
9d4005ec-57ac-5ce2-9ecc-2871697fb188 | note | Reference - MRTS03 Cl. 16, Cl. 21, Cl. 21.5.1
f70da951-6ac1-4b7e-8c06-791993299021 | checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
b31b3237-1552-5acf-bb5f-1a0909c8df83 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
957d58d0-accf-5d55-b588-811873d1e06a | note | Check Item - Check Item
ca91a712-1ed9-56e3-9412-e13dd36db4fc | note | Reference - MRTS03 Cl. 21.3
50855cce-0dc4-4043-b73a-db50126daa8c | section | Tolerances
1cf1eaaf-757e-478d-a7f1-6496e3e6f39c | checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
9e6386ac-16df-5798-a489-9a2a06684b9a | note | Acceptance Criteria & Frequency (Project Specific) - ±50mm (All points specified on drawings)
c623bffe-5dc2-5276-8fe9-0429712b9c07 | note | Check Item - Survey Results
816df3d1-ca4e-50b9-87bf-ac9ddc6f6fc6 | note | Reference - MRTS03 Cl.21.4.2
3c289424-e150-4ba3-a20c-9819ad34852b | checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
ddd7f75f-6f41-5730-83ac-e6c6139a267d | note | Acceptance Criteria & Frequency (Project Specific) - ±10mm (All points specified on drawings)
33cac536-3ed0-544c-b2d2-05bd134cb2bb | note | Check Item - Survey Results
d503f18a-1ee3-5487-93d5-a5993678a248 | note | Reference - MRTS03 Cl.21.4.2
5e18283e-f2c6-4123-b0fa-a3bd4f2036c5 | checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
7d890ec3-4f6d-536a-93e6-ad09f03d7141 | note | Acceptance Criteria & Frequency (Project Specific) - Gullies:
0b7acde8-5d1e-5b68-a074-188886500bbd | note | ○ ±100mm in road direction
9bbeba5b-86ef-52dc-96d8-2b1bd609f866 | note | ○ ±50mm perpendicular to road
cccfd0f9-0862-5a16-b424-9bcdce4319dc | note | Access Chambers:
32f744c4-b62a-5c0b-8a2a-328d3f8226c5 | note | ○ ±100mm (All points specified on drawings)
1c4f83e8-0736-5972-aded-428a1e7b98e4 | note | Check Item - Survey Results
a5626efa-1da9-522b-8efe-17cc34f4f8bc | note | Reference - MRTS03 Cl.21.4.1
bb6bca43-670e-4048-bd95-7666f333dcec | checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
abbf9d9a-ffde-51eb-898a-4a923ff05cf1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2effa425-4944-5cc9-8633-9ebd546583be | note | Check Item - Check Item
40ff6a50-95e3-5473-a497-b71e964b2b75 | note | Reference - MRTS03 Cl.21.4.2
2c5739d2-9a12-4a5c-aad7-89f4699acff1 | checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
2155b271-0044-559d-824f-5626cee988a2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5cecdcaa-2875-57ef-b881-663d4f16f85f | note | Check Item - Hold Point 5, Hold Point 6
2bd5c980-cbf0-549f-8052-f004c3b73fde | note | Reference - MRTS03 Cl.21.3
29ad9ebc-ec0b-46a0-b25f-10940d704601 | signoff | HOLD POINT
e5967744-e751-4fff-b57a-1a8915f752ba | section | Backfill
17e98b17-0156-4576-9d4e-8bd88d06de52 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
cdfb5c5c-fca5-5afd-964b-c0c8ae40b466 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4b27c998-d0c3-5f7f-942c-1296cafe20bf | note | Check Item - Hold Point 4
bba55770-fc3f-5e0d-b5c9-a711376c6509 | note | Reference - MRTS03 11.3.10
b7e4748e-e36e-4c83-a032-13c7652614d7 | signoff | HOLD POINT
ecb44aee-6676-4958-90d2-f91ac643f1d1 | checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
9f1f0523-2525-5ed2-892a-2e6b6c2d5002 | note | Acceptance Criteria & Frequency (Project Specific) - Quarry Material Test Results
b9a11194-6e19-5dd6-ad57-8cd54bd70020 | note | Check Item - Hold Point 8
90929707-b4de-5fe9-ad58-cab4697061e7 | note | Reference - MRTS04 Cl. 14.2.1
cc85bff4-8dae-4c55-83fd-6e87b3d0d423 | signoff | HOLD POINT
d8454d84-5c1b-4f8c-903a-214a0c6c19b2 | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
9fc0e4aa-d805-5986-9981-5bbf48e8f415 | note | Acceptance Criteria & Frequency (Project Specific) - Test Results
733f4e35-0a59-5ed2-b891-5d767f356840 | note | Check Item - Witness Point 5
be85af3f-3f58-56b8-9cc8-994e4bbd81df | note | Reference - MRTS04 Cl. 19.3.1
aec4f770-4a24-4611-8829-3cde6135c80e | checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pirs and so on have been completed and inspected and any specified curing periods have elapsed.
72dc4e89-dece-55be-84a5-3fe6fd03a812 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1518d4a6-c3e9-5315-ae0d-39d29387ebb4 | note | Check Item - Hold Point 14
e9cb7d1d-94bd-5137-b826-003856411d4d | note | Reference - MRTS04 Cl.19.3.3
5bf70abc-a311-4eb9-bf19-805196491fce | signoff | HOLD POINT
f21c44ef-0f4d-4aa2-a64d-85d6f67700eb | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
6d0a4642-fadf-5aeb-b275-e1edfe29e8ff | note | Acceptance Criteria & Frequency (Project Specific) - Class A: WPI < 1200, PI > 7, % passing 0.075mm: 15 - 30
cc923c5d-6890-5493-bb08-8cf4ff7ffc3c | note | ○ Class B: 1200 < WPI < 2200
b6147d87-28fc-5ede-8e83-f8b306c0f60d | note | ○ Class A/B: 100% passing 25mm
c0d75c70-a70a-5160-9d76-663cb2c74d04 | note | Check Item - Witness Point
0995805c-720f-5da0-9504-294f16bc4c0e | note | Reference - MRTS04 19.3.1, 19.2.2
d12b6bbf-aeb1-4556-914d-fdbc2a9c29fd | checkpoint | Compaction
11764cc0-1d39-522c-89ad-2c836b076f81 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
0c124c9b-fbfd-5481-8615-6f83fe1b935a | note | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
69b193c8-779c-51bc-898b-d8077a7c785a | note | Check Item - Test results
b1272ea1-a48d-5650-9933-d8994f2f23ee | note | Reference - MRTS04 Table 15.3(b) MRTS03.1 Cl.1
06131a47-1df3-4946-9950-7d4b7afeaf0b | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
fe6c5246-ef81-52fd-9542-6b1c55ec1e1d | note | Acceptance Criteria & Frequency (Project Specific) - Class A: 70-100%, Class B: 80-110%
6b601ee5-0602-51cb-b19d-bd4ad13f06a0 | note | Check Item - Test results
8e9bc64b-e8df-58a9-ad31-9d8581e399ed | note | Reference - MRTS04 Table 15.3(c)
a7535588-fe9e-4358-a908-a1605df4b16b | section | Completion
b37c7467-09a1-4c3b-bbbf-a783abf89386 | checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
954a8fc7-5b11-56d8-babb-63a0a4cc4268 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4428a0bd-c5f8-5183-a358-e62288bbba67 | note | Check Item - Witness Point
6f3eeb29-36f6-5820-b564-912fd754f826 | note | Reference - MRTS03 Cl. 21.6.2
0181a945-2ccf-4f8f-be99-b674a770170c | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
35dead0e-58b2-5278-80b9-d593a4dfd855 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
77307696-5c62-5a5f-91d5-7d00d3a25706 | note | Check Item - Hold Point 3
6385104f-f398-5438-bcb3-864fde5e1bc9 | note | Reference - MRTS03 Cl11.3.5
45530c11-d678-46d3-bcbf-bacf918805ed | signoff | HOLD POINT
230adf43-cd88-40bf-8cc6-6b737c8f7f27 | checkpoint | Final Verification
1b1030ed-bbac-55e9-b599-6a0f9f0464ac | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
8fbd286d-13a1-55f0-b45a-b9d7fc3d47c4 | textbox | Print Name:
8eb50f40-94d9-5347-bb2e-f913013ec469 | date | Date:
291e7a84-060d-552b-87e5-7c1357f6503b | note | Project Manager Verify that the Above has been Constructed according to Specification
8004b3fc-70e3-5801-a815-ea8b19fff14f | textbox | Print Name:
55b5ad1e-4c06-5e19-8e9b-365bc5310c12 | date | Date:
85ed9d3b-104f-46db-aa57-05b9c7b569e5 | signoff | Sign ITP
dd2b113d-7892-454b-835c-bf606878f81c | section | Final Sign Offs (to be completed at closure of Lot)
d43e1bf3-f12a-439e-af4c-165fbb51783a | checkpoint | Agreed Quantities
e6f5c693-6b94-4c9f-a6f1-48242861e66b | signoff | Agreed Quantities Sign Off
c6166300-6bfb-44c7-861b-937452d14e19 | checkpoint | Closure of Lot
0679dd3c-11a2-47ae-b5ed-6e9f521210f7 | signoff | Closure of Lot Sign Off
731eb439-bad8-4e1b-91fd-3af2766b6a0a | checklist | 03.22 - Subsoil Drainage | itp | 03.22 - Subsoil Drainage
612b07fc-fe34-4021-bb7a-488419272746 | section | Details
23ef6470-78eb-4f67-9863-21aa881937d0 | checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
d14d2af8-f266-5d6e-afbc-de16223813e4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b349647f-81cc-5cc2-84b8-378d2cd2b1b1 | note | Check Item - Check Item
ab0231fd-4e47-5860-a025-b67cbe99c25c | note | Reference - MRTS03 Cl 22
5e4646d7-9a3f-4b19-ac2a-0ff347276389 | checkpoint | Backfill material shall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
ea7a361e-43bb-57b0-9492-3a7f6a213381 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b716d949-e150-5f2f-a5f1-4567a79ec7ac | note | Check Item - Check Item
32ba3612-a1eb-5b86-9b40-6a1ccecdac0b | note | Reference - MRTS03 Cl 22.3
94f2ff9b-66a9-420f-9581-642bdfb26a1a | checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
ca6745a1-f589-5364-a5f3-3d02e670a977 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
223bf12b-5537-5d9c-8595-2751b0210850 | note | Check Item - Check Item
913647d8-e8e1-526e-9374-9b1cb43178de | note | Reference - MRTS03 Cl 22.3
10172aef-9503-4160-b372-d73f9325d6d4 | checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
0df6f023-1ac3-543b-81fb-dbea9b5ad89a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2f46c96e-bdb6-599b-8d0f-b0f4f7d44c94 | note | Check Item - Check Item
796049e2-f1fa-5ceb-90c4-9fc563d6de64 | note | Reference - MRTS03 Cl22.2
e585b1b5-1b90-42e9-b397-3d520f1450cf | checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
6a5b98b3-8ff3-5932-b768-7519b1cbb9ff | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f4afe2e4-8d4d-5a6c-843b-a7b54c3353fd | note | Check Item - Check Item
16c87e2f-8f57-5e44-81c2-9e39a61c64e8 | note | Reference - MRTS03 Cl22.3, TMR SD 1116
13b1bcdd-e8ba-4eb7-8c12-799f080e7edb | checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
fc546065-6c87-508a-aabd-ff0223edf1c6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7d06ac63-8d19-5e72-9b43-e0c6a0d3cab9 | note | Check Item - Check Item
ca8adf67-e039-57c4-8fe1-721e804b1382 | note | Reference - MRTS03 Cl22.2.7, TMR SD 1116
1fb09b6c-0196-413c-a597-f0487ae8b2af | checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
1ff309e6-577e-584e-8e55-078724eda044 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8daea9a4-d2ff-5e1e-a338-7ceeb0c8d70c | note | Check Item - Witness Point
3169adcc-407f-5af7-96df-919aa548414d | note | Reference - MRTS03 Cl22.3
c2f2de6d-9253-4b90-ae9c-9b8f2669e9c7 | checkpoint | As Constructed drawings prepared
60b92428-8013-5ffb-b951-0937822ffff8 | note | Acceptance Criteria & Frequency (Project Specific) - As constructed drawings submitted to Administrator
294b5168-fd6c-5311-9cf9-1c2c5398f1a4 | note | Check Item - Witness Point
bddbbab3-03f4-5f6b-a879-4ee65b627211 | note | Inspection: Administrator - To Be provided at completion of Project
0bc71eb2-e271-4f56-a105-40f3776aeb43 | checkpoint | All geometric tolerance requirements met
9f693dd9-fa07-5a43-8d07-e415cd8bc23d | note | Acceptance Criteria & Frequency (Project Specific) - Survey
05ac3379-7a09-5f76-ad92-e7e72c89d826 | note | Check Item - Check Item
67dc81df-1ae2-4c9a-8f74-adca3c4c3fd6 | checkpoint | Final Verification
935c1eff-51b1-5111-b548-8e626955d2e6 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
94fae6dd-5a07-5c15-ae08-da73c3cf455e | textbox | Print Name:
78575a92-f458-56db-8dc4-ef036d5eef70 | date | Date:
8b10fe5f-de58-592a-93ae-90e6367a1f30 | note | Project Manager Verify that the Above has been Constructed according to Specification
467e2ce2-8551-5b69-acde-0427ec7bd781 | textbox | Print Name:
80dd753a-122f-5ee2-b6a7-53e6db15461a | date | Date:
41f46617-7915-4139-8de1-692b9e7306c8 | signoff | Sign ITP
7abcdc7f-ae40-4b48-9b5b-565567398d21 | section | Final Sign Offs (to be completed at closure of Lot)
4e6c9219-13ae-41b4-b05f-d80f39336342 | checkpoint | Agreed Quantities
1175a123-f16f-439b-ada4-a8798d4ed93b | signoff | Agreed Quantities Sign Off
01ab19af-aed1-42f3-9c1e-35b0da677cb2 | checkpoint | Closure of Lot
6d57b0e9-c444-4df5-8588-4640137c5965 | signoff | Closure of Lot Sign Off
1ba1a88b-75db-422a-bc22-3d4333dda450 | checklist | 03.35 - Rock Protection | itp | 03.35 - Rock Protection
7675ca55-c736-4216-a6da-3f40942b1e32 | section | Details
16fd5c05-b3e7-4995-b7b1-276dc6d56cd8 | checkpoint | Rock employed as per drawings. If not specified, between 150 - 500mm, with at least 50% larger than twice the minimum size
45387444-c6fa-599c-b3c1-1959ce26c61e | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
9b480625-6719-5883-8f45-b96c7b041624 | note | Check Item - Check Item
5f66909d-c314-5fda-a52f-b4736473dc70 | note | Reference - MRTS03 Cl 35.2
a546cb09-0cfa-4232-b3da-a6b1b6e34510 | checkpoint | Uniform appearance overall, and shall not have noticeable overall irregularities in horizontal and vertical alignments. The layers of placed rock shall be of even thickness and of even grading
f5017e45-875d-5db9-8a19-d33d6d896786 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
4f2ce2dc-a909-53ff-95bb-182a3eb88fd2 | note | Check Item - Check Item
c4eefa08-75a6-5958-9582-a84862b13c5c | note | Reference - MRTS03 Cl 35.3
e3a4a67c-98be-4277-b4fc-af4d436eb1a1 | checkpoint | Ordering Geotextile - Documentation which demonstrates that the design of the geotextile is in accordance with MRTS27 Cl. 6 submitted to the Administrator and accepted prior to ordering.
ccc1ec77-d524-5c0c-979a-d58af2ebcd4f | note | Acceptance Criteria & Frequency (Project Specific) - Written Approval
61892458-2212-5ef4-80e0-0cbd658c06e6 | note | Check Item - Hold Point 1
7fffe91d-cec3-597c-ac71-04aa590ab4a7 | note | Reference - MRTS27 Cl 8.1
87df2067-8d7c-4290-b566-f6a7c371c74b | signoff | HOLD POINT
456be51f-f640-488e-98d0-6eaa4cafb11e | checkpoint | Geotextile - Inspection of product to be incorporated into works. Where Lot sites are greater than 5000m2, a representative sample covering approximately 15 m² of geotextile shall be cut from each sampled roll but not within two metres of the start or end of the roll. Where directed by the Administrator, samples shall also be cut and supplied to the Administrator.
50e5e517-11f5-5307-8923-b01c76517fd6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
4296c0cb-c6c4-5113-863d-5162389050f1 | note | Check Item - Witness Point
d7f43770-6e49-5688-8d4b-3458e3fb5791 | note | Reference - MRTS27 Cl 10.2
aa93b880-c75a-4965-b985-95b3c8b37ab7 | checkpoint | Compliance of delivered Geotextile - Geotextile shall not be placed prior to acceptance of the test results by the Administrator
74cb846b-2c35-5b64-ae54-c117da299cf7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
dcb65d54-7ab5-594c-b9aa-df69cb32c3e1 | note | Check Item - Hold Point 2
1cce580f-9eca-5d31-9e18-eb7fd5102774 | note | Reference - MRTS27 Cl 10.4
e76610a1-32b3-4543-8fc0-4f0dff2b4be8 | signoff | HOLD POINT
525e6f5f-071d-43cb-9871-e2300fd37d35 | checkpoint | Final Verification
ded9b1e4-341c-5ec1-94ef-d90857bffd87 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
935f2763-49b6-54d3-bd3e-f55b18284ee6 | textbox | Print Name:
f3e7b61c-82d7-53d2-b651-a3d5665f457c | date | Date:
2be439e3-cc6f-4c00-abeb-be8c0d98e303 | section | Final Sign Offs (to be completed at closure of Lot)
ef49273d-c48d-42af-8ef7-a031d759cdcf | checkpoint | Agreed Quantities
b7b15563-11d2-4a7c-a3f5-0447fd19477e | signoff | Agreed Quantities Sign Off
da0a5607-97cb-4860-bbf9-a4847534798a | checkpoint | Closure of Lot
e24fadbb-8c7c-4874-8ec7-7de6dbacc726 | signoff | Closure of Lot Sign Off
cee46c07-be59-48e3-af6b-9402b04cdab7 | checklist | 04.02 - Ground Surface Treatment | itp | 04.02 - Ground Surface Treatment
98e9e833-31a2-4390-82d4-efa472cf1801 | section | Details
c03095d0-5fd9-47bb-90ce-bdec706a3994 | checkpoint | Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the Site which could reasonably be expected to have a possible acid sulfate potential.
466d0e8d-096b-560f-8edb-c8076ceca137 | note | Acceptance Criteria & Frequency (Project Specific) - Field pH testing As per National Acid Sulfate Soils Guidance
0648eb7e-2200-50af-9c2f-2f2bccd764ac | note | Check Item - Hold Point 5
d7e7aa6b-9953-5770-8087-640e3423f16b | note | Reference - MRTS04 Cl. 10.1.4 Table A2
32c47a0d-e9ec-4724-b35b-f6807957a627 | signoff | HOLD POINT
38cf2774-f5c5-435a-9051-bd0c71d03c7d | checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
301fcd9b-8dd2-51c1-aa4f-8803fc06b4a0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
81cd14ac-b940-584f-a2ca-9708d6b3afd9 | note | Check Item - Check Item
8bdd3b6e-7446-5481-af00-3901a3cdc593 | note | Reference - MRTS04 Cl. 12.2.1.1
27e8e87a-67db-4bc8-89bc-6894accaf6ed | checkpoint | Holes and localised depressions filled with similar material to the surrounding ground surface or material specified and compacted in accordance with Cl.15
6f482148-b88b-5e20-be6b-279b4533a2cb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
cdb47630-62ab-5e78-8c6a-44b85b570ced | note | Check Item - Check Item
81c06566-b328-5643-b22c-92952cff2e88 | note | Reference - MRTS04 Cl. 12.2.1.2
29fb8cf3-398c-40b3-b3f9-fa8afdb59cbf | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim
c4b8e3cf-03e0-5f5b-9b07-96b5d446bb91 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
10556c5d-32a2-5c5a-9e96-a79ec38796b1 | note | Check Item - Hold Point 4
54b6e77b-0408-58c9-bc83-9d35a90a0c6a | note | Reference - MRTS04 Cl. 9.4
58a83d99-9d1f-4329-9bf2-ce85b0b6c71d | signoff | HOLD POINT
df1865d3-3313-4f4f-b01f-cb1ce8eaee25 | checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl. 15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a maximum depth of 300mm using appropriate methods. Material below this depth shall be assesed under Clause 9.2.
ae636c29-2ecb-5c71-8ddb-5811ff8ab1da | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f4c3e36a-bd3e-5b9c-bd6e-1bdc2c2c24d9 | note | Check Item - Check Item
94cb17b0-9db1-5264-bf76-68eb78f60a38 | note | Reference - MRTS04 Cl. 12.2.1.3
5bcea49c-716f-4779-9d51-3de369a6d12e | checkpoint | Relative Compaction - AS 1289.5.4.1 or AS 1289.5.7.1. After any clearing and grubbing, stripping of Topsoil and replacement of Unsuitable Material, the exposed ground surface on which an Embankment is to be placed shall, as a minimum, be scarified and re-compacted to a depth of at least 150 mm
4745df56-5df8-59a7-b2d4-35758c69d0b5 | note | Acceptance Criteria & Frequency (Project Specific) - CV 95% minimum - 1 tests per 500 m2 (min 1 per lot)
74b135b8-d25f-4544-8cfb-0b7c52b922ed | checkpoint | Final Verification
9eaf093f-32ba-5333-b6e2-38b111c3dc55 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
96f17425-f739-5795-bd6b-be1140afdfe3 | textbox | Print Name:
93d6e6fd-73a5-593c-b1fc-20f56148ef25 | date | Date:
9ceed3a2-c1ce-4a05-af84-1a5ab3d7df68 | section | Final Sign Offs (to be completed at closure of Lot)
b71f7a94-16c1-40c2-be60-84868acd2b32 | checkpoint | Agreed Quantities
c98b5232-224d-4800-a555-2441d741d933 | signoff | Agreed Quantities Sign Off
8911b013-cc74-4d31-864c-3efa62832bb2 | checkpoint | Closure of Lot
692c9f9f-9a80-470a-95a2-2a56e1b6c47f | signoff | Closure of Lot Sign Off
2d5bd5d3-906c-40b6-a6cf-05e1006e81f5 | checklist | 04.06 - General Excavation | itp | 04.06 - General Excavation
48bfa6d9-ce1d-4390-8645-ed450f57238b | section | Details
28415b61-5954-4629-9b39-60fa1fbe30e5 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
f54de1d9-8640-5396-a521-400891167ddb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ec4d2b3a-cb37-51ff-bffb-fd7f9d93c1b8 | note | Check Item - Hold Point 4
acf169bb-c7f8-5f2e-a822-a1f405912982 | note | Reference - MRTS04 Cl. 9.4
a0732c2b-0cda-4fd0-8d7a-229dc44f1fa3 | signoff | HOLD POINT
32851a91-8f48-425b-ab8a-57373af282f8 | checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
0a30f99d-b6d1-50b9-9a80-ba0d9908d61b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1210b5fa-088a-5df2-b16d-0d02a60ba5d4 | note | Check Item - Hold Point 8
d86f4a61-66ad-5730-9abf-932fec1ed5e4 | note | Reference - MRTS04 Cl. 13.3.2.1
af0d53e4-4c41-4842-8496-33866b6d3f4d | signoff | HOLD POINT
c541d40c-7500-4c48-a889-20068e9426ed | checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
252138e5-e1f3-5cdd-9f38-5aec11bcd5d3 | note | Acceptance Criteria & Frequency (Project Specific) - Survey
b2d125ab-9f38-5dbb-a85c-3cb6918dbf4e | note | Check Item - Check Item
14f23a0d-549b-5435-9e55-8dba04897601 | note | Reference - MRTS04 Cl.13.3.1, Cl. 6
14b67eea-aab8-4878-abb1-016c4cc61f53 | checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
a6db5755-3dba-584e-9ab7-bc3002f21b9d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7658379b-1d50-5372-821c-0ef2f5b0da82 | note | Check Item - Check Item
1a927129-51f6-53f2-84dd-634d0a7d7460 | note | Reference - MRTS04 Cl. 13.3.3.3
40db74ca-300e-4d5f-a50e-6f37c469c026 | checkpoint | Dewatering of excavations shall comply with requirements of EMP
5d4f130e-2e4b-505a-9260-c2f16c5d668f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
449f8118-da56-5101-819b-509ec3b8b167 | note | Check Item - Check Item
cba6a234-cdd8-5c28-8816-70778133ad48 | note | Reference - MRTS04 Cl. 13.3.8
3c53ecbd-9457-40d2-89d4-24f656db2002 | checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
1971c731-33b3-5515-9180-1a830c4cf4b7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d61836bb-43e8-5b6f-8fec-81de484ce177 | note | Check Item - Check Item
27b05482-6aa2-5351-8a62-f02fc56e2302 | note | Reference - MRTS04 Cl. 16.1
c183cc22-155e-4b0e-8597-3d42c541909c | checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
ed616e33-6341-545c-85c9-4bb7487745c9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3a228b8e-dcaf-5f36-937d-920d253567aa | note | Check Item - Check Item
810333d5-42ba-5a23-a2b3-f9f036f2b718 | note | Reference - MRTS04 Cl. 13.3.2.4
1b81f175-1f68-4d96-8a47-9f223a71e8b0 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
944e2944-3737-58ba-8168-b2ef4c12b84b | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
6b847c1d-7584-5e9e-af56-83fc67796d10 | note | ○ 10,000L water tanker with 600kPa tyre pressure.
396027f3-5aee-54e0-866e-c3c03dbfbd24 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
31d70de1-f097-5d21-950f-e3780c244b82 | note | Check Item - Witness Point
f9780ac5-53e2-531c-8222-5e8d3c666a4d | note | Reference - MRTS04 Cl18.3.2 RMS T198
e9162269-25c4-431c-bd27-6a0e2ccff054 | signoff | HOLD POINT
1ce22f46-f0f0-4483-8338-7d8a73134f20 | checkpoint | Final Verification
8e878198-0df9-5283-baee-4f1aaf509c00 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
f7c1c71f-3dc9-5546-a159-6fecb75bd3ea | textbox | Print Name:
b67ab0c3-3982-5a09-9fb8-1b51823030cd | date | Date:
daf5b1f6-cb35-48fb-8960-9b86f31e3940 | section | Final Sign Offs (to be completed at closure of Lot)
ff70bd08-67da-4191-ab2e-58ad410fbc3d | checkpoint | Agreed Quantities
e31b5272-a5ba-4dbc-9722-59042c8d7ba5 | signoff | Agreed Quantities Sign Off
a58b1194-16dc-4572-8794-88d340ee49df | checkpoint | Closure of Lot
dd50da82-4fb8-4eed-b791-82c111524994 | signoff | Closure of Lot Sign Off
668ec8f0-2e29-4d40-9456-8f6d536e9eaa | checklist | 04.08 - Embankment | itp | 04.08 - Embankment
e2de9987-9940-49ec-b43c-020b7eba5021 | section | Details
5fbd6017-3f3c-4bdc-914f-23efb7a4085a | checkpoint | Earthworks construction procedure shall be sumbitted to the Administrator at least seven days prior to commencing the Works.
0a34486e-2603-5e65-933d-afa0f08d7eee | note | Acceptance Criteria & Frequency (Project Specific) - Construction Procedure Acceptance
6ee302dc-b751-593c-9380-7aaf791b0d48 | note | Check Item - Hold Point 1
3dde39b0-1f31-5e77-844e-e9d3e450f55e | note | Reference - MRTS04 Cl. 5.2
5e63884a-2bfb-44d3-80bb-94144b6eea1d | signoff | HOLD POINT
1492e732-391b-4af5-9b89-26c53ce626a5 | checkpoint | Define lot size.
320db480-afde-5c0c-a29d-eab19955ad74 | note | Acceptance Criteria & Frequency (Project Specific) - Normal : Max 2000m2
16d5c57b-9332-59ff-9141-44b384ae941f | note | ○ Reduced Level : Max 4000m2
02f56449-7cf3-59ea-8763-a45d39497ff2 | note | Check Item - Check Item
c411c38b-f590-5c54-8c5f-e49be10a354d | note | Reference - MRTS04 App. A Table A.2
ab8f9a77-879a-4006-8dc9-3ab5ace9534e | checkpoint | Earth Fill Material stockpile or source material results submitted to Administrator
65e630c3-00b6-546b-aaca-3eac6569fd9e | textbox | Reference Stockpile Lot No.:
bf2f7b80-a69d-50a9-a77d-f8ad1ebf0eda | note | Acceptance Criteria & Frequency (Project Specific) - Stockpile Lot Acceptance
83e05e6a-6b1b-537c-b164-0b81d99a4537 | note | Check Item - Hold Point 10
8b7cd1d5-e54d-5cc2-99f6-8ced6239e29c | note | Reference - MRTS04 Cl. 14.2.1
539976f3-f8bf-49d0-9232-0bb30b4afab5 | signoff | HOLD POINT
64ac5853-8ef7-495b-9b5f-1e97faac0a1b | checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported, complies with General fill Class A1, A2 or B and is homogeneous.
c25fd32b-6f5b-549f-a841-2528e3ca1f12 | note | Acceptance Criteria & Frequency (Project Specific) - Stockpile Lot MRTS04 Table 14.2.2
542aa1e1-5e10-508d-b860-70fe8c3d2d86 | note | Check Item - Test reports
41c5a153-0a99-5c13-9095-3ad51e6e65fb | note | Reference - MRTS04 Cl. 14.3.1
ebf07a23-cd11-413b-9367-1fad6945c3e3 | checkpoint | Compacted Layer Method:
e95ecb7c-1f76-5c3e-8d8d-437e9e21f4c6 | note | ○ Fill material placed uniformly in layers. Uncompacted layer thicknesses;
7a2bbae3-9666-5efd-b8b2-0a1eb66583e6 | note | – General Fill 150-300m
09a77487-891d-5b87-bb3f-46dcead4d003 | note | – Fill material in water-retaining embankments 150- 200mm
9379d92d-fa7e-5bfb-85d7-76232bbb4a82 | note | – Backfill except Sand 100-150mm
76b2bb94-8fe2-5dda-bbf5-64e04e880ade | note | – Sand 150-300mm
d8d2e81b-10f1-55fe-99b4-f77c3c5e26a2 | note | ○ Fill compacted to required density (by Characteristic Value)
af29457d-532d-577c-9851-19a1da1fbdfb | note | Acceptance Criteria & Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
f8e0a26a-2b6c-57d0-9d20-83c8752ee2ba | note | ○ Top 300mm below Subgrade Level ≥97%
2d1ca41c-fbce-575e-a223-81c0c97e7c63 | note | ○ Greater than 300mm below Subgrade Level≥95%
65269d26-5e87-56fb-8c79-7973008b30fd | note | ○ Normal: 1 per 500m2 (per layer), 4 per lot
2516a9b2-6831-5895-a471-d4783902086e | note | ○ Reduced Level: 1 per 1000m2 (per layer) or 4 per lot
ef64879d-5af2-5d3e-9212-a51c7806004e | note | Check Item - Test reports
0276dc40-b7cd-5629-ab9e-916e75aa23ff | note | Reference - MRTS04 Cl. 15.3 Table 15.3(b)
a8dec7bf-5fb1-4a11-8d84-5281365f33e3 | checkpoint | Compacted Layer Method: Embankment moisture ratio within ranges specified Rainfall Zone: HIGH
0608476b-13cc-5cd2-8934-4a2f0073b3b6 | note | Acceptance Criteria & Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
eb77e7ad-0547-5182-a4ce-1fcd838f8dbf | note | ○ Class A1/A2: 70 - 100
3065fd16-a4bc-5c18-a1fe-dc267422b200 | note | ○ Class B: 80 - 110
b82e5aff-5d1d-51c8-ac3e-fdea60904539 | note | ○ Normal : 1 per 500m2/layer or 4 per lot
23bd6f9d-9781-528c-a4a6-9622e5284c68 | note | ○ Reduced Level : 1 per 1000m2/layer or 4 per lot
41093e94-4282-51d5-a9df-6170fc165e99 | note | Check Item - Test results
0b8030ce-772d-5a86-abe9-f6561261d6bf | note | Reference - MRTS04 Cl. 15.3 Table 15.3(c)
b463b0f0-42c3-40a4-ba29-f4a0f5944e24 | checkpoint | Testing of Each Layer - Each layer shall be tested to conform the requirements as per Clause 5.6 before placing the subsequent layers.
e6223c8d-70e0-5e9a-b26b-8d1f4d71b3ed | note | Acceptance Criteria & Frequency (Project Specific) - Testing after compaction on site Gradings: AS1289.3.6.1
c28b30d1-a8c1-50e2-b46e-c9a9a238a86b | note | ○ PI: AS1289.3.3.1 or AS1289.3.3.2
13939b4b-691d-56d7-ada4-f5b5b4a0f0ec | note | ○ WPI: Test Method Q252
303ee43a-a6b8-5e89-9ff1-890584162e4d | note | ○ 1 per 1000m2(per Layer), 2 per Lot
b86ac86a-3fc9-589d-887c-71fe7f27d885 | note | Check Item - Witness Point 5
79778d20-e360-573f-9775-a8be5c531724 | note | Reference - MRTS04 Cl. 15.3
f5c90917-526e-4019-a96d-d3cb97a4383b | checkpoint | Embankment Foundations; Under all embankments within the job site to a depth of 1.2m the minimum CBR shall be 3% in-situ
4e180313-a1dd-5d5d-8cc0-d4de99948221 | note | Acceptance Criteria & Frequency (Project Specific) - CBR 3%
51e32937-c684-53ba-88e9-efeebac6e4d9 | note | Check Item - Check Item
9319ccd7-64de-57f5-8c31-21e87d2bd6e4 | note | Reference - MRTS04.1 Cl 3
4558fce9-1428-4b32-a88d-ddd1cc4330bf | checkpoint | Embankments - Earth fill material shall have the following properties: All materials - 0.1m depth below subgrade level (if applicable) - min CBR 2%, CBR soaked condition 4 day soaked, CBR target density 97%, CBR target moisture content 100%
ef8cbe44-f313-5e11-afee-ecd9bebeba6f | note | Acceptance Criteria & Frequency (Project Specific) - Min CBR 2%
947bd6fc-0bf6-515b-914c-bfb828c372bb | note | ○ CBR Target Density 97%
d8849666-c3b3-56ff-825f-a0238a6d1a85 | note | ○ CBR Target Moisture Content
4350e011-907d-5ba5-8396-075d1654dd40 | note | Check Item - Check Item
4a6fb7fe-1070-554e-a278-c17b6cb0c160 | note | Reference - MRTS04.1 Cl 9.1
d488d252-5c94-4f44-8b1d-7efc5a9872af | checkpoint | Mechanical Interlock Method: Each layer rolled until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
90e003e7-f97d-5647-b709-c0610fe6b80e | note | Acceptance Criteria & Frequency (Project Specific) - Table 15.4
e533e74d-32a3-50d1-9f57-539fa8f2b2f0 | note | Check Item - Witness Point 6
568b66ea-6c37-588a-adbc-1428a20b1297 | note | Reference - MRTS04 Cl15.4
2bb77f2e-516a-4c6c-8735-9d12fb1f9b4f | checkpoint | Geotextile placed at interchange between compaction methods
9feef40e-628b-5d68-a7c5-f89c56e07f0d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
170a8a9c-d157-577a-a4de-5c646b3270f1 | note | Check Item - Check Item
11d1cd1e-a0f0-534a-89e8-7757b06cfd65 | note | Reference - MRTS04 14.3.2
48c25c69-4d75-4a14-84c4-648a61d44084 | checkpoint | Within Vertical Geometric Tolerance
bed10a9b-b078-5320-b85f-888f63ac284a | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
87ac2302-f90c-5483-a5c1-4d16b048415a | note | Check Item - Dip Sheet Records
210f3fe4-e5a1-57c3-a3f1-410bf75d9443 | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
d5f755b0-f296-48be-8b4e-e45f7e3d747e | checkpoint | Final Verification
508443a0-6373-5729-91c6-8fca156d704c | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
c2de7460-dc8d-5d55-9f3a-5dc54e09ce66 | textbox | Print Name:
f7fb3754-4321-59df-bc4f-a83676696b90 | date | Date:
f07e5c2c-016d-496b-9471-5f0e316c6627 | section | Final Sign Offs (to be completed at closure of Lot)
796e6851-eddc-4108-b24f-c80ae643e592 | checkpoint | Agreed Quantities
a3dcc0a8-039d-419d-a65c-6cfc871940c3 | signoff | Agreed Quantities Sign Off
5fb1ddaa-d90d-40e5-93ec-f92ebbf7975c | checkpoint | Closure of Lot
ef352dd5-f9ef-4064-9c80-a142e8b1e423 | signoff | Closure of Lot Sign Off
a5d1d41f-e223-486b-a951-b1d2a742708d | checklist | 04.08 - Stripping of Topsoil | itp | 04.08 - Stripping of Topsoil
0c0ab948-7d12-46fa-886c-d418c8c2bbbf | section | Details
a480c521-2377-47a0-8091-8e5bea73c328 | checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 75mm (+/-25mm) depth, or from areas and depths as specified in Clause 2.1 of Annexure MRTS04.1
d2c75919-ab67-5ee2-b576-bdedef1ec035 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
135324ee-b6c2-5f65-94ac-abb08b78f334 | note | ○ All areas within the earthworks footprint; beyond the back of existing kerb or where there is no kerb, beyond the existing road formation shall be stripped to an average depth of 100mm
772919e7-520a-52df-879e-09917e1fb6b7 | note | Check Item - Check Item
c9ec01f0-8a1d-5f8b-aa97-dd2f937725ea | note | Reference - MRTS04 Cl. 8.2 MRTS04.1 Cl. 2.1
7f58122d-3e4b-4292-9f06-5c4abeec4f6f | checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
06a28d27-4317-54a3-a523-190f74fd26d8 | note | Acceptance Criteria & Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
c5d7312c-73a3-5a0d-b97b-80cd59950bf8 | note | ○ Stockpile Topsoil - 2/500m3, min.1/soil type Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
2733ba28-ad49-5a1f-ae65-9bfbad93f464 | note | Check Item - Check Item
0fd19099-f552-525d-95ed-6bb2079b6ec0 | note | Reference - MRTS04 Cl. 8.3
5de07e94-999b-458c-bbf0-4409844bb35e | checkpoint | Surplus material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
2f64591c-3265-5314-929b-dc04cce5ed07 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7a5834bb-8c73-5f2b-9fd7-788d1034fa14 | note | Check Item - Check Item
43d182fd-6d55-5ad1-a837-cca9965c5d20 | note | Reference - MRTS04 Cl. 8.4.2
c991e7d8-7818-4057-95b7-b6c63e9ee2e0 | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
dc9ef9dd-2d9f-5a57-a800-5279e2a75aab | note | Acceptance Criteria & Frequency (Project Specific) - Visual
de3b5391-59ed-5766-9daf-8d5658202722 | note | Check Item - Check Item
78bf8924-7601-5ba3-a613-6528dc2552c0 | note | Reference - MRTS04 Cl. 8.4.3
15e5f921-5d5f-404a-b03a-ca8b5e959fce | checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor and approved by the Administrator, as stated in Cl. 2.2 of Annexure MRTS04.1. All costs associated with undertaking necessary earthworks required for the stockpile sites shall be deemed to be included in the Contractor’s scheduled unit rate for the corresponding earthwork items
7a5c896c-5e71-5b44-a2d6-052726487008 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6237f73c-d1b1-5e33-8f48-02f6b6218147 | note | Check Item - Check Item
b223fca1-51f0-5462-a8a6-b82ff10da0bd | note | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
ae8f0509-a3cc-4745-926e-2915efedbcd3 | checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
ddebe69f-816c-5bac-98e3-0239f755c25d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
85b189c0-f174-5e80-a2a0-0ba2585674c9 | note | Check Item - Check Item
a4947924-ec17-5916-84b4-c033c5005ce5 | note | Reference - MRTS04 Cl 8.4.5
ef6d4e5e-9ba3-4992-9212-800193b9e29d | checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
9c6845f7-72d0-5876-81ed-460ef6d87288 | note | Acceptance Criteria & Frequency (Project Specific) - As Constructed Survey
cc10e700-866e-5b87-93b2-692310657d81 | note | Check Item - Survey Report
33b52c11-303e-5138-be7e-4f7222a4fdad | note | Reference - MRTS04 Cl 8.4.5
e4942e21-6f98-4974-bfd9-cf2efb3f5e91 | checkpoint | Final Verification
6ce71907-5601-52b5-b627-5d562f872ef6 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
690f5f4d-c4d2-50e0-a224-0724d3db9efb | textbox | Print Name:
b73a9a11-168c-54fb-860d-8f50633c9888 | date | Date:
cede65f4-4a4d-4eb6-9f51-87ea78f487e8 | section | Final Sign Offs (to be completed at closure of Lot)
a319f8bd-a5b8-481e-bf11-d7b3fbd6ad10 | checkpoint | Agreed Quantities
3339885d-184f-44a7-8670-320afee46c24 | signoff | Agreed Quantities Sign Off
d5c355b7-5374-4ca1-867e-2ea81f686e5f | checkpoint | Closure of Lot
324e4e65-27c4-45a4-818f-efdea2a9e7fb | signoff | Closure of Lot Sign Off
1c72f58e-479f-4bae-8646-84b6ba2dafc8 | checklist | 04.09 - Clear and Grub | itp | 04.09 - Clear and Grub
912db3f2-0355-4fe8-8668-10fda2de91f2 | section | Details
462aa2a3-4ce2-4218-b10a-a0c0f66c61b6 | checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
347541e8-49b9-5c7c-8f20-8e10bd8fedc5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
16f22ed7-38ed-5186-aac3-2b6df0ed8642 | note | Check Item - Hold Point 2
b436295a-14e2-5265-9c05-dc2dd18c51b0 | note | Reference - MRTS04 Cl. 7.2.2
12906024-1a5a-45ca-92c3-9c4d823ef03d | signoff | HOLD POINT
896cdc27-7a7b-43fd-973a-47846184a110 | checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 1.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
384e27dd-0d36-5b8d-9b21-5ca2527b3648 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2873dca4-58eb-56b9-b185-6edb4296bff7 | note | Check Item - Hold Point 3
5edb36d9-46ad-5fa5-a7b6-e6f419f50f52 | note | Reference - MRTS04 Cl. 7.2.3
762b37c9-17a7-4172-add7-d5bc589b5dee | signoff | HOLD POINT
f3407923-cce5-458b-9107-9309c15089b8 | checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area shall be installed.
e66fc037-0dba-504f-94c8-94831569a0bb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b345643e-3704-5182-8fab-9ace3218635f | note | Check Item - Hold Point 2
4e0ab9d3-05eb-5f1d-896c-8fa9d5b534fa | note | Reference - MRTS52 Cl. 7.1
f9979d89-e8d0-4f99-bde1-0085994d44e4 | signoff | HOLD POINT
6b130809-b7e8-421c-8118-321597a96885 | checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
74d376b8-11db-5f65-9cc3-ac0d494a9d49 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8f50cacd-6d24-59e0-9dfd-f8748af924e5 | note | Check Item - Check Item
d48862db-7593-591d-9d45-5a585bbe3876 | note | Reference - MRTS04 Cl. 7.2.5
551ddb2a-31b0-4dd4-8453-45df9e1c66eb | checkpoint | Surplus material and material considered not suitable for use as topsoil in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
c867b2df-6a35-54f1-8e4c-91d1486e6873 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ad365cd2-e2b9-5114-bfa1-780eba7791bb | note | Check Item - Check Item
c62b9c5d-b176-53b9-a352-b1907e688c34 | note | Reference - MRTS04 Cl. 8.4.2
f1cab5cf-8520-46bc-a9cd-c707358ad6a0 | checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 & Cl. 1.4
105e1462-5dd5-522f-a225-fd9c240851b4 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
47ef9586-4dd9-50d9-b86a-c3b952dfb476 | note | Check Item - Check Item
f1f6e0d1-ee67-594b-b339-d17231246254 | note | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
f90f5d03-287d-4c2f-a4ae-dfbe27465fda | checkpoint | The additional width for clearing and grubbing the lessor of 2.0m beyond the extents of earthworks, or the property boundary (excluding any areas indicated on the Drawings as an Exclusion Zone) as per Annexure MRTS04.1 Cl. 1.1 . Any local infrastructure or landscaping within the 2m extents is to be assessed and confirmed with the Superintendent prior to clearing activities being undertaken. The Superintendent may direct the removal or retainment of any features at their discretion.
5e9c06cd-a42c-52b5-a1d0-e11c98bca670 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
72c96626-2eaf-5238-8007-2e33e5abb1d8 | note | Check Item - Check Item
11d4d41e-687b-545c-bbd2-fb26123e5978 | note | Reference - Annexure MRTS04.1 Cl. 1.1
f1858502-5052-4db8-b8e4-6e3a0aca933d | checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
470955c0-e712-5f91-afd4-d8c9e975793e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c711a358-f79c-5643-89c5-1f1b9d6ba170 | note | Check Item - Check Item
62895cd2-41f4-55a3-9cd5-4571a21e1a49 | note | Reference - MRTS04 Cl. 8.4.3
265f0d73-801d-4f97-8ee7-2499feb27108 | checkpoint | Final Verification
3f90eca6-0f0d-591b-acd1-2170c6888403 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
307e0fe6-d5de-5784-b1d6-77c28b4ec514 | textbox | Print Name:
28b0fee8-c7ca-504e-bb8a-bcf788c63e9f | date | Date:
a3790818-3c8a-4d69-9520-a531b8146d47 | section | Final Sign Offs (to be completed at closure of Lot)
0dc684a5-3643-4235-bf99-c2232d54ef18 | checkpoint | Agreed Quantities
46e3905a-03ed-4fa8-979b-67eb3bc8ea8d | signoff | Agreed Quantities Sign Off
bad8fd7c-dc91-452b-88af-c1a2c0dd343f | checkpoint | Closure of Lot
31b280ee-8998-4aa6-9988-7a6916fedc6a | signoff | Closure of Lot Sign Off
ec9a0299-7a08-4d97-9c12-044ab23fb545 | checklist | 04.09 - Subgrade Level | itp | 04.09 - Subgrade Level
3d723306-cc44-4119-8231-3185654cbcee | section | Details
f4f96f2d-c580-4ec0-b38e-464067ae91e5 | checkpoint | Define Lot
d1bdb2c6-9bae-50c1-9a0c-89ce49083ec1 | note | Acceptance Criteria & Frequency (Project Specific) - Normal : Max Lot Size : 4000m2
2d89da01-0fdd-5d4f-a52f-0e682d32128d | note | ○ Reduced : Max Lot Size : 2000m2
39e5d46a-904b-5951-b44a-19953744885d | note | Check Item - Lot Records
b975c840-9633-55a2-9c94-0a648a57ec84 | note | Reference - MRTS04 App A
e24ac0e3-1890-4a97-b12d-5da0d88be613 | checkpoint | Reporting Pavment Design Requirements - For Contracts where the Principal has supplied the pavement design (that is, Construct Only or similar Contracts), the Contractor shall submit the following information to the Administrator for each existing Subgrade Lot:
96a3769c-1223-58de-94e0-55e72c5ec4b7 | note | a) test pit logs
6c617b87-0720-5cc8-bff0-d1705497845e | note | b) all test results for each layer encountered within the test pit, including certified test certificates, and
3d0c4a7d-a674-5086-8ed1-83240a6b8245 | note | c) marked-up drawings accurately showing all test locations within the Lot.
391bc26b-10f0-53ec-99bd-3f9199a05f06 | note | The Contractor shall allow a minimum period of 14 days for the Administrator to review the information prior to any Subgrade treatment and the placement of any overlying materials.
600e2f0e-04a3-550e-9635-10d8d97522f3 | note | Acceptance Criteria & Frequency (Project Specific) - Submission to Administrator
22eb03bf-8d62-57a5-bab5-f578f64f5a57 | note | Check Item - Hold Point 16
96001efa-4a54-50fa-be49-9d1006783297 | note | Reference - MRTS04 App B.6.2
386c5468-a81f-433f-bc7d-5ef45009d3a0 | signoff | HOLD POINT
616a6d56-cb63-45d3-b8fb-7c0cc9026317 | checkpoint | Bottom of Excavation for Cuttings - Where subgrade is reached in cutting works shall cease until subgrade treatment type has been directed by the Administrator in accordance with Clause 13.3.2.1
540c7db1-288c-56a9-9c00-4a7bd523807f | textbox | Subgrade Treatment Type Directed:
c6b0e461-2edc-5513-85ac-85a21769664c | note | Acceptance Criteria & Frequency (Project Specific) - As directed by Administrator
dab916eb-450a-54b1-bdd3-2c24bfd31ce4 | note | Check Item - Hold Point 8
1e93eab2-6a1f-5093-8e3b-1fcac3026851 | note | Reference - MRTS04 Cl13.3.2.1 Cl 18.3.3
fde1afd0-cd47-4812-b341-b2e2fcb72bf6 | signoff | HOLD POINT
bbee0ca2-ad58-49ef-bc61-d9083cea4a09 | checkpoint | Subgrade Treatment Type A - As ordered by the Administrator at subgrade level on all section. The material below Subgrade Level shall be to compacted a density of not less than that stated in Table 15.3(b) and to a depth of 150 mm.
389ac352-7107-51ae-9ea9-34eca1e434ef | note | Acceptance Criteria & Frequency (Project Specific) - Treatment Depth - 150mm
6d347084-7278-5512-be15-40d170214cfc | note | ○ Compaction Standard: min 97%
42b2c252-e434-59d9-aa5b-f798c1fdfb64 | note | ○ Normal: 1 per 500m2, 4 per lot
957cd673-7302-528c-969d-f5e4d4806d20 | note | ○ Reduced: 1 per 1000m2, 1 per lot
7b5ef9d6-6736-5c1b-99d0-a09f2a179418 | note | Check Item - Test Reports
204561b8-5c64-5533-a081-4fc84a125c51 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
616b8a63-9a2e-4523-a933-8e6bd4b66ada | checkpoint | Subgrade Treatment Type B - As ordered by the Administrator at subgrade level on all section. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and to various depths, as directed by Administrator, typically between 150mm and 250mm.
9ae768e5-3257-57f3-8abf-e885898af932 | note | Acceptance Criteria & Frequency (Project Specific) - Treatment Depth - 150mm-250mm
7335bee1-0d1c-5f12-8f5b-46250d6f2477 | note | ○ Compaction Standard: min 97%
b891be08-3565-5a04-be14-f76e172fbc06 | note | ○ Normal: 1 per 500m2, 4 per lot
58ceff71-e53b-5b94-a18e-5fb279e58fce | note | ○ Reduced: 1 per 1000m2, 1 per lot
e176b736-1c52-5e14-a4bd-33a8222a2e04 | note | Check Item - Test Reports
f29c2b74-93ba-5f0c-b4b0-b7187e977998 | note | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
2d6ea3ce-c7ac-41c0-94d8-14c443bc0062 | checkpoint | Subgrade Emabankment - Material to be compacted to requirements not less than that specified in Table 15.3(b). Subgrade relative density tested to Q140A.
70ad41b9-f62c-59f6-b337-3af2cb3a1378 | textbox | Material Source Stockpile Lot Ref:
94bd78f1-4feb-546e-8772-5b80b7f91073 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
9777d834-9b00-5b9b-a925-772813e06176 | note | ○ Embankment Fill at subgrade: Class A1, B, Unbound Granular or stabilised material: min 97%
ace5d19f-d406-5625-add5-4afc261e18b4 | note | ○ Normal: 1 per 500m2, 4 per lot
8e347876-8de5-5ada-8ef0-157d94ca9769 | note | ○ Reduced: 1 per 1000m2, 4 per lot
c8b2c09f-1c81-5964-948b-c659a68c3198 | note | Check Item - Test Reports
e16be81d-f21b-57c2-bd41-2ab228878254 | note | Reference - MRTS04 Cl15.3(b) App A
31fd2a2c-350e-4ddc-99a0-23ab673cb686 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
3d168943-8300-52f8-98ac-d179f50ad515 | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
a93428a7-8770-5570-a575-7f0d4d48266e | note | ○ 10,000L water tanker with 600kPa tyre pressure.
1b2409af-9ea1-591d-b93b-07e3bfaf1305 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
7ab40af2-6128-5ed6-88ee-2413d10e6d8a | note | Check Item - Witness Point
033c658e-679b-54ed-b5b4-00fd98a24806 | note | Reference - MRTS04 Cl18.3.2 Q723
f5e3c9c2-452b-4d92-94a3-5b58fcf235f3 | signoff | HOLD POINT
9e14a4a9-f3a1-4611-a4dd-d281411231bf | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
48b684b0-12f7-55e7-ae75-a6f4239e35de | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
651949f5-bca8-5e18-90e5-5dadde3610d9 | note | Check Item - Dip Sheet Records MRTS04
303c3cf7-8d21-5eec-b0a2-8897e726e33d | note | Reference - Cl. 6, Cl.13.3.1 Table 6.3.1
d2e26e7d-d109-418e-b742-160581afdc37 | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
982be595-9c29-5b15-8d27-5cbadb741684 | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
3141cc04-84a9-5692-b00b-8971ed8224a2 | note | Check Item - Dip Sheet Records
5879072c-11f6-58e6-8787-49fd72fc5e89 | note | Reference - MRTS04 Cl. 6.3.2
cc9a47d8-2c18-4328-b2ad-aa52df062a50 | checkpoint | Subgrade shall not pond water and be free draining.
3c902505-9096-519f-a95c-9c6f85ed1692 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d1d4a3b0-999b-5d9d-a4ba-c762700bc4f7 | note | Check Item - Check Item
681d14db-a2f1-50ab-8b71-cece1ec87e46 | note | Reference - MRTS04 Clause 6.3.2
f7925881-fb34-4970-b0d2-2117d957dbcb | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
f0391b69-ae24-573b-924e-4c1d477142f1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
00cde754-6f6b-5731-8089-322c462729cf | note | Check Item - Hold Point 12
28621052-deed-5cae-8f19-06891d7b689b | note | Reference - MRTS04 Cl. 18.3.1
79aafb6f-83bf-493f-87f7-5cad841dd336 | signoff | HOLD POINT
63b91a1d-06a3-4598-b881-e5ea9a6e1939 | checkpoint | Final Verification
18836e4b-2081-53bd-b6cd-c42944801302 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
262e1018-9948-557e-b2bf-a0a72395f97c | textbox | Print Name:
02d3ba9b-b107-5b0f-82d3-bdf5ec352b62 | date | Date:
5baf8a78-adec-4e7a-9c23-a5ec98a56488 | section | Final Sign Offs (to be completed at closure of Lot)
5033d2ab-97db-43ea-999c-4abcf0f7303d | checkpoint | Agreed Quantities
a9bdd6e2-773a-49d1-be10-30bc067a5fa0 | signoff | Agreed Quantities Sign Off
0cb2deed-a818-4f54-821c-4fc6b8a342c4 | checkpoint | Closure of Lot
9969e3c6-14db-433c-a956-a86159329991 | signoff | Closure of Lot Sign Off
04cdcfa3-cc22-442e-b071-1128dbe6d32b | checklist | 04.09 - Unsuitable Material | itp | 04.09 - Unsuitable Material
7b960459-a2e7-4bb4-98ba-174ac23040c5 | section | Details
3353ede4-be83-4a5d-8a6d-771a5a9643ed | checkpoint | The identification of unsuitable material shall include items listed in MRTS04 Cl. 9.2
9755b726-155e-5042-8ac9-7afd6841aa26 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4af352d9-d747-522e-9086-51c34652d0bb | note | Check Item - Check Item
72d17d28-3899-5732-a796-6f41ad879f88 | note | Reference - MRTS04 Cl. 9.2
6398e16c-3bf2-4ef1-a123-3de926b11df0 | checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
2780be98-329b-5bad-b54b-682b5810300e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
513a7726-c342-51f2-9beb-d5af37bc3087 | note | Check Item - Hold Point 4
005e4e2a-84bc-5487-bf3e-f46947ede752 | note | Reference - MRTS04 Cl. 9.4
c29a237e-5af7-4827-b751-a4ffa0a10bfe | signoff | HOLD POINT
d19bc550-2004-4206-b88c-8c3f1eaf3fc0 | checkpoint | Excavated as per MRTS04
a8ece1ab-c136-5705-9ef7-5cfb34d22bee | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (General Excavation ITP)
e33c2298-2244-5b89-80e0-eafca6f4f6a1 | note | Check Item - Check Item
73ff65df-c34e-5b3e-88e0-4f190bb6a411 | note | Reference - MRTS04 Cl. 13
9d02c5ee-5532-4d8b-ac8b-2dc4fb3fda3f | checkpoint | Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 and notice of such Works provided to the Administrator
99c38545-ce2c-585b-b384-a2eebaebf27c | note | Acceptance Criteria & Frequency (Project Specific) - Survey Report
30ec849e-a4db-5286-ac67-2797101d4222 | note | Check Item - Check Item
f87de7a5-b86b-5f00-9517-6e7a6995e450 | note | Reference - MRTS04 Cl. 13.3.2.2
72772839-483a-4c9b-b42b-cd0520bdf14b | checkpoint | Backfill as per MRTS04 - Replacement fill material shall be placed uniformly in layers and compacted using compacted layer method
08224c51-9862-55ab-b8c7-9d19f5bafc5e | note | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Backfill ITP)
f9d77bb2-0056-5eae-b701-5147c7a6486f | note | Check Item - Check Item
bd252d1e-0dc6-586e-8e60-b0e67857c942 | note | Reference - MRTS04 Cl. 13.3, MRTS04 Cl 15.3
c51804ac-ffbb-4e08-acd7-6bea5b20faf5 | checkpoint | After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken.
64a17f88-3a6a-5b6d-a278-df6ce652dc8a | note | Acceptance Criteria & Frequency (Project Specific) - Survey Report
7cdf1554-7152-52ee-892e-327576b82d52 | note | Check Item - Check Item
44deea10-8ac0-510b-9e00-537c6788563a | note | Reference - MRTS04 Cl. 13.3.2.2
3045ef69-7979-4fac-b44e-9f7dc270be6e | checkpoint | All surplus material and/or Unsuitable Material shall be disposed of off the Site
5e97cce6-9324-5fa0-908f-b74f983f002d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1ca467ec-1901-5f91-9774-2cafcbcc0895 | note | Check Item - Check Item
d4cfc91b-dd6e-5171-8470-5c385534909e | note | Reference - MRTS04 Cl. 11.3
78d10c6a-2e52-4178-ad3f-232e3a4b36c2 | checkpoint | Final Verification
054b89da-d766-55b8-8cfe-9863cb30f7fe | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
2eb36f4d-44f2-5572-9f7d-e60f3c0e183c | textbox | Print Name:
7f0273cd-af68-5a98-9806-4d466e88ccd8 | date | Date:
9a805a7c-6df6-4f03-8a51-6390232c90ed | section | Final Sign Offs (to be completed at closure of Lot)
1029363d-63fb-4acb-bf5b-69e080170dec | checkpoint | Agreed Quantities
830c784f-d960-4a22-9136-9702bbbd5926 | signoff | Agreed Quantities Sign Off
f6ea80f2-8de0-4fa9-b347-37ce3a2bb282 | checkpoint | Closure of Lot
eb354d0f-feb2-45b8-885e-b23cf93937fb | signoff | Closure of Lot Sign Off
65b8aebf-4d03-44f5-8ad5-797ea31b4391 | checklist | 04.20 - Installation of Steel beam Guardrail and End Treatments | itp | 04.20 - Installation of Steel beam Guardrail and End Treatments
336693be-0d72-487b-932f-a4a8ed14ccd1 | section | Details
3c03eb25-9995-4d27-9b85-0369ccbe7ba5 | checkpoint | Manufacture of steel beam guardrail post, panel components and end treats are manufactured by an approved manufacturer.
ae987d9c-8513-5338-8948-ea96c4cc23b0 | note | Acceptance Criteria & Frequency (Project Specific) - Approved Manufacturer
ef309ad4-875c-5d73-9a78-73070e772940 | note | Check Item - Check Item
015786d6-152f-5a83-81f9-3c06ee49467b | note | Reference - MRTS14 Cl. 20.2
68e7a2be-5e98-4032-be0b-bf6993974fc7 | checkpoint | Steel beam guardrail components and end treatments shall only be supplied by an approved supplier.
03b7c519-fda4-5b43-bd88-8dfd91f9350e | note | Acceptance Criteria & Frequency (Project Specific) - Approved Supplier
04246fa4-12b8-5dd9-a140-49b4991199a9 | note | Check Item - Check Item
3894f495-c5e9-5974-b502-7d04e6fd208d | note | Reference - MRTS14 Cl 20.3
3f8719db-af36-4127-b326-bcb543a3599d | checkpoint | Hexagonal head bolts and nuts shall be manufactured to the dimensions shown on Standard Drawings, and tested in accordance with MRTS78. Mushroom head (C) bolts shall be manufactured to the details shown on Standard Drawing 1479. Circular washers shall conform to the requirements of AS 1237.
99e50099-c26e-588b-83fa-8b7ddb658d7a | note | Acceptance Criteria & Frequency (Project Specific) - Test Certificates
4e155bf3-8bdc-547e-9da7-ad21370b4c07 | note | Check Item - Check Item
5f966ece-5fd7-5cdb-a54c-91bc5e1365de | note | Reference - MRTS14 Cl 20.4.7
18d48442-c291-445a-9229-b2da8eb0d437 | checkpoint | All panels, steel posts and blockouts shall be batch stamped during the manufacturing process with manufacturer's ID, Metal grade and thickness, and batch number. Single batch <2000 items.
8e597d4a-c650-5ac2-b707-f9ec704b578d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
aae1d83f-be4d-53cd-b485-45fd8dca2c12 | note | Check Item - Check Item
ea15c331-3177-529c-b9a8-d1306a2ee423 | note | Reference - MRTS14 Cl20.4.2.2 Cl. 20.4.3.2
fd6e497d-e24e-4d37-b2b1-3876c5828521 | checkpoint | All steel components shall be hot-dipped galvanised after manufacture in accordance with the requirements of AS/NZS 4680.
319c65fc-5f4b-5cae-9c5d-cdaeeef4b356 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
47706136-4dd0-56af-8a6f-5b4a35d4319d | note | Check Item - Check Item
0594dede-af05-5b07-bfa7-f4a4abc3c6d7 | note | Reference - MRTS14 Cl20.4.1
8a74784b-4268-4b6f-84f2-d948b6859c8a | checkpoint | All the steel manufacturer material test certificates shall be supplied to the Administrator. The test certificates shall show the full chemical composition including the carbon equivalence, and mechanical test results for yield, tensile and elongation
92e403b7-33fa-51a9-9777-605e2885d2b1 | note | Acceptance Criteria & Frequency (Project Specific) - Test Certificates
9429244a-1bdb-575e-b43e-15c23adc9a90 | note | Check Item - Hold Point 7
7a625cf7-c9f9-5c16-9fc5-87b438e4a7de | note | Reference - MRTS14 Cl20.4.5
b2390695-2b77-4bbb-8212-45138bf8f24f | signoff | HOLD POINT
5c2992a3-df4f-4467-8c3a-78bea0f7ff28 | checkpoint | If required, the Administrator shall randomly select two post and two panels from each batch number for audit testing.
28036ea0-7444-5301-b49d-5f74927808d6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
69a879c2-8cca-51c2-b649-5a51643cfabb | note | Check Item - Witness Point
75590ae5-810a-50d1-ae8a-3737191eb44c | note | Reference - MRTS14 Cl20.4.6.1
e5385725-ae31-464c-a2b9-2151797b1ca1 | checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied for the batch of guardrail components.
b3fb7120-e137-5a00-b522-ec3f6c2cfbcb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
691db4f8-95de-5830-b544-6ddd61a60781 | note | Check Item - Hold Point 8
e27ce6b4-1567-5b81-96f6-9e98202299f8 | note | Reference - MRTS12 Cl20.4.6.3
d4b098b9-efa4-4c34-860b-94ee8d71ef36 | signoff | HOLD POINT
1cf615f1-4c68-4a43-bb4e-34310ac48b46 | checkpoint | A list of component parts and fabrication drawings defining the dimensions and weld sizes of the various components and the grade of materials and relevant standards with which the component materials are required to comply shall be provided to the Administrator prior to commencement of installation of the device or system.
dbae97c0-8e3e-5749-9527-610c3d74e6a5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
11271c08-8ed1-53c1-95da-b70f4d2742a2 | note | Check Item - Hold Point 11
4f03d794-82f6-5f5e-a73d-2972d0ef905d | note | Reference - MRTS14 Cl21.2
cbc23ba7-d511-43da-a7b6-87b4be42bfb2 | signoff | HOLD POINT
90c368b2-57f2-4d50-aebe-a66ce792cbd7 | checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
4702f3a6-c893-5fad-a345-5656df420b4c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
43dea991-cad4-50c2-8e64-f0fc64e85709 | note | Check Item - Hold Point 1
143d2e26-cf70-583b-8ca2-91b7cb2c6d38 | note | Reference - MRTS01 Cl.8
9ed6e79a-663b-4b82-812b-a1d2f3254c10 | signoff | HOLD POINT
77fb40bb-b765-4301-a9e2-4223bfee6655 | checkpoint | Dial before you dig consulted and services located where required prior to excavation or driving of posts
9fe66d00-46a6-544a-9875-13c166e261f7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c5b19635-9350-58d0-a06c-f803557fa88c | note | Check Item - Check Item
9ad2b6a2-daf8-4459-b487-c50147b8bd31 | checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings.
6ad11a4a-b9fd-5794-b661-9f6a6518e7a1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
4153ac90-4107-5b39-b486-ffc7a33250c7 | note | Check Item - Check Item
7fb782f8-3511-5f5c-afc5-10b7a3e37dba | note | Reference - MRTS14 Cl20.6.1
2feeb462-f12d-4532-9502-7f24ce314874 | checkpoint | A proprietary road safety barrier system and/or end treatment shall be installed as shown in and required by the design documentation, and in accordance with the requirements of the installation manual
93e2750a-6ad3-54e9-b8fa-254096cf7a9f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
61681abe-cae9-5e30-b594-f4d66dc052ce | note | Check Item - Check Item
b8e61337-2eb6-56fc-ad88-234cb09e08a8 | note | Reference - MRTS14 Cl.21.4.1
f3548a0c-94c6-4bec-9668-6e63a05ddb65 | checkpoint | Public Domain (Departure Terminal): Soil plate on type 2 departure terminal shall not be omitted
9a4a0aec-41a1-5bd8-9715-c9fc9b216c5f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d00756d3-a385-5e05-b67a-c5c96d7b8c61 | note | Check Item - Check Item
50be96f3-be95-5b6e-806a-fd0e2ee37a5c | note | Reference - MRTS14 Cl20.6.3
eb01bc5d-9985-4694-aaa9-72aa9d46d93c | checkpoint | Delineators installed on steel beam guardrail in accordance with the MUTCD Part 2
c3d991d0-7a62-51dd-b852-f77046c2fd69 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5e982527-46c6-5a04-86bb-3d99977a288f | note | Check Item - Check Item
5a17ef2c-b803-5686-81e3-e881049a224b | note | Reference - MRTS14 Cl20.6.5
5f90f009-78ec-479f-ae8f-ed8ad7bd9ec4 | checkpoint | Installed within Geometric Tolerances
0f87aff0-8e8a-5f8d-a1ad-6ce0ddcdaf7e | note | Acceptance Criteria & Frequency (Project Specific) - Post Verticality: ± 15mm
64a96182-3881-5eae-a223-f27c6712f30d | note | ○ Post Height: ± 10mm
829c5057-bab8-58b1-838c-65184651a30c | note | ○ Rail Height: ± 10mm
1a3b5a24-4e66-5398-9bcf-4e5d78114624 | note | Check Item - Check Item
09609562-bf39-5496-bcd4-5777cb67ae94 | note | Reference - MRTS14 Cl21.4.6.2
3b1e3987-3b10-4b9f-8f13-c051e91e388a | checkpoint | Administrator accepts guardrail installation as per the design documentation
241985fe-1a7d-59ee-8b91-fc7a41643ec5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2e6607e5-97db-5d3d-a9ad-d764de900719 | note | Check Item - Hold Point 10
3ba40c7a-758e-50dd-bb65-15dca1263047 | note | Reference - MRTS14 Cl 20.6.7
2e863d6a-5ae0-4f76-8529-fd6acf6da070 | signoff | HOLD POINT
d6ab180f-a655-405b-905b-bebcaa97fd50 | checkpoint | Final Verification
b1ed18fc-abc5-5829-9772-82a69248b0f8 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
48f6bdd4-22b4-5ea4-99d6-03a2560a8211 | textbox | Print Name:
2acd5874-3837-5f6a-a37a-7b0975ccd392 | date | Date:
ce01f164-c35a-428f-8055-0b2305577e01 | section | Final Sign Offs (to be completed at closure of Lot)
11105dd9-1557-4dd8-b446-3f677e3879ec | checkpoint | Agreed Quantities
6a2182fd-88a5-4390-ae1d-79f6c8f2a8a5 | signoff | Agreed Quantities Sign Off
a2271af4-2c9a-4598-94ac-7cc61d50e5d0 | checkpoint | Closure of Lot
b2a236bf-2141-4d7d-bcef-32b73cac396c | signoff | Closure of Lot Sign Off
c0eb53fb-4184-482f-9892-53c8ceac964e | checklist | 04.091 - Subgrade Treatment Type A | itp | 04.091 - Subgrade Treatment Type A
65c8368e-5519-4c84-922f-53208dd447d0 | section | Details
2ae0e122-16e3-448d-b053-19ebddefbf89 | checkpoint | Define Lot
1ef94f60-0448-5783-a9ba-690a8041e33d | note | Acceptance Criteria & Frequency (Project Specific) - single layer produced in a continuous operation in one day
c8987aea-eaa9-50fa-92a5-e082aeb1c39d | note | Check Item - Lot Records
507aecbf-3ee0-57eb-82f5-f173aa1af9aa | note | Reference - MRTS04 App A
6b2cba09-76f0-4fc5-a13b-dda1b917b6e3 | checkpoint | Trim and compact existing - Subgrade Density requirements Q140A -Material to be compacted to a density of not less than that stated in Table 15.3(b)
3fc5a642-e02d-525e-a9bd-d32b757ac359 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
3fb30cd5-8554-5411-bda1-a09dcc776449 | note | ○ Existing material in cuttings: min 97%
feb54ad4-53d2-5538-b4ae-ab2dc53c0067 | note | ○ Normal: 1 per 500m2, 1 per lot
6262d666-455e-5deb-a672-a3a863f32623 | note | ○ Reduced: 1 per 1000m2, 1 per lot
0dc9661b-4a42-5bb1-abf3-1a88d3f126f3 | note | Check Item - Test Reports
b57ff1d7-ee12-5ca2-966d-c15b43792206 | note | Reference - MRTS04 Cl15.3(b) App A
ac856e2a-2657-46dd-873b-88d27513cb70 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
c3cbb032-0fdf-54b4-82be-ac985b845839 | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
6cc8a129-3335-501c-a789-94a66fa0d899 | note | ○ 10,000L water tanker with 600kPa tyre pressure.
b151abeb-4573-5158-9dea-d2911e35754d | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
b94ab110-545c-5389-85d2-fdec3f315c80 | note | Check Item - Witness Point
9ff1f352-5c31-57af-924f-494594d85a0e | note | Reference - MRTS04 Cl18.3.2 RMS T198
ce2eb6c7-44d4-4f22-865f-57ecd6bde752 | signoff | HOLD POINT
619e60bb-830a-45ab-87d9-d10a9c250f43 | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
1c4c5a36-e5b2-5126-ab73-decfe10034cd | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
b0e486e4-e478-556c-96be-32edfbfc2356 | note | Check Item - Dip Sheet Records
4390e6be-48d6-5a49-a3e9-af401f302a9b | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
5d036c7a-425a-405b-a2a1-2b75b724e839 | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
7f7ad6de-2f57-50f0-84f7-4901b6ad865a | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
2b7d106d-2be3-5793-b2b7-8cdfd37f7353 | note | Check Item - Dip Sheet Records
f56100fd-145d-5540-9417-d368b7d369bf | note | Reference - MRTS04 Cl. 6.3.2
13bed220-bb1a-43ec-afe1-92073796a4d8 | checkpoint | Subgrade shall not pond water and be free draining.
87709fbc-e8b7-591e-9464-9214d49dcea8 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c61e64c7-28b9-52f4-84cf-f0c9e95ee425 | note | Check Item - Check Item
e69f0a87-3063-589d-9b47-eb1163355a24 | note | Reference - MRTS04 Clause 6.3.2
005cffd9-b580-49d3-b950-1c242415d5ec | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
d20c28c9-ab91-558c-bc73-d9b51736d2a5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
aa5487c4-3005-5df0-a2ca-a36b05b5c123 | note | Check Item - Hold Point 10
a56b27ec-13fa-5c87-9594-ef10d92b6eea | note | Reference - MRTS04 Cl. 18.3.1
7b5feced-987b-4c97-8ce2-2148f5c46ca0 | signoff | HOLD POINT
fb9002c4-db38-4d36-8375-a9c7fc9511b3 | checkpoint | Final Verification
02dde255-dcb3-5f9c-92b9-9aa3aafe40dc | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
89d159d7-8853-50fe-8f50-2574102a83f9 | textbox | Print Name:
921d3fcd-bf54-5406-8e47-2c02fc2581dc | date | Date:
23ba9913-8b9d-4b33-b234-7326458af098 | section | Final Sign Offs (to be completed at closure of Lot)
9a7d66dd-505b-4dff-b805-63af88fe27f5 | checkpoint | Agreed Quantities
98bc84b5-82b4-4173-80fa-1f48dfee780a | signoff | Agreed Quantities Sign Off
a1fd8e0d-3f56-4daa-ad62-50220534eb92 | checkpoint | Closure of Lot
622ec525-beb8-482a-b147-628f431f6466 | signoff | Closure of Lot Sign Off
8df6920e-3711-4c7e-8cc0-94dc0a6ecb93 | checklist | 04.092 - Subgrade Treatment Type C | itp | 04.092 - Subgrade Treatment Type C
226e1ae6-a9fc-4370-bd35-875b37f332d5 | section | Details
79669948-8a98-4ba3-b6e1-3fffd8f12886 | checkpoint | Define Lot
fe7fb26b-3dd6-589a-a3d4-57251c7abdf3 | note | Acceptance Criteria & Frequency (Project Specific) - single layer produced in a continuous operation in one day
ef400e12-7c86-574d-8276-85d045936aab | note | Check Item - Lot Records
76d56de4-e49c-5ca4-bb8f-990e5cb678a0 | note | Reference - MRTS04 App A
f3dff0a9-4a8a-4004-810b-34637039d139 | checkpoint | Unbound Granular Material incorporated into unbound treatment shall be as specified in MRTS04.1 Cl. 12.1 and meet the material requirements specified in MRTS05 Cl. 7.
0a15ca94-a180-5198-9a4f-fd2146397315 | textbox | Material Type:
ca5c4c7b-be09-5330-9f30-3f3afee85562 | textbox | Material Source Stockpile Lot Ref:
db6592a0-ca9b-5df6-8d45-f54a7de62fc7 | note | Acceptance Criteria & Frequency (Project Specific) - Unbound Granular Material Stockpile Lot
f2c08ed6-6b43-5cab-9de0-7cb544b6c097 | note | Check Item - Check Item
dd155413-0252-56e6-98d4-fdb1c42608f7 | note | Reference - MRTS04.1 Cl 12.1, MRTS05 Cl 7
f215275f-9c7b-46f1-90f3-8d2b07e9348e | checkpoint | Subgrade Density requirements - Material to be compacted to a density of not less than that stated in Table 15.3(b)
0531d8c8-6a6f-5176-958c-f567fc9acc47 | note | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below subgrade level -
297fd154-6707-5a62-9d2c-3021b6b98cd4 | note | ○ Existing material in cuttings: min 97%
96c899d2-ec18-5802-af65-2b86fffde895 | note | ○ Normal: 1 per 500m2, 1 per lot
0d9b9415-4e9f-53ec-ac48-62f6797f67aa | note | ○ Reduced: 1 per 1000m2, 1 per lot
bd98b7c8-447e-513d-92f2-bcc12324172b | note | Check Item - Test Reports
dc96323f-5c37-5baa-8bd6-8e49e47ba6fa | note | Reference - MRTS04 Cl15.3(b) App A
4ba8ab5e-7533-4f13-a45c-3d72f1f127f9 | checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
5423f85d-c33f-5fac-a277-7e36665237b4 | note | ○ pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
465c65e7-37cb-5818-8e87-e04323bd7cd9 | note | ○ 10,000L water tanker with 600kPa tyre pressure.
8a338ae4-7b0a-5c4a-99de-5d48eb89f729 | note | Acceptance Criteria & Frequency (Project Specific) - Visual, No Deflection Continuous
cbd3b5f7-1f39-51f5-ad2d-ba6a376942db | note | Check Item - Witness Point
13b81c99-7f89-5baa-a316-7287c937c657 | note | Reference - MRTS04 Cl18.3.2 RMS T198
0fd23471-7df0-4d2c-b3d1-9b51bc7506a7 | signoff | HOLD POINT
23e18093-81c9-42ae-bf69-0c180b539760 | checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
55bc053c-b47d-5fe5-a1f9-13515423f820 | note | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25 average ± 10, 1 test /20m
ca6e97a7-c2ff-5165-84cb-8a0c16b9ee17 | note | Check Item - Dip Sheet Records
65c06375-9eb2-511c-aeea-f3b5ea2d432b | note | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
ca6834ae-1f48-4630-b55b-0f8b350dbd65 | checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
a5f79162-680a-5a83-8019-0bb94e0fa4b8 | note | Acceptance Criteria & Frequency (Project Specific) - 1 test per 20m (Left and rigt)
dc0d43c2-987a-5dbb-9391-878f21eca4ba | note | Check Item - Dip Sheet Records
59ccbed9-2c0a-5a9e-ba0f-584c5cca3744 | note | Reference - MRTS04 Cl. 6.3.2
16cecebb-15e6-4c54-9889-7fb5c169465b | checkpoint | Subgrade shall not pond water and be free draining.
473b992d-7fa6-5af0-90cf-377572b82b3b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
292e2662-5ad1-5f49-bb43-62263c0f93a5 | note | Check Item - Check Item
d2f22fc2-21b4-5a42-a216-b9bd45ad6042 | note | Reference - MRTS04 Clause 6.3.2
f27ae47a-af9b-4716-ae91-42b6b6aaacf2 | checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
8f82313c-899b-5e20-a810-e957de41057a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
fc752bec-6518-5334-a023-18e0b0085ce6 | note | Check Item - Hold Point 10
0a3ca54c-c003-5706-83d9-311b20ae26f6 | note | Reference - MRTS04 Cl. 18.3.3.1
a98e640d-2290-4ab6-a73a-9e2e2bab219a | signoff | HOLD POINT
0aa78ca5-6ad6-4140-96bf-fbef14589c42 | checkpoint | Final Verification
b3648b15-f7f5-5073-b6d1-f2301ce8bb83 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
06ec6481-c464-5820-9db3-88ef8c716de7 | textbox | Print Name:
b348a896-6be5-50e4-a36d-893787c09b58 | date | Date:
112cc4a0-a4f5-40a1-b428-ccaa3dbc2655 | section | Final Sign Offs (to be completed at closure of Lot)
be853ccc-36bd-4072-a2bb-023608e3d29a | checkpoint | Agreed Quantities
ad8b6949-d411-4082-9445-738b1621fd6a | signoff | Agreed Quantities Sign Off
92d0739c-dcff-4820-a984-978ccdf2de12 | checkpoint | Closure of Lot
b1bdb9d1-63f1-4ef5-bed0-d723d3c703ee | signoff | Closure of Lot Sign Off
1912b0f2-1509-45cf-95a5-db33911d9f08 | checklist | 05.01 - Unbound Pavement | itp | 05.01 - Unbound Pavement
0e7d8755-efe6-4deb-98ec-2c0bcc8146f5 | section | Details
98454b91-7006-4284-b3a8-9799ef81bd28 | checkpoint | Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
550bc815-7e68-592d-84a1-2ec2b9f6dd45 | note | Acceptance Criteria & Frequency (Project Specific) - Supply of unbound pavement materials - 5000tn
0206fc9d-46c3-5616-8725-0a9090462f19 | note | ○ Maximum lot size - A continuous single layer constructed in 1 day's production Road rouhness testing: maximum lot size 100m
91b8ce98-03fc-53f2-bf24-eca72950aeb9 | note | Check Item - Check Item
04007d4e-2b30-59d9-bae7-fb5ee5ae1590 | note | Reference - MRTS05 App. A Table A1
ecdb6440-018e-43df-b594-7299d4e38efc | checkpoint | Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
6977c7a2-245d-5557-ba95-07508e3a03ff | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Registration Certificate per quarry
a862b091-91f9-5b29-aca8-e1f300971545 | note | Check Item - Milestone
8762c4fc-6f82-5459-952e-99ad83b7f6ad | note | Reference - MRTS05 Cl.6.2
da2cc59b-33d1-4ba0-8d66-3543f0913465 | checkpoint | No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator.
5262c5b6-6c07-51d3-a446-95dc6baddad6 | note | Acceptance Criteria & Frequency (Project Specific) - Approval of procedure by from the Administrator
a0525b19-bba3-5ad1-b976-763d1a2d5c64 | note | Check Item - Hold Point 1
3822a1fa-f421-555e-b535-4ac228ceff91 | note | Reference - MRTS05 Cl 5.2.1
45a93879-6cf7-4754-add0-e3b971e6ce68 | signoff | HOLD POINT
2814b56d-e5de-461c-879e-11d9002f25e7 | checkpoint | The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the works.
4763a557-cba1-5469-8b6a-10be65143692 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of production procedure
0d11b9e3-68d3-5bd4-9502-d1a6b4930741 | note | Check Item - Milestone
92bca496-723b-51d6-9d13-44827b583215 | note | Reference - MRTS05 CL 5.2.2
2a3d0837-308a-4325-877c-9269261f851c | checkpoint | Submission of Construction Procedure for unbound pavement construction at least 14 days prior to commencement of works.
eb35132c-80b8-57a3-8d2f-97be0dec1cc9 | note | Acceptance Criteria & Frequency (Project Specific) - Approval of procedure by from the Administrator
26392876-a3de-5cdc-b5f7-f33238a48db1 | note | Check Item - Milestone
9f4f3138-63a1-501d-9521-c9ef73f06e87 | note | Reference - MRTS05 Cl 5.2.3
6f6c3fc4-6a64-4eee-97a4-768aca21efbb | checkpoint | The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works.
c79fa0ab-b7fe-5182-93fe-acb8b78d45b7 | note | Acceptance Criteria & Frequency (Project Specific) - Written Permission from Administrator
df2b95e3-18fd-5847-bd48-391af3e6099f | note | Check Item - Hold Point 2
20d34b1a-44c3-5407-9f08-aedd9a9cc211 | note | Reference - MRTS05 Cl.6.1
7e1e81d6-8304-4344-9dfe-e63235c9d7d9 | signoff | HOLD POINT
afdab425-c71b-4e72-a259-c1a2831550f2 | checkpoint | Layer Thickness between 75mm and 250mm for all subtypes excluding Type 1 (HSG).
41134252-f28f-5469-9544-c32fd5fd2911 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Layer Thickness 75mm - 250mm
d243047a-4b55-5fd3-8cd8-6e99a6ab671d | note | Check Item - Check Item
efb51ccc-340a-5404-bc69-f6632e92b473 | note | Reference - MRTS05 Table 8.3.3
634043db-0fbe-48a5-beef-bcb65be977bf | checkpoint | Minimum value of Relative Dry Density Requirements C.V of RDD = 100% MDD for Base course 2.1, 2.2, = 100%, SDD for other than base course 2.1, 2.2 and 100% SSD for all layers of 2.3, 2.4 and 2.5.
2b97d3d8-69a9-5481-956f-0ce6a63cd2fb | note | Acceptance Criteria & Frequency (Project Specific) - C.V of RDD >= 100% MDD
c5ebebe2-b972-5667-b266-238c9e6781c5 | note | ○ Normal: 1 test / 500m2, 4 per lot, Reduced: 1 test / 1000m2, 4 per lot
7d178423-c805-5b97-84f7-5e87c54f2b84 | note | Check Item - Check Item
6efe6634-6a0d-5dc0-8f13-337125144033 | note | Reference - MRTS05 Table 8.4.3
6c0dc768-4efa-4ce4-9105-c75cff3899aa | checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
bf26f059-47c0-554c-8a8b-026642ab3ea5 | note | Acceptance Criteria & Frequency (Project Specific) - All tests as described by this ITP and MRTS05
17ab98d6-2128-5db6-b6c2-dabb70c44e1c | note | Check Item - Hold Point 3
d0f42beb-c5b0-50b5-b97d-063e741b59a0 | note | Reference - MRTS05 Cl. 8.2
34eb1902-abdc-499e-b152-903d47da1c70 | signoff | HOLD POINT
43aa9e3e-574c-4196-aa7e-1c2469790c71 | checkpoint | Moisture content such that the degree of saturation is less than 70%(modified).
0fcd5fac-a9a7-538c-9c84-87a33b20c28f | note | Acceptance Criteria & Frequency (Project Specific) - S < 70%
317c8fee-a911-534a-8257-b0cb45e37435 | note | ○ Normal: 1 test / 500m2, 4 per lot, Reduced: 1 test / 1000m2, 4 per lot
ce635989-3d92-5f3c-ab5f-0260b6903c59 | note | Check Item - Hold Point 4
ce852f9d-01bb-54a8-b4a8-3c4f181f6b53 | note | Reference - MRTS05 Table 8.3.4.1
d5c5d8cc-5bf6-4d95-b137-395212bcc94e | signoff | HOLD POINT
6e003471-84a9-4053-9d07-85f812521dcf | checkpoint | No visible segregation of material. Particle Size Distribution Q103A.
f43bf596-051c-5475-a851-b27a278f6efe | note | Acceptance Criteria & Frequency (Project Specific) - Min 1 per lot, Additional tests as directed by the Administrator
12a11679-5fc2-5300-aed1-75bbb4d748cc | note | Check Item - Check Item
6313cd4d-2e4a-55aa-8931-2052e9db00eb | note | Reference - MRTS05 Table A3
d7aa5fb1-b98a-4830-860e-f1c2968c71a0 | checkpoint | Geometric Tolerances in accordance with MRTS05 Cl.8.4.4.3
fd340ecd-f772-56d4-86c0-9780acd5b6b5 | note | Acceptance Criteria & Frequency (Project Specific) - ±10mm when covered by AC, ±15 mm in all other cases (1 test / 20m)
589c7493-c0d4-5b29-9c1f-bdd074507422 | note | Check Item - Check Item
0875821c-3439-5e19-9e57-19bb6388f955 | note | Reference - MRTS05.1 Cl.8.4.4.3
ee10cc79-ec71-4c41-a05a-57fc66f9dea9 | checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
05523f63-24c6-5381-8cf2-80c1cd1e6984 | note | Acceptance Criteria & Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
3245528d-15d3-53f7-bdf8-945a6b2409dd | note | Check Item - Check Item
6f3ed19d-7531-5992-9b7a-3c068af1fd06 | note | Reference - MRTS05 Cl.8.4.4.2 Table A4
2315ab3d-0cc8-4a7e-bbbd-8e2b937ef19e | checkpoint | Deviation from a 3m straight edge shall be less than 5mm for material types 1,2,3 and 4
51610d83-a8b2-5243-b977-97256ad7679b | note | Acceptance Criteria & Frequency (Project Specific) - Straight Edge Test Less than 5mm 1 test per 20m
95ba279f-448f-560d-89ae-14659ad4667d | note | Check Item - Check Item
89e46826-b628-5554-9833-8e651717ffe0 | note | Reference - MRTS05 Cl. 8.4.5
00a4ac57-fff2-4abb-ae69-2f48bddf8458 | checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
cb02e4df-2df1-5b0e-ad89-045d31e8dbd3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual Continuous testing
2986b4f2-d9d5-5a26-af4a-f344238d6e71 | note | Check Item - Witness Point 2
b0d3c1e1-0787-5671-8177-8c73fb024fc6 | note | Reference - MRTS05 Cl.9.4.7
cdd8d192-403d-41f4-8cd2-4d482678867d | checkpoint | Additional Geometrics (final layer only) The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
7d75e10c-b409-5b68-8b06-871b8b9fdc42 | note | Acceptance Criteria & Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
c2820f77-d620-5d74-adf3-1e0fdc85b6b4 | note | Check Item - Check Item
4b5cac1e-872c-5b85-86ea-3feff24a9a25 | note | Reference - MRTS05 Cl.8.4.4.4
097e32a2-4d35-4013-940c-3ad53586c53f | checkpoint | The contractor shall provide a methodology and calculations to determine the road roughness to the Administrator for acceptance. Roughness shall be less than 2.31m/km.
651ef515-485f-54bd-ae24-ead792f3d58c | note | Acceptance Criteria & Frequency (Project Specific) - Less than 2.31m/km 1 test per 500m
fc868932-ef45-54fa-94b9-c52936132c59 | note | Check Item - Check Item
5b323ef9-6ea2-5943-ac79-8382daf6a983 | note | Reference - MRTS05 Cl.8.4.6
969e6c5c-431d-434d-bea3-b99bbd92f1d9 | checkpoint | The finished surface of any unbound pavement layer shall:
dcae3e94-2b6c-560e-9db5-646ebe7afaa3 | note | ○ be hard and homogenous in apperance
daafa5b5-777f-557f-b56b-950e2b631dcf | note | ○ not have any loose, segregated or contaminated areas
1db804c7-10d5-5576-bac6-678bb551efa2 | note | ○ have the coarse particles slightly exposed
22b95441-d6bb-54c4-a360-4f11fd2b0319 | note | ○ not be affected by delamination
69b41ac1-8386-5e4d-8407-a5cc922ba7aa | note | ○ not show signs of water pumping, and
3c34030e-4a0a-55c4-b890-c6a20ea279f0 | note | ○ not visibly deflect under load when proof rolled in accordance with Cl 9.4.7
a11a48d1-47ae-55c3-9f05-c0e272032e35 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3cfa16e8-4654-5526-88da-3c48a19d2497 | note | Check Item - Check Item
dd0b0b02-a755-55f3-9b4e-5208bb846733 | note | Reference - MRTS05 Cl.8.3.5.1
282c0aed-3824-4a90-b44e-1a1c4d13e22c | checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
7052d05f-b4f4-5537-813f-344a60e272d4 | note | Acceptance Criteria & Frequency (Project Specific) - Test Results per lot
05d59969-c841-52eb-afaf-9464ceb5934b | note | Check Item - Hold Point 5
fe4a7dc5-df08-58e4-9abf-d2e1b6d3a8d0 | note | Reference - MRTS05 Cl.9.1
dfcdd8a7-7a0d-4c86-89bc-395c34d62de9 | signoff | HOLD POINT
3a1e203b-a984-4c64-a865-0cd88d54fe60 | checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
82b30aae-031f-5556-8434-8d724f54e1da | note | a) all testing has been completed
e9a304d1-cc85-51f2-b7ba-5eb1985bf83b | note | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
31ed0803-d1ae-5511-ab37-b84995d4abb9 | note | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
ce2fd56a-85dc-57c3-b44a-bf3636471fa0 | note | d) the layer has been presented to the Administrator for inspection, and
582622fe-ed71-5b79-a5b8-e016bb2ef80f | note | e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
b0b5783c-5bbd-5c70-a162-9650299e3f4a | note | Acceptance Criteria & Frequency (Project Specific) - Adminstrator Acceptance
af4796c3-f643-5516-9adf-de20e87f6cb0 | note | Check Item - Hold Point 6
0a3ac3da-15d4-5aad-8c4b-a33b73115690 | note | Reference - MRTS05 Cl.9.5.1
ecbeed89-b271-4b27-b259-925241d8d8d2 | signoff | HOLD POINT
a5abfdd7-93e9-4c0b-890b-8b301f6ef94a | checkpoint | Final Verification
6822cddb-5f8a-51a1-be36-f881b4da53fb | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
702d3e5b-3fb9-57e4-aca6-b4714e0236fa | textbox | Print Name:
04dd5589-c1e8-54a5-bb6e-669554e18e45 | date | Date:
acdf4546-6c16-4119-9d5d-9907e4cabe2f | section | Final Sign Offs (to be completed at closure of Lot)
6b1cd4f1-0fda-4988-b2ec-4a626067793c | checkpoint | Agreed Quantities
09900bd4-455a-46dd-ba78-0f2130a798da | signoff | Agreed Quantities Sign Off
f2b40c45-28f0-46ad-8f89-b792bfbe4946 | checkpoint | Closure of Lot
65df9372-52ea-4d82-a984-f653a24fee1d | signoff | Closure of Lot Sign Off
e9ae2134-b890-43a1-b16f-099671d30a6b | checklist | 10.01 - Plant Mixed Lightly Bound Pavements | itp | 10.01 - Plant Mixed Lightly Bound Pavements
5c948b6f-ddd7-485b-a055-2f24d7c259fa | section | Details
d7981711-0738-485a-b0ac-c4d867099ca9 | checkpoint | Construction Procedure: Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator)
bfb40890-e4db-5774-a594-089f4839a2a6 | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
39aa658e-8809-53a0-a647-884f7aa735d6 | note | Check Item - Hold Point 1 Milestone
fc89ff5d-3528-5774-82d9-e833c6af14e2 | note | Reference - Clause 5.2 MRTS10
992c9b42-67fc-4ea6-9ace-cf35b2e019a9 | signoff | HOLD POINT
a51548af-e282-4b02-b440-df104aaed7ba | checkpoint | Material Requirements - Unbound Pavement Material - The Contractor shall not incorporate unbound pavement material into the works unless it has been demonstrated that the unbound pavement material lot conforms fully to the requirements of MRTS10. All conformance results shall be no more than six months old.
9873cc81-e474-5775-b8c6-af2915a690d4 | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
025c04e9-fcf6-5d42-a32f-34d24f4f1113 | note | Check Item - Hold Point 2
05a01c10-7f2d-52e0-aee6-85f4686b2489 | note | Reference - MRTS10 Clause 6.1.1
40cc745c-a96d-4a29-88cc-4f18db287124 | signoff | HOLD POINT
c0ef00ba-1997-42f8-99af-134cdecf599c | checkpoint | Mix Design Report: A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator.
6898e151-ab16-57b7-9a19-f9b566845fbf | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
c226aeba-dde7-5a00-bc52-d091280211cd | note | Check Item - Hold Point 3
ff046f64-6c5e-525f-9524-b54132bce4bd | note | Reference - MRTS10 Clause 7.1
ac5b2bdc-02e6-4730-be0f-d7fb00389041 | signoff | HOLD POINT
76b2c4d9-8c5e-4024-84e8-ffe5cc556751 | checkpoint | Moisture Content - The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure:
80d0bcf5-e836-56d9-b8b6-d24ca5ef1269 | note | a) there is adequate moisture to achieve the specified compaction standard
0926dcaf-b2a2-584f-a8c8-eeafe63d21f6 | note | b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and
66542960-35f9-58f9-a913-264ad4b326ef | note | c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A.
d4b7f3a3-9b98-5ea6-9ee2-bd312b2b395b | note | Acceptance Criteria & Frequency (Project Specific) - Testing - AS1289.2.1.1 1 per 500m2, 4 per lot
a8e912fa-cc22-53c6-bd35-f32ebe3ce269 | note | Check Item - Test Report
9f04b2ad-f952-50d8-bef4-c90e89ac3c48 | note | Reference - MRTS10 Clause 8.2.5, Clause 9.4.8 Table A3
efd5de3f-d3c7-4f04-8e10-f76fbdb6ebcc | checkpoint | Construction - Trial Pavement
cf9f8ac4-5f95-5221-9ec5-09b7a01f6fa5 | note | ○ Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
fe457406-6223-58c3-b8fd-68f2df3e5805 | note | ○ The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression.
db1498f6-b596-5b65-bfad-416ab1b925ce | note | ○ The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken.
e906813c-beeb-5328-8e06-8265792af88e | note | Acceptance Criteria & Frequency (Project Specific) - Visual & Check
f651dfbe-b643-5af3-995a-adb48b677dcf | note | Check Item - Witness Point 1/Hold Point 4
d1e1c01c-c6ea-57c6-92ea-0c111e64d9a6 | note | Reference - MRTS10 Clause 8.1
d2ad3642-8a3d-4e0f-9d9d-ac002065db5f | signoff | HOLD POINT
5480d59a-d4dc-4376-9968-54fa9e1f8a31 | checkpoint | Material Compliance Testing - Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
009bd2d3-e10a-5cac-b1ab-59d8db6752ac | textbox | Material Type:
b6499639-00f0-5326-9b5a-c9965c1c158f | textbox | Material Stockpile Lot Ref:
51afc2f5-dc70-5d78-9497-c4aa51f2343c | note | Acceptance Criteria & Frequency (Project Specific) - MRTS05 Cl. 7, Table A1 MRTS10, Cl.6, Table A2
9cdc4d8c-d2b5-54f6-b33f-7711522d8ede | note | Check Item - Check Item
de8d6334-c622-50e7-8a3a-38a41936e50b | note | Reference - MRTS05 Clause 7
54150820-6caf-461e-8385-14a0c83d9a7b | checkpoint | Equipment - Equipment as specified in approved construction procedure
5f6647cb-984b-5641-841d-20b8b99b501d | note | Acceptance Criteria & Frequency (Project Specific) - Construction Procedure Approval
e47251d4-472f-596d-800d-7f43608c8c11 | note | Check Item - Contract Notice
b32cb426-bc8a-5ed9-98d3-d7f45f425fb0 | note | Reference - MRTS10 Cl.8.2.1.4
a4600a61-e9bf-4d3a-ad2f-a45a7ddd49e5 | checkpoint | Weather Conditions - CMB material shall not proceed when:
6126ed22-dbed-54ec-a283-30170e1171a9 | note | a) air temperature is less than 10°C or greater than 40°C
e1e70f8f-4f7a-5bd1-bf48-bfbb41ffc0d0 | note | b) during rain or when rain is likely to fall during placement
1e29b809-2f15-5c19-b9f4-ebe5d70d86a8 | note | c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB
895a579d-74e0-5f54-9de8-455d823af0d6 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
4201b49f-b112-5173-aaa7-1a905c3de34f | note | Check Item - Check Item
87845d68-c4b4-5f95-9212-bab6f36db183 | note | Reference - MRTS10 Clause 8.2.4
02b949eb-1a3d-45e0-bf5f-e7186d5d64d5 | checkpoint | Allowable Working Time - Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction. The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following:
d0bdebeb-2f86-534b-a907-8672bbd7dd33 | note | a) Working time determined in accordance with Test Method Q136A
f2f2def1-f15d-5aed-a5d6-9f569a892096 | note | b) Four hours
fa79626a-6fed-5c17-b681-7eb24ea5dd7e | note | Acceptance Criteria & Frequency (Project Specific) - Monitor
d43ee4bc-6bdb-50e2-9f29-1b868bfac784 | note | Check Item - Check Item
c11de871-4f07-5ec9-94bd-b5bf35e4f1ea | note | Reference - MRTS10 Clause 8.2.3
3da23b60-e8ea-437d-9fcd-95a3dd8467ef | checkpoint | Construction Joints - Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm.
e59bb4d5-fc04-5415-8bca-5b0738809671 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
81b5f7f2-8313-592f-aa74-f30202e230af | note | Check Item - Check Item
7eae7a64-ad09-59bc-a088-2c58bddad75f | note | Reference - MRTS10 Clause 8.2.10
2aad5e23-9a70-43f5-9f9c-38d870e89b50 | checkpoint | Fresh Joints - Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
707bb01c-b13c-5dc2-9cb6-a62e549405af | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
23e6ecfe-a751-51e1-b9c8-d888f5c13841 | note | Check Item - Check Item
1ded127f-75e3-58b5-b3be-b70e770ed5dc | note | Reference - MRTS10 Cl. 8.2.10.1
23140aa9-5e26-4fb8-a7ad-4ebb111722de | checkpoint | Other (Cold) Joints - Joints that are not fresh shall be cut back to form a neat, clean vertical face. Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
b534f1ab-681a-5577-ac86-8a58ef9fa70a | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
749d329c-f42b-55f1-9c3c-bf259da1853c | note | Check Item - Check Item
8f724e0e-654e-5e18-9e1a-33eed167d52e | note | Reference - MRTS10 Cl. 8.2.10.2 Cl.6.4
20d8c287-26f8-4db3-b389-fc1459f55565 | checkpoint | Curing of CMB Layers - The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5
cb3f6c8d-4332-572c-b25a-e0d0857cfe8d | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
6d1718ae-ab9f-5cb2-8372-fd9dd1d1a66f | note | Check Item - Check Item
cd2ca8f3-772b-5d81-b850-517c6a249334 | note | Reference - MRTS10 Clause 8.2.9
469d8d64-f5e3-4953-aee5-5af3c66a4ab0 | checkpoint | Trafficking of CMB Layers during Construction - Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10)
133336d0-ebe0-59de-9933-515d8ea76aad | note | Acceptance Criteria & Frequency (Project Specific) - Check
da36efdd-c45e-52aa-93e4-07b44476c773 | note | Check Item - Check Item
84c6aa73-09a5-5a4f-b6b5-60b867df5a26 | note | Reference - MRTS10 Clause 8.2.11
7953b7b8-7ae9-467e-8d5f-40fdc995d5c8 | checkpoint | Compaction Standard - The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard
d0505b20-8d3f-5570-9263-9fbe2a5e6080 | note | Acceptance Criteria & Frequency (Project Specific) - 102% standard upper most layer
e96e67ca-209c-5690-903c-d0aa1a855560 | note | ○ 100% standard lower layers (1/500m2, min 4/lot) (1/1000m2, min 4/lot)
2fb1e8f2-670e-56b3-a66a-a9c8fbd2dd1b | note | Check Item - Test Report
ae618b80-f5cd-577e-8e6f-63ac71267c10 | note | Reference - MRTS10 Clause 8.3.4
858f25f5-d67c-4a6e-85a7-9dbd1729388a | checkpoint | UCS - Unconfined compressive strength between 1 - 2MPa
1860644d-9632-5548-9fb4-a6b038f3f843 | note | Acceptance Criteria & Frequency (Project Specific) - UCS 1-2MPa (1 per lot)
a1413125-efdc-5ab1-bc22-35a0b36ddd9c | note | Check Item - Check Item
812fe237-fbf5-5620-819e-9766121e53b7 | note | Reference - MRTS10 Clause 9.4.9
0ba9e16c-93d2-43c9-a4ba-9e5fff9dbe56 | checkpoint | Stabilising Agent Content - The actual content of stabilising agent for each lot shall be represented by both the:
8b986d8c-f7bd-5bb6-aab2-7376cf11f1b0 | note | a) minimum characteristic value of the actual content of stabilising agent, and
25c3a4fc-e920-5afb-a1c3-4a5578d92c4b | note | b) maximum characteristic value of the actual content of stabilising agent.
ae5fda76-54aa-56e7-aa72-804f3a06e1c5 | note | ○ When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content.
36e55c50-07c5-5f0e-8630-f445408c0b12 | note | Acceptance Criteria & Frequency (Project Specific) - Target content minus MPV Min. test 1 per lot
b8a63a73-330c-5c74-80c0-2171d41935cc | note | Check Item - Check Item
2437b9e1-13be-5790-aeec-2dd2968b2572 | note | Reference - MRTS10 Clause 9.4.6
d5d18093-f71e-4799-ad17-069097af0679 | checkpoint | Geometrics - Horizontal Tolerances - Shall not be more than ± 50mm except for the following:
dba8551a-db79-5ebd-96df-9f18f6533f10 | note | a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm
aed68904-c86c-5e25-989d-2c9cb7d7aec8 | note | b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner
8b555157-5b01-5d61-a1a1-662d1915fb96 | note | Acceptance Criteria & Frequency (Project Specific) - -50mm/+250mm (1 per 20m)
4e496ece-e2e3-5af3-9208-aabf2e7c2ed8 | note | Check Item - Survey Report
9d65bf69-5ef5-579e-b2c1-5128fb8a11b9 | note | Reference - MRTS10 Clause 8.3.5.2
2d9aaa9d-5aa5-4d2f-bef8-eed19cea167b | checkpoint | Geometrics - Primary Vertical Tolerances - The vertical tolerances specified in Table 8.3.5.3 shall apply or:
f3b6ef10-c9c8-55c9-b1f0-a824f5bf15c6 | note | ○ the surface level measured at any point on the surface of any layer.
37295067-ecbb-5a8c-985e-288ef736b533 | note | ○ the average total thickness of the constructed course compared to the specified total thickness.
37ca74fe-921c-577a-9c0a-bba8b16b90a4 | note | Acceptance Criteria & Frequency (Project Specific) - ±15mm for layers that have been hard cut
96ddc65a-3a9b-5c0e-bda2-38c78bfcef58 | note | ○ ±10mm for all other layers Layer thickness -20mm, +unspecified (1 per 20m at shoulders, lane lines & grade changes)
6406c8a0-4ec5-51cc-9dca-9dc3f4bcfbc8 | note | Check Item - Survey Report
c4e67334-4fe3-5168-a1f0-f9553518c3f0 | note | Reference - MRTS10 Clause 8.3.5.3
52deb78a-4467-484e-ac4d-07868886d164 | checkpoint | Geometrics - Deviation from a Straight - Edge - Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m
0aaf9dcd-4276-5a56-a209-aecc06aed3c1 | note | Acceptance Criteria & Frequency (Project Specific) - 5mm over 3m (1 per 20m and at joints)
5a9918c3-f1ad-5cf8-b7bd-730bc91ce897 | note | Check Item - Check Sheet
986d54a6-56b2-5d10-922e-eca17d6cef46 | note | Reference - MRTS10 Clause 8.3.6
cdf06e5c-389b-4866-86f1-6b2eba9a37e0 | checkpoint | Geometrics - Crossfall - Shall not differ from the designed crossfall by more than 0.5% absolute.
368fc097-0f26-502f-a114-1cde6f68d76b | note | Acceptance Criteria & Frequency (Project Specific) - Check
e64405ee-783c-5b9b-93d1-f323116b6a35 | note | Check Item - Survey Report
58b77fa1-7794-500f-ae31-4d2c90d886b5 | note | Reference - MRTS10 Clause 8.3.5.4
eb286ccb-5f0e-42a1-bf28-eda1f811ce8e | checkpoint | Proof Rolling - The perceptible surface deformation test (Q723) shall be undertaken in the presence of the Administrator
42478aa8-864d-57a0-aac0-b6ba30fe476b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
054f2dd5-74fb-5571-a6ef-5524ac11fc35 | note | Check Item - Witness Point
3487ecb8-26ad-5e0b-9130-4c7d294fa6d6 | note | Reference - MRTS10 Clause 9.4.10
c2373bc3-9589-4d02-9c4f-189eb3b6bdfd | checkpoint | Acceptance - No CMB layer shall be covered by a subsequent layer of pavement or surfacing untill all testing has been completed (other than UCS), the surface finish comlies with Clause 8.2.8 and the layer presented to the Administrator.
0e916aee-866b-5c78-86c2-8bbe183ace9e | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
f577dc81-0768-57c2-9eb1-ccafce583a83 | note | Check Item - Hold Point 5
54fc40d8-8af6-58cc-bfff-8571da899b75 | note | Reference - MRTS10 Clause 9.5.1
f2484f8f-d1bf-4bbe-9671-420ffb629c49 | signoff | HOLD POINT
f1feb1c7-d471-4cc7-86c4-7e875946666c | checkpoint | Final Verification
844de267-79ab-55af-8087-6616c54b913b | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
f238f3ff-ba09-5f50-ac1d-9f0cb4c7a28e | textbox | Print Name:
959b149b-8218-51e9-a9ae-1e820140c32b | date | Date:
8d6fdf85-37e1-5394-ae20-56f5fdb44b4d | note | Project Manager Verify that the Above has been Constructed according to Specification
a52c9bef-f857-5bef-81d7-a085bd76b6f1 | textbox | Print Name:
7e0a9e2c-f7c4-5eb4-8edd-009ba8fe70a6 | date | Date:
26977107-730a-4b4a-8f96-decde4e684ea | signoff | Sign ITP
6833cf3b-dc0e-4e74-8499-f08537f01b83 | section | Final Sign Offs (to be completed at closure of Lot)
cf05467f-1d19-4840-9c00-8891f9d1cf7b | checkpoint | Agreed Quantities
6ebec534-e1ed-4798-bd4a-99e434249521 | signoff | Agreed Quantities Sign Off
a79cc1e6-29c3-4235-9816-3e81c8fc6223 | checkpoint | Closure of Lot
991f8c0e-88c0-46fa-9b51-11321be445f0 | signoff | Closure of Lot Sign Off
16e60bf7-0d3c-4d19-83c3-b43d5cb2705f | checklist | 14.07 - Demolition and Removal of Road Furniture | itp | 14.07 - Demolition and Removal of Road Furniture
56988f28-699c-4a50-881d-1e2ab5deffc1 | section | Details
6ac291cd-a93d-4a7f-8a5a-eb49480c5775 | checkpoint | Road furniture to be removed are as listed in MRTS14.1.
a4ec0073-2a18-555e-8451-74f96e07684b | note | Acceptance Criteria & Frequency (Project Specific) - Signange/REGP's and Lighting to be removed
c9d73c5a-dcde-5bb9-b1fe-cb88d1a6e735 | note | Check Item - Check Item
ae0a5b70-1c0c-5550-84ec-96d5b38fc0c7 | note | Reference - MRTS14.1
3363a168-14aa-4ab9-badc-b5e4da788867 | checkpoint | Existing road furniture demolished and removed in a manner which avoids damaging any adjacent work.
a2e84296-21c8-53df-991b-cb24821aedda | note | Acceptance Criteria & Frequency (Project Specific) - Visual
31968a50-93a2-5ad8-aad1-b7d8188e586c | note | Check Item - Check Item
06726545-71a7-5274-8c34-2c0e8783fda9 | note | Reference - MRTS14 Cl.7.3
699bb880-f658-4374-9d13-97f2da5349ef | checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state.
999d1f00-00b8-5129-b222-7787663f063a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
127b5179-0fa5-5c62-be3c-bcc09d7b0757 | note | Check Item - Check Item
06a886f2-e7f3-5120-9180-81c8820a2c56 | note | Reference - MRTS14 Cl.7.3
85653295-6767-4d91-8ef4-f5c37ebe6088 | checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be salvaged in accordance with the provisions of the design documentation
4db71f98-f8f1-5c69-8957-b61a552b45ac | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Schedule
9df8cc93-02b2-5d24-9fa1-4d764fcaa4ab | note | Check Item - Milestone
c41c9d71-987e-5a9f-87cb-39374b7b4711 | note | Reference - MRTS14 Cl8.2
b45d8043-32b5-4974-85cf-02cfe1432a2f | checkpoint | Dismantling and removal shall not commence until expiration of the seven day period
e9aa63c1-68eb-5e69-af8b-2fb703e7b90f | note | Acceptance Criteria & Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
5d70a7e4-2385-552b-8422-7a75241331fa | note | Check Item - Hold Point 1
6f6b3856-8fdf-5dc2-b91d-33ec9957978e | note | Reference - MRTS14 Cl8.2
ab09459e-45be-4693-a45b-e9fb4e9334e5 | signoff | HOLD POINT
694fa459-c732-4161-a5bf-83954c40eafc | checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation
7250561b-44ce-5276-891a-35202b2d7b3e | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Schedule
545e75c7-6b25-55c0-9fb5-18de98f28392 | note | Check Item - Milestone
7ebc9818-bf2a-58b6-938d-aec996abde9e | note | Reference - MRTS14 Cl9.2
11e88710-be3a-4f38-b6a3-585604274435 | checkpoint | Dismantling and removal shall not commence until epiration of the seven day period
3c9e8eed-7f5f-5b14-bfc8-f0af1d2add11 | note | Acceptance Criteria & Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
018ce1ec-54b4-5c5c-997a-7dbc7f825c2e | note | Check Item - Hold Point 2
ad8cc499-3075-5e30-9b9e-7e5192acb89e | note | Reference - MRTS14 Cl9.2
13ecdeff-8955-47a8-8767-b561b4c226be | signoff | HOLD POINT
d027ed43-ffa3-4be2-8b66-6e4c5522db89 | checkpoint | Final Verification
14d71a6d-aa05-5ce7-99f3-b59b2095ddfe | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
fda87176-488c-53db-b4bd-1d9ec5895fda | textbox | Print Name:
3738c0d4-0c1f-5cb2-ab92-3a34b754a503 | date | Date:
ae204c50-423e-5d90-bd75-af234e0402a3 | note | Project Manager Verify that the Above has been Constructed according to Specification
a38f0561-870b-5271-95e6-ce49d7cefcfd | textbox | Print Name:
55e9c2a0-6c0e-534c-9549-fda48d6259d2 | date | Date:
b864ab72-76ed-4e94-b139-e382d107306d | signoff | Sign ITP
fad50c3f-adda-4c54-ad6a-c49a6dfe830e | section | Final Sign Offs (to be completed at closure of Lot)
31696f87-76c9-418c-a56a-89305947342d | checkpoint | Agreed Quantities
15b0d0da-8a10-4f3a-8114-bfb2909c6ac9 | signoff | Agreed Quantities Sign Off
87f8861b-2c0c-458a-a1c7-ab45e1595183 | checkpoint | Closure of Lot
1f9fe8f6-f987-49e0-9788-3e3daa1d7ceb | signoff | Closure of Lot Sign Off
80716c1f-f2c3-44e0-bf70-761c05762d8b | checklist | 14.13 - Supply and Installation of Road Signs | itp | 14.13 - Supply and Installation of Road Signs
f76963a3-45d8-438c-ba79-5ec17c6717b8 | section | Details
886b3376-f949-494b-a371-603f590ad502 | checkpoint | Not less than seven days prior to commencement of dismantling and removal of existing road furniture, the Contractor shall submit a schedule of items of existing road furniture to be disamantled or re-erection in accordance with the provisions of the design documentation.
1c9871e0-a9a5-5616-b225-d65ff9d40e0d | note | Acceptance Criteria & Frequency (Project Specific) - Submission of Schedule
e8b30230-88d0-5a2c-adb2-7979a28dffd4 | note | Check Item - Milestone
18011e6d-2dc2-50b1-b6c2-93b497bf7c58 | note | Reference - MRTS14 Cl 9.2
df94bf44-7cb2-4574-a4ba-0bf7ffb0cff8 | checkpoint | Dismantling and removal shall not commence until the experation of the seven day period.
44112eb1-c914-5c49-a14e-021a9a3fbb5c | note | Acceptance Criteria & Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
a9c92287-2a0e-5c02-a4ed-60b121d1f2c4 | note | Check Item - Hold Point 2
52d09a6e-53dc-5718-bffd-6e2d033abc6f | note | Reference - MRTS14 Cl 9.2
70f79046-bd08-42f3-afc4-219a8ea794a0 | signoff | HOLD POINT
a4a1f80a-fa0b-4274-9c22-666992a7393c | checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings.
d2a66c35-f4a4-5125-957a-13b75831f563 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
28b06a0e-d328-58ea-8cdb-55bd8ab35ae9 | note | Check Item - Check Item
83dc8d53-a9e8-5a9e-852c-9b13b312e27c | note | Reference - MRTS14 CL 13.2
25797cbd-5cc1-41bf-86aa-a69ab49c7bc5 | checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744.
d813140c-86e0-5878-900b-34f842dcdc06 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
49c35b5b-b69e-5123-b187-9fa28714e40b | note | Check Item - Check Item
64d482cc-049c-5f6f-94b4-613421740d81 | note | Reference - MRTS14 CL 13.2
9e5af0c6-49de-4c04-b1a6-6c00faeb97bc | checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3.
6573ba17-f195-5793-ad76-69d3374e454e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
68679b56-a6b2-51b0-bea4-d9c68185a989 | note | Check Item - Check Item
f9210ff5-f26d-56e0-b419-88ac93c12811 | note | Reference - MRTS14 Cl 13.3
cd176b60-3fed-44b2-a175-df6540320ba2 | checkpoint | The sign substrate shall be manufactured from aluminium. Other materials may be considered but evidence of the full approval of the department will be provided to the Administrator prior to their use.
de4265f8-d078-506b-b721-6f63b1376d11 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ad5f2c53-8de0-5d68-85a1-4015dd62f2be | note | Check Item - Hold Point 3
07a91449-e25d-5c3f-be03-8e6f65ee38ba | note | Reference - MRTS14 CL 13.3.1.1
d7f0b5d7-9374-4a38-8450-5952746a49b0 | signoff | HOLD POINT
152821b3-76f3-42a8-9a9d-cf89538ee5db | checkpoint | Sign faces are fabricated in accordance with the requirements of Traffic and Road Use Management Manual (TRUM) Volume 3, Part 5.
a7a0deb1-931a-5fd0-9503-a59abcaf4522 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
023fb784-c454-5c05-b488-7be52b0b50a6 | note | Check Item - Check Item
18479e4e-6928-5518-8cb6-1f487924dd0f | note | Reference - MRTS14 Cl 13.4
462b1c75-a710-4045-9d8d-3baf23a60874 | checkpoint | Sign posts shall be circular or rectangular hollow sectionsunless specifically shown otherwise in the design documentation.
34f1adc1-e459-5bec-b47c-bcad687eb68b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f18d6509-9b96-5deb-9789-445784a3255a | note | Check Item - Check Item
02e307dc-5274-5b4b-9d78-458a6bc3b784 | note | Reference - MRTS14 Cl 14.2.3
e7871c97-2cbb-4fae-bce5-f13896a88244 | checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required.
0481e016-cab5-5c7a-8f2d-65d3ed1c468b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c8fcf5eb-2900-52b4-8802-fdd7c381b4dc | note | Check Item - Check Item
04740e09-fe62-5098-b763-67f6f2c3c3c6 | note | Reference - MRTS14 Cl 14.2.3
65c8b408-a3e7-45c6-9d6e-ffb81668b65d | checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
45ae0a30-f62d-5df0-8fd7-0b0f20e2e043 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
3bc2f108-585b-5f7f-91f7-6a7406a47b91 | note | Check Item - Check Item
fd77b70c-0a7f-56b8-b998-e185c393e241 | note | Reference - MRTS14 Cl 14.3
0a7437ad-bae3-4d3f-834a-d4d1d4f257f4 | checkpoint | Erection of Road Signs.
6d642279-eca5-5685-af6e-21d001dcfbf0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
878ba2d8-8a31-5d45-ad5b-3ed0a1c73d35 | note | Check Item - Witness Point
ff1f1276-4f35-5676-a977-e30f82767304 | note | Reference - MRTS14 Cl 14.4
399678dd-1472-47df-9c2e-d6b449606f58 | checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD.
c984a307-2f1b-5726-bfca-b7c93b7c559f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
40ffa1b2-045b-5280-b9ad-3049b102efaa | note | Check Item - Check Item
a39938f8-8565-5ebf-9445-26f2dd4fa02a | note | Reference - MRTS14 Cl 14.4.2
c4a7445f-a52e-4ebb-b35d-3b90af44b571 | checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete.
34713893-75af-5a0e-8892-1dea7d7f508d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0be0b87c-9c66-579b-b6b9-ec26def99d5b | note | Check Item - Check Item
476a8803-388a-5e10-96c9-4fc99a0be753 | note | Reference - MRTS14 Cl14.4.5
a5010691-2808-4a32-9bad-8f28235c774f | checkpoint | Final Verification
048a7cd2-3ce1-5e6e-8a37-ea3704108017 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
2d374eaa-a704-523d-9e7a-ae885970d749 | textbox | Print Name:
b2e4224c-ccb6-5572-8c3d-917b50aed962 | date | Date:
30608e7c-03dc-569c-9c3a-ba1355cb0d18 | note | Project Manager Verify that the Above has been Constructed according to Specification
5e77e1a9-63fb-5bd2-9aad-fbcc0223486e | textbox | Print Name:
b121451a-da72-5dac-8513-9ec2216b8fbd | date | Date:
b4377da4-02cc-45f0-b007-dc261efb1265 | signoff | Sign ITP
d16ec035-6c9a-46c0-9c6f-dfb7e7040c27 | section | Final Sign Offs (to be completed at closure of Lot)
1bc06009-bf17-4685-9597-c911c340c14b | checkpoint | Agreed Quantities
461427ae-6b4c-4144-b39f-b0831fa69676 | signoff | Agreed Quantities Sign Off
6dbf20ef-67dc-4473-9503-f1a6518bc069 | checkpoint | Closure of Lot
f82a8a50-414f-42bc-bc52-40ceecfcb1f6 | signoff | Closure of Lot Sign Off
1f39f4af-24a1-45cf-b245-b15d0ecef77d | checklist | 16.01 - Landscape and Revegetation Works | itp | 16.01 - Landscape and Revegetation Works
1abcad98-8539-4b48-b209-da4c0a41d982 | section | Landscape and Revegetation Works
568bb472-086c-4811-93ba-37c8bae7f2f0 | checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
f530ca1e-83c8-5d98-a7fd-67d98cf49b7b | note | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
e2f72d3b-f4de-58cf-936e-647868eb62de | note | Check Item - Hold Point 1
53c2cb82-b4ac-564f-b387-a7c9a3233dbe | note | Reference - MRTS16 Cl 5.2.1
a2badec1-d92f-4998-85f4-f374d29286be | signoff | HOLD POINT
6a91907e-d435-4095-99a9-cdc6e2b8e8b0 | checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
89856836-feaf-52d7-8742-0b2f87af3885 | note | Acceptance Criteria & Frequency (Project Specific) - Plan
ac641708-f031-5ce2-a5c1-36c75c6e1ac6 | note | Check Item - Hold Point 2
9c18c2de-2067-5f61-a475-67af7e710924 | note | Reference - MRTS16 Cl 5.2.2
3e1b0337-bbed-4761-8e61-810335945e50 | signoff | HOLD POINT
cfadb94a-8fd8-4b9f-86e4-f6877a2d31dd | checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
2951c563-28f7-5d4d-ad07-c2b35646fce5 | note | Acceptance Criteria & Frequency (Project Specific) - Plan
3b084d5c-9209-5426-8afe-3004b720f6b5 | note | Check Item - Hold Point 3
522dca63-9412-52e3-af9c-4e5f244ca91b | note | Reference - MRTS16 Cl 5.3.1
f1ed91f2-2b03-40a9-b653-618cda7dbc46 | signoff | HOLD POINT
641515c6-11f1-4fdc-ba9f-d6b788f3715b | checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
fd82b83f-366b-51f9-b31d-a8904ae6c688 | note | Acceptance Criteria & Frequency (Project Specific) - Plan
4567a987-38e9-5f1c-90de-8af87b5bb8df | note | Check Item - Hold Point 5
35f312e1-e80d-5111-b596-ea54294376eb | note | Reference - MRTS16 Cl 5.3.3
6c3ad2b1-8bb2-403a-b01b-6a10f0f2a79d | signoff | HOLD POINT
fd6c4a94-19f2-4411-862f-0ff38dc9d544 | checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
2df05650-ffba-542e-b404-06a2fbd43db1 | note | Acceptance Criteria & Frequency (Project Specific) - Plan
d720d0e2-68cb-5530-a489-3db86e772de7 | note | Check Item - Hold Point 6
0248c35d-139e-5fef-8e70-616ff812275f | note | Reference - MRTS16 Cl 5.3.4
d59ae119-7b56-4a48-a825-10169b5718c6 | signoff | HOLD POINT
1a2b6c0a-0155-4aab-8749-335350188087 | section | Materials
da9d4724-8a3f-4a4f-9508-d35e7e38b86a | checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
41ea45ed-605f-5ee4-9228-c1d560dd643c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6cedfc81-79c5-5130-b6ea-811714691cd1 | note | Check Item - Check Item
16cbf462-9fbc-5536-8022-721c2156c214 | note | Reference - MRTS16 Cl 7
94aa8f8c-f30b-493f-8c1f-418b1b4dc03e | checkpoint | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm
83bfe313-54e3-54de-a2d6-cb0cd0771be5 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5f1b4885-6c7b-56c2-b48d-62b916950ba6 | note | Check Item - Check Item
d15e58dc-b7b8-5108-adce-6d9ef6f1406a | note | Reference - MRTS16 Cl 7
7fd2f95b-581a-488b-a274-e2608623337f | checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
c3b3de1f-42dc-524e-86d5-e3a9125453ad | note | Acceptance Criteria & Frequency (Project Specific) - Visual
43a67866-fe6c-504e-8dc0-2f40e0547bc7 | note | Check Item - Check Item
1770674b-f8fc-535a-a5b8-1b5fda15bde9 | note | Reference - MRTS16 Cl 7
ea0dcb36-68ee-44ff-b7ab-b92185010b1c | checkpoint | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
ec2017ff-dba6-5d51-8cdc-9ef529586830 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ed2ed405-90dd-502b-8bb8-df22cbb1b0bf | note | Check Item - Check Item
b7516cee-188e-52d9-b42b-85c50617641a | note | Reference - MRTS16 Cl 7.6.2
7658119f-7c7b-4d3a-a552-da63afab3416 | checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
d85420bf-71da-5cca-9703-df2565b35758 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
931f9778-a819-53e9-9f1d-6093c2b8d81c | note | Check Item - Check Item
8c9f7c68-fa68-5113-b71f-617ff179da3b | note | Reference - MRTS16 Cl 8
ee395764-c230-4949-a9c6-852301fb50c0 | section | Subsoil and Topsoil Amelioration
5c05918b-189b-468b-8c3b-4afe71928136 | checkpoint | Site is weed free prior to ground preparation operations
121f0eac-e54b-507a-bc1b-a15998d923b7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8eeded36-1029-564d-be7e-edc57dec6d6f | note | Check Item - Witness Point
ca9ec2a1-dc8c-5ce3-a364-abebcabc3932 | note | Reference - MRTS16 Cl 8.3
198dfa39-70e9-4c0e-83cd-834375ee1b73 | checkpoint | Administrator notified at least 3 days before each of the following: application and incorporation of amelioration agents ripping cultivation roughening
5515fd10-4323-563f-be27-2ae58b532125 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a4ba9f89-c88c-56da-8b67-3539aea133f4 | note | Check Item - Witness Point 3, 4, 5
8868a580-9ce0-5d6a-9f6c-1814c269b00f | note | Reference - MRTS16 Cl 8.1.1
a44e948e-c504-5ac7-b09e-cb0d0032d8e6 | note | ○ Cl 8.4.1.1
380adfc6-e46a-5663-8420-c0990c10075f | note | ○ Cl 8.4.1.2
e227422c-b332-5fa1-8a2f-c4ec9b0b4ab7 | note | ○ Cl 8.4.1.3
c00b96a0-3582-5372-947d-4950b54cf049 | note | ○ Cl 8.4.1.4
f07ec2ce-406e-45da-8dbd-631b708ea7c7 | checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
def7e768-afce-5ebf-bc73-a21fb17913e6 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c53e07ae-acd2-5c3e-8384-e1df5cba9969 | note | Check Item - Hold Point 8
b5b839ea-8d72-528f-8f21-af3443c3dce0 | note | Reference - Cl 8.4.1.1
5bbf1e24-f816-4939-bb94-4851e5cd5edb | signoff | HOLD POINT
349f72d2-afcf-4803-b30f-fc4557d973a6 | checkpoint | Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used.
23a0c86c-ce76-53bd-b0ba-ffaa2ff86f07 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
76f72dd8-0bee-5369-b2cc-133969f8e84f | note | Check Item - Hold Point 7
0ef29f69-3311-554f-bffe-872d4f4bc82f | note | Reference - MRTS16 Cl 8.2.1
a54c2e7e-ffe0-4486-802c-a9ee0d9cd7cd | signoff | HOLD POINT
03a5c59e-893b-42d3-b062-83f8dc5b80fc | checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
a401415c-4677-5f9d-9ab8-579601576b24 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ad0dc1e3-afe3-50b2-ba02-2f1710e19de3 | note | Check Item - Witness Point 6
fe392164-1492-5e4d-9e65-b55b613a4e6b | note | Reference - MRTS16 Cl 8.4.2.1
462cf19b-1e81-4be3-b53e-5cc1b4435803 | section | Grass seeding, Hydromulching and Turfing
c1d73fbd-69f2-4eeb-b1cf-06e88c5d66e1 | checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by:
20e35351-a7fc-5105-b020-9c55d2b59689 | note | a) spreading fertiliser over the topsoil and raking the surface smooth
cc37bf97-c133-524a-82d3-2a54c5a1e949 | note | b) to the prepared surface that has been moistened with a solution of water and wetting agent
a0cebdb9-7793-537b-bcc0-ea50115f2df4 | note | c) on the day turf is delivered to site
5e94055f-8e6b-5151-9873-d9b704815c74 | note | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
ebd1f410-7128-52ac-a425-dcbac3bfcd62 | note | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
3e71b72b-95af-56bf-8c09-6586dd8c1cfb | note | Acceptance Criteria & Frequency (Project Specific) - Visual
0b602911-0f30-51b4-b371-7cbd86029f22 | note | Check Item - Check Item
14d4c3ed-9f8b-5133-8e75-77b2c1fb9746 | note | Reference - MRTS16 Cl 8.5.2
7d42c5e8-a3cb-4590-ad6f-6818d655080d | checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
7997b85c-79d5-5e41-8ef1-c7f89f59e75e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
89e81bdc-c0e1-5f13-9739-334ca2edcbd7 | note | Check Item - Check Item
10c60692-8579-51d5-9b4f-490a445d7385 | note | Reference - MRTS16 Cl 8.5.2
e44ef816-524a-4b58-bffa-b843a45619db | checkpoint | For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1
a2caa136-d73e-5a47-a0b2-1e5248365cec | note | Acceptance Criteria & Frequency (Project Specific) - Visual
e1239f08-3623-5153-bf2a-822342dd5087 | note | Check Item - Hold Point 9
df4f9877-e65a-5df1-9b25-26b15505e813 | note | Reference - Cl 8.5.1
dc6eea9b-0fca-4e2c-81be-ec8141cdda73 | signoff | HOLD POINT
b20bc2d5-22e2-4805-9e54-e45b4f398df3 | checkpoint | All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities
28b7ad9f-e223-5fc7-9ae2-6cf1aab42d22 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a5991d21-390f-5fc5-8555-094fff0e3df2 | note | Check Item - Hold Point 7
c956ae1c-7d61-5052-b6b7-eb8c8ef5bff2 | note | Reference - Cl 8.5.1
a0d72032-db1c-4d6a-a169-e8189a5ca049 | signoff | HOLD POINT
277805c5-467e-40ab-ae1b-8f5b934d5528 | checkpoint | Broadcast seeding installed as per Cl 8.5.1.2
33887324-1064-5065-b352-16e043e151bc | note | Check Item - Check Item
46075282-f4b6-5903-8a70-40137aad1e7a | note | Reference - Cl 8.5.1.2
798d68a9-742d-4125-872a-47d53bd9fd2e | checkpoint | Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4
b3e35110-830f-5a57-a794-f17d6f8550f0 | note | Check Item - Check Item
3b4ba4c3-4892-56b6-8be8-db44473d962f | note | Reference - Cl 8.5.1.4
396a5c86-8796-4e27-98c7-334ed0df1062 | section | Establishment, Monitoring and Finalisation
e1b456a8-6928-4f09-bfbd-3a489d44a4f2 | checkpoint | Commencement of the Establishment Period
887fefd7-0524-5b01-9434-6393355390fa | note | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator
95f4d731-2eb2-50b6-bb76-9d20397d0695 | note | Check Item - Milestone
73dbb737-16e8-588b-962e-f2ced259473a | note | Reference - MRTS16 Cl 9.1
1bf83a0a-42f3-4a45-972e-cc0af04e62b7 | checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
af3f1b55-0003-58f6-b8de-491370f7573b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1324c2b6-3838-5169-8e5d-566ec498662a | note | Check Item - Check Item
6c6a971c-f6dc-5465-b1fc-95beeff5bf1c | note | Reference - MRTS16 Cl 9.1.1
5207892c-3edd-4f36-bc94-d486e2f52cfe | checkpoint | Commencement of the Monitoring Period
37679cb5-0fc2-5a20-8f51-b6f6c98f521f | note | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator
9ae67463-e90d-5fce-af88-a699c0a5fdf5 | note | Check Item - Milestone
14750821-38f5-536d-a5b7-065a958fac28 | note | Reference - MRTS16 Cl 9.2
2979bb46-7cd8-48c3-8c8f-85e74b552ad2 | checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
01952a3b-70d8-5887-870e-f9478531ab61 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f30de797-9a77-58d0-8742-02f849f9b184 | note | Check Item - Check Item
749d4153-dca5-52a4-a500-7328e7ba8d15 | note | Reference - MRTS16 Cl 9.2.1
128bff41-dbb5-46cd-88c6-11ef3afc5a78 | checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
8c57f31f-6fda-5e94-a565-4ecd64e8e278 | note | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator
439ca093-2cdd-5a93-ac3f-f512f2b9ce24 | note | Check Item - Milestone
42b3f826-5da0-5101-9252-41b1b1a8640b | note | Reference - MRTS16 Cl 9.2.2
794518f7-ab4a-46a8-809a-aac39c46d41d | checkpoint | Final Verification
3300566c-33bc-593e-9860-1a72592496f6 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
0fb17aab-1739-54f7-bc44-590ade5d8751 | textbox | Print Name:
f45d7541-2480-57b4-96e2-900e604efdaf | date | Date:
d02144ea-a172-4bfa-bdf4-302aa44b6979 | section | Final Sign Offs (to be completed at closure of Lot)
0a27a1d4-bafb-4837-acc5-7e1c58397ea6 | checkpoint | Agreed Quantities
a84bb592-de80-4a87-81e7-6d9cb2eb1248 | signoff | Agreed Quantities Sign Off
8362aec0-e055-4ed3-a032-50d206741881 | checkpoint | Closure of Lot
309279da-2694-44ed-9c0d-96f7e8a05b9b | signoff | Closure of Lot Sign Off
75ef9224-a329-438c-a4ef-dac5c3cbbf4b | checklist | 28.01 - Contractor's Camp and Site | itp | 28.01 - Contractor's Camp and Site
0bba35d4-4518-48e2-b696-43a55fdceebb | section | Details
685f6770-6e66-4dac-beae-350bb6ad9491 | checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
dbee6c8b-04f2-5a35-a548-412d33eddc32 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7861d815-ce39-56f5-b0b3-1868c6f753dd | note | Check Item - Check Item
514c1406-fc96-5d4d-bbe1-420988046fa1 | note | Reference - MRTS28 Cl. 4.2
2a17d59d-6696-4270-b98b-21f8364469b5 | checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
4e7737f7-17b6-59a9-8e92-89a3d8e1a429 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a1c47ce0-1227-5659-9993-69d7f71bfb25 | note | Check Item - Check Item
6fe7bae2-546e-5569-b1e2-40cd1604cb58 | note | Reference - MRTS28 Cl. 4.3
2211bf43-79ea-47fe-9295-649e9bbd2e17 | checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
ca1e4120-65ff-5243-b187-793d20a16a4f | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5290af74-0c62-507a-88bb-96b793f56af2 | note | Check Item - Check Item
292134f1-523a-50ad-9c22-ced6a7be0466 | note | Reference - MRTS28 Cl. 4.5.6
eda58660-eae9-4dbe-bff6-5acca8af7afd | checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
3563e64f-8100-5931-9dfb-97fc5bc2a066 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7af32aa9-2008-5e78-b06f-5531865a5792 | note | Check Item - Check Item
1c1b357c-a17a-5d2c-9bc2-354c20b7776a | note | Reference - MRTS52 Cl. 6
7e0c008e-5eab-416f-a0ab-b220ebd6a930 | checkpoint | Contractors camp complies with all requirements of MRTS28 annexure with a proposed site facility layout submitted to the administrator.
1c5e6e57-8479-5923-ac8b-26ca4314d0e1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
dc8e6a05-45a7-5e35-9ed6-f64864bfbce8 | note | Check Item - Check Item
251fc8f8-b9ff-50d9-a14d-6e892f3fccbd | note | Reference - MRTS28.1
3d14f9a6-d274-4fb5-9ff3-b6dfca9527e7 | checkpoint | Final Verification
b13e8a53-9a74-502a-b0df-23eea46d4c42 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
a5cb8f18-546b-5e5f-a9c9-a75e50fef7e7 | textbox | Print Name:
2ae274f6-e2dc-5eaf-aa17-0bfec1c65fb0 | date | Date:
452992d8-283c-435f-a966-8893bf988d9c | section | Final Sign Offs (to be completed at closure of Lot)
45ff23be-6ebc-47f0-ac17-2b40bdabdb78 | checkpoint | Agreed Quantities
e742c26f-ceea-4100-8872-f715021150a9 | signoff | Agreed Quantities Sign Off
9e7d5c42-6c72-4d86-b961-41e8f01f96e0 | checkpoint | Closure of Lot
e9cb1463-6036-4d84-bd7b-3dbeca2cf2eb | signoff | Closure of Lot Sign Off
5ccbd4c2-6756-4348-a7f0-ae7f9d725af8 | checklist | 30.01 - Asphalt Pavements | itp | Asphalt
003bcbc4-8181-4c64-9c53-e5bef4641c95 | section | Subcontractor ITP
2b552f21-a540-4640-85c5-418ac3eab64e | checkpoint-no-value | Attachments
f622aea8-d841-4feb-930f-fdc300b7fe37 | section | Final Sign Offs (to be completed at closure of Lot)
0cd225f4-8d9b-4685-8de1-7c29a2f46f56 | checkpoint | Agreed Quantities
4fb1cba4-8e35-4e71-9c2c-52cb2ed794b2 | signoff | Agreed Quantities Sign Off
134bbec9-d8e4-4b22-a48f-a92cf3d0c62e | checkpoint | Closure of Lot
2c718034-b9de-4bce-abd9-846b585dd904 | signoff | Closure of Lot Sign Off
14e4bbc9-d6d9-40af-974c-7a64d7deb825 | checklist | 45.01 - Road Surface Delineation | itp | 45.01 - Road Surface Delineation
02783ef4-5888-4d6d-af35-a281feefb8ce | section | Road Surface Delineation
368e038c-a438-43e2-ae6b-3dd2962b2c01 | checkpoint | All material conforms to requirements set out in Clause 6
e86299ca-a771-5b87-aee5-bb782bd79fb1 | note | Acceptance Criteria & Frequency (Project Specific) - Material product sheets
75a515c1-5c28-55a3-be98-00293562d7eb | note | Check Item - Check Item
6110c491-6a60-5c62-b592-6f1b99fe4734 | note | Reference - MRTS45 Cl 6
01d39661-8bf5-429b-b84c-564974858a21 | checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
15ff6302-5acf-5cc3-a308-301534f9aa81 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2e059ea1-e0ed-5d64-996b-288cae96a0df | note | Check Item - Check Item
23bd6f82-52ec-51e2-b6ea-57f7a8dc2e11 | note | Reference - MRTS45 Cl 7.2
d5eb0917-7f30-4430-9c8b-d63888dd9b7e | checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
6673a5f6-9154-5267-b62b-474cc529488d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
91db9eff-c518-595b-b36a-e9afadfc61e7 | note | Check Item - Check Item
31037b1f-58f5-50a2-a493-159947635d96 | note | Reference - MRTS45 Cl 7.3
acc4743f-5697-4223-9336-afa3dc7a345d | checkpoint | In addition to the above requirements, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
cca57cc6-87c7-594e-9e58-dc56cfb5f876 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1a9a7b05-744c-5188-b445-e71fd816b039 | note | Check Item - Hold Point 1
47f79705-fa01-522b-9f53-f3d72aeffc2f | note | Reference - MRTS45 Cl 7.3
92652e71-9a81-4958-8caa-417b88bc1cd5 | signoff | HOLD POINT
9f40ec44-1c00-49ec-9a1d-59d8ab915181 | checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
4af3e282-368c-5b15-ba23-df7aaa74da60 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5f3694f7-850c-54f8-9384-3b76d34fd3b8 | note | Check Item - Hold Point 2
2b5f48cb-2700-5b74-8095-2962eb23bad0 | note | Reference - MRTS45 Cl 7.4.1
ea555c65-db1e-495d-933e-5656b2dde19b | signoff | HOLD POINT
c923d950-133e-4d2d-a2aa-03dba9d3fe3c | checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
1f1e12b2-2189-58f1-bd81-64ecd445ec3e | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6033a59c-0f9c-595f-9246-b3164e1a122a | note | Check Item - Check Item
18531553-07ad-5028-bf57-cd8b3d1fdae7 | note | Reference - MRTS45 Cl 7.5
17f777c1-b8a8-4bc4-858a-454f0054ba2b | checkpoint | All Markings are of uniform thickness and intensity
d36d81c1-f1d1-5f1a-af8b-a49bb552de44 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
46bb10d8-8b13-531d-aeb7-18a32be996ae | note | Check Item - Check Item
b8f8ce65-6891-5f28-bcab-e2d4adebb99e | note | Reference - MRTS45 Cl 7.5.2.3
02072170-e6bb-4689-9322-4ea0d2c18a07 | section | Waterborne
cc6bd627-7a9d-47ef-b881-33dc7a36851e | checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
d96ed25b-544d-5dce-9184-3a8bbb4306ad | note | Acceptance Criteria & Frequency (Project Specific) - Visual Table 7.5.2.4
a818b7f0-5409-5383-82e8-82428dbcca3a | note | Check Item - Check Item
f7bf0924-ed52-5e00-9421-add94e55e702 | note | Reference - MRTS45 Cl 7.5.2.3, Cl 7.5.2.4
a8bb980f-e94b-4b67-84c4-2630dd18dfce | section | Thermoplastic
a473f3ac-11ee-42da-8ef5-f06d00e657b7 | checkpoint | If required, a primer of type recommended by manufacturer of the thermoplastic material shall be applied to the surface immediately in advance of, but concurrent with, the application of thermoplastic material
3a49e5c0-1d10-5169-86a7-aa69d9979cbc | note | Acceptance Criteria & Frequency (Project Specific) - Visual
77689c2b-6381-57a4-b013-251576bc2481 | note | Check Item - Check Item
434c3abc-e90f-5e82-9759-058fb50e3135 | note | Reference - MRTS45 Cl 7.5.3.1
9e205652-71d1-466b-8b4f-e16f1dde952f | checkpoint | Thermoplastic shall be applied at a temperature between 180C-200C or as per the manufacturer's specifications
efe0df38-55f4-531f-addd-e22fc4379ca2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c55b743e-d568-5aa1-a315-3d69b2491a32 | note | Check Item - Check Item
e2b0d665-9236-5e1a-84ac-8a2b170d6011 | note | Reference - MRTS45 Cl 7.5.3.2
6d2be028-e6c3-4c99-baf5-6356492a4452 | checkpoint | Thermoplastic applied at a minimum of 2mm thickness
bc6e91c0-aa41-5fd7-b332-7a93c8bc8dab | note | Acceptance Criteria & Frequency (Project Specific) - Visual
da41f3e6-28c1-5e89-bf21-9aa0053018c6 | note | Check Item - Check Item
39fe94ad-ae44-5757-a330-8dff28ac1808 | note | Reference - MRTS45 Cl 7.5.3.3
90f7aa5a-7aaf-4ade-9a53-b1bf1a209ba2 | section | Cold Applied Plastic
cc009d42-a627-46ca-9743-43a79c05fae2 | checkpoint | If required, a primer of the type reccommended shall be applied to the surface immediately in advance of, but concurrent with the application of the Cold Applied Plastic materials
998fbd7f-5f8d-586f-8518-85e904006325 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c3903d34-a6a3-5789-bab2-2639d53cb3e5 | note | Check Item - Check Item
e7f799f2-372c-51b4-9b1a-dc474a20d081 | note | Reference - MRTS45 Cl 7.5.4.1
142b9233-6974-4f34-85c3-19ac8f7b28b0 | checkpoint | Cold Applied Plastic shall be applied at a temperature as per the manufacturers specifications
24da9713-aaee-52d5-bdf4-ebf419b80ed3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a165f79b-37a6-5f17-909a-18cf49799778 | note | Check Item - Check Item
e3aff93b-33d5-54fd-94cd-989348679b8d | note | Reference - MRTS45 Cl 7.5.4.2
ffd81d9d-4ab2-4d26-87dc-483b86d7b661 | checkpoint | Cold applied Plastic shall be applied at the rates specified in Table 7.5.4.2
579194a4-7a72-5fb5-9d13-b963877b4a6a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2e53e7db-8c6a-52ac-9643-62f1c603c2bc | note | Check Item - Check Item
b94c1323-da75-5d0a-96ae-4c621dc805ae | note | Reference - MRTS45 Cl 7.5.4.2
8ff55d2e-6ec9-4e09-8aec-7a4978194696 | checkpoint | The use of Raised Retroreflective Pavement Markers shall be in accordance with Cl 5.6.2 of the MUTCD Part 2
02aa43e7-5001-553d-ad65-867e402eba7a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
b3ffa329-d995-55a2-897d-3ae2a3bdd5e7 | note | Check Item - Check Item
d7ffb4da-a5fd-50a3-9cd5-b7a1b2b985ef | note | Reference - MRTS45 Cl 7.6.14
1ed4c427-94b6-48f9-8f25-9554d5cfd13e | checkpoint | Material complies with luminance and retro-reflectivity requirements.
6260ded5-6787-5eac-a892-b088f23b856b | note | Acceptance Criteria & Frequency (Project Specific) - Test procedure AS 4049.4
385027cc-09a4-5242-95d4-a982c4b45cae | note | Check Item - Check Item
eb7a2df5-22f8-5c55-91f4-98e3aa647750 | note | Reference - MRTS45 Cl 5.3 & Cl 7.7.6
2a01bdb4-cb32-485d-b4fc-811fd6c67c24 | checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
adf57047-87c6-5f66-bec4-903dcb3686a3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
985224a7-819b-5e18-8242-c981a18bdf7b | note | Check Item - Check Item
98b1e972-bae6-5297-9507-7f1feebf4f77 | note | Reference - MRTS45 Cl 7.8
8750f2f6-6c8c-4c30-8385-c9ef5c61b352 | checkpoint | Completed Pavement Markings shall be uniform, clean and well-defined edges without deformation and conforms to dimensions as set out in the MUTCD
4bf19a10-0705-5973-bed2-876934cc0883 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f5ca604b-d2be-5757-a25a-fec4806fbec1 | note | Check Item - Check Item
522a5716-a6bc-5f85-b6e1-371b77259e46 | note | Reference - MRTS45 Cl 7.9
ff5bfe43-1e8b-49a2-9c16-99db8241cccb | checkpoint | Pavement Markings conform to all tolerances
c4d0cc06-0a48-5964-801f-7dbad8c7c09a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
52a959aa-d210-5fbf-99aa-9113e363aa6f | note | Check Item - Check Item
2b48935b-c10f-5b84-8897-5cd66bcb850d | note | Reference - MRTS45 Cl 7.9.1
4a44ae8b-b3f3-43bf-87b6-6bb01559b80c | checkpoint | Final Verification
7797926b-0e51-5d99-8326-293f16135d09 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
584f8d65-500b-55a8-9f05-68bda8f002db | textbox | Print Name:
0f1e96fd-0e4f-5f2f-a711-36e9984fd500 | date | Date:
666fa32a-d9c5-5267-8970-78eb7e788e95 | note | Project Manager Verify that the Above has been Constructed according to Specification
a3f573e7-9337-5aec-b161-d75bd39449a5 | textbox | Print Name:
bda5f0c4-6e5e-5583-ae8f-f78a3eec3a86 | date | Date:
4f673fdd-c82a-4c8b-8e7c-19b69c6510a1 | signoff | Sign ITP
65669220-376b-4a07-9609-ad3783c11d6f | section | Final Sign Offs (to be completed at closure of Lot)
79d2ce59-4761-4cf1-a9a9-e75d6b73f350 | checkpoint | Agreed Quantities
2351c879-e5c0-4a48-a6c7-7f6a9a6a1716 | signoff | Agreed Quantities Sign Off
ada8af48-1e4e-4ad1-a80b-6dfb7616c200 | checkpoint | Closure of Lot
b32d7d7d-49d8-4b8b-b8e6-2c68aa1f4f2c | signoff | Closure of Lot Sign Off
e238810d-b970-49f5-92d2-562bff5b4087 | checklist | 51.01 - Environmental Management Systems | itp | 51.01 - Environmental Management Systems
b7f25f13-1b43-426f-a886-6019737aa172 | section | Details
28e229da-fad4-4296-9561-0bb4d9205b0b | checkpoint | Environmental Management Plan (Construction) EMP(C) submitted in accordance with General Conditions of Contract.
71f9f703-fb05-52c1-b9da-f451ca7f48a9 | note | Acceptance Criteria & Frequency (Project Specific) - Submission of EMP
2f22347d-af27-5a6a-a196-595f21ce0d93 | note | Check Item - Milestone
bd06bf8d-b8b9-5f68-a106-a4461ca7e618 | note | Reference - MRTS51 Cl. 6.3
358513b2-45e4-4b46-90e9-27ead148e4d4 | checkpoint | Works under the Contract shall not start until the EMP(C) is assessed for suitability by the Administrator.
bd8b22f5-7a28-5223-84b3-58fe68ca6b0a | note | Acceptance Criteria & Frequency (Project Specific) - EMP Approved by Administrator
b404fb3a-d11a-5fb1-b323-35665204e9b6 | note | Check Item - Hold Point 1
e45476ef-b1c0-5a36-bbda-43a72a4322d5 | note | Reference - MRTS51 Cl. 6.3
fc7a6ba9-92b3-44e1-9cdb-137161276f2b | signoff | HOLD POINT
4a068e37-cbe4-4bef-88e3-3f9416247603 | checkpoint | Any amendments to the EMP(C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
31882e83-3f19-5436-b69c-014ed1634535 | note | Check Item - Hold Point 2
bdc0aceb-03c3-5bec-9d2a-f85de76c2c2a | note | Reference - MRTS51 Cl. 6.4
acb2e2b5-fb0a-47d9-b722-537fb121f877 | signoff | HOLD POINT
8c3c66af-cb23-4279-810a-efd5317d418b | checkpoint | Environmental site inspections to be conducted daily, against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a monthly basis.
ebb7c98f-89aa-5358-a6e8-9561e2ebf925 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
a890f5d7-c83e-59e8-9450-a9bd7bf420da | note | Check Item - Check Item
32b90158-42b7-5269-84e1-4a90fcf6bedb | note | Reference - MRTS51 Cl. 7.1
39c3deff-7b5e-431f-a7b3-750e690a3883 | checkpoint | Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request.
4b8921b4-013e-5fe7-9ba6-22c16fc37225 | note | Check Item - Hold Point 3
d6488bb7-f97f-543e-8545-2edaf599ef1a | note | Reference - MRTS51 Cl. 7.8
5fe63dc2-63fe-4782-83b6-e0ba1786ce73 | signoff | HOLD POINT
1695a399-7012-42c3-a0a3-1a3e38fa8ca4 | checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite
2b53df0d-a807-57cf-aa20-42eeb158e4ed | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c17dac8b-2c13-5e9c-bf07-616cf0afea2f | note | Check Item - Check Item
b177dfa6-678f-5a21-8f6c-3eb38545d2ee | note | Reference - MRTS51 Cl. 8.4.1
3da5af31-d4cf-449b-8c1b-5a434cdec141 | checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
23144d92-8e81-57cb-b005-740bafd5e4fe | note | Acceptance Criteria & Frequency (Project Specific) - Visual
dee02806-3f86-5b24-82ce-5e117ca861c9 | note | Check Item - Check Item
d28df110-7187-5440-a87e-7e60b3646ba5 | note | Reference - MRTS51 Cl. 8.5.2
b26b6aa6-fa52-431c-aa12-962a962b8224 | checkpoint | Project records shall include all noise monitoring results if required
cb21bd69-ac5a-5ac2-b314-dcbdb13c2aec | note | Check Item - Check Item
c9170918-d5a6-562b-9ee5-b98c0808b068 | note | Reference - MRTS51 Cl. 8.5.3
9926c0b8-586c-4422-b6a1-302aee9de7c0 | checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
4417b0ae-03f9-5415-b9af-653f2214e73b | note | Acceptance Criteria & Frequency (Project Specific) - Visual (Survey Recorded)
b0bf9acd-003a-506e-9dc8-6e39fcf40d67 | note | Check Item - Check Item
af1b7ed8-88a8-5af7-9ca7-a1d1ffe32803 | note | Reference - MRTS51 Cl. 8.6.2.3
2684c4c3-8b0f-4590-92d5-a3175f9c56b7 | checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
cd7388e0-5ac1-56ad-9175-6e37683ff7ea | note | Check Item - Check Item
3da3e22b-53a3-5423-b847-15e5745e7649 | note | Reference - MRTS51.1 Cl. 8.6.2
a9cd35ea-df47-49db-9e6d-b2589a8b39a2 | checkpoint | The contractor shall at all times take reasonable and practicable management measures to avoid cuasing environmental nuisance or harm due to air quality. Burning of material shall not be permitted
6597e9e9-66c1-5577-aac7-f6eed6cf4059 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
550bea2d-e8d1-58f1-8ee4-fdb321080ac7 | note | Check Item - Check Item
c33972ba-800b-5433-a8cd-3308a5214021 | note | Reference - MRTS51 Cl. 8.7.2
4cee86ee-c3b4-4800-af80-d027637f24e6 | checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
18f33de4-cecd-558a-9f99-579d3ddeadab | note | Acceptance Criteria & Frequency (Project Specific) - Visual
20e19e71-e338-5e78-a561-6412f68dba4c | note | Check Item - Check Item
110b2114-800a-56bf-80bc-d87bba8b4302 | note | Reference - MRTS51 Cl. 8.8
2f637802-2f22-4f0f-be0d-a632d55909f1 | checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
30e47c3d-e509-5db4-a3e3-31f4d16de5ba | note | Acceptance Criteria & Frequency (Project Specific) - Visual
af38d246-2a3b-5b8e-bda6-2a320ffaf98b | note | Check Item - Check Item
8636c7dc-864f-5514-968f-d9f82a431586 | note | Reference - MRTS51 Cl. 8.9.1
1acabe6f-e1dc-4a4a-95be-c837b80e4cea | checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list.
dc5a611d-6d5c-534a-986d-c7c57dc0932b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
d0f474de-37cb-51c2-aebe-791ee3e3a6fa | note | Check Item - Check Item
58e0ca1e-b358-56a3-ac70-e117c9a5c689 | note | Reference - MRTS51 Cl. 8.10.1
3e0395a0-e12c-4596-9146-03fdbe40bfe9 | checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
8b2be1b0-987d-581f-bb00-3e343c080797 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
ecc0f09b-1793-5998-97a6-e47f33a13af6 | note | Check Item - Check Item
f4884451-3f35-5865-a378-aea0a7de274a | note | Reference - MRTS51 Cl. 8.13.2
99b21921-e525-4192-bd2d-7413948a148f | checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
51f5c66c-0137-555e-b9bb-d0e2ff30a55c | note | Acceptance Criteria & Frequency (Project Specific) - Visual
bb762c24-2603-594a-9a44-644c55d06060 | note | Check Item - Check Item
82b78ec7-d3cc-55c6-a38a-7b69f3c93bfa | note | Reference - MRTS51 Cl. 8.14.1
52515b3b-d20e-4b93-9314-706b04048c5b | checkpoint | Final Verification
f67ef1aa-1c84-5acf-b518-8d22b1ecf406 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
1afee84b-8a1c-5caf-b904-9ef515101edd | textbox | Print Name:
c76758fe-2971-5f41-ac26-f33d7ba02198 | date | Date:
1e12a083-d0b4-5908-bba0-710ad9e5116c | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
47c3d366-2fea-57ff-a68f-6f4a9152c4bc | textbox | Print Name:
0fd638ea-5f22-5412-85a7-3b0d9c6c40b9 | date | Date:
cbc4fa94-96c3-4c1a-af25-c6e3b77aeff7 | signoff | Sign ITP
0a987576-3f7b-4ee9-81ba-b6c58504e5f1 | section | Final Sign Offs (to be completed at closure of Lot)
bd8f804c-03e3-437a-9cc4-62ddb34ec17b | checkpoint | Agreed Quantities
258b772d-f9cf-45d5-9354-43b0bdd8f54f | signoff | Agreed Quantities Sign Off
093def38-8896-477e-b05c-0d26d139c3d8 | checkpoint | Closure of Lot
e12d7735-6c5f-4194-90ff-7be315035c51 | signoff | Closure of Lot Sign Off
0bba64b1-7dde-48a2-9ccf-187924b8447f | checklist | 52.01 - Erosion and Sediment Control | itp | 52.01 - Erosion and Sediment Control
963e52dc-6008-4ca2-bf06-8ea9ca61cd91 | section | Details
bdc88645-c49b-4a0c-9cd6-de59039b0343 | checkpoint | Clearing and grubbing (or the use of the area for stockpiles) for that section shall not start until the ESCP for that section is assessed as suitable by the Administrator.
c5e7c37b-d93b-50fc-97a3-ad5023e135fc | note | Acceptance Criteria & Frequency (Project Specific) - Approval of ESCP by Administrator
f2bb6538-7a2a-50f4-93f3-784faf32da78 | note | Check Item - Hold Point 1
7c83cca4-282f-5096-86b9-99ca28b8c687 | note | Reference - MRTS52 Cl. 6.1
721c2c5b-7c89-4d5e-aefd-88d50a2d1c14 | signoff | HOLD POINT
c47a2d93-b7d2-49e7-b3c7-36abcb599bf4 | checkpoint | Prior to initial earthworks operations, the Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
9a574387-099f-5915-9202-62b4b5f5bba8 | note | Acceptance Criteria & Frequency (Project Specific) - In accordance with approved ESCP.
8d6eaa18-e5b2-5aa7-ac9a-9484099e616e | note | Check Item - Hold Point 2
778282a7-5573-53d5-9cbd-37594d0927f3 | note | Reference - MRTS52 Cl. 7.1
c6abc9c7-32b4-4bcd-a7dd-42ba361ac7e4 | signoff | HOLD POINT
e34c7999-7438-4300-9325-4679c92bc162 | checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
08b56a49-5987-5e3e-a232-3e26abf85e2c | note | Check Item - Check Item
758e64ad-3ece-52ec-a48a-d0ab743fb464 | note | Reference - MRTS52 Cl. 8.1
87e1a6f0-a8ad-4a1f-9012-960069a40597 | checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
48350804-0064-5ecb-899d-45bb65350888 | note | Check Item - Check Item
9ed31aa1-3209-5d33-98c7-1a9f222c7705 | note | Reference - MRTS51 Cl. 8.2.3.2.1
6ec7a8c8-8dcc-48d0-b27d-e89159b4e2a0 | checkpoint | Final Verification
caa0a574-b487-50ad-8797-56b49717fddd | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
2d897a1d-9c83-565f-9a78-48e2f62c39f1 | textbox | Print Name:
9b2ce103-f17c-5e04-a670-6d5e957e8284 | date | Date:
631924a7-35ee-587c-9796-27204cfb7bd5 | note | Administrator's Representative Verify that the Above has been Constructed according to Specification
65663998-e069-589a-8c98-479c758109fd | textbox | Print Name:
7a5ab010-267b-5e69-8a05-fc9b3b359111 | date | Date:
c31ce34b-3e6a-4548-bedf-c97b7170e33d | signoff | Sign ITP
5ebf4fae-6dd9-48ca-9a0b-de735b366cbd | section | Final Sign Offs (to be completed at closure of Lot)
c291caa3-0bcc-4aee-a52d-1f4cb66329a0 | checkpoint | Agreed Quantities
79d4b5bd-3ccf-4951-8b09-76df14f17dc7 | signoff | Agreed Quantities Sign Off
7578c63e-4bb6-4668-9e6b-e97f670be59c | checkpoint | Closure of Lot
c8651e62-fb31-447f-922a-e821ddcaa048 | signoff | Closure of Lot Sign Off
f2b26bfc-a77f-4825-8717-1cfef0037e86 | checklist | 70.01 - Concrete | itp | 70.01 - Concrete
1bb04d19-e7cb-41c9-b8e7-c4330ed3508a | section | Concrete Details
47484cd2-b2b8-40cc-8f4d-24c3e81ad4bc | checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
e0f32880-768c-5dcc-8a9b-d2cecec799f2 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6e3ad5b9-b20f-5d22-9c20-e31ffe5164ac | note | Check Item - Milestone
cf27eaea-cb74-5f57-a1ec-1da16c6f31cd | note | Reference - MRTS70 Cl 9.2
23775585-26bc-4d39-822e-d2284c641063 | checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
7af2e476-f756-51f8-9a45-d239fa8e5e0d | note | Acceptance Criteria & Frequency (Project Specific) - Visual
c1892902-4939-5857-ae88-d9d78a594db8 | note | Check Item - Milestone
5b9df116-0a4f-503c-8408-48a4d13525ff | note | Reference - MRTS70 Cl 13.1
1ae9f285-4137-4b4f-aee5-4312ba755fd7 | checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
703bdc02-92f4-59b3-bda9-1947c503a8e3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
94f5c015-a1b9-599a-b668-8b04c3012ee3 | note | Check Item - Milestone
bdc1814c-5cb6-5103-a4dd-8907c2e2f528 | note | Reference - MRTS70 Cl 15.11.1
6224e2d2-f9de-4d8c-86fc-44a301319759 | checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour.
d42fc24f-c9aa-57cf-86c7-8410758fa9d0 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
7273d9b4-0521-5bc0-8e00-28023f899452 | note | Check Item - Milestone
4d4c6be5-9d53-56a2-a1ed-3da9ead75cb2 | note | Reference - MRTS70 Cl15.5
dd1a0a96-43b3-4baf-a4f8-6701d095d106 | checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. Each trial mix shall be a Witness Point with a notice peroid of 3 days. The minimum volume of trial mix is 25% of the rated capacity of the mixer.
b78fd2f0-b412-56dc-bb08-46bce83d53fc | note | Acceptance Criteria & Frequency (Project Specific) - f'c Each Mix
43a2d0c4-0186-5aba-9934-b3a10d31da25 | note | Check Item - Witness Point
348194a2-1877-5333-b50d-ea8aee0ff34e | note | Reference - MRTS70 Cl 15.1.1
e50d7fe1-6a4c-46d2-ad91-c539902efdf1 | checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
c39f5cb7-b49f-5420-883f-12c3b8dddcc9 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1163eb44-1704-590a-868e-696402a19064 | note | Check Item - Hold Point 1
e406139c-629a-51f9-8484-9a20338abb2d | note | Reference - MRTS70 Cl 15.1
0e020697-4a9e-4738-8274-9acd09f870cc | signoff | HOLD POINT
59e03bc2-7d8b-434a-b6f3-c04d7863419a | checkpoint | Concrete placed within 75minutes (conc. Temp<=32 degrees) or 1hour (32>conc. temp < 35 degrees) from the time of charging the mixer. These times may be extended at the Administrator's discretion where set-retarding admixtures are used. No concrete may be placed the temperature of the concrete is less than 10°C or exceeds 35°C.
da88fbd4-c84f-5707-a4b8-0ecb8242ce3c | note | Acceptance Criteria & Frequency (Project Specific) - 10< Temp <35 Continuous
a00fab90-8c1e-5bf0-9fe1-3ddf8808997e | note | Check Item - Check Item
cd03f72f-a6ef-5bc7-8053-137612ccc4e9 | note | Reference - MRTS70 Cl 13.1
2880c826-7127-4120-a028-ca1473284184 | checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
9619a3be-a567-51b3-b4c7-79e27e0e766a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
2d0c1c7d-daef-575d-9f97-4f5b62df9cc6 | note | Check Item - Milestone
0accb9fc-67e8-5102-9069-78ae120e67b4 | note | Reference - MRTS70 Cl 15.3
6355ec84-dd11-4e33-b912-ea05c30d1a05 | checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
98bb64bc-e491-57c4-9b0d-ee97b6ba26c3 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
878fd460-e2ce-5515-bd1a-5e0ca3a80917 | note | Check Item - Hold Point 2
adc7fcad-8d43-59d2-972a-10989e7a7428 | note | Reference - MRTS70 Cl 15.3
b7b6cda2-ae54-439e-ae8f-28e76f9f0c27 | signoff | HOLD POINT
637947d5-48be-4669-ae3b-a9c657604590 | checkpoint | All formwork shall be subject to inspection and approval by the Administrator.
54b1bccc-92bf-58c6-9896-2d0b04199aba | note | Acceptance Criteria & Frequency (Project Specific) - Visual
48524e13-bc0a-53ad-b337-933516340394 | note | Check Item - Hold Point 3
f9e79fc1-54d2-54c9-94fa-95e3139f20cd | note | Reference - MRTS70 Cl 15.4.1
f20ed524-7849-4616-a312-0b5a139d2fea | signoff | HOLD POINT
b63cd405-3bae-4321-988f-82670631f621 | checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
b1a52d46-1b8b-50ce-b539-97496d0c7f2a | note | Acceptance Criteria & Frequency (Project Specific) - Visual
8f50ede2-ae24-5d32-a40f-05cb6bf1574c | note | Check Item - Hold Point 4
342ea25a-1c61-55ab-b808-aa11be7b2baf | note | Reference - MRTS70 Cl 15.6
d4ac4e0f-2f57-416e-a770-5d8bd0445c90 | signoff | HOLD POINT
b70f5c5c-09a5-4507-bc79-8ecb8278ea60 | checkpoint | No concrete shall be placed in the Works until:
c60d36af-ebad-5ffc-aeb5-d177d0898266 | note | a) the formwork and reinforcement have been inspected
a74f54fb-e52c-5bc3-b648-a44e91e88c3b | note | b) all foreign material has been completely removed from the forms
3d7dec2f-e48c-528f-9360-7cdd8adde887 | note | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
69bb217b-37da-55b1-85ff-aeaa83083e2b | note | Acceptance Criteria & Frequency (Project Specific) - Visual
35a67bbd-1ef5-5cf2-9dd3-2d18c6c322c3 | note | Check Item - Hold Point 5
4a58915a-feed-557a-8153-9694dd891db9 | note | Reference - MRTS70 Cl 15.6.1
81cb7b72-b51e-45d8-968a-4d305c8782f1 | signoff | HOLD POINT
4d06b893-b774-4d56-8a45-835480fa3357 | checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
7a744354-c2cb-5652-a295-2637f7118b35 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
be775d9d-049e-5480-846b-7d31e29ebe56 | note | Check Item - Witness Point 2
ab9d3555-6541-5791-9057-ee8ce99388fb | note | Reference - MRTS70 Cl 15.6.1
b2396720-1bc0-40c2-875e-e4424e9baf7f | checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
ef950271-6c01-50d5-ac8b-0e219a05596f | note | Acceptance Criteria & Frequency (Project Specific) - Slump Test:
a1117eda-aa11-5704-b851-b67b89ca1b35 | note | ○ <60 - ±10
07bc1488-2c7f-501e-bc96-a342df437e17 | note | ○ ≥60≤80 - ±15
d152225d-c544-53ad-8d1e-e499ca4326df | note | ○ >80≤110 - ±20
0dce78ac-a323-5166-9c60-b24a3682c1e8 | note | ○ >110≤150 - ±30
d197dcf0-f9d6-57af-be68-158b02d63bc2 | note | ○ >150 - ±40
9907e12d-8494-508f-a170-a6984774e8d2 | note | (Every Load)
a8eff781-3e0b-5e07-a35d-b26d6973ce03 | note | Check Item - Check Item
f266486a-1497-524d-97d9-9f16f2c131e4 | note | Reference - MRTS70 AS 1379 Table 5.1
f00ebc6d-b7f4-4900-a14d-e0aa2c5c19bc | checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample.
0436142c-9208-5a4a-9f08-c8e063962fd0 | note | Acceptance Criteria & Frequency (Project Specific) - 1-3 Loads - Every Batch 4-10 Loads - 4 Samples
5f53e152-c6d7-556b-97e0-adb0b62393c2 | note | ○ 11-23 Loads - 5 Samples
7bc6edcb-b091-5fd4-a62f-fee60c73e1fa | note | ○ >23 Loads - 1 per 4 loads
b4e2a054-82e2-5b1b-83c3-dafe33b0d1c1 | note | Check Item - Test Results
e86dfc28-9c60-5f1b-94ed-34f2a68cf248 | note | Reference - MRTS70 Cl 15.2
088d8bf8-1b1d-47e3-a334-50e9c9495e34 | checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour.
1d3852d9-1132-54de-8340-4d0e726e0060 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
34729872-7e6c-52b8-8cbb-1c8500a64fb3 | note | Check Item - Check Item
1f35ca1b-2d1c-53d1-9a3e-14522f80f325 | note | Reference - MRTS70 Cl 16.5.2
01e8578d-2768-49d7-b695-34031059408d | checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set. If an interruption greater than 45 minutes occurs, without prio approval from the Administrator, or a cold join occurs, the precast member shall be rejected.
d243bb3e-3f5d-5961-b414-ff25f36a6075 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
5856890e-0b7c-5986-a660-5ddd8626c8b6 | note | Check Item - Check Item
28000354-bd60-5429-a994-c69ec9958a91 | note | Reference - MRTS70 Cl.16.5.1
bfa331e0-3ed7-4d51-8659-1010b1ba1b87 | checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
2c1074a5-f45c-5f20-a3e5-6bdf673782e7 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
1f7bb6e6-8cb7-543d-894c-131b246d4a88 | note | Check Item - Hold Point 7
af3f9b20-9c2f-5b29-8b1a-f90e06f63e9d | note | Reference - MRTS70 Cl 15.13
e15c0d30-1ca8-47dc-bcd4-c68c9fb4ed8e | signoff | HOLD POINT
e5e4b3a2-fc6b-42c2-a30e-08f085db6e11 | checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting.
57f61fcb-3e32-5a9f-90a8-5ef27d9076d1 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
6a051038-351e-5e87-aaad-36b6010d35ac | note | Check Item - Hold Point 6
3799dfbb-3895-56be-be27-bcdbe6201ce8 | note | Reference - MRTS70 Cl 15.8
d7ec030a-5d07-4247-8162-965814353c9a | signoff | HOLD POINT
0e13d712-cc86-4008-9175-fd0579bd47c9 | checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure.
a208c2ab-349d-590a-b561-f96f91707436 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
f827a8b6-75f3-524d-9113-89392f546dee | note | Check Item - Witness Point 4
0a9f50e3-87d0-5f65-aee0-e438eed210a4 | note | Reference - MRTS70 Cl 15.8
5b58ddef-e805-47f2-89df-747d1d9485e7 | checkpoint | Following removal of forms
b5482db5-72f8-5a97-896d-3d47abe75b4c | note | ○ Fins and unwanted projections are ground off
24fef854-f385-51d6-a4d0-88a0a37eb71d | note | ○ Where required in the drawings surfaces achieve class 1 finish or are bagged within 4 hours of stripping, then cured
0155ba9f-c509-5782-9dd2-6093cb5d768d | note | ○ Where surface finish is not specified, class 2 finish is required. Where surfaces of concree do not achieve class 2, surface shall be bagged.
7e94636c-7528-5f0a-8220-6706f0f67655 | note | Acceptance Criteria & Frequency (Project Specific) - Visual
712aa51d-deea-52a6-ae91-bc662dec8436 | note | Check Item - Check Item
0ff561b5-e4ca-5f8c-8257-d5babc5e3625 | note | Reference - MRTS70 Cl 16.8.1
1dc68a82-2c66-4a83-aaa3-7c65c4453bb2 | checkpoint | Positional tolerances, listed in Table 15.7.3, refer to the departure of any point, plane or component of a structure from its correct position within the layout of the structure as shown in the Drawings.
40c9c815-86f8-585d-8b32-95797db8049d | note | Acceptance Criteria & Frequency (Project Specific) - Visual <Specified MRTS70 Cl15.7.3
548b81dd-fe27-5ad4-ad57-0d7d5ecbd328 | note | Check Item - Check Item
8a25a12d-791d-5191-92ce-979e35c32284 | note | Reference - MRTS70 Cl 15.7.3
c964e0a2-61b8-48a0-993a-7b03e2f871d1 | checkpoint | Acceptance or Rejection of Hardened Concrete on the Basis of Strength
057415d0-b7ce-5740-b953-4983a2d41801 | note | Acceptance Criteria & Frequency (Project Specific) - a) < 0.9 Fc (Any sample)
54f2c5ca-1e1e-56bd-916e-a9b1687f8018 | note | b) < Fc (Ave 3 consective samples from Lot)
b3e7f8aa-6bb4-5824-886f-ec3218024b66 | note | c) > 1.4 Fc (Ave 3 consective samples from Lot)
8a852544-09df-5754-86b0-d6c8b4546b30 | note | In addition
abc79245-12f8-53f1-bd94-24fb4b27fa63 | note | d) < 0.5 (Fc+Ft) (10 or more samples for Class of concrete in 4 consective weeks)
e80b7a1b-aa36-5b9b-b4ab-85069c972a4b | note | Check Item - Test Results
ff1b647c-b059-54c4-b9b5-c884846ad0ab | note | Reference - MRTS70 Cl 12.5 & Table 12.4
ff6d00bd-2832-401d-b720-e927b22ea815 | checkpoint | Final Verification
cf1838e5-ac4c-535c-93b4-73e886161c12 | note | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
9b6a0cc0-3436-5ff0-a002-6ef969dd07fb | textbox | Print Name:
fcd96c93-ce40-5b00-9180-6f267a32f174 | date | Date:
aa8c1624-b4b0-440b-aa05-bff4717a7707 | section | Kerb and Channel
679e5c59-3d57-460f-a051-7f0f14ac1193 | checkpoint | Concrete shall be in accordance with the requirements of MRTS70 Concrete.
e0cb4ce1-6bb5-540a-89a1-337ae20ffa87 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
318730db-43a4-5510-b3f6-cba0f9d0a4f7 | note | Check Item - Check Item
f732088f-b528-51f1-8d9c-c41a6dbd301d | note | Reference - MRTS03 Clause 5.4
2906ee82-f2d7-459e-9a19-23b453628b7c | checkpoint | Cast-in-place concrete kerb, channel, and kerb and channel, including kerb crossings, shall be provided in the locations specified in the drawings and in accordance with SD1033
b347f94d-4342-5192-9527-73593eb77008 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
f1da55cc-635f-5376-bac1-ac2d4643a2db | note | Check Item - Check Item
300da50f-ea07-55a3-af32-33bccab12d98 | note | Reference - SD1033
92a65a56-12b2-47c2-8117-e2866cc88da4 | checkpoint | Where insitu material on or against which kerbs or channels are to be constructed is other than rock, the material shall be compacted as for material at the bottom of excavations in accordance with MRTS04 General Earthworks.
8eacc9ef-2358-5778-88ec-8221cdabb49b | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
39fb2de4-f296-5fdf-8e64-e73391017180 | note | Check Item - Check Item
58a6cb6b-939a-52dc-8999-4ececdcb3e5a | note | Reference - MRTS03 Clause 18.3
6f2e868c-e220-45f5-ba2b-8ecfa01b5816 | checkpoint | Manually-placed concrete shall be in accordance with Clause 6.1. Exposed surfaces shall have a steel-trowelled finish.
3096932f-8e9a-53bd-8c44-14ba5d7a630c | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
f7b78cc1-0e0a-5250-8ec5-7e2a6ca014c6 | note | Check Item - Check Item
1774a68a-6023-5b09-b0b3-7af68070edb4 | note | Reference - MRTS03 Clause 18.3
9ec54fec-8d0e-4125-a956-5c48ae400d9d | checkpoint | Where kerb, channel and/or kerb and channel is constructed by an extrusion process, concrete shall comply with a maximum aggregate size not exceeding 20 mm and a minimum of 320 kg of cement per cubic metre of concrete. The extrusion machine shall be fitted with a tamper and an automatic control which allows adjustment of the position of the forming mould while the machine is in operation.
f3f16616-5401-52fa-8962-0cbf179001b7 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
149e3d0b-546c-51cd-a6c5-d78e0a109443 | note | Check Item - Check Item
330fea20-536f-57dd-96b0-52f5a673428d | note | Reference - MRTS03 Clause 18.3
27e0de79-be9c-4a32-a08c-1b6b0ce4678f | checkpoint | The finished kerb, channel and/or kerb and channel shall be well compacted and shall have exposed surfaces free from voids and honeycombing.
23070cbc-048a-5218-9cbe-e87f97f50b4b | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
dcc7b740-60a1-538d-bff8-244175e11bd7 | note | Check Item - Check Item
8368f291-11f2-5b60-8c7c-98670013d8e1 | note | Reference - MRTS03 Clause 18.3
5f1bc267-1128-4226-9c5f-c5e1a578dae7 | checkpoint | Expansion joints shall be installed at regular intervals not exceeding 20 m. The joints shall be constructed by installing 6 mm maximum thickness compressible packing in the full cross-section of the kerb, channel and/or kerb and channel. Where relevant, joints shall be located to line up with expansion joints in adjacent structures.
30661e70-c861-5bb8-943d-b4862aa93d53 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
461b0d9a-6014-5d14-81d3-51cdb4247799 | note | Check Item - Check Item
09ec0fcd-2f5c-5d69-bc9b-9e089665589e | note | Reference - MRTS03 Clause 18.3
bc51129e-818e-4fba-b568-4ac060fbf4ef | checkpoint | Contraction joints between expansion joints shall be installed at regular intervals not exceeding 5 m. The joints shall be constructed by forming grooves 40 mm deep and not more than 6 mm wide in all exposed surfaces of the kerb, channel and/or kerb and channel.
5e472170-7cf5-5cf8-8c34-7a00979f0eb1 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
398ebd9c-2e86-51c3-a549-3e2a2a03a194 | note | Check Item - Check Item
3ab5170f-db70-55ba-b605-8665615737c1 | note | Reference - MRTS03 Clause 18.3
bf9befe9-183a-4ae3-b6a6-2892a769f748 | checkpoint | Concrete shall be cured for a period not less than seven days before any other roadworks operations are carried out adjacent to the kerb, channel or kerb and channel.
556e7fd3-4612-5b4b-804c-9016c65f63eb | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
1133111c-fd29-5695-8cb9-8f325e659667 | note | Check Item - Survey Results
c23a6aa4-ca4a-563f-b6e8-f073387804d5 | note | Reference - MRTS03 Clause 18.3
fd5d65ee-906f-4f2f-993d-a380c8d07a8a | checkpoint | The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm.
c5d9ccc9-73d2-5248-8ed6-3ba37945552a | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
5deeb4e4-0350-5fc4-a1ba-1464805c7d50 | note | Check Item - Check Item
17b4059f-d1ad-5e82-9944-0cc6fa311b0d | note | Reference - MRTS03 Clause 18.4
f12e4eca-f35f-40b8-997c-1ed3d3037272 | checkpoint | Where the longitudinal grade of channels is less than 1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened.
b1f00f1c-ed84-5eb2-9a7c-39991b2c7e09 | note | Acceptance Criteria & Frequency (Project Specific) - Check and Verify
df111cb5-d29f-5988-b9a2-2e60de2c8a4c | note | Check Item - Witness Point
e9ec1a05-1248-54f1-808e-8b16e14f1cb1 | note | Reference - MRTS03 Clause 18.5
a578b140-0b48-4a1c-8822-992c84cba9d2 | checkpoint | Final Verification
125bbb2d-ad87-5b3c-9e73-85d02fa66718 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
7d65cd0c-122c-55df-a418-842a6c1d4af6 | textbox | Print Name:
372e4997-3cdb-534e-8548-365d7995bcfb | date | Date:
cfb0a94a-f4f5-436f-ac20-256c5294bb5e | section | Final Sign Offs (to be completed at closure of Lot)
a42b95a3-94b5-4fa2-86fc-7e920695f77b | checkpoint | Agreed Quantities
ff63dc93-d608-45d6-b61e-c7441fd24da8 | signoff | Agreed Quantities Sign Off
14d9192d-177c-46b2-b925-67bf81da072c | checkpoint | Closure of Lot
f6046d11-ea30-4450-a351-c83e484c84f1 | signoff | Closure of Lot Sign Off
f8443ba2-1a0c-4ff5-87c7-e3aaea629357 | checklist | Electrical | itp | Electrical
3feb9059-c7f6-4ac8-b10f-ecba9a711c75 | section | Subcontractor ITP
6ccd00f1-c9c3-40fb-aaf4-650a0857371a | checkpoint-no-value | Attachments
f8ff1c50-ba38-454d-a96e-bb6c95e11339 | section | Final Sign Offs (to be completed at closure of Lot)
15d08a8d-ce57-4db6-b22b-cc42e07184a5 | checkpoint | Agreed Quantities
ce4fd17e-4a00-4bf8-b08a-78988820df44 | signoff | Agreed Quantities Sign Off
61e89b43-a7d9-4ad2-a8bd-418c6d23f99f | checkpoint | Closure of Lot
22ae7996-f6a3-4b13-8be7-bf8bf66fb53e | signoff | Closure of Lot Sign Off
a5587f5b-bc44-4a86-91d1-0d60cb995be8 | checklist | Sprayed Bituminous Treatment | itp | Sprayed Bituminous Treatment
b3790762-1258-4ab7-83a5-1a1e1b8ec2b0 | section | Subcontractor ITP
8b9fcd36-a1a1-456c-81a4-a0e0eae18047 | checkpoint-no-value | Attachments
019b8d7b-4d96-4801-bb59-9f2e37bf3ab8 | section | Final Sign Offs (to be completed at closure of Lot)
e5d6fab1-fdde-456f-b537-ac0a9cee3562 | checkpoint | Agreed Quantities
32167c6f-244b-4048-b080-373b7e14df45 | signoff | Agreed Quantities Sign Off
49a7b345-e7f3-4d77-a1d3-10fdef8f2df9 | checkpoint | Closure of Lot
68121773-492b-4153-865c-1713cd14b795 | signoff | Closure of Lot Sign Off