## JOB STRUCTURE
Folder Structure
BANCHORY GROVE
INSTALLATION
WOOLWORTHS
|  |  | MSSB-WW | Mechanical Switchboard Commissioning
|  |  | MSSB-E | Mechanical Switchboard Commissioning
|  |  | AHU-1 | EQUIPMENT Testing
|  |  | ACU-C.1 / CU-C.1 | EQUIPMENT Testing
|  |  | ACU-G.3-1 / CU-R.3-1 | EQUIPMENT Testing
|  |  | ACU-G.1-1 | EQUIPMENT Testing
|  |  | ACU-G.1-2 | EQUIPMENT Testing
|  |  | ACU-G.2-1 | EQUIPMENT Testing
|  |  | ACU-G.2-2 | EQUIPMENT Testing
|  |  | CU-R.1-1 | EQUIPMENT Testing
|  |  | CU-R.2-1 | EQUIPMENT Testing
|  |  | HHWP-01 | EQUIPMENT Testing
|  |  | CHWP-01 | EQUIPMENT Testing
|  |  | EF-R.1 | EQUIPMENT Testing
|  |  | EF-R.2 | EQUIPMENT Testing
|  |  | EF-R.3 | EQUIPMENT Testing
|  |  | EF-R.4 | EQUIPMENT Testing
|  |  | EF-R.5 | EQUIPMENT Testing
|  |  | EF-R.6 | EQUIPMENT Testing
|  |  | EF-R.7 | EQUIPMENT Testing
|  |  | EF-R.8 | EQUIPMENT Testing
|  |  | EF-R.9 | EQUIPMENT Testing
|  |  | EF-R.10 | EQUIPMENT Testing
|  |  | EF-R.11 | EQUIPMENT Testing
|  |  | TEF-R.1 | EQUIPMENT Testing
|  |  | SAF-R.1 | EQUIPMENT Testing
|  |  | OAF-R.1 | EQUIPMENT Testing
|  |  | OAF-G.1 | EQUIPMENT Testing
|  |  | DSF-G.1 to DSF-G.4 | EQUIPMENT Testing
|  |  | SEF-R.1 | EQUIPMENT Testing
|  |  | SEF-R.2 | EQUIPMENT Testing
|  |  | SEF-R.3 | EQUIPMENT Testing
|  | PUBLIC | MSSB-1 | Mechanical Switchboard Commissioning
|  |  | AC-G-01 | EQUIPMENT Testing
|  |  | AC-G-02 | EQUIPMENT Testing
|  |  | AC-G-03 | EQUIPMENT Testing
|  |  | AC-M-01.1 | EQUIPMENT Testing
|  |  | AC-M-01.2 | EQUIPMENT Testing
|  |  | CU-M-01 | EQUIPMENT Testing
|  |  | ACT-M.1 – M.4 | EQUIPMENT Testing
|  |  | OAF-G.1 | EQUIPMENT Testing
|  |  | OAF-G.2 | EQUIPMENT Testing
|  |  | GEF-R.1 | EQUIPMENT Testing
|  |  | GEF-R.2 | EQUIPMENT Testing
|  |  | GEF-R.3 | EQUIPMENT Testing
|  |  | TEF-R.1 | EQUIPMENT Testing
|  |  | TEF-R.2 | EQUIPMENT Testing
|  |  | TEF-R.3 | EQUIPMENT Testing
|  |  | FPREF-G.01 | EQUIPMENT Testing
TENANCIES
|  |  | AC-T-01 | EQUIPMENT Testing
|  |  | AC-T-01-01 | EQUIPMENT Testing
|  |  | AC-T-01-02 | EQUIPMENT Testing
|  |  | AC-T-01-03 | EQUIPMENT Testing
|  |  | AC-T-01-04 | EQUIPMENT Testing
|  |  | CU-T-01 | EQUIPMENT Testing
|  |  | AC-T-02 | EQUIPMENT Testing
|  |  | AC-T-03 | EQUIPMENT Testing
|  |  | AC-T-04 | EQUIPMENT Testing
|  |  | AC-T-05 | EQUIPMENT Testing
|  |  | AC-T-06 | EQUIPMENT Testing
|  |  | AC-T-07 | EQUIPMENT Testing
|  |  | AC-T-08-1 | EQUIPMENT Testing
|  |  | AC-T-08-2 | EQUIPMENT Testing
|  |  | CU-T-08 | EQUIPMENT Testing
|  |  | AC-T-09-1 | EQUIPMENT Testing
|  |  | AC-T-09-2 | EQUIPMENT Testing
|  |  | AC-T-09-3 | EQUIPMENT Testing
|  |  | CU-T-09 | EQUIPMENT Testing
|  |  | AC-T-10-1 | EQUIPMENT Testing
|  |  | AC-T-10-2 | EQUIPMENT Testing
|  |  | AC-T-10-3 | EQUIPMENT Testing
|  |  | CU-T-10 | EQUIPMENT Testing
|  |  | AC-T-11-1 | EQUIPMENT Testing
|  |  | AC-T-11-2 | EQUIPMENT Testing
|  |  | CU-T-11 | EQUIPMENT Testing
|  |  | AC-T-12 | EQUIPMENT Testing
|  |  | AC-T-13 | EQUIPMENT Testing
|  |  | AC-T-14 | EQUIPMENT Testing
|  |  | AC-T-15 | EQUIPMENT Testing
|  |  | AC-T-16 | EQUIPMENT Testing
|  |  | AC-T-17-1 | EQUIPMENT Testing
|  |  | AC-T-17-2 | EQUIPMENT Testing
|  |  | CU-T-17 | EQUIPMENT Testing
|  |  | AC-T-18 | EQUIPMENT Testing
|  |  | AC-T-19 | EQUIPMENT Testing
|  |  | AC-T-20-1 | EQUIPMENT Testing
|  |  | AC-T-20-2 | EQUIPMENT Testing
|  |  | AC-T-20-3 | EQUIPMENT Testing
VARIATIONS
DEFECTS
|  | WOOLWORTHS | All isolator labels all equipment | Defect
|  |  | All sensor labels | Defect
|  |  | Relief damper covers | Defect
|  |  | Seal conduits on tray going through roof | Defect
|  |  | VRV on deck mech protection for conduit | Defect
|  |  | AHU tray cover | Defect
|  |  | Fix pump conduits with tray and cover | Defect
|  |  | Updated legend | Defect
|  |  | MSSB drawings markups | Defect
|  |  | Fresh set in MsSb | Defect
|  |  | MSSB labels | Defect
|  |  | Check all overload settings | Defect
|  |  | Fire trip test | Defect
|  |  | Emerson online to remote monitoring | Defect
|  |  | Plantroom temp PB and interlock tested | Defect
|  |  | Relive danger signs at completion | Defect
|  |  | AC units controller labels | Defect
|  |  | Stockroom temp label | Defect
|  |  | Shop floor labels | Defect
|  |  | Managers indicator lights and labels | Defect
PUBLIC
|  |  | Pips all isolators | Defect
|  |  | Isolator labels for MSSB equipment | Defect
|  |  | Public BMS labels | Defect
|  |  | Air curtain fitoff | Defect
|  |  | Mid bus loop in T9 | Defect
|  |  | AC indoor units and thermostats | Defect
|  |  | Comms room unit fitoff | Defect
|  |  | OAF inline fans for off | Defect
|  |  | Rough in waste fan | Defect
|  |  | Check fans roughed in, missing TEF 1 and GEF R2, have 2 x TEF-2 | Defect
PUBLIC BMS
|  |  | OA temp and hum | Defect
|  |  | OAF-G1 CO2 sensor managers office | Defect
|  |  | AC units thermostats | Defect
|  |  | 6 x water meters find out which is which | Defect
|  |  | WW meter rough in | Defect
|  |  | RDM head end | Defect
|  |  | Main board power meter | Defect
|  | TENANCIES | All controllers on concrete walls are coiled up | Defect
|  |  | Tenancy isolator labels | Defect
|  |  | Seal around all isolators outside wall units | Defect
|  |  | T1 - VRV isolator, TEF fit off in board (control?) | Defect
|  |  | T2 - TEF fit off in board (control?) | Defect
|  |  | T3 - TEF fit off in board (control?) | Defect
|  |  | T4 - TEF fit off in board (control?) | Defect
|  |  | T5 no plaster on wall for thermostat | Defect
|  |  | T10 extra FCY not installed | Defect
|  |  | T11 extra cassette done, upgrade condenser amps | Defect
|  |  | T14 Jbox damaged cable | Defect
|  |  | T15 - TEF to wire | Defect
|  |  | T19 - TEF to wire | Defect
|  |  | T20 VRV relocate, wire 2 x thermostats, | Defect
MALL DECK 1
|  |  | Seal 50mm conduits | Defect
|  |  | Pips in isolators | Defect
|  |  | Seal decktitie | Defect
MALL DECK 2
|  |  | Cut ties on tray | Defect
|  |  | Pips in isolators | Defect
|  |  | Seal conduits | Defect

## CHECKLISTS
type | name | values
Checklist | EQUIPMENT Testing
checkpoint | AS3000 Testing Completed
checkpoint | Voltage and Amp Draw Tested
checkpoint | All labels installed
checkpoint | Conduit, decktites installed, penetrations watersealed
checkpoint | Ensure all rubbish and materials have been picked up and area is clean
type | name | values
Checklist | Mechanical Switchboard Commissioning
checkpoint | AS3000 Testing Completed
checkpoint | All Circuits Fitoff and Operational
checkpoint | Fire Trip Tested with Fire Contractor
checkpoint | All AOM's Operational
checkpoint | All labels installed
checkpoint | As-installed Drawings and legend in MSSB
checkpoint | All penetrations/glands sealed
checkpoint | MSSB cleaned (photos)
type | name | values
Checklist | Defect
checkpoint | Complete
checkpoint | Photo
type | name | values
Checklist | Variation
checkpoint | Equipment Type, Name
checkpoint | Complete
checkpoint | Tested and Photo