## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: INSTALLATION
| step |  |  | Tier 2: WOOLWORTHS
Mechanical Switchboard Commissioning | checklist |  |  | Tier 3: MSSB-WW
Mechanical Switchboard Commissioning | checklist |  |  | Tier 3: MSSB-E
EQUIPMENT Testing | checklist |  |  | Tier 3: AHU-1
EQUIPMENT Testing | checklist |  |  | Tier 3: ACU-C.1 / CU-C.1
EQUIPMENT Testing | checklist |  |  | Tier 3: ACU-G.3-1 / CU-R.3-1
EQUIPMENT Testing | checklist |  |  | Tier 3: ACU-G.1-1
EQUIPMENT Testing | checklist |  |  | Tier 3: ACU-G.1-2
EQUIPMENT Testing | checklist |  |  | Tier 3: ACU-G.2-1
EQUIPMENT Testing | checklist |  |  | Tier 3: ACU-G.2-2
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-R.1-1
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-R.2-1
EQUIPMENT Testing | checklist |  |  | Tier 3: HHWP-01
EQUIPMENT Testing | checklist |  |  | Tier 3: CHWP-01
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.2
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.3
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.4
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.5
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.6
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.7
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.8
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.9
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.10
EQUIPMENT Testing | checklist |  |  | Tier 3: EF-R.11
EQUIPMENT Testing | checklist |  |  | Tier 3: TEF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: SAF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: OAF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: OAF-G.1
EQUIPMENT Testing | checklist |  |  | Tier 3: DSF-G.1 to DSF-G.4
EQUIPMENT Testing | checklist |  |  | Tier 3: SEF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: SEF-R.2
EQUIPMENT Testing | checklist |  |  | Tier 3: SEF-R.3
| step |  |  | Tier 2: PUBLIC
Mechanical Switchboard Commissioning | checklist |  |  | Tier 3: MSSB-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-G-01
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-G-02
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-G-03
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-M-01.1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-M-01.2
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-M-01
EQUIPMENT Testing | checklist |  |  | Tier 3: ACT-M.1 – M.4
EQUIPMENT Testing | checklist |  |  | Tier 3: OAF-G.1
EQUIPMENT Testing | checklist |  |  | Tier 3: OAF-G.2
EQUIPMENT Testing | checklist |  |  | Tier 3: GEF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: GEF-R.2
EQUIPMENT Testing | checklist |  |  | Tier 3: GEF-R.3
EQUIPMENT Testing | checklist |  |  | Tier 3: TEF-R.1
EQUIPMENT Testing | checklist |  |  | Tier 3: TEF-R.2
EQUIPMENT Testing | checklist |  |  | Tier 3: TEF-R.3
EQUIPMENT Testing | checklist |  |  | Tier 3: FPREF-G.01
| step |  |  | Tier 2: TENANCIES
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-01
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-01-01
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-01-02
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-01-03
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-01-04
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-T-01
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-02
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-03
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-04
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-05
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-06
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-07
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-08-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-08-2
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-T-08
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-09-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-09-2
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-09-3
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-T-09
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-10-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-10-2
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-10-3
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-T-10
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-11-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-11-2
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-T-11
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-12
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-13
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-14
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-15
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-16
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-17-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-17-2
EQUIPMENT Testing | checklist |  |  | Tier 3: CU-T-17
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-18
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-19
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-20-1
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-20-2
EQUIPMENT Testing | checklist |  |  | Tier 3: AC-T-20-3
| step |  |  | Tier 1: VARIATIONS
| step |  |  | Tier 1: DEFECTS
| step |  |  | Tier 2: WOOLWORTHS
Defect | checklist |  |  | Tier 3: All isolator labels all equipment
Defect | checklist |  |  | Tier 3: All sensor labels
Defect | checklist |  |  | Tier 3: Relief damper covers
Defect | checklist |  |  | Tier 3: Seal conduits on tray going through roof
Defect | checklist |  |  | Tier 3: VRV on deck mech protection for conduit
Defect | checklist |  |  | Tier 3: AHU tray cover
Defect | checklist |  |  | Tier 3: Fix pump conduits with tray and cover
Defect | checklist |  |  | Tier 3: Updated legend
Defect | checklist |  |  | Tier 3: MSSB drawings markups
Defect | checklist |  |  | Tier 3: Fresh set in MsSb
Defect | checklist |  |  | Tier 3: MSSB labels
Defect | checklist |  |  | Tier 3: Check all overload settings
Defect | checklist |  |  | Tier 3: Fire trip test
Defect | checklist |  |  | Tier 3: Emerson online to remote monitoring
Defect | checklist |  |  | Tier 3: Plantroom temp PB and interlock tested
Defect | checklist |  |  | Tier 3: Relive danger signs at completion
Defect | checklist |  |  | Tier 3: AC units controller labels
Defect | checklist |  |  | Tier 3: Stockroom temp label
Defect | checklist |  |  | Tier 3: Shop floor labels
Defect | checklist |  |  | Tier 3: Managers indicator lights and labels
| step |  |  | Tier 2: PUBLIC
Defect | checklist |  |  | Tier 3: Pips all isolators
Defect | checklist |  |  | Tier 3: Isolator labels for MSSB equipment
Defect | checklist |  |  | Tier 3: Public BMS labels
Defect | checklist |  |  | Tier 3: Air curtain fitoff
Defect | checklist |  |  | Tier 3: Mid bus loop in T9
Defect | checklist |  |  | Tier 3: AC indoor units and thermostats
Defect | checklist |  |  | Tier 3: Comms room unit fitoff
Defect | checklist |  |  | Tier 3: OAF inline fans for off
Defect | checklist |  |  | Tier 3: Rough in waste fan
Defect | checklist |  |  | Tier 3: Check fans roughed in, missing TEF 1 and GEF R2, have 2 x TEF-2
| step |  |  | Tier 2: PUBLIC BMS
Defect | checklist |  |  | Tier 3: OA temp and hum
Defect | checklist |  |  | Tier 3: OAF-G1 CO2 sensor managers office
Defect | checklist |  |  | Tier 3: AC units thermostats
Defect | checklist |  |  | Tier 3: 6 x water meters find out which is which
Defect | checklist |  |  | Tier 3: WW meter rough in
Defect | checklist |  |  | Tier 3: RDM head end
Defect | checklist |  |  | Tier 3: Main board power meter
| step |  |  | Tier 2: TENANCIES
Defect | checklist |  |  | Tier 3: All controllers on concrete walls are coiled up
Defect | checklist |  |  | Tier 3: Tenancy isolator labels
Defect | checklist |  |  | Tier 3: Seal around all isolators outside wall units
Defect | checklist |  |  | Tier 3: T1 - VRV isolator, TEF fit off in board (control?)
Defect | checklist |  |  | Tier 3: T2 - TEF fit off in board (control?)
Defect | checklist |  |  | Tier 3: T3 - TEF fit off in board (control?)
Defect | checklist |  |  | Tier 3: T4 - TEF fit off in board (control?)
Defect | checklist |  |  | Tier 3: T5 no plaster on wall for thermostat
Defect | checklist |  |  | Tier 3: T10 extra FCY not installed
Defect | checklist |  |  | Tier 3: T11 extra cassette done, upgrade condenser amps
Defect | checklist |  |  | Tier 3: T14 Jbox damaged cable
Defect | checklist |  |  | Tier 3: T15 - TEF to wire
Defect | checklist |  |  | Tier 3: T19 - TEF to wire
Defect | checklist |  |  | Tier 3: T20 VRV relocate, wire 2 x thermostats,
| step |  |  | Tier 2: MALL DECK 1
Defect | checklist |  |  | Tier 3: Seal 50mm conduits
Defect | checklist |  |  | Tier 3: Pips in isolators
Defect | checklist |  |  | Tier 3: Seal decktitie
| step |  |  | Tier 2: MALL DECK 2
Defect | checklist |  |  | Tier 3: Cut ties on tray
Defect | checklist |  |  | Tier 3: Pips in isolators
Defect | checklist |  |  | Tier 3: Seal conduits