## ITP Cover Page
Sculpture Foundation Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: 1208 - 305 - Rev B
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | SH1/29 Intersection Upgrade |  |  |  |  | ITP Number: |  |  | 305
Project Number: |  |  | 1208 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Sculpture Foundation Inspection and Test Plan |  |  |  |  | Revision: | 1000 |  | B
Contract Number: |  |  | 7991 |  |  |  |  | Drawing Sets:
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification:
Quality Specified: |  |  | Z8
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | - | 2025-01-09 |  | Hennie van der Walt |  | First Draft Sculpture Foundation ITP |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | IFC | 2025-01-10 |  | Michael Randall |  | Comments in red added to ITP |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
C | [9 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Artwork Base Construction
Sculpture Foundation Inspection and Test Plan
Project: SH1/29 Intersection Upgrade
Number and Revision: 1208 - 305 - Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Testing Quantity Required | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
1 | Base Materials - Concrete
1.00.1 | Concrete Plant | All plants supplying concrete to the project shall hold and maintain a current quality Certificate of Audit in accordance with NZS 3104 throughout the duration of their supply of concrete for the contract. A copy of each plant’s current Certificate of Audit shall be submitted to the Engineer prior to their initial supply of concrete. | PS 19.7.1 & IFC drawing | Audit Cert | Prior to their initial supply of concrete |  | HP | ENG
1.00.2 | Concrete - Blinding | Blinding concrete shall have a minimum 28 days compression strength of 10 MPa with a maximum aggregate size of 20mm and comply with the requirements for Prescribed Mix concrete specified by NZS 3104. | PS 19.5.1 PS 19.7.10 & IFC drawing | Approved Mix Design | Submitted to and approved by the Engineer prior to concreting |  | HP | ENG
1.00.3 | Concrete - Structural | Structural concrete shall have a minimum 28 days compression strength of 30 Mpa with a maximum aggregate size of 20mm and comply with the requirements for Prescribed Mix concrete specified by NZS 3104. | PS 19.5.1 PS 19.7.11 & IFC drawings | Approved Mix Design | Submitted to and approved by the Engineer prior to concreting |  | HP | ENG
1.00.4 | Reinforcement cover spacer blocks | Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas. | PS 19.7.8 & IFC drawing | Datasheets | Prior to use |  | R | SE
1.01 | Base Materials - Reinforcement
1.01.1 | Reinforcement bars | All Reinforcement bars shall be of New Zealand origin unless otherwise accepted, grade 500 ductility class E and shall be manufactured by the micro-alloy process. Quenched and tempered reinforcement shall not be permitted. | PS 19.17.23 & IFC drawing | Mill Certs | Each Item |  | R | SE
1.01.2 | Bar Schedule | The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars. | PS19.17.20 & IFC drawing | Bar Schedule | At least 14 days before the start of placing |  | HP | ENG
1.01.3 | Reinforcing Mill Certs | Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of ay work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work. | PS19.17.23 & IFC drawing | Mill Certs | At least one week before the programmed commencement of ay work incorporating these materials |  | HP | ENG
SECTION 2 – CONSTRUCTION ACTIVITY – CONCRETE POURS
2 | Setting out
2.00.1 | Setting out | The Contractor shall be responsible for the correct setting out of all works, including set out of the direction of the sculpture, anchor bolts and formwork | IFC drawing | survey record | Each Pour |  | HP | PE
2.00.2 | Setout Approval | On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer. |  | Onsite inspection | Each Pour |  | HP | PE
3.01 | Concrete Pour - Pad Footing
3.01.1 | Blinding Concrete Subgrade Inspection | A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer. | PS 19.5.1 & IFC drawing | Pre Pour Checksheet | Prior to Pour |  | HP | ENG
3.01.2 | Reinforcement Pre Pour Inspection | Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete. | PS 18.2 PS 19.9 PS 19 & IFC drawing | Pre pour | Each Pour |  | HP | ENG
3.01.3 | Pre-Pour Inspection | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area. | PS 18.2 PS 19.9 PS 19 & IFC drawing | Signed Pre-Pour | 48 Hours Notice Prior to Each Occurrence |  | HP | ENG
3.01.4 | Formwork | Formwork shall be inspected for shape, size and position and minimum covers achieved as per C3 of 310205972-STN-00-210-DR-ST-000002 | PS 19.15 & IFC drawing | Pre Pour Survey Records | Each Pour |  | HP | ENG
3.01.5 | Delivery Dockets | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | PS 18.2 PS 19.9 PS 19 & IFC drawing | Dockets | Each Pour |  | M | PE
3.01.6 | Compression Testing Insutu Concrete | The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting. | PS 18.2.5 PS 18.2.1 PS 18.2.2 & IFC drawing | Concrete Plant Test Results | One Set Daily consist of at least six field specimens |  | HP | PE
3.02 | Concrete Pour - Plinth
3.02.1 | Reinforcement Pre Pour Inspection | Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete. | PS 18.2 PS 19.9 PS 19 & IFC drawing | Pre Pour | Each Pour |  | R | PE
3.02.2 | Pre-Pour Inspection | Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area. | PS 18.2 PS 19.9 PS 19 & IFC drawing | Signed Pre-Pour | 48 Hours Notice Prior to Each Occurrence |  | HP | ENG
3.02.3 | Finish surface of th base | The joint surface shall be " type B" cold joint as defined in NZS3109 | IFC drawing | Site inspection | Each Pour |  | HP | ENG
3.02.4 | Formwork | Formwork shall be inspected for shape, size and position and minimum covers achieved as per C3 of 310205972-STN-00-210-DR-ST-000002 | PS 19.15 & IFC drawing | Pre Pour Survey Records | Each Pour |  | HP | ENG
3.02.5 | Delivery Dockets | The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size. | PS 18.2 PS 19.9 PS 19 & IFC drawing | Dockets | Each Pour |  | M | PE
3.02.6 | Compression Testing Insutu Concrete | The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting. | PS 18.2.5 PS 18.2.1 PS 18.2.2 & IFC drawing | Concrete Plant Test Results | One Set Daily consist of at least six field specimens |  | HP | PE
3.02.7 | Anchor bolts | All bolt, threaded rod, and stud connections shall be installed in accordance with AS/NZS 5131 Section 8.2. Tightening shall be to the snug tight condition as specified in Section 8.3 of AS/NZS 5131 after the mortar packing or grout has hardened. Where shown on the drawings, lock nuts shall be fitted, and snug tightened against the nut | PS 19.19.2& IFC drawing | Pre Pour | 48 Hours Notice Prior to Each Occurrence |  | HP | ENG |  |  | Supplied by others
3.03 | Post Pours
3.03.1 | Post Pour Inspection | Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings. | PS 18.2 PS 19 PS 19.15& IFC drawing | Post Pour | Each Pour |  | R | PE
3.03.2 | Concrete Curing | Concrete shall be cured for at least 7 days as per the drawings / specification. | PS 18.2 PS 19 PS 19.12& IFC drawing | Post Pour | At least 7 days after pour |  | R | PE
3.03.3 | Stripping | No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete. | PS 18.2 PS 19& IFC drawing | Post Pour | At least 3 days after pour |  | R | PE
3.03.4 | Protection of Completed Works | Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage. | PS 18.2 PS 19& IFC drawing | Post Pour | During the remainder of the construction period |  | R | PE
3.03.5 | Defective Concrete Finishes | Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer. | PS 18.2 PS 19 PS 19.13& IFC drawing | NCR | Prior to non Minor Repair |  | V | SE
3.03.6 | Asbuilt | All construction withing the tolerances |  |  | Survey report |  | HP | ENG