## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Sculpture Foundation - 305 - Rev B | itp |  |  |  |  | ITP - Sculpture Foundation - 305 - Rev B
section | 1.00 - Base Materials - Concrete
checkpoint | 1.00.1 - Concrete Plant
label | Acceptance / Conformance Criteria - All plants supplying concrete to the project shall hold and maintain a current quality Certificate of Audit in accordance with NZS 3104 throughout the duration of their supply of concrete for the contract. A copy of each plant’s current Certificate of Audit shall be submitted to the Engineer prior to their initial supply of concrete.
label | Standard / Specification - PS 19.7.1 & IFC drawing
label | Verifying Document - Audit Cert
label | Frequency - Prior to their initial supply of concrete
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.00.2 - Concrete - Blinding
label | Acceptance / Conformance Criteria - Blinding concrete shall have a minimum 28 days compression strength of 10 MPa with a maximum aggregate size of 20mm and comply with the requirements for Prescribed Mix concrete specified by NZS 3104.
label | Standard / Specification - PS 19.5.1, PS 19.7.10 & IFC drawing
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.00.3 - Concrete - Structural
label | Acceptance / Conformance Criteria - Structural concrete shall have a minimum 28 days compression strength of 30 Mpa with a maximum aggregate size of 20mm and comply with the requirements for Prescribed Mix concrete specified by NZS 3104.
label | Standard / Specification - PS 19.5.1, PS 19.7.11 & IFC drawings
label | Verifying Document - Approved Mix Design
label | Frequency - Submitted to and approved by the Engineer prior to concreting
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.00.4 - Reinforcement cover spacer blocks
label | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
label | Standard / Specification - PS 19.7.8 & IFC drawing
label | Verifying Document - Datasheets
label | Frequency - Prior to use
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
section | 1.01 - Base Materials - Reinforcement
checkpoint | 1.01.1 - Reinforcement bars
label | Acceptance / Conformance Criteria - All Reinforcement bars shall be of New Zealand origin unless otherwise accepted, grade 500 ductility class E and shall be manufactured by the micro-alloy process. Quenched and tempered reinforcement shall not be permitted.
label | Standard / Specification - PS 19.17.23 & IFC drawing
label | Verifying Document - Mill Certs
label | Frequency - Each Item
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 1.01.2 - Bar Schedule
label | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
label | Standard / Specification - PS19.17.20 & IFC drawing
label | Verifying Document - Bar Schedule
label | Frequency - At least 14 days before the start of placing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.3 - Reinforcing Mill Certs
label | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of ay work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
label | Standard / Specification - PS19.17.23 & IFC drawing
label | Verifying Document - Mill Certs
label | Frequency - At least one week before the programmed commencement of ay work incorporating these materials
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 2.00 - Setting out
checkpoint | 2.00.1 - Setting out
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the direction of the sculpture, anchor bolts and formwork
label | Standard / Specification - IFC drawing
label | Verifying Document - survey record
label | Frequency - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - PE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.00.2 - Setout Approval
label | Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer.
label | Verifying Document - Onsite inspection
label | Frequency - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - PE
holdpoint | AUTHORITY HOLDPOINT
section | 3.01 - Concrete Pour - Pad Footing
checkpoint | 3.01.1 - Blinding Concrete Subgrade Inspection
label | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
label | Standard / Specification - PS 19.5.1 & IFC drawing
label | Verifying Document - Pre Pour Checksheet
label | Frequency - Prior to Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.2 - Reinforcement Pre Pour Inspection
label | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19 & IFC drawing
label | Verifying Document - Pre pour
label | Frequency - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.3 - Pre-Pour Inspection
label | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19 & IFC drawing
label | Verifying Document - Signed Pre-Pour
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.4 - Formwork
label | Acceptance / Conformance Criteria - Formwork shall be inspected for shape, size and position and minimum covers achieved as per C3 of 310205972-STN-00-210-DR-ST-000002
label | Standard / Specification - PS 19.15 & IFC drawing
label | Verifying Document - Pre Pour, Survey Records
label | Frequency - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.5 - Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19 & IFC drawing
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 3.01.6 - Compression Testing Insutu Concrete
label | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2 & IFC drawing
label | Verifying Document - Concrete Plant Test Results
label | Frequency - One Set Daily consist of at least six field specimens
label | Verification Activity: Activity - HP
label | Verification Activity: By - PE
holdpoint | AUTHORITY HOLDPOINT
section | 3.02 - Concrete Pour - Plinth
checkpoint | 3.02.1 - Reinforcement Pre Pour Inspection
label | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19 & IFC drawing
label | Verifying Document - Pre Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 3.02.2 - Pre-Pour Inspection
label | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19 & IFC drawing
label | Verifying Document - Signed Pre-Pour
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.3 - Finish surface of th base
label | Acceptance / Conformance Criteria - The joint surface shall be " type B" cold joint as defined in NZS3109
label | Standard / Specification - IFC drawing
label | Verifying Document - Site inspection
label | Frequency - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.4 - Formwork
label | Acceptance / Conformance Criteria - Formwork shall be inspected for shape, size and position and minimum covers achieved as per C3 of 310205972-STN-00-210-DR-ST-000002
label | Standard / Specification - PS 19.15 & IFC drawing
label | Verifying Document - Pre Pour, Survey Records
label | Frequency - Each Pour
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.5 - Delivery Dockets
label | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
label | Standard / Specification - PS 18.2, PS 19.9, PS 19 & IFC drawing
label | Verifying Document - Dockets
label | Frequency - Each Pour
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
checkpoint | 3.02.6 - Compression Testing Insutu Concrete
label | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
label | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2 & IFC drawing
label | Verifying Document - Concrete Plant Test Results
label | Frequency - One Set Daily consist of at least six field specimens
label | Verification Activity: Activity - HP
label | Verification Activity: By - PE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.02.7 - Anchor bolts
label | Acceptance / Conformance Criteria - All bolt, threaded rod, and stud connections shall be installed in accordance with AS/NZS 5131 Section 8.2. Tightening shall be to the snug tight condition as specified in Section 8.3 of AS/NZS 5131 after the mortar packing or grout has hardened. Where shown on the drawings, lock nuts shall be fitted, and snug tightened against the nut
label | Standard / Specification - PS 19.19.2& IFC drawing
label | Verifying Document - Pre Pour
label | Frequency - 48 Hours Notice Prior to Each Occurrence
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 3.03 - Post Pours
checkpoint | 3.03.1 - Post Pour Inspection
label | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
label | Standard / Specification - PS 18.2, PS 19, PS 19.15& IFC drawing
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 3.03.2 - Concrete Curing
label | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
label | Standard / Specification - PS 18.2, PS 19, PS 19.12& IFC drawing
label | Verifying Document - Post Pour
label | Frequency - At least 7 days after pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 3.03.3 - Stripping
label | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
label | Standard / Specification - PS 18.2, PS 19& IFC drawing
label | Verifying Document - Post Pour
label | Frequency - At least 3 days after pour
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 3.03.4 - Protection of Completed Works
label | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
label | Standard / Specification - PS 18.2, PS 19& IFC drawing
label | Verifying Document - Post Pour
label | Frequency - During the remainder of the construction period
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 3.03.5 - Defective Concrete Finishes
label | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
label | Standard / Specification - PS 18.2, PS 19, PS 19.13& IFC drawing
label | Verifying Document - NCR
label | Frequency - Prior to non Minor Repair
label | Verification Activity: Activity - V
label | Verification Activity: By - SE
checkpoint | 3.03.6 - Asbuilt
label | Acceptance / Conformance Criteria - All construction withing the tolerances
label | Frequency - Survey report
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature