## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-015 - Drilling & Setting of Bonded Anchors | itp |  |  |  |  | ITP-015 - Drilling & Setting of Bonded Anchors
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for Correct Documentation
label | FREQUENCY: Prior to commencing works.
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the complete set of the correct and most current drawings.
label | REFERENCE DOCUMENTS: Project IFC Drawings and Drawings Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP*
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any works on site.
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, ECP, TMP, SWMS
label | REFERENCE DOCUMENTS: PMP, EMP, ECP, TMP, SWMS
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.3 - Service Identification & Excavation Permit
label | FREQUENCY: Prior to commencing any works on site.
label | ACCEPTANCE CRITERIA: All services are located, and the relevant service authorities have been consulted and permits obtained.
label | ○ Ensure an excavation permit is issued and all involved personnel are briefed about the services in the area before signing onto the permit.
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Training and Competency
label | FREQUENCY: Prior to commencing any works on site.
label | ACCEPTANCE CRITERIA: The bonded anchor installers, and all of its site personnel, shall be certified by the AEFAC, and shall provide evidence of this certification and of its competency acceptable to the Superintendent.
label | ○ All personnel, including supervisory personnel, who are required to install bonded anchors shall also be trained on-site by the supplier of the bonded anchor system in the specific installation requirements of the project before bonded anchor installation works commence.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Supervisor/ Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey & Set Out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure line and level of all bonded anchor holes is in accordance with design levels, survey files and drawings.
label | REFERENCE DOCUMENTS: Project IFC Drawings and Survey Data
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP*
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Trial Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall not proceed with the permanent bonded anchor installation works until the trial system installation have been carried out and the outcomes reviewed and approved by the Superintendent.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.11
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP
label | RESPONSIBILITY: Project Engineer/ Site Supervisor/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Drilling & Roughening of Anchor Holes
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: The Contractor shall not proceed with drilling or cutting holes into the concrete, installation or removal of bonded anchor works until the WMS and ITPs have been reviewed and approved by the Superintendent.
label | ○ Ensure hole depths and widths are drilled in accordance with Project IFC Drawings.
label | REFERENCE DOCUMENTS: Drawing No.578259 – 578276, VicRoads Standard Section 680, Clause 680.11
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP
label | RESPONSIBILITY: Project Engineer/ Site Supervisor/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Placement of Bonded Anchors
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure materials being used are in accordance with standard specifications and design drawings.
label | ○ Chemical adhesives shall be allowed to gain strength for the minimum time specified by the manufacturer’s installation instructions before torque is applied to bolts and load is applied to the bonded anchor system.
label | ○ Ensure bonded anchor casting register is populated including relevant details such as cast date, cast time, ambient temperature and time of casting, material batch no., and material batch expiry date.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 680
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed Inspection & Test Plan (ITP)
label | HP*
label | RESPONSIBILITY: Project Engineer/Site Supervisor/Supe rintendent
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Calibration of Testing Equipment
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: One week prior to testing the Contractor shall submit to the Superintendent calibration certificates conforming to the requirements of AS 2193 Grade B for the jack and pressure gauges or other force measuring devise to be used.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.09
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report
label | HP
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Test Method
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Details of the test method including load increments and duration of sustained loading shall be submitted to the Superintendent for review not later than one week prior to the testing.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.09
label | INSPECTION/TEST METHOD:
label | RECORD OF CONFORMITY:
label | HP
label | RESPONSIBILITY: Project Engineer/Site Supervisor/Supe rintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Testing of Bonded Anchors
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure a minimum of 20% of all bonded anchors subject to tensile loads, a combination of tensile and shear loads, or fatigue loads are tested and deemed to meet the minimum strength requirements.
label | ○ 50 kN
label | — The Contractor shall provide a test report to the Superintendent for review.
label | — If a bonded anchor fails either the ultimate load testing for suitability or the bonded anchor proof load test, the Contractor shall submit rectification proposals for review by the Superintendent prior to any further bonded anchor installation.
label | REFERENCE DOCUMENTS: VicRoads Standard Section 680, Clause 680.09
label | INSPECTION/TEST METHOD:
label | RECORD OF CONFORMITY:
label | HP
label | RESPONSIBILITY: Project Engineer/Site Supervisor/Supe rintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the SWA’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP