## Table 1
Chevaline Dexx Application of Chevaline Dexx to new plywood surfaces. Specification No: P3011 Date Prepared: May 2020
Project & Address: Certified Applicator: Building Contractor: Building Owner/Property Manager: 1. Statement of Intent (a) This checklist is to be completed by both the Equus Applicator and the Building Contractor, as a step by step record of compliance with both the Equus Specification provided for the contract, and the requirements of the Manufacturers for Warranty. (b) A copy of this checklist must be forwarded to the nearest Regional Office of Equus Industries Ltd. A Warranty will not be issued by Equus Industries Ltd. without a copy of this Checklist being filed. (a) A copy of this checklist should form part of the Contract Documentation filed with the Property Manager on job completion. 2. Areas Treated The areas to which Membrane is applied are detailed below, with reference to plans (where appropriate). 3. Sign Off We confirm that all applicable processes listed in Section 4 have been correctly completed and that sign-off on each stage has been made by a person with the authority to do so. For: (Signature) (Building Contractor) Date: / / (Name) For: (Signature) (Equus Applicator) Date: / / (Name)
4. Checklist And Method Statement * Denotes those processes which must be signed off by the Building Contractor as well.
No. | Process | Completed On | Building Contractor | Equus Contractor | Notes
1.* | Plywood shall be a minimum of 17mm C-D structural plywood for roof areas , and a minimum of 21mm for trafficable deck areas.
2.* | Timber framing correctly sized spaced and laid in accordance with NZS 3604.
3.* | Plywood correctly laid - tight butted and screw fixed in adhesive bead with correct fixing spacings for site condition.
4.* | Corrosion resistant fasteners used.
5.* | Treated timber fillets installed at all upstand transitions. All plywood/timber edges chamfered. Outlets in place.
6.* | Plywood surface accepted as satisfactory for Dexx installation by Equus Applicator.
7 | All exposed surfaces correctly primed with
(Nominate primer used)
8 | All Dexx detail strips of fibreglass in place at transitions, in doorways, and at wall upstands. Outlets in place.
9 | First full Dexx coat in place with one layer of 300gsm E-mat embedded and wetted out and fibreglass mat correctly laid with teased laps.
10 | Filling coat of Dexx laid and m fibreglass mat totally sealed off.
11 | Second coat of Dexx applied at correct spreading rate to fill and cover surface.
12 | Third coat of Dexx applied at correct spread- ing rate to fill and cover surface.
13.* | Dexx surface checked for adequate cover and absence of pinholes, blemishes and proud fibreglass. Dexx recoated where necessary to achieve required finish and base membrane complete.
14 | Dexx Wearcoat correctly applied where a non-slip finish has been specified Fine/ Medium/Coarse (delete if non-applicable)
15 | Final top coat(s) correctly applied using
(Nominate topcoat used)
16 | For surfaces to receive tile overlay—full 24 hour pond test carried out successfully.
17.* | Completed installation inspected and signed off.
Equus Industries Ltd PO Box 601 Blenheim Phone: 03 578 0214 Email: admin@equus.nz www.equus.nz
Quality Assurance