## SikaProof A+ 12
QUALITY ASSURANCE PROGRAMME Application of SikaProof A+ Waterproofing system
Prior to application commencing:
a) The Approved Contractor shall provide evidence to the Main Contractor that the applicator is currently approved by Sika (NZ) Ltd (the Manufacturer) for the application of SikaProof A+. b) The Approved Contractor shall provide a Quality Assurance Plan to the Main Contractor prior to commencing work. c) The Main Contractor's Site Engineer or representative shall determine that all surface preparation work has been completed to the agreed standards, before the product shall be applied. d) The Contractor's Site Engineer should ensure that all joints and penetrations to be sealed have been prepared to the required standard. Alternatively, in lieu of inspecting all joints and penetrations, the Contractor’s Site Engineer shall agree with the Approved Contractor the standard to be achieved by way of a sample area prepared by the Approved Contractor. During application, the Approved Contractor shall keep the following records: 1. One SikaProof A+ Application Record shall be completed for every day of application, including confirmation of:  The specific area of the project applied that day.  The amount and batch numbers of all SikaProof A+ system components used.  The weather conditions. (These shall be measured and recorded at least three times during the day and at any time that there is a significant change in the weather.) 2. The construction joints in the substrate shall be clearly designated on a copy of the plans. This designation is to be used when referring to these joints. This information shall be recorded on the form provided and be verified by the Main Contractor's Site Engineer or representative. The Approved Contractor shall maintain a register of the completed Application Records, which shall be available for inspection on request by the Engineer and shall supply a copy of these records to the Engineer and Sika (NZ) Ltd on completion of the works.
SIKAPROOF A+ APPLICATION PLAN
Project: | [7 empty] | Date:
Client: |  |  |  |  | Site Address:
Approved Contractor: |  |  |  |  | Operative:
Surface preparation required:
Method of preparing joints:
Method of preparing pipe penetrations:
Method of preparing pile caps:
Method of sealing corner details:
Method of sealing cross joints:
Method of sealing tie bolt holes:
Method of sealing any external joints:
Method of repairing any damage:
Proposed protection board:
SIKAPROOF A+ APPLICATION RECORD
Project: | [7 empty] | Date:
Client: |  |  |  |  | Site Address:
Surface prepared in accordance with specification:
Joints and penetrations prepared in accordance with specification:
All membrane overlaps inspected:
Area applied: |  |  | Identification:
Square metres: m²
SikaProof A+ 12, 2m x 20m: |  |  | Number of rolls used:
Batch Numbers:
SikaProof Tape A+: |  |  | Number of rolls used:
Batch Numbers:
SikaProof Sandwich Tape: |  |  | Number of rolls used:
Batch Numbers:
Heat-welded overlaps (applicable to horizontal field areas only) |  |  | Amount in metres:
Weather Conditions:
|  | Start of day |  | Mid-day |  | End of day |  |  | (Other) | (Other)
Time
Ambient Temperature (oC)
Sunny/Overcast/Rain
Approved Contractor: |  |  |  | Client:
Name: | Signature: |  |  | Name: |  |  | Signature:
Copies to: Sika (NZ) Ltd · Client · Approved Contractor