## Table 1
Below Ground Tanking for Installation Version 1.0
Date Started
Approved Applicator Company
Viking Licenced Installer
Project Name & Address
Main Contractor
Membrane Type
Add any notes or comments:
Purpose: This Checklist is to ensure correct Site substrate and installation meeting Viking Specification for Viking Under-slab, BG Tanking membrane system and Drainage / Protection board Checklist is to be completed by Viking Licensed Installer onsite.
Under-slab □ Site Conditions and Tidy Slab meet the requirements of BGT Site and Substrate Checklist by builder. □ Boxing/formwork has been installed to both sides providing membrane form and keeping it square. All exterior footings must have boxing/framework installed. Ensure no sharp objects can puncture the Viking Under-slab membrane. □ Check all Viking Under-slab laps are well sealed with a visible bitumen bleed. □ All corner transitions must have gussets applied after the Viking Under-slab has been installed. □ Before concrete pour. Advise Main-contractor to sign-off Under-slab installation as undamaged before and after the reinforcing is installed. □ Do not remove boxing/framework until four days after pour, minimum. Care must be taken during removal of formwork not to damage Tanking membrane. Slab to wall □ In-situ poured concrete walls will require 21 days to cure. Grout or plaster must be flush finished and cured by minimum two days before priming and installation of Tanking membrane □ Walls and footings are clean and free of sharp aggregate. Remove plaster/concrete that has dropped onto the footings and down the walls. Remove / clean off any laitance by Wire brush □ Bitumen Fillets (IMT603) at slab to wall transitions. Otherwise use Mortar Fillet □ Prime: All walls and footings must be primed with the correct primer for the Tanking system installed □ Protection / Drainage Board: A full inspection of the completed Tanking membrane must be made prior to installation of protection drainage board before backfilling □ Tanking membrane must be terminated correctly at the top edge 150mm above the finished soil/ground level. See Viking details for terminations □ A drain coil with a filter sock must be installed by the builder 200mm min. below the finished floor level on a gradient of 1-200
NOTES: • Ensure the applicator has adequate and safe room to work. • Banks must be battered or shored in accordance with NZ Health and Safety at Work Act 2015 • Refer to the Viking Technical Note Below Ground Tanking Methodology for best results and site preparation. Information regarding our products, specifications and warranties is available at www.vikingroofspec.co.nz If you have a query regarding this substrate specification, please call Viking on 0800 729 799
Auckland office Christchurch office Wellington office 80 Alexander Crescent, 2 Nazareth Avenue, 19 Pretoria St, T: 0800 729 799 info@vikingroofspec.co.nz Otara PO Box 14-541, Middleton, PO Box Lower Hutt 5010, F: 0800 729 788 www.vikingroofspec.co.nz Panmure, Auckland 9117, Tower Junction New Zealand 1741, New Zealand Christchurch 8149, A division of Viking Group Limited New Zealand