## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Allco - 20-YEAR SYSTEM WARRANTY CHECKLIST - For projects over 200m2 / Full Encapsulation | [5 empty] | Allco - 20-YEAR SYSTEM WARRANTY CHECKLIST - For projects over 200m2 / Full Encapsulation
section | Details
checkpoint | Project must be at least 200m2 of Allco supplied products.
checkpoint | Work must only be carried out by an Allco pre-approved applicator.
checkpoint | Applicator must notify Allco a minimum of 2 weeks prior to starting the project using Allco’s Applicator Portal.
checkpoint | Specification must be assessed by Allco prior to pre-install meeting with TA team representative.
checkpoint | Pre-install meeting with relevant parties including contractor, applicator, steel fixers, concreters and an Allco TA representative.
checkpoint | If site is hydrostatic, adequate water control measures must be in place during construction.
checkpoint | Full encapsulation; footings, under-slab & walls, including Waterstop RX in all cold joints.
checkpoint | Have followed specification or in the absence of a specification, followed detail provided by Allco.
checkpoint | Followed Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint | An adequate collection of photos showing pre, during & post installation details.
checkpoint | Photos must show all products used in installation. (Failure to do so will mean that the project will be ineligible for a System Warranty.)
checkpoint | All applicators on site are Allco Approved, trained and licensed applicators and are employees of the Approved Applicator at time of installation.
checkpoint | Allco TA must be notified at least 48 hours before any major steps throughout the project.
checkpoint | If walls are shotcrete then water control is required during and post construction (nonhydrostatic).
checkpoint | Complete and submit a Warranty Request form
checkpoint | Applicator will supply copies of the Workmanship Warranty*, Allco Warranty Document and appropriate Care and Maintenance Plan to the Building Owner.
label | *Under System Warranty, the Workmanship Warranty (also known as Certificate of Work) must be of at least 5 years in the case of commercial buildings and as required by consumer law applicable at the time for residential buildings.
checklist | Allco - 20-YEAR SYSTEM WARRANTY CHECKLIST - For projects under 200m2 | [5 empty] | Allco - 20-YEAR SYSTEM WARRANTY CHECKLIST - For projects under 200m2
section | Details
checkpoint | Must notify Allco of project a minimum of 7 days prior to starting the project using Allco’s Applicator Portal.
checkpoint | Must follow job specification, or in the absence of one, follow detail provided by Allco.
checkpoint | Must follow Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint | An adequate collection of photos showing pre, during & post installation details. Photos must clearly show all products used in installation.
checkpoint | All applicators on site are Allco Approved, trained and licensed applicators and are employees of the Approved Applicator at time of installation.
checkpoint | Complete and submit a Warranty Request Form.
checkpoint | Applicator will hand over Warranty Documents and Care and Maintenance Plan to the Building Owner.
checklist | Allco - 20-YEAR SYSTEM WARRANTY CHECKLIST - FOR SMALL LIFT PITS | [5 empty] | Allco - 20-YEAR SYSTEM WARRANTY CHECKLIST - FOR SMALL LIFT PITS
section | Details
checkpoint | Work must only be carried out by an Allco pre-approved applicator.
checkpoint | Applicator must notify Allco a minimum of 1 week prior to starting the project using Allco’s Applicator Portal.
checkpoint | Site presence by an Allco TA representative is at the discretion of Allco.
checkpoint | If site is hydrostatic, adequate water control measures must be in place during construction.
checkpoint | Full encapsulation; footings, under-slab & walls, including Waterstop RX in all cold joints.
checkpoint | Have followed specification or in the absence of a specification, followed detail provided by Allco.
checkpoint | Followed Allco QA requirements using either CONQA, Allco’s QA manual forms or a pre-approved 3rd party QA System.
checkpoint | An adequate collection of photos showing pre, during & post installation details.
checkpoint | Photos must show all products used in installation. (Failure to do so will mean that the project will be ineligible for a System Warranty.)
checkpoint | At least one Allco Approved, trained and licensed applicators who are employee of the Approved Applicator at time of installation.
checkpoint | Complete and submit a Warranty Request form via Allco Applicator Portal.
checkpoint | Applicator will supply copies of the Workmanship Warranty*, Allco Warranty Document and appropriate Care and Maintenance Plan to the Building Owner.
label | *Under System Warranty, the Workmanship Warranty (also known as Certificate of Work) must be of at least 5 years in the case of commercial buildings and as required by consumer law applicable at the time for residential buildings.
checklist | Allco - QA Pre-work & Warranty Checklist | [5 empty] | Allco - QA Pre-work & Warranty Checklist
section | SECTION A: PROJECT INFORMATION
checkpoint-no-status | Project Information
textbox | Project Name & Address
textbox | Main Contractor
textbox | Key contact of Main Contractor
textbox | Project Manager contact details
date | Estimated Start Date
textbox | Key Allco Contact
label | Allco Contact (if none): Adrian Crow adrian@allco.co.nz 0275 420 226 or Giovanni giovanni@allco.co.nz 0275420225 (Giovanni).
checkpoint | Is this warranty for full encapsulation?
checkpoint | Project notified to Allco before construction?
checkpoint | Attach photo evidence of notification sent to Allco with date stamp.
checkpoint | Involved Allco in the pre-installation meeting? Project notified to Allco before construction?
checkpoint | Attach photo evidence of Allco involvement in pre-installation meetings.
checkpoint | Photo evidence of Voltex, Sweltite and RX installation with QS checklists compiled together and sent to Allco?
checklist | Allco - QA Voltex Checklist | [5 empty] | Allco - QA Voltex Checklist
section | SECTION A: SITE & SUBSTRATE PREPARATION
checkpoint-no-status | Attach substrate photos with document along with QA questions completed below.
checkpoint | Appropriate site conditions for installation?
checkpoint | Appropriate water control in place?
date | Concrete Pour Date:
checkpoint | Appropriate substrate prepared for the installation of the membrane?
section | SECTION B: VOLTEX INSTALLATION - WALLS, UNDERSLAB AND FOOTINGS
checkpoint-no-status | Attach application photos with document (1 photo per 20m2) along with QA questions completed below.
textbox | Areas of installation (description, grid sections, etc):
checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up?
checkpoint | Are there 100 mm overlap between each sheet, and stagger sheets end at a minium of 300mm?
checkpoint | Laps are fixed tightly to hold the membrane in place?
checkpoint | Appropriate detailing done to external/internal corners
checkpoint | Appropriate detailing done to floor/wall joints
section | SECTION C: VOLTEX INSTALLATION – TRANSITIONS
checkpoint-no-status | Attach application photos with document (1 photo per 20m2) along with QA questions completed below.
textbox | Areas of installation (description, grid sections, etc):
textbox | Areas of other products Voltex is transitoning to:
checkpoint | Lap transitions detailed with appropriate overlap lengths and approved products (if nessesary)?
section | SECTION D: VOLTEX INSTALLATION – PENETRATIONS DETAILS
checkpoint-no-status | Attach application photos with document (1 photo per relevant penetration) along with QA questions completed below.
textbox | Areas of installation (description, grid sections, etc):
checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
checkpoint | Appropriate site conditions for installation?
checklist | Allco - QA Waterstop-RX Checklist | [5 empty] | Allco - QA Waterstop-RX Checklist
section | SECTION A: WATERSTOP-RX PRE-CHECK
checkpoint-no-status | Areas of installation
textbox | Areas of installation (description, grid sections, etc):
checkpoint | All parties aware of Waterstop-RX reqirements with exposure to climaic conditions?
checkpoint | Check to make sure substrate is acceptable?
checkpoint | Confirm apporpriate Waterstop-RX is going to be used in relation to concrete thickness?
checkpoint | Confirm minimum concrete coverage can be maintained where waterstop is applied
checkpoint | Ensure Waterstop RX will not be exposed to a wet enrioment for more than 24 hours
section | SECTION B: WATERSTOP-RX INSTALLATION
checkpoint-no-status | Attach application photos with document (1 photo per 20m2) along with QA questions completed below.
checkpoint | RX Waterstop has been mechanically fixed or adhered in position
checkpoint | RX Waterstop is in full contact to the concrete substrate where applied
checkpoint | RX Waterstop is detailed well on all corners?
checkpoint | All penetrations are detailed with RX Waterstop?
checklist | Ardex - Quality Assurance Checklist - Butynol | [5 empty] | Ardex - Quality Assurance Checklist - Butynol
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
textbox | Architect:
section | ARDEX CONTRACTOR
checkpoint-no-status | Details
textbox | Contractor Name:
button | Is the contractor an approved ARDEX applicator? | Yes,No
textbox | Installation Supervisor:
textbox | ARDEX Installer no.:
textbox | Installation Team:
date | Date Started:
date | Date Completed:
section | BUTYNOL CHECKLIST
checkpoint | Correct ARDEX material, colour, and thickness has been ordered
textbox | Product code:
textbox | Batch no:
textbox | Colour:
textbox | Thickness:
checkpoint | Work areas are clean and tidy and conforms with the relevant ARDEX Substrate Specification documents, completed seperately
checkpoint | Substrate moisture content acceptable?
checkpoint | Install underflashing tape in correct locations
checkpoint | Membrane laid over clean substrate using correct adhesive
checkpoint | Sheets well set out, parallel lines, laps running correct direction and to correct fall
checkpoint | Membrane lying flat on substrate with no bubbling
checkpoint | Laps primed and taped, with clean edges, no excess seam tape, glue overspray
checkpoint | Outlets detailed to correct ARDEX specification
checkpoint | Membrane termination completed to ARDEX details
checkpoint | Post-installation rubbish removed from work area
checkpoint | Conforms with ARDEX specifications
checkpoint | Any nonstandard details installed as per pre-approved specifications
label | Attach approved drawing
checkpoint | ARDEX membrane installation completed to specification
textbox | Ambient Temperature: |  |  | °C
textbox | Substrate Temperature: |  |  | °C
date | Installation Date:
textbox | Installation Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
textbox | Issues to note or to be raised during installation:
textbox | Remedial action required:
textbox | Note of damaged areas repaired: (include photographs)
section | FINAL SIGN OFF
checkpoint | FINAL SIGN OFF
holdpoint | Applicator / Main Contractor / Owner Signatures:
checklist | Ardex - Quality Assurance Checklist - Torch-Applied Membranes | [5 empty] | Ardex - Quality Assurance Checklist - Torch-Applied Membranes
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
textbox | Architect:
section | ARDEX CONTRACTOR
checkpoint-no-status | Details
textbox | Contractor Name:
button | Is the contractor an approved ARDEX applicator? | Yes,No
textbox | Installation Supervisor:
textbox | ARDEX Installer no.:
textbox | Installation Team:
date | Date Started:
date | Date Completed:
section | TORCH APPLIED CHECKLIST
checkpoint | Correct ARDEX material, colour, and thickness has been ordered
label | Base Sheet
textbox | Base Sheet - Code:
textbox | Base Sheet - Gauge
textbox | Base Sheet - Colour:
label | Intermediate Sheet
textbox | Intermediate Sheet - Code:
textbox | Intermediate Sheet - Gauge
textbox | Intermediate Sheet - Colour:
label | Top Sheet
textbox | Top Sheet - Code:
textbox | Top Sheet - Gauge
textbox | Top Sheet - Colour:
checkpoint | Work areas are clean and tidy and conforms with the relevant ARDEX Substrate Specification documents
checkpoint | Substrate checklist completed
checkpoint | Membrane laid over clean substrate using correct adhesive
checkpoint | Sheets well set out, parallel lines, laps running in correct direction and to fall. Membrane lying flat on substrate with no bubbling
checkpoint | Laps welded, with clean edges and good bleed
checkpoint | Additional layers offset 500mm to base layer
checkpoint | Outlets detailed to correct ARDEX specification
checkpoint | Membrane termination completed to ARDEX details
checkpoint | Post-installation rubbish removed from work area
checkpoint | Conforms with ARDEX Specification
checkpoint | Any nonstandard details installed as per pre-approved specifications Attach approved drawing
checkpoint | ARDEX membrane installation completed to specification
textbox | Ambient Temperature: |  |  | °C
textbox | Substrate Temperature: |  |  | °C
textbox | Product Code:
textbox | Batch Number:
date | Installation Date:
textbox | Installation Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
textbox | Issues to note or to be raised during installation:
textbox | Remedial action required:
textbox | Note of damaged areas repaired: (include photographs)
section | FINAL SIGN OFF
checkpoint | FINAL SIGN OFF
holdpoint | Applicator / Main Contractor / Owner Signatures:
checklist | Ardex - Quality Assurance Checklist - WeldTec External | [5 empty] | Ardex - Quality Assurance Checklist - WeldTec External
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
textbox | Architect:
section | ARDEX CONTRACTOR
checkpoint-no-status | Details
textbox | Contractor Name:
button | Is the contractor an approved ARDEX applicator? | Yes,No
textbox | Installation Supervisor:
textbox | ARDEX Installer no.:
textbox | Installation Team:
date | Date Started:
date | Date Completed:
section | WATERPROOFING CHECKLIST
checkpoint | Correct ARDEX material, colour, and thickness has been ordered
textbox | Product code:
textbox | Batch no:
textbox | Colour:
textbox | Thickness:
checkpoint | Work areas are clean and tidy and conforms with the relevant ARDEX Substrate Specification documents
label | Attach photograph - required for SystemARDEX Warranty
checkpoint | Substrate checklist completed
checkpoint | Membrane laid over clean substrate using correct adhesive
label | Attach photograph - required for SystemARDEX Warranty
checkpoint | Sheets well set out, parallel lines, laps running correct direction and to correct fall
label | Attach photograph - required for SystemARDEX Warranty
checkpoint | Membrane lying flat on substrate with no bubbling
checkpoint | Test membrane welds, destruction test
label | Attach photograph - required for SystemARDEX Warranty
checkpoint | Outlets detailed to correct ARDEX specification
label | Attach photograph - required for SystemARDEX Warranty
checkpoint | Membrane termination completed to ARDEX details
label | Attach photograph - required for SystemARDEX Warranty
checkpoint | Post-installation rubbish removed from work area
checkpoint | Conforms with ARDEX WeldTec Installation Documents
checkpoint | Any nonstandard details installed as per pre-approved specifications
label | Attach approved drawing - required for SystemARDEX Warranty
checkpoint | ARDEX membrane installation completed to specification
textbox | Ambient Temperature: |  |  | °C
textbox | Substrate Temperature: |  |  | °C
date | Installation Date:
textbox | Installation Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
textbox | Issues to note or to be raised during installation:
textbox | Remedial action required:
textbox | Note of damaged areas repaired: (include photographs)
section | FINAL SIGN OFF
checkpoint | FINAL SIGN OFF
holdpoint | Applicator / Main Contractor / Owner Signatures:
checklist | Ardex - Quality Assurance Checklist - WeldTec Undertile | [5 empty] | Ardex - Quality Assurance Checklist - WeldTec Undertile
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
textbox | Architect:
section | ARDEX CONTRACTOR
checkpoint-no-status | Details
textbox | ARDEX Applicator:
textbox | Number: ANZ
textbox | Contact Persons:
textbox | Job Size: |  |  | m2
textbox | Product Use:
textbox | Support/Substrate:
textbox | ARDEX Membranes:
section | WATERPROOFING CHECKLIST
checkpoint | ARDEX X 18 to be installed as per drawings
textbox | Ambient RH: |  |  | %
textbox | Substrate Moisture Content: |  |  | %
checkpoint | Apply ARDEX WPM 300 if above 75% RH as per NZ18884/3114
checkpoint | Install metal channel into screed where required as per plans using ARDEX CA 20 P to fix channel to substrate
checkpoint | ARDEX screeds A 38/A 48 to waste as per drawings. Refer to datasheets for product details
textbox | Ambient Temperature: |  |  | °C
textbox | Substrate Temperature: |  |  | °C
textbox | Product Code:
textbox | Batch Number:
textbox | Installation Date:
textbox | Installation Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
checkpoint | ARDEX WPM 750 to be installed as per drawings
textbox | Ambient RH: |  |  | %
textbox | Ambient Temperature: |  |  | °C
textbox | Substrate Temperature: |  |  | °C
textbox | Product Code:
textbox | Batch Number:
dropdown | Adhesive: | WA 98,AF 620
date | Installation Date:
textbox | Installation Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
checkpoint | Test ARDEX WPM 750 welds, destruction test
label | Include photograph
checkpoint | Glazing bar installed. Bedded with ARDEX CA 20 P
checkpoint | Membrane termination completed to ARDEX details
textbox | Ambient Temperature: |  |  | °C
textbox | Substrate Temperature: |  |  | °C
textbox | Product Code:
textbox | Batch Number:
date | Installation Date:
textbox | Installation Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
textbox | Include photographs of completed membrane installation showing terminations and glazing bar
textbox | Issues to note or to be raised during installation:
textbox | Remedial action required:
textbox | Note of damaged areas repaired: (include photographs)
section | TILING CHECKLIST
checkpoint | Ensure that the whole of the back of the tile is in good contact with the adhesive with no voids. Remove a tile periodically during installation to ensure correct coverage. Do not fix tiles over skinned adhesive.
label | ○ Notched trowel method
label | — Adhesive application to be as described in AS 3958.1, clause 5.6.2(a). 6mm x 6mm x 6mm, 10mm x 10mm x 10mm, 12mm x 12mm x 12mm. Use an appropriately notched trowel to achieve full coverage.
label | ○ Buttering method
label | — Adhesive application to be as described in AS 3958.1, Clause 5.6.2(c).
label | ○ Tiles in awkward locations
label | — The buttering method may be required, or fixing might be necessary to achieve full bedding, even though the notched trowel method is used generally.
checkpoint | Setting out, cutting and fitting of tiles to be as described in AS 3958.1, clauses 5.4.2 and 5.4.3. Set out tiling as shown on the drawings. Confirm bond and pattern before installing.
label | Provide even and correct falls to floor tiles where required, including falls to floor wastes. Ensure that a level finish is provided at wall lines. Where falls are not required ensure that the tiles are laid level.
checkpoint | Provide tile finish and joints, including tolerances, as described in AS 3958.1, clause 5.4.6. Joint widths to be suited to tile and to the manufacturer’s instructions.
checkpoint | Lift selection of tiles to check for transfer of adhesive and 90% coverage to back of tile.
label | Include photograph
checkpoint | Provide movement joints as described in AS 3958.1, clause 5.4.5 and AS 3740, clause 3.13.7.
label | ○ Depth: Movement joints to go right through the tile and bed to the background.
label | ○ Width: Minimum 6mm.
label | ○ Corner locations: In wall tiling at internal vertical corners; in floor tiling at walls, columns, nibs, hobs and similar.
label | ○ Interruptions: Around sanitary fixtures, around fixtures interrupting the tile surface; at junctions with joinery fixtures, including window and door frames and built in cupboards; at changes in substrate or background.
label | ○ Large areas: In floor tiling provide joints at not less than 4.5 metres spacing in both directions and 3.5 metres externally. In wall tiling provide vertical joints at not less than 3.5 metres spacing along the length of a wall. In wall tiling, provide horizontal joints at each story rise in the height of a wall. Over all existing expansion joints
textbox | Issues to note or to be raised during installation:
textbox | Remedial action required:
textbox | Note of damaged areas repaired: (include photographs)
section | FINAL SIGN OFF
checkpoint | FINAL SIGN OFF
holdpoint | Applicator / Main Contractor / Owner Signatures:
checklist | Ardex - Quality Assurance Checklist - Damp Proofing Membranes | [5 empty] | Ardex - Quality Assurance Checklist - Damp Proofing Membranes
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Unit:
textbox | Area being installed: |  |  | m2
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
section | WATERPROOFING CONTRACTOR
checkpoint-no-status | Details
textbox | Contractor Name:
button | Is the contractor an approved ARDEX applicator? | Yes,No
textbox | Installation Supervisor:
textbox | ARDEX Installer no.:
textbox | Installation Team:
date | Date Started:
date | Date Completed:
textbox | ARDEX INSTALLER NUMBER
section | CONSTRUCTION
checkpoint | CONSTRUCTION
dropdown | Horizonal Substrate: | New concrete,Old concrete,Sand BlindingCompacted Mud Slab,Other
textbox | Other:
dropdown | Wall Substrate: | New concrete,Old concrete,Concrete Block,Polyblock,Other
textbox | Other:
label | New Concrete Details:
label | Floors
date | Date concrete poured:
label | Walls
date | Date concrete poured:
section | SUBSTRATE PREPARATION
checkpoint | SUBSTRATE PREPARATION
button | Any surface contamination? | Yes,No
button | Curing compound? | Yes,No
dropdown | Surface Preparation: | Captive Shotblasting,Diamond Grinding,Concrete Planer,Concrete Scabbler,Other
textbox | Other:
dropdown | Substrate Cracks/Joints: | Filled,Slip Tape/Bandage,Injection,Other
textbox | Other
dropdown | Prefill/Substrate Repair Required: | Spalling,Substrate Deviation,None
button | Wall substrate installed in accordance with manufacturers instruction? | Yes,No
button | Surface Struck Smooth / Rendered? | Yes,No
button | Coving Installed? | Yes,No
textbox | Product Installed?
button | Edges Radiused Min 5mm and Underflashed? | Yes,No
button | Method of Termination? | Chase Flashing,Pressure Bar,Other
textbox | Other:
checkpoint | Surface Preparation Contractor:
textbox | Name:
textbox | Site Supervisor:
date | Date Completed:
holdpoint | Signed:
checkpoint | Surface Preparation: Contractor Acceptance
textbox | Installation Supervisor:
date | Date of Acceptance:
holdpoint | Signed:
checkpoint | Client Acceptance:
textbox | Name:
textbox | Site Supervisor:
date | Date Completed:
holdpoint | Signed:
section | SUBSTRATE RELATIVE HUMIDITY
checkpoint | SUBSTRATE RELATIVE HUMIDITY
bool | Substrate RH tested?
textbox | Substrate RH: |  |  | %
date | Date:
textbox | Time: |  |  | –– / –– / ––
dropdown | am / pm | am,pm
section | PRIMERS
checkpoint | PRIMERS
dropdown | Product Used: | ARDEX WPM 240 (solvent based),ARDEX WPM 247 (water based),Other
textbox | Coverage Rate Achieved:
button | Under Flashings? | Yes,No
dropdown | Installed to: | Horizontal / Vertical Corners,Penetrations
section | MEMBRANE INSTALLATION
checkpoint | ARDEX WPM 3000X - Under flashings installed correctly?
checkpoint | ARDEX WPM 3000X - Primer dry?
checkpoint | ARDEX WPM 3000X (Mainsheet Installed) - Laps rolled
checkpoint | ARDEX WPM 3000X (Mainsheet Installed) - Laps 60mm on sheet edge
checkpoint | ARDEX WPM 3000X (Mainsheet Installed) - 100mm on end
checkpoint | ARDEX WPM 3000X (Mainsheet Installed) - Membrane terminated correctly
checkpoint | ARDEX WPM 3000X (Mainsheet Installed) - ARDEX DRS 10 GC installed
checkpoint | ARDEX WPM 3000X (Mainsheet Installed) - Site left clean and tidy - free from offcuts
checkpoint | ARDEX WPM 5000HD - Under flashings installed correctly?
checkpoint | ARDEX WPM 5000HD - Primer dry?
checkpoint | ARDEX WPM 5000HD (Mainsheet Installed) - Laps rolled
checkpoint | ARDEX WPM 5000HD (Mainsheet Installed) - Laps 60mm on sheet edge
checkpoint | ARDEX WPM 5000HD (Mainsheet Installed) - 100mm on end
checkpoint | ARDEX WPM 5000HD (Mainsheet Installed) - Membrane terminated correctly
checkpoint | ARDEX WPM 5000HD (Mainsheet Installed) - ARDEX DRS 10 GC installed
checkpoint | ARDEX WPM 5000HD (Mainsheet Installed) - Site left clean and tidy - free from offcuts
section | FINAL JOB APPROVAL & ACCEPTANCE
checkpoint | FINAL JOB APPROVAL & ACCEPTANCE
holdpoint | ARDEX Waterproofing Installer / Main Contractor / Architect/Client/Client Representative / ARDEX Personnel (For system warranties only) Signatures:
checklist | Ardex - Quality Assurance Checklist - Waterproofing over Concrete Substrates | [5 empty] | Ardex - Quality Assurance Checklist - Waterproofing over Concrete Substrates
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
textbox | Architect:
section | ARDEX CONTRACTOR
checkpoint-no-status | Details
textbox | Contractor Name:
button | Is the contractor an approved ARDEX applicator? | Yes,No
textbox | Installation Supervisor:
textbox | ARDEX Installer no.:
textbox | Installation Team:
date | Date Started:
date | Date Completed:
section | SUBSTRATE CONSTRUCTION
checkpoint | SUBSTRATE CONSTRUCTION
dropdown | Substrate: | New Concrete,Old Concrete,Other
textbox | Other:
label | New Concrete Details:
date | Date concrete poured:
date | Date concrete protected from external elements:
section | SUBSTRATE PREPARATION
checkpoint | SUBSTRATE PREPARATION
dropdown | Surface Preparation: | Captive Shotblasting,Diamond Grinding,Concrete Planer,Concrete Scabbler,Other
textbox | Other:
button | Moisture testing carried out? (max 75%RH) | Yes,No
bool | RH of concrete
textbox | Method of testing:
checkpoint | Surface Preparation Contractor:
textbox | Name:
textbox | Site Supervisor:
date | Date Completed:
holdpoint | Signed:
checkpoint | Surface Preparation: Contractor Acceptance
textbox | Installation Supervisor:
date | Date of Acceptance:
holdpoint | Signed:
section | SUBSTRATE REPAIR
checkpoint | SUBSTRATE REPAIR
dropdown | Substrate Cracks/Joints: | Filled,Slip Tape/Bandage,Injection,Other
textbox | Other:
textbox | Substrate Cracks/Joints - Products used:
dropdown | Prefill/Substrate Repair Required: | Spalling,Substrate Deviation,None
textbox | Prefill/Substrate Repair - Products used:
dropdown | Prefill - Falls/Levels Required: | Falls to Drains,Fill falls to level,None
dropdown | Products used: | A 46,ARDITEX NA,A 38,A 48
checkpoint | Client Acceptance:
textbox | Name:
textbox | Site Supervisor:
date | Date Completed:
holdpoint | Signed:
section | WALL: COVE/UPSTAND DETAILS
checkpoint | Wall Details
dropdown | Wall Details: | Concrete,Insitu Concrete,Concrete Block,Insulated Panel,Plywood,Other
textbox | Other:
checkpoint | Coves/Upstands/Fillets
dropdown | Created from: | A 46,Timber (Not LOSP),Plastic Not required
section | DRAINS/SUMPS
checkpoint | Required?
checkpoint | Set at correct height? Correct type for membrane?
checkpoint | Falls to drains/sumps correct? If no: do falls need rectification?
textbox | Site Supervisor:
date | Date of Acceptance:
holdpoint | Signed:
checkpoint | System Drains/Sumps
textbox | Name of Nominated Outlets:
section | HEALTH, SAFETY & ENVIRONMENT
checkpoint | Trained staff identified
checkpoint | SDS on site
checkpoint | PPE on site
checkpoint | Electrical equipment tagged & current
checkpoint | Fire extinguishers
checkpoint | “Danger” tape
checkpoint | Spill Kits
checkpoint | Waste Disposal
checklist | Ardex - Quality Assurance Checklist - Waterproofing over Plywood Substrates | [5 empty] | Ardex - Quality Assurance Checklist - Waterproofing over Plywood Substrates
section | PROJECT DETAILS
checkpoint-no-status | Details
textbox | Project Name:
textbox | Site Address:
textbox | Location on Site:
textbox | Owner:
textbox | Builder:
textbox | Site Supervisor:
textbox | Architect:
section | ARDEX CONTRACTOR
checkpoint-no-status | Details
textbox | Contractor Name:
button | Is the contractor an approved ARDEX applicator? | Yes,No
textbox | Installation Supervisor:
textbox | ARDEX Installer no.:
textbox | Installation Team:
date | Date Started:
date | Date Completed:
section | SUBSTRATE CHECKLIST
checkpoint | Framing supports in accordance with plywood supplier’s recommendation. All plywood edges must also be supported. Do not use tounge and groove plywood. If thicker plywood is to be used, support spacing needs to meet NZBC and NZS3604, or engineer specific design.
textbox | How long has the plywood been exposed?
checkpoint | Minimum 17mm F8 CCA H3.2 treated structural plywood (not LOSP treated).
checkpoint | Minimum CD grade with the sanded C face upwards
checkpoint | Minimum required falls are met, Correct falls to outlets
checkpoint | Plywood laid with face grain at right angles to supports
checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges. ARDEX Bond breaker tape to be applied to all plywood sheet joints prior to membrane application.
checkpoint | All outlets and overflows fitted and rebated into the substrate
checkpoint | Plywood is screwed with 10g x 50mm SS counter sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint | Provide 20mm timber fillets (not required for Ultraply TPO or Weldtec Undertile)
checkpoint | Chamfer all external edges with a minimum radius of 5mm
checkpoint | Plywood is to be kept dry at all times during construction. Blow drying or torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisture content.
checkpoint | All drains and outlets are membrane compatible
checkpoint | Has the installer accepted the condition of the plywood?
checkpoint-no-status | NOTE
label | ○ DO NOT blow torch the plywood surface prior to membrane application.
label | ○ Failure to comply with substrate specification may affect the product warranty.
label | ○ Refer to the SystemARDEX Warranty for further details.
label | ○ Correct substrate installation is critical to the durability and performance of the membrane.
label | ○ All constructions should comply with the New Zealand Building Code. Contact your local council for further details.
label | ○ Communication between the Applicator and Construction Company will assist to ensure this specification is met.
label | ○ Information regarding our products, specifications and warranties is available at www.ardex.co.nz
label | ○ If you have a query regarding this substrate specification, please call 0800 2 ARDEX
textbox | Issues to note or to be raised during installation:
textbox | Remedial action required:
textbox | Note of damaged areas repaired: (attach photographs)
holdpoint | Applicator / Main Contractor / Owner Signatures:
checklist | Equus - Chevaline Dexx P3011 | [5 empty] | Equus - Chevaline Dexx P3011
section | Details
checkpoint-no-status | Details
textbox | Project & Address:
textbox | Certified Applicator:
textbox | Building Contractor:
textbox | Building Owner/Property Manager:
checkpoint | 1. - Plywood shall be a minimum of 17mm C-D structural plywood for roof areas , and a minimum of 21mm for trafficable deck areas.
holdpoint | Signed off by Building Contractor
checkpoint | 2. - Timber framing correctly sized spaced and laid in accordance with NZS 3604.
holdpoint | Signed off by Building Contractor
checkpoint | 3. - Plywood correctly laid - tight butted and screw fixed in adhesive bead with correct fixing spacings for site condition.
holdpoint | Signed off by Building Contractor
checkpoint | 4. - Corrosion resistant fasteners used.
holdpoint | Signed off by Building Contractor
checkpoint | 5. - Treated timber fillets installed at all upstand transitions. All plywood/timber edges chamfered. Outlets in place.
holdpoint | Signed off by Building Contractor
checkpoint | 6. - Plywood surface accepted as satisfactory for Dexx installation by Equus Applicator.
holdpoint | Signed off by Building Contractor
checkpoint | 7 - All exposed surfaces correctly primed with (Nominate primer used)
textbox | (Nominate primer used)
checkpoint | 8 - All Dexx detail strips of fibreglass in place at transitions, in doorways, and at wall upstands. Outlets in place.
checkpoint | 9 - First full Dexx coat in place with one layer of 300gsm E-mat embedded and wetted out and fibreglass mat correctly laid with teased laps.
checkpoint | 10 - Filling coat of Dexx laid and m fibreglass mat totally sealed off.
checkpoint | 11 - Second coat of Dexx applied at correct spreading rate to fill and cover surface.
checkpoint | 12 - Third coat of Dexx applied at correct spread- ing rate to fill and cover surface.
checkpoint | 13. - Dexx surface checked for adequate cover and absence of pinholes, blemishes and proud fibreglass. Dexx recoated where necessary to achieve required finish and base membrane complete.
holdpoint | Signed off by Building Contractor
checkpoint | 14 - Dexx Wearcoat correctly applied where a non-slip finish has been specified Fine/ Medium/Coarse (delete if non-applicable)
checkpoint | 15 - Final top coat(s) correctly applied using (Nominate topcoat used)
textbox | (Nominate topcoat used)
checkpoint | 16 - For surfaces to receive tile overlay—full 24 hour pond test carried out successfully.
checkpoint | 17. - Completed installation inspected and signed off.
holdpoint | Signed off by Building Contractor
checkpoint | We confirm that all applicable processes listed have been correctly completed and that sign-off on each stage has been made by a person with the authority to do so.
holdpoint | Building Contractor / Equus Applicator Signatures
checklist | Equus - Chevaline Dexx P3012 | [5 empty] | Equus - Chevaline Dexx P3012
section | Details
checkpoint-no-status | Details
textbox | Project & Address:
textbox | Certified Applicator:
textbox | Building Contractor:
textbox | Building Owner/Property Manager:
checkpoint | 1. - Concrete surface correctly laid to falls and cured 28 days.
holdpoint | Signed off by Building Contractor
checkpoint | 2. - Concrete surface finish U3 (NZS3114) achieved and free of laitance/detritus.
holdpoint | Signed off by Building Contractor
checkpoint | 3. - Plaster coves and/or treated timber fillets installed and concrete edges chamfered.
holdpoint | Signed off by Building Contractor
checkpoint | 4. - Concrete surface accepted as satisfactory for installation by Equus Applicator.
holdpoint | Signed off by Building Contractor
checkpoint | 5. - All exposed surfaces correctly primed with (Nominate primer used)
textbox | (Nominate primer used)
holdpoint | Signed off by Building Contractor
checkpoint | 6. - All Dexx detail strips of fiberglass in place at transitions, in doorways, and at wall upstands. Outlets in place.
holdpoint | Signed off by Building Contractor
checkpoint | 7 - First full Dexx coat in place with one layer of 300gsm E-mat embedded and wetted out and fiberglass mat correctly laid with teased laps.
checkpoint | 8 - Filling coat of Dexx laid and m fiberglass mat totally sealed off.
checkpoint | 9 - Second coat of Dexx applied at correct spreading rate to fill and cover surface.
checkpoint | 10 - Third coat of Dexx applied at correct spreading rate to fill and cover surface.
checkpoint | 11 - Dexx surface checked for adequate cover and absence of pinholes, blemishes and proud fiberglass. Dexx recoated where necessary to achieve required finish and base membrane complete.
checkpoint | 12 - Dexx Wearcoat correctly applied where a non-slip finish has been specified Fine/ Medium/Coarse (delete if non-applicable)
checkpoint | 13. - Final top coat(s) correctly applied using (Nominate topcoat used)
textbox | (Nominate topcoat used)
holdpoint | Signed off by Building Contractor
checkpoint | 14 - For surfaces to receive tile overlay—full 24 hour pond test carried out successfully.
checkpoint | 15 - Completed installation inspected and signed off.
checkpoint | We confirm that all applicable processes listed have been correctly completed and that sign-off on each stage has been made by a person with the authority to do so.
holdpoint | Building Contractor / Equus Applicator Signatures
checklist | Equus - Matacryl Carpark System - Application of Matacryl Carpark system to concrete surfaces | [5 empty] | Equus - Matacryl Carpark System - Application of Matacryl Carpark system to concrete surfaces
section | Details
checkpoint-no-status | Details
textbox | Project & Address:
textbox | Certified Applicator:
textbox | Building Contractor:
textbox | Building Owner/Property Manager:
checkpoint | 1. - All concrete surfaces shall be prepared with suitable methods to achieve a clean and porous surface. Check corresponding Specification for further instructions.
holdpoint | Signed off by Building Contractor
checkpoint | 2 - Surface imperfections shall be patched, using Ready Rep Mortar.
checkpoint | 3 - Shrinkage cracks in the concrete surface, which are 1 mm wide or greater, shall be ground out to a minimum 6 mm-wide by 12 mm deep. Pour Matacryl Thix into the crack, after the Matacryl 108 H Primer has been applied.
checkpoint | 4 - Cracks which are 3mm wide or greater, shall be ground out a min. 6 mm wide by 12 mm deep. Pour Matacryl Manual LM into the crack, after the Matacryl 108 H Primer has been applied.
checkpoint | 5 - Apply to concrete surfaces the suitably- catalysed Matacryl 108 H Primer to achieve a spreading rate of 0.3 - 0.5 kg per m2, depend- ing on surface porosity, to obtain a continuous resin film.
checkpoint | 6 - Apply to metal or plastic surfaces the suitably- catalysed Matacryl 107 CM Primer to achieve a spreading rate of 0.2 kg per m2 to obtain a continuous resin film. Allow to cure for 45 – 60 minutes, depending on site condi- tions and percentage of Catalyst added.
checkpoint | 7 - Apply suitably catalyzed Matacryl Thix mem- brane to coving turndowns and upstands.
checkpoint | 8 - Apply suitably-catalysed Matacryl Manual to achieve a spreading rate of 2 kg per m2. Apply this coat by notched trowel or squeegee and then spike roll.
checkpoint | 9 - Apply over turning and high-traffic areas a coat of Matacryl STC to achieve a spreading rate of 0.2 kg per m2. Allow to cure for 45 – 60 minutes, depending on site conditions and percentage of Catalyst added.
checkpoint | 10 - Mix Matacryl 215 WL with SNL Powder (1:1 ratio in weight) and catalyst as per mixing instructions. Pour onto deck, spread out to 2.5 kg/m2 and broadcast 0.7 – 1.2 mm quartz into the wet wear layer at approx. 3-4 kg per m2 (or to refusal)
label | Allow to cure 45 to 60 minutes. Once this coat has cured, remove surplus aggregate by brooming/vacuum . -
checkpoint | 11 - Apply suitably-catalysed Matacryl STC to achieve a spreading rate of 0.5 kg per m2. Allow to cure for 45 – 60 minutes, depending on site conditions and percentage of Catalyst added.
checkpoint | 12 - Apply a second coat of Matacryl STC to achieve a spreading rate of 0.3 kg per m2. Allow to cure for 45 – 60 minutes, depending on site conditions and percentage of Catalyst added.
checkpoint | 13 - Penetrations in the Matacryl System. Fixing holes filled with Tremco Dymonic FC (PU sealant) and bolts half screwed in, leaving the sealant to cure for at least 6 hours. After 6 hours, finish the screwing process. This will act as a gasket.
checkpoint | We confirm that all applicable processes listed have been correctly completed and that sign-off on each stage has been made by a person with the authority to do so.
holdpoint | Building Contractor / Equus Applicator Signatures
checklist | Nuralite - Bituthene Preprufe Check Lists - Bituthene Substrate Readiness/Post-installation Checklist | [5 empty] | Nuralite - Bituthene Preprufe Check Lists - Bituthene Substrate Readiness/Post-installation Checklist
section | Details
checkpoint-no-status | Details
textbox | Project name:
textbox | Form completed by:
textbox | Company:
textbox | Area ready:
textbox | Applicator:
section | Bituthene Substrate Readiness Checklist
checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content or 75 RH.
checkpoint | Concrete cavities and cracks filled with repair mortar (Nurapatch or equivalent), flushed off and cured
checkpoint | Concrete surface firm with any soft concrete or laitance removed.
checkpoint | Substrate clean, firm, and suitable condition for laying the Bituthene system.
checkpoint | All unwanted protrusions removed.
checkpoint | Bituthene LM fillets to all internal angles and upstands
checkpoint | Chamfer and radius all external corners to a minimum of 15mm
checkpoint | If terminating into a chase, pre-form the chase, ensure its straight and 20mm x 6mm
holdpoint | Signed:
section | Bituthene Post-installation Checklist
checkpoint | Concrete Substrate checklist completed before work commenced.
checkpoint | Any movement joints installed to approved specification/detail.
checkpoint | Bituthene LM fillets fitted to all internal junctions and corners chamfered at a 45°.
checkpoint | All corners and upstands incorporate reinforcing or under flashing
checkpoint | Side laps and end laps fully bonded and seamed.
checkpoint | All penetrations installed to specification.
checkpoint | Junction of the floor and wall membranes are installed to specification, fully bonded and watertight.
checkpoint | All details installed as per consented details (or Nuralite details if necessary.)
checkpoint | Any mechanical damage to membrane repaired to specification.
checkpoint | Membrane termination completed to approved detail.
checkpoint | Suitable drainage system installed below footing as per specification.
checkpoint | Membrane protection boards installed correctly.
checkpoint | Membrane fully adhered to substrate with no bridging, bubbling, or delaminating.
checkpoint | Overall installation free of wrinkles, bubbles, creases, and splits.
holdpoint | Signed:
checklist | Nuralite - Bituthene Preprufe Check Lists - Preprufe Substrate Readiness/Post-installation Checklist | [5 empty] | Nuralite - Bituthene Preprufe Check Lists - Preprufe Substrate Readiness/Post-installation Checklist
section | Details
checkpoint-no-status | Details
textbox | Project name:
textbox | Form completed by:
textbox | Company:
textbox | Area ready:
textbox | Applicator:
section | Preprufe Substrate Readiness Checklist
checkpoint | Waterstop installed to construction joint – refer to specification.
checkpoint | All unwanted protrusions removed.
checkpoint | Formwork is fully supported to prevent deflection.
checkpoint | Slab/footing substrate is site concrete or fully compacted hardfill with smooth blinding.
checkpoint | Rockwork: smooth with variations less than 12mm, any larger protrusions removed
checkpoint | Rockwork: large voids struck smooth and level with shotcrete, small voids patched with Nurapatch or similar.
checkpoint | All penetrations grouted for stability
holdpoint | Signed:
section | Preprufe Post-installation Checklist
checkpoint | Concrete Substrate checklist completed before work commenced.
checkpoint | Any movement joints installed to approved specification/detail.
checkpoint | All corners and upstands incorporate reinforcing or under flashing
checkpoint | Under-slab membrane extends beyond footing and protected until vertical membrane installed.
checkpoint | Side laps and end laps fully bonded and seamed.
checkpoint | Preprufe tape to end and cut laps
checkpoint | All penetrations installed to specification.
checkpoint | Junction of the floor and wall membranes are installed to specification, fully bonded and watertight.
checkpoint | All details installed as per consented details (or Nuralite details if necessary.)
checkpoint | Any mechanical damage to membrane repaired to specification.
checkpoint | Membrane termination completed to approved detail.
checkpoint | Suitable drainage system installed below footing as per specification.
checkpoint | Membrane protection boards installed correctly.
checkpoint | Membrane fully adhered to substrate with no bridging, bubbling, or delaminating.
checkpoint | Overall installation free of wrinkles, bubbles, creases, and splits.
holdpoint | Signed:
checklist | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - Safe2Torch Check List (Prior to base sheet Installation) | [5 empty] | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - Safe2Torch Check List (Prior to base sheet Installation)
section | Project Details
checkpoint-no-status | Details
textbox | Project name:
textbox | Form Completed by:
textbox | Company:
textbox | Area ready:
textbox | Applicator:
section | Decks and Insulation
checkpoint | Timber / Other combustible materials.
checkpoint | Metal deck (refurbishment) where old materials may accumulate in the troughs.
checkpoint | Insulation – unless specifically designed and tested for use with torch-o membranes.
section | Details
checkpoint | Expansion joints with voids and/or combustible fillers.
checkpoint | Bitumen or timber fillets.
checkpoint | Detail under all abutments to roof tiles, slates and roofing iron.
checkpoint | All timber substrates.
checkpoint | Change in level details with fixed timber or plastic facias and/or all soffits, gutters or restricted spaces.
checkpoint | Windowsills and frames, door sills, louvered vents, air ducts, intakes and outtakes.
checkpoint | Junctions to existing waterproofing with flammable insulation/deck materials. Vulnerable plastic curbs, domes, pipes and the like.
checkpoint | Working when in close proximity to potentially flammable coatings and shrinkwrap.
checkpoint | Cladding and roofing underlays.
checkpoint | Working in close proximity to stored chemicals, flammable liquids and explosives
section | Existing weathering components with concealed flammable materials. These include:
checkpoint | Timber, DPC or sarking membranes beneath fixed metal capping systems. Existing kitchen extraction plant coated in oils or fats.
checkpoint | Flammable wrapping to trunking/ducting/bitumen sheet rolls and roll inserts. Timber cladding.
checkpoint | Existing metal or plastic copings/capping’s.
checkpoint | Signed
holdpoint | Add Signature:
checklist | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - 3PT, 3PTM, 3PG and 3PC Concrete Substrate Readiness Checklist | [5 empty] | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - 3PT, 3PTM, 3PG and 3PC Concrete Substrate Readiness Checklist
section | Project Details
checkpoint-no-status | Details
textbox | Project name:
textbox | Form Completed by:
textbox | Company:
textbox | Area ready:
textbox | Applicator:
section | 3PT, 3PTM, 3PG and 3PC Concrete Substrate Readiness Checklist
checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content.
checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured.
checkpoint | Nuraswell installed to construction joints as per specification - located 50mm from rebar.
checkpoint | Concrete surface firm with any soft concrete or laitance removed. All protrusions removed. Surface free from foreign matter
checkpoint | All protrusions removed. Surface free from foreign matter
checkpoint | Mortar or bitumen fillets to all upstands and smooth 5mm radius to all external edges
checkpoint | If terminating into a chase, pre-form the chase and ensure it’s straight and 20mm deep.
checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite system.
checkpoint | Signed
holdpoint | Add Signature:
checklist | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - 3PT, 3PTM, 3PG and 3PC Installed Product Checklist on Concrete Substrate | [5 empty] | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - 3PT, 3PTM, 3PG and 3PC Installed Product Checklist on Concrete Substrate
section | Project Details
checkpoint-no-status | Details
textbox | Project name:
textbox | Form Completed by:
textbox | Company:
textbox | Area ready:
textbox | Applicator:
section | 3PT, 3PTM, 3PG and 3PC Installed Product Checklist on Concrete Substrate
checkpoint | Concrete Substrate checklist completed before work commenced.
checkpoint | Any movement joints installed to approved specification/detail.
checkpoint | Mortar/concrete fillets fitted to all internal junctions and corners chamfered at a 45°.
checkpoint | All corners and upstands incorporate reinforcing or under flashing
checkpoint | Under-slab membrane extends beyond footing and protected until vertical membrane installed.
checkpoint | Side laps 100mm and end laps 150mm fully torched and seamed. Bleed visible on all joints.
checkpoint | All penetrations installed to specification including under/over flashings.
checkpoint | Junction of the floor and wall membranes installed to specification fully bonded and watertight.
checkpoint | All non-standard details installed as per pre-approved specification (attach approved drawings).
checkpoint | Any mechanical damage to membrane repaired to specification. Membrane termination completed to approved detail.
checkpoint | Suitable drainage system installed below footing as per specification. Membrane protection boards installed correctly.
checkpoint | Membrane fully adhered to substrate with no bridging, bubbling, or delaminating.
checkpoint | Overall installation free of wrinkles, bubbles, creases and splits.
checkpoint | Signed
holdpoint | Add Signature:
checklist | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - 3PT, 3PTM, 3PG and 3PC Checklist for Project Signoff | [5 empty] | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - 3PT, 3PTM, 3PG and 3PC Checklist for Project Signoff
section | Project Details
checkpoint-no-status | Details
textbox | Project name:
textbox | Form Completed by:
textbox | Company:
textbox | Area ready:
textbox | Applicator:
section | Project Review
checkpoint | Under flashings installed to all corners and upstands
checkpoint | Drains & overflows installed to specification and watertight
checkpoint | Nuraflux adhesive used in correct quantities. Membrane fully adhered to substrate with no evidence of bubbles or lifting.
checkpoint | In two-layer system, Cap sheet and NURAPLY 3PT fully bonded together, no areas of delamination.
checkpoint | Cap sheet side laps 80mm and end laps 100mm fully welded and tidily seamed off.
checkpoint | No sign of overheating/excessive bitumen bleed from laps (over 2-3mm).
checkpoint | Cap sheet and base sheet laps offset satisfactorily. No three-layer lap build-ups
checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint | All penetration details completed to specification including under/over flashing
checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint | Any damage to cap sheet repaired to specification.
checkpoint-no-status | Remedial action required:
textbox | Remedial action required
checkpoint | Signed
holdpoint | Add Signature:
checklist | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - Nuraply 3PC Maintenance Programme | [5 empty] | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - Nuraply 3PC Maintenance Programme
section | Nuraply 3PC Maintenance Programme
checkpoint-no-status | Details
label | Nuraply 3PC Maintenance Programme
label | ○ To get the longest life from a car park it must be regularly inspected & maintained.
label | ○ When first installed there should be inspections each spring and autumn, to enable the effects of annual extremes of weather to be checked. Following that an annual program of roof inspection and cleaning should be established by the building owner as part of general building maintenance.
label | ○ Roofs exposed to high levels of pollution or in close proximity to trees might require more frequent inspection.
label | ○ Any inspection of a roof should include the interior of the building for signs of water penetration or condensation and for alterations, which may have affected the roof. Externally, abutting construction, which can affect the performance of the roof, should also be inspected.
label | Annual Inspections & Cleaning Inspections
label | ○ The inspection should concentrate on “high risk” areas such as drains and outlets equipment, as well as a general inspection of the entire car park. Inspections should also include the examination of the car park deck if possible from the underside for evidence of leaks, deteriorated decking, structural cracks or movement and other deficiencies. Parapets and edging should also be examined for evidence of cracking, deterioration and moisture infiltration.
label | Damage
label | ○ If damage is found on the roof surface it should be repaired immediately by an approved Nuralite Applicator. They will use NURAPLY 3PC - 3PM component products and special techniques to achieve neat, unobtrusive reinstatement of the NURAPLY 3PC - 3PM.
label | Cleaning
label | ○ Location, traffic level, effective drainage, and service use will dictate cleaning requirements. Sweeping clean followed by hose and broom washing of the NURAPLY 3PC car park is recommended, not waterblasting. If mould does appear it should be removed with a long-term mould killer such as Nuracide.
label | ○ You may do this yourself or talk to your applicator if you would like them to include you in an annual program of inspections & cleaning.
label | Five Year Authorised Service Checks
label | ○ To maintain your warranty, every five years you must have an Approved Applicator visit to inspect the roof and ensure it remains in good condition.
label | ○ The Applicator will thoroughly check the Car park for signs of damage, water ingress or potential problems.
checkpoint | Inspection
dropdown | # | 1,2,3,4
textbox | Applicator
holdpoint | Signed:
checklist | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - Wabo Maintenance Programme | [5 empty] | Nuralite - Nuraply 3P Covered Check Sheets and Maintenance Programme - Wabo Maintenance Programme
section | Wabo Maintenance Programme
checkpoint-no-status | Details
label | To get the longest life from a WABO joint it must be regularly inspected & maintained.
label | When first installed there should be inspections each spring and autumn, to enable the effects of annual extremes of weather to be checked by the approved WABO installer.
label | WABO joints are exposed to different levels of movement to the rest of the structure which may require more frequent inspection.
label | Any inspection of a WABO joint should include the interior of the building for signs of water penetration or condensation and for alterations, which may have affected the WABO joint. Externally, abutting construction, which can affect the performance of the WABO joint, should also be inspected.
label | Annual Inspections & Cleaning
label | ○ Inspections
label | — The inspection should concentrate on “high risk” areas, such as cover plates and fixings also a general inspection around the WABO joint. Inspections should also include the examination of the underside for evidence of leaks, if possible.
label | — Deteriorated structural cracks or movement and other defects in the surrounding area of the WABO joint should also be inspected to ensure the WABO joint will continue to work as intended.
label | ○ Damage
label | — If damage is found on the WABO joint it should be repaired immediately by an approved WABO Applicator. They will use WABO component products and special techniques to achieve neat, un-obtrusive reinstatement of the WABO joint
label | ○ Cleaning
label | — Location, traffic level, effective drainage, and service use will dictate cleaning requirements. Sweeping clean followed by hose and broom washing of the WABO joint is recommended, not water blasting.
label | ○ Annual Authorized Service Checks
label | — To maintain your warranty, every year you must have the Approved WABO installer who carried out the installation to inspect the WABO and ensure it remains in good condition.
label | — The installer will thoroughly check the WABO joint for signs of damage, water ingress or potential problems. As well, they will also check on the condition of the WABO joint.
label | — These checks are inexpensive and are the best way to ensure the WABO joints continues to work as intended and stays in top condition.
label | ○ Year one checks
label | — For the first year after installation two visual checks should be carried out by the installer.
label | — The first of these checks should be 3 months after original installation the second should be carried our 6 months after the first visual inspection.
section | First year’s visual inspection
checkpoint | Check all cover plates are inline
checkpoint | Check all cover plates fixings
checkpoint | Check for any signs of damage to cover plates.
checkpoint | Remove cover plate over drain out let and ensure the drain is free of any debris
checkpoint | Inspection
dropdown | # | 1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20
textbox | Applicator
holdpoint | Signed:
section | Inspection Sequence
checkpoint | All safety equipment and fences to be supplied and installed by installer to perimeter of the seismic joint.
checkpoint | Remove all cover plates to expose seismic joint.
checkpoint | Ensure the moisture barrier is free of any debris
checkpoint | Provide a continues flow of water from high point to low point
checkpoint | Check all centering bars for any damage replace if damaged.
checkpoint | Check the full circumference of the WABO create to ensure no damage
checkpoint | Check all cover plates for any damage
checkpoint | Replace all cover plates
checkpoint | Check all cover plate`s for alignment
checkpoint | Re fix all cover plate’s fixings
checklist | Nuralite - Nuraply TPO Check Sheets - NURATHERM PLYWOOD & STRANDBOARD SUBSTRATE READINESS CHECK SHEET FOR NURAPLY TPO (Prior to vapour barrier Installation) | [5 empty] | Nuralite - Nuraply TPO Check Sheets - NURATHERM PLYWOOD & STRANDBOARD SUBSTRATE READINESS CHECK SHEET FOR NURAPLY TPO (Prior to vapour barrier Installation)
section | NURATHERM PLYWOOD & STRANDBOARD SUBSTRATE READINESS CHECK SHEET FOR NURAPLY TPO (Prior to vapour barrier Installation)
checkpoint-no-status | Details
textbox | Project Name:
textbox | Form Completed by: Company:
textbox | Area ready:
textbox | Applicator
checkpoint | Structure complies with the New Zealand Building Code and plywood complies with AS/NZ 2269
checkpoint | H3.2 CCA treated plywood sheets 17mm thick for roofs, 21mm thick for decks.
checkpoint | Plywood sheets supported at 400mm centred rafters and nogs for roofs and decks.
checkpoint | Strandboard laid as per plywood with rafters and nogs at 400mm centres. Unless otherwise specified.
checkpoint | Sheets stagger lay (fully offset) with falls as per plan.
checkpoint | Smm clearances from all abutments, Smm radius to all exposed edges.
checkpoint | All sheet edges supported, fixed 150mm on edges and 200mm through girth, edges butt-jointed with no gaps except at abutments.
checkpoint | Sheets fixed by gluing and Stainless Steel countersunk screw fixing.
checkpoint | Mitres neatly formed.
checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface.
checkpoint | Sharp edges and lips removed and cavities filleted. All joints flush.
checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
checkpoint | Substrate dry, (less than 20% moisture), clean, firm and suitable condition for laying.
holdpoint | Signed by main contractor (Builder)
checklist | Nuralite - Nuraply TPO Check Sheets - METAL TRAY SUBSTRATE READINESS CHECK SHEET (Prior to vapour barrier Installation) | [5 empty] | Nuralite - Nuraply TPO Check Sheets - METAL TRAY SUBSTRATE READINESS CHECK SHEET (Prior to vapour barrier Installation)
section | METAL TRAY SUBSTRATE READINESS CHECK SHEET (Prior to vapour barrier Installation)
checkpoint-no-status | Details
textbox | Project Name:
textbox | Form Completed by: Company:
textbox | Area ready:
textbox | Applicator
checkpoint | Diamond sheet installed with the narrow trough down
checkpoint | Fastening the metal tray sheet in the pan with 6 fasteners per purlin support.
checkpoint | If using timber supports, installed bitumen tape between timber and metal tray.
checkpoint | Confirm the substrate slope complies with specification.
checkpoint | Rainwater outlets and overflow recesses formed to fit outlets.
checkpoint | Ensure only approved accessories to be used for drainage.
checkpoint | Review penetrations to minimise number and complexity.
checkpoint | All edges of insulation supported by timber to prevent damage.
checkpoint | Plinths formed for any exterior ventilation, fixtures or similar.
checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
holdpoint | Signed by Applicator
checklist | Nuralite - Nuraply TPO Check Sheets - ENERTHERM SUBSTRATE READINESS CHECK SHEET (Prior to Enertherm Installation) | [5 empty] | Nuralite - Nuraply TPO Check Sheets - ENERTHERM SUBSTRATE READINESS CHECK SHEET (Prior to Enertherm Installation)
section | ENERTHERM SUBSTRATE READINESS CHECK SHEET (Prior to Enertherm Installation)
checkpoint-no-status | Details
textbox | Project Name:
textbox | Form Completed by: Company:
textbox | Area ready:
textbox | Applicator
checkpoint | Structure complies to the New Zealand Building Code
checkpoint | Confirm the substrate slope complies with plans.
checkpoint | Rainwater outlets and overflow recesses formed to fit outlets rebated into the surface.
checkpoint | Ensure only approved accessories to be used for drainage and venting.
checkpoint | Review penetrations to minimize number and complexity.
checkpoint | Ensure the NURAPLY ALU vapour barrier is installed correctly and that any damage has been repaired.
checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
holdpoint | Signed by Applicator
checklist | Nuralite - Nuraply TPO Check Sheets - ENERTHERM SUBSTRATE READINESS CHECK SHEET (Prior to Membrane Installation) | [5 empty] | Nuralite - Nuraply TPO Check Sheets - ENERTHERM SUBSTRATE READINESS CHECK SHEET (Prior to Membrane Installation)
section | ENERTHERM SUBSTRATE READINESS CHECK SHEET (Prior to Membrane Installation)
checkpoint-no-status | Details
textbox | Project Name:
textbox | Form Completed by: Company:
textbox | Area ready:
textbox | Applicator
checkpoint | Sheets stagger lay (fully offset).
checkpoint | Any gaps in the insulation filled to prevent thermal bridging.
checkpoint | Material fastened with the correct quantity of IKofix Thermal Break Flanges and Fixing Screws (as per the Technical Note document up to 3.33 kPa ULS).
checkpoint | Edges of insulation supported by metal sheet ridges
checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
holdpoint | Signed by Applicator
checklist | Nuralite - Nuraply TPO Check Sheets - CONCRETE SUBSTRATE READINESS CHECK SHEET (Prior to vapour barrier Installation) | [5 empty] | Nuralite - Nuraply TPO Check Sheets - CONCRETE SUBSTRATE READINESS CHECK SHEET (Prior to vapour barrier Installation)
section | CONCRETE SUBSTRATE READINESS CHECK SHEET (Prior to vapour barrier Installation)
checkpoint-no-status | Details
textbox | Project Name:
textbox | Form Completed by: Company:
textbox | Area ready:
textbox | Applicator
checkpoint | Structure complies to the New Zealand Building Code and concrete complies with NZS 3101 (2006)
checkpoint | Concrete cured with curing membranes removed. Concrete substrate contains less than 5% moisture content.
checkpoint | Surface smooth and clean with falls as per plan.
checkpoint | Cavities and cracks filled with repair mortar, flushed off and cured.
checkpoint | Concrete surface firm with any soft concrete or laitance removed.
checkpoint | Ponding areas removed.
checkpoint | Roof drains and overflow recesses formed to fit rebated outlets.
checkpoint | If terminating into a chase, pre-form the chase and ensure it's straight and 20mm deep.
checkpoint | Plinths formed for any exterior ventilation, solar panels or fixtures.
checkpoint | Construction joints incorporated in slab as per designers specification.
checkpoint | Substrate clean, firm and suitable condition for laying the Nuralite systems.
holdpoint | Signed by main contractor (builder)
checklist | Nuralite - Nuraply TPO Check Sheets - CHECKLIST FOR PROJECT SIGNOFF | [5 empty] | Nuralite - Nuraply TPO Check Sheets - CHECKLIST FOR PROJECT SIGNOFF
section | Project Review
checkpoint | Substrate readiness form completed
checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint | Adhesive used in correct quantities. Membrane fully adhered to substrate with no evidence of bubbles or lifting.
checkpoint | Correct quantity of fastenings used if Mechanically fastened.
checkpoint | All laps fully welded and tidily appearance.
checkpoint | Overall installation free of wrinkles, creases and splits
checkpoint | All penetration details completed to specification including under/overflashing
checkpoint | All non standard details installed as per pre-approved specifications (attach approved drawing)
checkpoint | Any damage to membrane repaired to specification.
checkpoint | Gutters correctly and neatly installed, particularly the internal corners
checkpoint | Roof drains & overflows installed to specification and watertight
checkpoint-no-status | Remedial action required:
textbox | Remedial action required
checkpoint | Signed
holdpoint | Add Signature:
checklist | Nuralite - Nuraply TPO Check Sheets - NURAPLY MAINTENANCE PROGRAMME | [5 empty] | Nuralite - Nuraply TPO Check Sheets - NURAPLY MAINTENANCE PROGRAMME
section | NURAPLY MAINTENANCE PROGRAMME
checkpoint-no-status | Details
label | To get the longest life from a roof it must be regularly inspected & maintained.
label | When first installed the building owner should arrange inspections each spring and autumn, to enable the effects of annual extremes of weather to be checked. Following that an annual program of roof inspection and cleaning should be established by the building owner as part of general building maintenance.
label | Roofs exposed to high levels of pollution or in close proximity to trees might require more frequent inspection.
label | Any inspection of a roof should include the interior of the building for signs of water penetration or condensation and for alterations, which may have affected the roof. Externally, abutting construction, which can affect the performance of the roof, should also be inspected.
label | Annual Inspections & Cleaning
label | ○ Inspections
label | — The inspection should concentrate on "high risk" areas such as hatches, drains and around all roof top equipment, as well as a general inspection of the entire roof. Inspections should also include the examination of the roof deck if possible from the underside for evidence of leaks, deteriorated decking, structural cracks or movement and other deficiencies. Parapets and edging should also be examined for evidence of cracking, deterioration and moisture infiltration.
label | ○ Damage
label | — If damage is found on the roof surface it should be repaired immediately by an approved Nuralite Applicator.
label | — They will use NURAPLY TPO component products and special techniques to achieve neat, unobtrusive reinstatement of the NURAPLY TPO.
label | ○ Cleaning
label | — Location, traffic level, effective drainage, and service use will dictate cleaning requirements. Sweeping clean followed by hose and broom washing of the NURAPLY TPO roof is recommended, not water blasting. If mould does appear it should be removed with a long-term mould killer such as Nuracide.
label | — The building owner may do this them self or engage an approved applicator if they prefer.
label | ○ Five Year Authorised Service Checks
label | — To maintain the material defects warranty, every five years the owner must engage an Approved Applicator to inspect the roof and ensure it remains in good condition. Failure to maintain the roof system will void the warranty.
label | — The Applicator must thoroughly check the roof for signs of damage, water ingress or potential problems.
checkpoint | Inspection
dropdown | # | 1,2,3,4
textbox | Applicator
holdpoint | Signed:
section | 1) Surface:
checkpoint | a) accumulation of silt or vegetation;
checkpoint | b) areas of ponding.
section | 2) Membrane:
checkpoint | a) blistering, ripples, rucking, detachment;
checkpoint | b) cracks, splits, tears, punctures, indentations;
checkpoint | c) pimpling, pitting, crocodiling;
checkpoint | d) pulled, unbonded laps;
checkpoint | e) softening of surface.
section | 3) Substrate:
checkpoint | a) depressions in surface;
checkpoint | b) lack of support/soft support to membrane.
section | 4) Rainwater outlets:
checkpoint | a) blocked;
checkpoint | b) not bonded to membrane (if bonded type);
checkpoint | c) clamping ring loose (if clamped type).
section | 5) Upstands:
checkpoint | a) damaged/detached flashings;
checkpoint | b) sagging membrane;
checkpoint | c) splits, cracks, tears;
checkpoint | d) membrane unsupported at junction;
checkpoint | e) unbonded laps;
checkpoint | f) blistering.
section | 6) Eaves/verge:
checkpoint | a) unbonded or peeling membrane;
checkpoint | b) cracking/splitting or strain in membrane;
checkpoint | c) displacement or signs of movement of edge trim.
section | 7) Movement joints, upstand type:
checkpoint | a) unsealed capping joints;
checkpoint | b) dislodged flashing/capping;
section | 8) Abutting construction:
checkpoint | a) parapet copings cracked, loose, unsealed;
checkpoint | b) damaged damp-proof course, lack of continuity in damp-proofing;
checkpoint | c) open joints, cracking in construction;
checkpoint | d) loose/missing pointing.
section | 9) Roof fixtures and penetrations:
checkpoint | a) damaged/missing flashings;
checkpoint | b) balustrade/vent pipe, loose or missing flashing or collar;
checkpoint | c) plant plinth damaged/missing flashing;
checkpoint | d) lightning conductor tape, fixing loose