## General
SECTION 1 – GENERAL DETAILS
Project Name: | Stoke Stream Erosion Mitigation |  |  |  |  | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 553805.100. |  |  |  |  | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Transpower |  |  |  |  | B | Report by Breach | CM | Construction Manager | Wayne Oldfield
Contract Number: | SUP-16780 |  |  |  |  | C | Check | CR | Cust. Representative
Area/ Sub-System: |  |  | Lot ID Number: |  |  | D | Dimension Inspection | IP | Inspection Personnel
[6 empty] | E | Examine | MC | Material Controller
ITP Number: | 1 |  | Version: | 1 |  | H | Hold Point | OP | Operations Manager
ITP Description: | Stoke Stream Erosion Mitigation |  |  |  |  | I | Inspection | PM | Project Manager | Mark Frost
Discipline: | Civil Construction |  |  |  |  | M | Monitor on Random Basis | SE | Site Engineer | Louis Fleming
Specification: | CGW Drawings: 220518, Sheet C-00-01 |  |  |  |  | O | Operation | QE | Quality Engineer
[6 empty] | R | Review | QM | QA Manager
Drawings: | CGW Drawings: 220518 |  |  |  |  | S | Subcontractor | SP | Supervisor | Mike Kennedy
[6 empty] | V | Visual Verification | ST | Superintendent
Prepared By: | Rebecca Squires |  | Date: | 2024-10-17 |  | W | Witness Point | SV | Surveyor
Quality Specified: | [7 empty] | WS | Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  | Name: |  |  | Signature: |  |  |  |  | Date:
Downer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  | Signature: |  |  |  |  | Date:

## Inspection & Test Plan
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection
[7 empty] | Key | By (Role Key)
1 | Pre Construction
1.1 | Site Set Up | Enviornmental controls implemented as per DESCP | DESCP | Checksheet | Pre-Construction | Visual, hold point |  | Downer
1.2 | Work Boundaries Confirmed | Engineer to confirm the boundaries of work. | Engineer Approval | Email Confirmation from engineer | Pre-Construction | Inspection, Hold point |  | Engineer
1.3 | Vegetation Clearance | Removal of debris and vegetation using cut and stack method. Cleared with hand tools followed by an excavator. | Area cleared of vegetation and approval from ecologist | Email confirmation from Ecologist | Pre-Construction | Operation, Hold point |  | Ecologist
1.4 | Services Located | Service Locations complete and stream banks walked, stormwater pipes cleared around and identified with bright wooden peg. | Services identified, approved controls are in place. Transpower sent info and approves continuation. | Service Location Report | Pre-Construction | Inspection, Hold point |  | Downer, Transpower
1.5 | Wingwall Installed | Sandbags laid on filter fabric in stream. Platform level and wingwall structure lowered into stream and braced with steel piles into stream bed. Sandbags wrapped in filter fabric at wings of wall and bypass pipe installed through sandbags. | Max water storage height 1m | Photos | Pre-Construction | Inspection, Hold point |  | Downer
1.6 | Fish Relocation | All fish relocated. | Confirmation from Project Ecologist. | Email confirmation from Project Ecologist. | Pre-Construction | Inspection, Hold point |  | Ecologist
2 | Stream Bed Excavations & Rock Channel
2.1 | Material Approval | Rock and Geotextiles as specified | D50/700: 100% < 1000mm 50% < 700mm 15% < 300mm Geotextile: Class E | Quarry Certs / Photos | Prior to placement of Rip Rap | Visual |  | Downer
2.2 | Stream Bed Excavations | Stream bed excavated to typical section profiles. Cut matieral transferred to laydown area. | As per drawings C-03-01, C-03-02 | Email Confirmation from engineer | Every 50m of chainage | Inspection, Hold point |  | Engineer
2.3 | Subgrade Inspection | Scala penetrometer test to assess subgrade strength | Engineer to assess subgrade strength | Email Confirmation from engineer | Every 50m of chainage | Inspection, Hold point |  | Engineer
2.4 | Geotextile | Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications | As per drawings C-03-01, C-03-02 | Photos | Every 50m of cahinage | Visual |  | Downer
2.5 | Stream Base Rock Channel | Rocks carried and placed in stream base as per new design profile. | As per drawings C-03-01, C-03-02 | Email Confirmation from engineer | Every 50m of chainage | Inspection, Hold point |  | Engineer
3 | Gabion Construction - CH85-140 True Right Hand Side
3.1 | Material Approval | Gabion basket, rock, and rip rap as specified | Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK | Photos / Material Certs | Prior to Gabion Construction | Visual |  | Downer
3.2 | Cut Face Inspection | Inspect Cut face | As per drawing C-03-01 | Email Confirmation from engineer | Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face. | Inspection, Hold point |  | Engineer
3.3 | Subgrade Inspection | Scala penetrometer test to assess subgrade strength | Engineer to assess subgrade strength | Email Confirmation from engineer | Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth. | Inspection, Hold point |  | Engineer
3.4 | Concrete Foundation | Insitu poured gabion wall concrete foundation | Concrete mix as per design. 200mm thick | Concrete dockets | Prior to first layer of gabion basket installation | Inspection, Hold point |  | Downer, Engineer
3.5 | Gabion Base Row Alignments | Gabion position marked out, inspection to confirm in correct location as per the specifications | Positioned so base extends minimum 0.5m each side of basket | Photos / Asbuilts | Prior to backfill of first gabion layer | Visual verification |  | Downer
3.6 | Drianage Inspection | ID04 DPM and drainage coil behind retaining wall | DN100 NOVACOIL placed at base of batter and heel of benches | Approval from Building Inspector | Prior to backfill of first gabion layer | Inspection, Hold point |  | NCC Building Inspector
3.7 | Gabion Layer Inspections | Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications | Max 4 high gabion baskets on true right bank each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket. | Photos / Asbuilts | Each gabion layer, prior to backfill | Visual |  | Engineer
3.8 | Gabion Row Backfill | NDM testing on backfill at 200mm lifts | 200mm lifts, 95% MDD | NDM Report | Every "x" Lineal m, Each 200mm life, Each Gabion Layer | Inspection, Hold point |  | Downer
3.9 | Rock Armouring | Placement of riprap | Directed by Engineer on site | Email Confirmation from engineer | After completion of Gabion Wall | Visual |  | Engineer
3.1 | Completion of Gabion Wall | Engineer to inspect completed gabion wall | Gabion wall constructed as per drawings | Email from Engineer as confirmation of Approval | After completion of Gabion Wall | Inspection, Hold point |  | Engineer
4 | Gabion Construction - CH95 - CH125 True Left Hand Side
4.1 | Material Approval | Gabion basket, rock, and rip rap as specified | Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK | Photos / Material Certs | Prior to Gabion Construction | Visual |  | Downer
4.2 | Cut Face Inspection | Inspect Cut face | As per drawing C-03-01 | Email Confirmation from engineer | Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face. | Inspection, Hold point |  | Engineer
4.3 | Subgrade Inspection | Scala penetrometer test to assess subgrade strength | Engineer to assess subgrade strength | Email Confirmation from engineer | Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth. | Inspection, Hold point |  | Engineer
4.4 | AP65 Compaction Testing | NDM Testing done on AP65 base. CONCRETE? | 95% MDD approved by Engineer | NDM Report | Prior to first layer of gabion basket installation | Inspection, Hold point |  | Downer, Engineer
4.5 | Gabion Base Row Alignments | Gabion position marked out, inspection to confirm in correct location as per the specifications | Bottom two layers to be two units wide with every third unit laid perpendicular. Positioned so base extends minimum 0.5m each side of basket. | Photos / Asbuilts | Prior to backfill of first gabion layer | Visual verification |  | Downer
4.6 | Drianage Inspection | ID04 DPM and drainage coil behind retaining wall | DN100 NOVACOIL placed at base of batter and heel of benches | Approval from Building Inspector | Prior to backfill of first gabion layer | Inspection, Hold point |  | NCC Building Inspector
4.7 | Gabion Layer Inspections | Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications | Each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket. | Photos / Asbuilts | Each gabion layer, prior to backfill | Visual |  | Engineer
4.8 | Gabion Row Backfill | NDM testing on backfill at 200mm lifts | 200mm lifts, 95% MDD | NDM Report | Every "x" Lineal m, Each 200mm life, Each Gabion Layer | Inspection, Hold point |  | Downer
4.9 | Rock Armouring | Placement of riprap | Directed by Engineer on site | Email Confirmation from engineer | After completion of Gabion Wall | Visual |  | Engineer
4.1 | Completion of Gabion Wall | Engineer to inspect completed gabion wall | Gabion wall constructed as per drawings | Email from Engineer as confirmation of Approval | After completion of Gabion Wall | Inspection, Hold point |  | Engineer
4.11 | II06 Final - Residential | Residential final inspection. When all building consent requirements are complete. | Gabion Wall constructed as per design | II06 Report | After completion of Gabion Wall | Inspection, Hold point |  | NCC Building Inspector
5 | Revetments
5.1 | Material Approval | Rip Rap and Geotextiles as specified | D50/700: 100% < 1000mm 50% < 700mm 15% < 300mm Geotextile: Class E | Quarry Certs / Photos | Prior to placement of Rip Rap | Visual |  | Downer
5.2 | Excavation profile | Excavated to typical section profiles. Cut matieral transferred to laydown area. | As per drawings C-03-01, C-03-02 | Photos / Asbuilts | Every 50m of cahinage | Visual |  | Downer
5.3 | Geotextile | Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications | As per drawings C-03-01, C-03-02 | Photos | Every 50m of cahinage | Visual |  | Downer
5.4 | Placement of rock | Rocks carried and placed in stream base as per design profile. | As per drawings C-03-01, C-03-02 | Photos | Every 50m of cahinage | Visual |  | Downer
5.5 | Final Inspection | Inspection to confirm Revetment is correct depth, sufficient placement of infill material |  | Photos | Every 50m of cahinage | Visual |  | Downer
6 | Drainage
6.1 | New Sump & Pipe Outlet Installed | New sump & pipe outlet to stream installed and placed through gabion baskets at approx. CH116 | as per LDM | Photos / Asbuilts | After Installation | Visual |  | Downer
6.2 | New concrete surround & flapgate | New concrete surround & flapgate on existing SW pipe at CH195 | as per manufacturer's specs | Photos / Asbuilts | After Installation | Visual |  | Downer
7 | Final Inspection and Disestablishment
7.1 | Practical Completion Walkover | Walkover with Eng, Client and Contractor | Contract works agreed to be practically complete with construction defects noted. | Construction defects list, PC Cert | Upon Completion of Works | Inspection | PM,ENG, Client Rep.
7.2 | As-built drainage plan | Registered drainlayer to provide a colour as-built drainage plan to Council, which includes a north point. | Conforms to design and engineer approvals | Surmmary as-built report and redline drawings | Upon Completion of Works | Action |  | Downer