## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DG-QA-TP018 Inspection and Test Plan (ITP) Stoke Substation | itp |  |  |  |  | DG-QA-TP018 Inspection and Test Plan (ITP) Stoke Substation
section | 1 - Pre Construction
checkpoint | 1.1 - Site Set Up
label | Inspection Point: Quality Control Activity - Enviornmental controls implemented as per DESCP
label | Acceptance Criteria - DESCP
label | Verifying Document - Checksheet
label | Frequency - Pre-Construction
label | Inspection Type (Visual, other) - Visual, hold point
label | Inspection: By - Downer
checkpoint | 1.2 - Work Boundaries Confirmed
label | Inspection Point: Quality Control Activity - Engineer to confirm the boundaries of work.
label | Acceptance Criteria - Engineer Approval
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Pre-Construction
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 1.3 - Vegetation Clearance
label | Inspection Point: Quality Control Activity - Removal of debris and vegetation using cut and stack method. Cleared with hand tools followed by an excavator.
label | Acceptance Criteria - Area cleared of vegetation and approval from ecologist
label | Verifying Document - Email confirmation from Ecologist
label | Frequency - Pre-Construction
label | Inspection Type (Visual, other) - Operation, Hold point
label | Inspection: By - Ecologist
holdpoint | HOLD POINT
checkpoint | 1.4 - Services Located
label | Inspection Point: Quality Control Activity - Service Locations complete and stream banks walked, stormwater pipes cleared around and identified with bright wooden peg.
label | Acceptance Criteria - Services identified, approved controls are in place. Transpower sent info and approves continuation.
label | Verifying Document - Service Location Report
label | Frequency - Pre-Construction
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Downer, Transpower
holdpoint | HOLD POINT
checkpoint | 1.5 - Wingwall Installed
label | Inspection Point: Quality Control Activity - Sandbags laid on filter fabric in stream. Platform level and wingwall structure lowered into stream and braced with steel piles into stream bed. Sandbags wrapped in filter fabric at wings of wall and bypass pipe installed through sandbags.
label | Acceptance Criteria - Max water storage height 1m
label | Verifying Document - Photos
label | Frequency - Pre-Construction
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Downer
holdpoint | HOLD POINT
checkpoint | 1.6 - Fish Relocation
label | Inspection Point: Quality Control Activity - All fish relocated.
label | Acceptance Criteria - Confirmation from Project Ecologist.
label | Verifying Document - Email confirmation from Project Ecologist.
label | Frequency - Pre-Construction
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Ecologist
holdpoint | HOLD POINT
section | 2 - Stream Bed Excavations & Rock Channel
checkpoint | 2.1 - Material Approval
label | Inspection Point: Quality Control Activity - Rock and Geotextiles as specified
label | Acceptance Criteria - D50/700:
label | ○ 100% < 1000mm
label | ○ 50% < 700mm
label | ○ 15% < 300mm
label | – Geotextile: Class E
label | Verifying Document - Quarry Certs / Photos
label | Frequency - Prior to placement of Rip Rap
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 2.2 - Stream Bed Excavations
label | Inspection Point: Quality Control Activity - Stream bed excavated to typical section profiles. Cut matieral transferred to laydown area.
label | Acceptance Criteria - As per drawings C-03-01, C-03-02
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Every 50m of chainage
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 2.3 - Subgrade Inspection
label | Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength
label | Acceptance Criteria - Engineer to assess subgrade strength
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Every 50m of chainage
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 2.4 - Geotextile
label | Inspection Point: Quality Control Activity - Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications
label | Acceptance Criteria - As per drawings C-03-01, C-03-02
label | Verifying Document - Photos
label | Frequency - Every 50m of cahinage
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 2.5 - Stream Base Rock Channel
label | Inspection Point: Quality Control Activity - Rocks carried and placed in stream base as per new design profile.
label | Acceptance Criteria - As per drawings C-03-01, C-03-02
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Every 50m of chainage
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
section | 3 - Gabion Construction - CH85-140 True Right Hand Side
checkpoint | 3.1 - Material Approval
label | Inspection Point: Quality Control Activity - Gabion basket, rock, and rip rap as specified
label | Acceptance Criteria - Gabion Baskets: 2x1x1m PVC coated
label | ○ Gabion Rock: xxx
label | ○ Riprap: 700 ESD ROCK
label | Verifying Document - Photos / Material Certs
label | Frequency - Prior to Gabion Construction
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 3.2 - Cut Face Inspection
label | Inspection Point: Quality Control Activity - Inspect Cut face
label | Acceptance Criteria - As per drawing C-03-01
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face.
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 3.3 - Subgrade Inspection
label | Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength
label | Acceptance Criteria - Engineer to assess subgrade strength
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth.
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 3.4 - Concrete Foundation
label | Inspection Point: Quality Control Activity - Insitu poured gabion wall concrete foundation
label | Acceptance Criteria - Concrete mix as per design. 200mm thick
label | Verifying Document - Concrete dockets
label | Frequency - Prior to first layer of gabion basket installation
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Downer, Engineer
holdpoint | HOLD POINT
checkpoint | 3.5 - Gabion Base Row Alignments
label | Inspection Point: Quality Control Activity - Gabion position marked out, inspection to confirm in correct location as per the specifications
label | Acceptance Criteria - Positioned so base extends minimum 0.5m each side of basket
label | Verifying Document - Photos / Asbuilts
label | Frequency - Prior to backfill of first gabion layer
label | Inspection Type (Visual, other) - Visual verification
label | Inspection: By - Downer
checkpoint | 3.6 - Drianage Inspection
label | Inspection Point: Quality Control Activity - ID04 DPM and drainage coil behind retaining wall
label | Acceptance Criteria - DN100 NOVACOIL placed at base of batter and heel of benches
label | Verifying Document - Approval from Building Inspector
label | Frequency - Prior to backfill of first gabion layer
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - NCC Building Inspector
holdpoint | HOLD POINT
checkpoint | 3.7 - Gabion Layer Inspections
label | Inspection Point: Quality Control Activity - Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications
label | Acceptance Criteria - Max 4 high gabion baskets on true right bank each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket.
label | Verifying Document - Photos / Asbuilts
label | Frequency - Each gabion layer, prior to backfill
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Engineer
checkpoint | 3.8 - Gabion Row Backfill
label | Inspection Point: Quality Control Activity - NDM testing on backfill at 200mm lifts
label | Acceptance Criteria - 200mm lifts, 95% MDD
label | Verifying Document - NDM Report
label | Frequency - Every "x" Lineal m, Each 200mm life, Each Gabion Layer
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Downer
holdpoint | HOLD POINT
checkpoint | 3.9 - Rock Armouring
label | Inspection Point: Quality Control Activity - Placement of riprap
label | Acceptance Criteria - Directed by Engineer on site
label | Verifying Document - Email Confirmation from engineer
label | Frequency - After completion of Gabion Wall
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Engineer
checkpoint | 3.10 - Completion of Gabion Wall
label | Inspection Point: Quality Control Activity - Engineer to inspect completed gabion wall
label | Acceptance Criteria - Gabion wall constructed as per drawings
label | Verifying Document - Email from Engineer as confirmation of Approval
label | Frequency - After completion of Gabion Wall
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
section | 4 - Gabion Construction - CH95 - CH125 True Left Hand Side
checkpoint | 4.1 - Material Approval
label | Inspection Point: Quality Control Activity - Gabion basket, rock, and rip rap as specified
label | Acceptance Criteria - Gabion Baskets: 2x1x1m PVC coated
label | ○ Gabion Rock: xxx
label | ○ Riprap: 700 ESD ROCK
label | Verifying Document - Photos / Material Certs
label | Frequency - Prior to Gabion Construction
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 4.2 - Cut Face Inspection
label | Inspection Point: Quality Control Activity - Inspect Cut face
label | Acceptance Criteria - As per drawing C-03-01
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face.
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 4.3 - Subgrade Inspection
label | Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength
label | Acceptance Criteria - Engineer to assess subgrade strength
label | Verifying Document - Email Confirmation from engineer
label | Frequency - Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth.
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 4.4 - AP65 Compaction Testing
label | Inspection Point: Quality Control Activity - NDM Testing done on AP65 base. CONCRETE?
label | Acceptance Criteria - 95% MDD approved by Engineer
label | Verifying Document - NDM Report
label | Frequency - Prior to first layer of gabion basket installation
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Downer, Engineer
holdpoint | HOLD POINT
checkpoint | 4.5 - Gabion Base Row Alignments
label | Inspection Point: Quality Control Activity - Gabion position marked out, inspection to confirm in correct location as per the specifications
label | Acceptance Criteria - Bottom two layers to be two units wide with every third unit laid perpendicular. Positioned so base extends minimum 0.5m each side of basket.
label | Verifying Document - Photos / Asbuilts
label | Frequency - Prior to backfill of first gabion layer
label | Inspection Type (Visual, other) - Visual verification
label | Inspection: By - Downer
checkpoint | 4.6 - Drianage Inspection
label | Inspection Point: Quality Control Activity - ID04 DPM and drainage coil behind retaining wall
label | Acceptance Criteria - DN100 NOVACOIL placed at base of batter and heel of benches
label | Verifying Document - Approval from Building Inspector
label | Frequency - Prior to backfill of first gabion layer
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - NCC Building Inspector
holdpoint | HOLD POINT
checkpoint | 4.7 - Gabion Layer Inspections
label | Inspection Point: Quality Control Activity - Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications
label | Acceptance Criteria - Each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket.
label | Verifying Document - Photos / Asbuilts
label | Frequency - Each gabion layer, prior to backfill
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Engineer
checkpoint | 4.8 - Gabion Row Backfill
label | Inspection Point: Quality Control Activity - NDM testing on backfill at 200mm lifts
label | Acceptance Criteria - 200mm lifts, 95% MDD
label | Verifying Document - NDM Report
label | Frequency - Every "x" Lineal m, Each 200mm life, Each Gabion Layer
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Downer
holdpoint | HOLD POINT
checkpoint | 4.9 - Rock Armouring
label | Inspection Point: Quality Control Activity - Placement of riprap
label | Acceptance Criteria - Directed by Engineer on site
label | Verifying Document - Email Confirmation from engineer
label | Frequency - After completion of Gabion Wall
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Engineer
checkpoint | 4.10 - Completion of Gabion Wall
label | Inspection Point: Quality Control Activity - Engineer to inspect completed gabion wall
label | Acceptance Criteria - Gabion wall constructed as per drawings
label | Verifying Document - Email from Engineer as confirmation of Approval
label | Frequency - After completion of Gabion Wall
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - Engineer
holdpoint | HOLD POINT
checkpoint | 4.11 - II06 Final - Residential
label | Inspection Point: Quality Control Activity - Residential final inspection. When all building consent requirements are complete.
label | Acceptance Criteria - Gabion Wall constructed as per design
label | Verifying Document - II06 Report
label | Frequency - After completion of Gabion Wall
label | Inspection Type (Visual, other) - Inspection, Hold point
label | Inspection: By - NCC Building Inspector
holdpoint | HOLD POINT
section | 5 - Revetments
checkpoint | 5.1 - Material Approval
label | Inspection Point: Quality Control Activity - Rip Rap and Geotextiles as specified
label | Acceptance Criteria - D50/700:
label | ○ 100% < 1000mm
label | ○ 50% < 700mm
label | ○ 15% < 300mm
label | – Geotextile: Class E
label | Verifying Document - Quarry Certs / Photos
label | Frequency - Prior to placement of Rip Rap
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 5.2 - Excavation profile
label | Inspection Point: Quality Control Activity - Excavated to typical section profiles. Cut matieral transferred to laydown area.
label | Acceptance Criteria - As per drawings C-03-01, C-03-02
label | Verifying Document - Photos / Asbuilts
label | Frequency - Every 50m of cahinage
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 5.3 - Geotextile
label | Inspection Point: Quality Control Activity - Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications
label | Acceptance Criteria - As per drawings C-03-01, C-03-02
label | Verifying Document - Photos
label | Frequency - Every 50m of cahinage
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 5.4 - Placement of rock
label | Inspection Point: Quality Control Activity - Rocks carried and placed in stream base as per design profile.
label | Acceptance Criteria - As per drawings C-03-01, C-03-02
label | Verifying Document - Photos
label | Frequency - Every 50m of cahinage
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 5.5 - Final Inspection
label | Inspection Point: Quality Control Activity - Inspection to confirm Revetment is correct depth, sufficient placement of infill material
label | Verifying Document - Photos
label | Frequency - Every 50m of cahinage
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
section | 6 - Drainage
checkpoint | 6.1 - New Sump & Pipe Outlet Installed
label | Inspection Point: Quality Control Activity - New sump & pipe outlet to stream installed and placed through gabion baskets at approx. CH116
label | Acceptance Criteria - as per LDM
label | Verifying Document - Photos / Asbuilts
label | Frequency - After Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
checkpoint | 6.2 - New concrete surround & flapgate
label | Inspection Point: Quality Control Activity - New concrete surround & flapgate on existing SW pipe at CH195
label | Acceptance Criteria - as per manufacturer's specs
label | Verifying Document - Photos / Asbuilts
label | Frequency - After Installation
label | Inspection Type (Visual, other) - Visual
label | Inspection: By - Downer
section | 7 - Final Inspection and Disestablishment
checkpoint | 7.1 - Practical Completion Walkover
label | Inspection Point: Quality Control Activity - Walkover with Eng, Client and Contractor
label | Acceptance Criteria - Contract works agreed to be practically complete with construction defects noted.
label | Verifying Document - Construction defects list, PC Cert
label | Frequency - Upon Completion of Works
label | Inspection Type (Visual, other) - Inspection
label | Inspection: Key - PM,ENG, Client Rep.
checkpoint | 7.2 - As-built drainage plan
label | Inspection Point: Quality Control Activity - Registered drainlayer to provide a colour as-built drainage plan to Council, which includes a north point.
label | Acceptance Criteria - Conforms to design and engineer approvals
label | Verifying Document - Surmmary as-built report and redline drawings
label | Frequency - Upon Completion of Works
label | Inspection Type (Visual, other) - Action
label | Inspection: By - Downer