## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Usage Count | Resource Id
df5c59b1-6213-4cb0-b11b-e5ee56e8dca3/3 | checklist | DN1211-003 ITP Earthworks (Excavation, Subgrade, Sub-Base) Rev2 | itp | DN1211-003 ITP Earthworks (Excavation, Subgrade, Sub-Base) Rev2 | 21 | 6fa8b451-0ffc-42cf-8781-63f94f26997c
ace71d99-7590-4b60-84ca-8562cc459726 | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
8e6ce5d8-fc80-4d85-bd14-f42a914fb65a | checkpoint | 3.1 - Pre- construction
ff4041d3-eefc-50a8-bbd5-5bb9cda1560c | note | Acceptance/Conformance criteria - Site Clearance and service location completed. Before U Dig, GPR service locate and pilot holing as required. Protect existing services and liaise with utility providers as necessary
a473c20d-01cd-5b95-9819-7bff37be6bd5 | note | Standard/Specification - Aurecon Civil Spec 19.5
14298c7e-070e-5276-a77c-3fe505ae084d | note | Verifying Document - Service Locate or Asbuilts / Sample Dig permit
3ca754fd-44bf-5a98-a8fa-c9dfb2d53119 | note | Frequency - Prior excavation
c54ec032-8640-5dee-95d1-20b581ce443e | note | Verification Activity: Activity - H
e92e1b37-392b-52eb-bb28-05ac30f5fc98 | note | Verification Activity: By - SE
0b548170-090d-5213-b11a-51155b891cd2 | note | Downer Signature - H
bcd75f4d-0789-50dd-af6e-8b7c07c2d54b | note | Engineer Rep Signature - I
f61e956a-aecf-484b-a649-02ed87447703 | signoff | AUTHORITY HOLDPOINT
9fe84e94-f4fb-456f-981b-7fdc4b7dc038 | section | SECTION 4 - MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
3bbab417-d3e9-4e47-ad77-5723f15ae196 | checkpoint | 4.1 - Aggregate MAR
fb236df5-dd6b-5477-9b65-6278738381be | note | Acceptance/Conformance criteria - Sub-Base to be ATAP40 and comply with TNZ M/4 specification for aggregate properties - At least seven working days prior to delivery of Sub-Base course the contractor shall deliver to the engineer the results of production property tests carried out by an IANZ accredited lab in accordance with the relevant NZ standards
893555e1-10ef-5261-af5c-a25d147fcaef | note | Standard/Specification - Aurecon Spec 7.5.1
571005ec-00fd-5e68-b4f0-c5e1a0dad899 | note | Verifying Document - Approved MAR / IANZ test report
eae2e3e3-565b-538a-9f70-15e8092685de | note | Frequency - Once prior Sampling rate as per civil 6.5.1
5ddf5cab-cf1c-5a0a-a47c-f84146824b19 | note | Verification Activity: Activity - H
976ccc07-16ab-548d-9859-7cfa97863a17 | note | Verification Activity: By - DES
285b46d4-dddd-5aee-9241-1b80949827bc | note | Downer Signature - H
379a4e40-f982-501c-9163-b59c8b21f2f6 | note | Engineer Rep Signature - R
d193c427-efca-572f-90fd-501055f74ea4 | note | MSQA - I
31ffd868-f6bb-41e1-8fac-fc126e036f00 | signoff | AUTHORITY HOLDPOINT
cab42782-a0da-4a33-ba7b-d0323d6823f4 | section | SECTION 5 - CONSTRUCTION ACTIVITY
12f38ade-7d6f-41d5-b4d5-bcfb053b85d1 | checkpoint | 5.1 - Excavation
b894e34d-03b1-5791-95f1-761ebdada396 | note | Acceptance/Conformance criteria - Set- out position completed RL marked. For excavation level
d017c624-d5dc-5e6b-9213-40e2e1366a16 | note | Standard/Specification - Aurecon Civil Spec Section 19.11.2
d00f4e8f-9b97-5f99-a969-4017be3e26d5 | note | Verifying Document - ITP sign off
a60ce95e-7604-518a-b9f3-d9910b860c2a | note | Frequency - In Process Check
e7e73d05-006c-5f6a-a19f-4073cda23581 | note | Verification Activity: Activity - V
45aa8f54-916b-5ea9-8c40-9426b45700bc | note | Verification Activity: By - SV
99b6a560-a379-59e4-a1ce-bb3cf145839f | note | Downer Signature - V
d935b566-d07f-5c27-828b-eb253358953d | note | Engineer Rep Signature - I
30b82867-c9c1-42ea-8ebb-cdcd19072387 | section | Site Clearance
094ec8f5-ac29-4080-b31c-833d84019202 | checkpoint | 5.2 - Site Clearance (Cut to Subgrade)
c30d62a1-3574-5c8f-a38f-96ba896fa722 | note | Acceptance/Conformance criteria - Area of work Cleared in accordance with Resource consent andlocal authority requirements. Discovery of unsuitable materials to be advised to the engineer and disposed of or repalced as directed.
62538f25-ef86-5f73-b615-ebf3098a7364 | note | Standard/Specification - Aurecon Civil Spec; Section 3.3 and 3.6
ae9adcce-a36d-581a-848e-8bbf4931acf4 | note | Verifying Document - ITP Sign off
853a8297-65af-5108-8d7a-4bf6ea45c5bd | note | Frequency - In Process Check
e077800c-6d6f-53d9-8531-f6140ff31b7e | note | Verification Activity: Activity - W
91f370fb-3b69-5d09-815e-5d632a9ca0b0 | note | Verification Activity: By - SE
eaf6f3a4-987f-573f-a9a5-d02042d2ef72 | note | Downer Signature - V
0c6ab31b-7812-52de-a927-7754424e1216 | note | Engineer Rep Signature - I
cab926f5-221c-4acc-8ca9-853506a53dcf | checkpoint | 5.3 - Discovery of antiques and valuables (If applicable)
7db73c8e-4765-5aa2-ab87-e1d1d00da2fa | note | Acceptance/Conformance criteria - Arcaheology: Works to be completed as per CMP Archaeoligical discovey protocol, records in site diary and Aconex sent to the Engineer.
53f97b25-4928-55e3-bac8-d65f24d43790 | note | ○ Antiques: Owners must contact the Heritage New Zealand for authority to proceed.
9dc26e3d-260d-545a-a9d9-1feb4df44ecc | note | Standard/Specification - Aurecon Spec 3.10 and Heritage New Sealand
5302fe05-30bc-563a-bcce-2283cf55569b | note | Verifying Document - ITP Sign off
1fc8a831-8c52-599d-88e9-99e629ce8998 | note | Frequency - Upon Discovery (May not be Applicable)
fca5829a-c2c1-5652-963a-4b22a4ddce0d | note | Verification Activity: Activity - H
476efa48-b0ac-53e7-8697-e118cae2b8a4 | note | Verification Activity: By - PE
f3fa93f9-80fe-530a-94af-02ac7637684f | note | Downer Signature - H
a88503a7-da51-52c1-8308-d424a53c588d | note | Engineer Rep Signature - I (IF APPLICABLE ONLY)
ff82ae73-3a2a-4f9d-80ff-1b17063c7343 | signoff | AUTHORITY HOLDPOINT
a94b7c9f-d69e-4f87-a61e-b715b2673503 | section | Removal of Structures and Obstructions
bd80a347-8588-4ff5-b8ae-f39e0f551e97 | checkpoint | 5.4 - Discovery of Contaminated or Hazardous Material (May not be Applicable)
9b92b695-8425-56dd-9dd3-9a2b3adb9841 | note | Acceptance/Conformance criteria - Contaminated material or Waste exhibitning hazardous characteristics handled and removed asper work safe guidnlines and taken off site to be tested. Hazardous or contaiminted materials disposed at approved landfills only. Volume or any disposed hazardous or contaminated materials to be recorded.
88560b09-e5c7-5468-9844-942b86b48523 | note | Standard/Specification - Arecon Civil Spec 4.5.6 and management plan
f031d704-835c-53d5-8b04-c533b43bc93b | note | Verifying Document - Disposal dockets (If applicable) /Site Diary (If applicable)
fc26ebd6-7358-5356-8756-ddda31648990 | note | Frequency - Upon Discovery (May not be Applicable)
570647aa-7d05-557d-a4eb-c578ba0c583b | note | Verification Activity: Activity - H
aec8e483-3fd1-5658-9058-b7322ade5323 | note | Verification Activity: By - PE
c3d4f7bb-d5e9-5d7f-ae6f-4974f2b4fe1d | note | Downer Signature - H
6e2930d2-331c-5c2f-a406-eba8c0bc34fe | note | Engineer Rep Signature - H (IF APPLICABLE ONLY)
d0cde45f-d143-4dbc-a194-a4cf2b321493 | signoff | AUTHORITY HOLDPOINT
1df1efc4-d6ed-4a72-9c34-9ea1b8c8780a | checkpoint | 5.5 - Disposal of materials
124d76cb-654a-5850-a314-c7326114739f | note | Acceptance/Conformance criteria - Demolished Materials sorted as required and disposed of correctly. Materials or item salvaged for re-use as appropriate
11ef7a89-029e-561e-afc4-5f81cd7c1d34 | note | Standard/Specification - Aurecon Civil Spec 4.5.7
a8972989-14e6-570e-8516-c7ba8f31cdd0 | note | Verifying Document - Daily Diary (If applicable)
b8d5f968-9e53-500f-bc3d-567e0e5501a0 | note | Frequency - In Process Check
0d3ba357-c32f-51a6-837d-1f81b9215242 | note | Verification Activity: Activity - I
cc4eef03-4570-594b-ac4e-fcc273c3232f | note | Verification Activity: By - SE
2759368c-d3fd-578e-8cf4-0c59956242da | note | Downer Signature - I
fd4f12f9-df3b-44bb-8128-52d989d42d3c | checkpoint | 5.6 - Demolition and removal of obstructions
72a70df0-d7b7-5706-be30-8484485e08d0 | note | Acceptance/Conformance criteria - Submit works over approvlas for Relevant NUO's where utilities found. Confirm approval to remove structure or protection requirements as per Aurecon DRG's
ad7fc044-92f7-5d5c-a8dd-a8635b14b5ea | note | Standard/Specification - Aurecon Civil Spec 4.5.5
1999a1fa-713a-54d0-af48-2c61e6fee695 | note | Verifying Document - Email confirmation where applicable or works over permit algining with the consent
5271d8c6-f4ce-5108-9f18-89fe660eb6e9 | note | Frequency - Upon Discovery (May not be Applicable)
23c9e276-7ce3-5f1b-8b95-d141ac06afb9 | note | Verification Activity: Activity - H
e358d265-7e69-5b2e-97db-e32c35e3be0d | note | Verification Activity: By - PE
bcc1e6fd-6bb5-5c4b-b1fc-24d541659d67 | note | Downer Signature - H
69bb49fc-138a-501e-b026-26ca60951f73 | note | Engineer Rep Signature - I (IF APPLICABLE ONLY)
8f2075a6-93c3-4171-89a1-c6aaf3bbfc36 | signoff | AUTHORITY HOLDPOINT
86eaeac8-3b79-4114-8fa1-2ccc9991d5d2 | checkpoint | 5.7 - Tree Removal (If applicable)
9216cda7-9b51-548f-845b-c2d5f1c04034 | note | Acceptance/Conformance criteria - Refer to Tree Management Plan, Tree Management plan certification and relevant resource consents/approvals
1c6d8a21-5539-562e-8e23-3528e85f5ce1 | note | Standard/Specification - Resource Consent
c7eb60b0-6a95-5c2d-8152-ec67dcc2e994 | note | Verifying Document - Resource consent
8d22fc03-f820-59f1-bb5e-90d3f696b82a | note | Frequency - Each Tree (If applicable)
efce7e94-26e2-5a34-8649-60993d94b904 | note | Verification Activity: Activity - W
08d0871b-c315-55ff-9970-a8afd8f84f75 | note | Verification Activity: By - PE/DES/ENG
45b2561d-aa2f-5ae6-b942-efbf433bad6d | note | Downer Signature - W
216618cf-3201-5b4d-8fae-9cecc2f52537 | note | Engineer Rep Signature - I
0ab2e537-2e6c-580b-b04c-2fbdf89bf248 | note | MSQA - R
12611ff3-5c86-4d3b-9792-9c4d24936106 | checkpoint | 5.8 - Services/Sun Surface infrastrucure removal
eb1bf017-e62b-50a5-ab91-2701ed304e39 | note | Acceptance/Conformance criteria - Existing services and drainage structures to be located where possble or as agreed with the Engineer. Pilot hole, disconnect or isolate live services prior to demolitions as required. Services or pipes to be abandoned are to be completely removed or grout filled as per drawing or approval by assest owner if different.
8182fe47-8b96-5482-a2a4-39caf363f3ae | note | Standard/Specification - Aurecon Civil Spec 4.5.4 and 4.5.5
0958450c-8719-501e-ab65-a1a6a71b69ca | note | Verifying Document - Service As built
55131228-a7fc-51cd-ad51-2c901b147f7f | note | Frequency - As Encountered
88356190-9274-597e-bbed-c7f8a4ecafad | note | Verification Activity: Activity - H
d09e11a6-ab67-5913-af54-576ec9aafa31 | note | Verification Activity: By - PE/ENG
3f443a11-94bd-545a-ae4a-5b6ffd826ed7 | note | Downer Signature - H
a26dc229-d921-585d-a1fa-80588a09c1b6 | note | Engineer Rep Signature - R (IF APPLICABLE ONLY)
261e0b4a-7a96-4f9a-9ebd-6d949a69285e | signoff | AUTHORITY HOLDPOINT
d11f3b49-1062-4af8-87de-e1225d3623ee | section | Excavation
66a8b671-0afd-4fde-82a6-460171fbe408 | checkpoint | 5.9 - Subgrade Testing
6967eb8e-b19c-5a47-8b87-726c2f8c2120 | note | Acceptance/Conformance criteria - Contractor to Confirm subgrade strength and report to Engineer via Inspection. Clegg to be ≥ 10 value.
c123a86c-52ab-55dc-a216-9ff5ba76e506 | note | Standard/Specification - Aurecon Civil Spec 5.6.11
b73ba664-789b-5051-b7ad-45d79bcbd8b1 | note | Verifying Document - QA sheet
0cb73695-5357-5514-8deb-dd4ec0b3e911 | note | Frequency - Every 20m or as agreed by the Engineer
b5501518-f598-5787-9396-834367a05d87 | note | Verification Activity: Activity - H
49fe3fb1-4315-5ad3-ad8c-6bf9a802a849 | note | Verification Activity: By - SE
7a6bbf69-3722-543b-9c6a-cae672a27843 | note | Downer Signature - H
58d99fa0-7bf2-5f9c-824a-8777f76a3a7b | note | Engineer Rep Signature - R
3d12b03a-ef00-5af4-b4ae-cc7aa50d7b03 | note | MSQA - I
8d776011-757b-4c7d-ba22-76a7142683f3 | signoff | AUTHORITY HOLDPOINT
105a52fd-100d-4ac2-bf44-9f39f2e41bbc | checkpoint | 5.10 - Line and Level of subgrade
e916c287-c22f-5d1e-9d58-fe4e9c726d58 | note | Acceptance/Conformance criteria - Pavement Subgrade tolerance +/-10mm from design subgrade level (or as applicable with existing services). Excavation depth must be at least the design pavement depth for LMC locations. Subgrade shape as per survey set out. To be verified on site.
36bd24cf-d0e4-5cf7-8fa9-aa12cac87c91 | note | Standard/Specification - Aurecon Civil Spec 5.6.9
3224cd23-42b2-5c14-b651-61d9c865a532 | note | Verifying Document - As builts
e61235a8-c42a-5b20-a0b2-5686ea754d47 | note | Frequency - Each Subgrade section
ec3c57b4-acd6-58ec-8807-d1999f868b3d | note | Verification Activity: Activity - H
cfdeb5f7-ba5e-548b-9ef9-9f4c1f8d8350 | note | Verification Activity: By - PE
e752214e-25c9-50f7-b496-419c32901325 | note | Downer Signature - H
b948f073-ad29-5d4f-994d-d2dbd6c098ff | note | Engineer Rep Signature - R
cf246ba4-958d-5948-9c74-a4367d067a64 | note | MSQA - W
5dc78e02-6d86-4aba-ae0f-3e099cc405ba | signoff | AUTHORITY HOLDPOINT
50229bf5-9f05-4a92-933f-79f5b725dc00 | section | Sub-Base
67ea49e8-12b8-4a0b-b844-fe4bb1ad7514 | checkpoint | 5.11 - Sub-Base Level and Shape
f429d50b-6a9c-52d5-b93b-094a94edf37d | note | Acceptance/Conformance criteria - Construct lifts between 2.5 to 5X maximum stone size to ensure good compaction (100-200m). Surface shape, finished and tolerances shall comply with requirments of TNZ B/02- -25mm/+5mm to design FL measured between centreline and pavement edge
e04543af-13d1-53a9-960b-7a246a320236 | note | Standard/Specification - Aurecon Civil Spec 6.7.4 TNZ B/2
b0cefe15-e409-53c2-acb1-16df6b333028 | note | Verifying Document - QA cheetsb and as built survey
09051cfe-7831-5841-8af3-0186266728a2 | note | Frequency - Every 10m for each section of basecourse
db622578-3d9c-5f4d-b6a9-ad7c13202883 | note | Verification Activity: Activity - H
f7952678-1b48-5f69-bb4a-82d252c09954 | note | Verification Activity: By - SE
6d135904-c407-5793-b3c9-85912964e24d | note | Downer Signature - H
25cdad00-f174-5d9f-85bc-ffa986fae855 | note | Engineer Rep Signature - R
cc6c4c16-be5d-5560-ae5e-b27f302e9030 | note | MSQA - I
e8a46aa4-7ee5-4c17-b04c-fe483812b9a2 | signoff | AUTHORITY HOLDPOINT
b49b8c92-b5fb-49d8-b24c-cb823df44de0 | checkpoint | 5.12 - Sub base Compaction
a9f324de-bd5b-5cee-a141-1555dc18f668 | note | Acceptance/Conformance criteria - Clegg testing of Sub-base course to achieve CIV 25+
9ec98ca9-ae5f-5859-a4e6-8cad6a3b4d2b | note | Standard/Specification - Aurecon Spec 6.1 and GCOR-0042
10ddb4d3-d9b1-5a09-9cef-8e8c717acd68 | note | Verifying Document - QA sheets
da51b825-3d34-56d4-b6e0-0f674fcefa37 | note | Frequency - Every 10m for each section of basecourse
e8bb3690-474a-5ea4-bcdf-acbe99d0c406 | note | Verification Activity: Activity - H
61b2bdc2-d69a-5eed-b212-3dc84c75a6d9 | note | Verification Activity: By - SE
53bde335-ba9d-5aee-be44-c25e47590d6a | note | Downer Signature - H
7c211728-44c9-5890-8b98-331deaeb3730 | note | Engineer Rep Signature - R
0c0056b9-c5a6-59be-b046-05eac96dc016 | note | MSQA - R
15919276-5ce0-45ef-a71a-3f3ef1553e3e | signoff | AUTHORITY HOLDPOINT
f5e9fc48-a751-49b6-8a7d-499945da7310 | section | SECTION 6 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
14199a51-90eb-4e11-bf40-2e82d736c699 | checkpoint | 6.1 - Construction Record Compilation
1fbc5eb9-4ac0-56f7-ab12-29a773ab3993 | note | Acceptance/Conformance criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
6b6c84e9-7641-5bab-be4e-23717491bebd | note | Standard/Specification - Downer
ddc89d8f-ccf9-58ae-845e-7bd9a90ab38c | note | Verifying Document - Records
9be18f34-a31a-57d0-9fb4-3bb48c7e9da6 | note | Frequency - Post construction
ab7ef68a-7f92-5ccb-9aa1-598fd99ceabc | note | Verification Activity: Activity - H
27574554-2145-57b9-9b47-02c9e8ce1784 | note | Verification Activity: By - ENG
0b4e6472-a59b-580e-bbca-2d4df034b068 | note | Downer Signature - H
e4f759c8-d340-5363-ba51-4953b18da370 | note | Engineer Rep Signature - H
90bbdd32-fb07-5e77-97f8-48e4a5103ba5 | note | MSQA - R
24f24fb9-56bb-48a5-9469-b14a831b1cef | signoff | AUTHORITY HOLDPOINT
6e82c65b-e598-4c85-9e54-cd5715399d46 | checkpoint | 6.2 - Survey Record
dab791a1-567f-5816-bd38-cbf951ebb66e | note | Acceptance/Conformance criteria - Installation of works under contract completed compliant in accordance with all relevant regulations, COP and standards
2ffdebc2-b75d-5304-b441-9dc1660c8e03 | note | Standard/Specification - Design Specification / Downer
7375d42b-a4f4-5067-a151-843d944298cf | note | Verifying Document - QA Checksheet, Redlines
455db852-f7d0-591f-85e6-a06b6813a48b | note | Frequency - Post Construction
6b9a81ac-af89-517d-8105-2baecd5ee0be | note | Verification Activity: Activity - H
4a563c05-7a4f-5d0a-8973-87cfdd1b9dad | note | Verification Activity: By - ENG
90b4d2b2-a3a5-5f14-b65e-adef3cfa2d84 | note | Downer Signature - H
fab60652-0f7d-58a2-aa02-2952abe70691 | note | Engineer Rep Signature - H
f01b3191-e9cb-5544-aa5c-eccab3724349 | note | MSQA - R
5bdd24d5-7e38-43c0-afe8-9265b45feb73 | signoff | AUTHORITY HOLDPOINT
7e2902a8-18bb-4ae2-a431-c1153a039f15 | checkpoint | 6.3 - Redline Drawings
96d60e2f-df8b-500c-808a-d7efa178179d | note | Acceptance/Conformance criteria - Ensure all items have been installed create a Redline Drawings for Asbuilt creation noting all changes with RFI numbers and departures in red pen
4ab4d7b8-426a-5740-86e9-2e08dd5cf791 | note | Standard/Specification - Downer
2b47d52c-057f-5469-8bd2-f28a5deedd77 | note | Verifying Document - Redlines
c2ab2b52-5f78-5a70-8cbb-0b022927816f | note | Frequency - Post Construction
964ff206-1400-55a6-896d-5be8ce513a48 | note | Verification Activity: Activity - H
b7953067-92f9-5fee-8d72-0a7a221f8648 | note | Verification Activity: By - ENG
ed8ddaff-fcd0-5c4c-abb1-3128c2efba6b | note | Downer Signature - H
9500d528-efaf-57f9-9d0c-bc1ba877ee5e | note | Engineer Rep Signature - H
f94fce0f-a5ce-5ac6-bd9c-d2c97a4a293e | note | MSQA - R
1c35f19b-7914-417b-a22d-bd1420370cb1 | signoff | AUTHORITY HOLDPOINT
68118900-ee6a-4f2f-9523-0a301ed9fde4 | checkpoint | 6.4 - Defect, Snag and Punch List
e7efd3b0-ff3d-528e-85a7-b064eb8b539f | note | Acceptance/Conformance criteria - Update the project defects, snag and punch list register
bc6b536a-8bd3-54d4-b048-26971085fd83 | note | Standard/Specification - Downer
2b1eadd7-362b-5629-8f5e-96029f14ad25 | note | Verifying Document - Redlines
6d28c682-9670-5f3e-b708-ff9c21364883 | note | Frequency - Post Construction
af3302e1-1718-5797-8b39-09fd6a032b71 | note | Verification Activity: Activity - H
5ef68211-60b4-575c-9ca6-4033554b14af | note | Verification Activity: By - ENG
3dc004b7-4de3-5fc5-811d-597729b0b633 | note | Downer Signature - H
7ebbb442-e33d-550d-96db-f114c9808959 | note | Engineer Rep Signature - H
dd31e2e8-669c-5461-9c25-c502911ad651 | note | MSQA - R
9e0d01ca-8801-498a-a74f-45d478cfaee4 | signoff | AUTHORITY HOLDPOINT
004a2451-3e4e-4606-91ef-32f2246c79b9 | section | SECTION 7 - SIGN OFF
b3f4e0fc-2cd1-4f1d-91dc-8bd201bbea15 | checkpoint | Customer Release Granted:
924c9d68-8da7-5b29-b401-9029b5153107 | textbox | Certificate Number:
893dd132-4466-5fa3-9f1e-59f744167c3f | date | Date:
f259dc66-0893-47f8-bcb5-4019e2ca4f59 | signoff | Sign Off
b80d3e11-ad18-4a7a-987f-e939491cf2a6 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
eeff83fe-9d68-575e-86dc-0075572d98c4 | textbox | Contractor's Rep Name:
108f4bac-0c48-5ebb-ba75-908597fe59b4 | textbox | Engineer's Rep. Name:
135764f4-ce24-5f2f-a59e-f31922c27e46 | date | Date:
d3d09d47-7640-41eb-acaf-ad6bf2f694ef | signoff | Add Signature