## Asphalt - Surfacing
|  |  |  | Process Control Plan |  | FHIMS-QA-6076 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
|  |  |  | Procedure: | Asphalt - Surfacing (SMA/OGPA) |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7076 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | M | Provide vendor’s certified test reports for all bituminous material proposed to be used on Site for approval by Engineer | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Pre seal inspection | W | Inspect surface before Prime coat to determine application rate and allow for inspection | Prior to commencement | Visual Inspection | The surface should have no free water, and the moisture content should not be less than 2% below the modified optimum moisture content as determined for the material. | Photos
3 | Material Compliance | H | Bituminous primer | Prior to commencement | submission | CRS 60 emulsion product complying with NZTA M02 and base binder confirming with NZTA M/1 2020 unless otherwise approved by the Engineer. | Testing documentation, confirmation of acceptance by Engineer
|  | H | Aggregates, all aggregates used should comply with section 10.6 of the contract specifications, unless changed in Risk register. | Prior to commencement | Testing | The Contractor shall supply test certificates for all aggregate fractions proposed for use in the Works. The test certificates shall cover all test properties specified in Table 10.1 and Table 10.2 for each aggregate fraction and shall not be more than one month old. The test certificates specified above shall be submitted to the Engineer not less than 5 working days prior to the commencement of mix design and this shall constitute a Hold Point. | Testing documentation, confirmation of acceptance by Engineer
|  | H | Bituminous Materials. As outlined in section 10.7 of contract specifications or amended in Risk register. Witness point | Prior to commencement | Lab Testing | The source/s from which all bituminous materials are to be obtained, the details of the manufacturer/s and the manufacturing process/es and test results for each material indicating full compliance with this Specification shall be supplied to the Engineer 5 working days prior to the date on which the laboratory asphalt mix design is commenced. | Testing documentation, confirmation of acceptance by Engineer | Site Engineer | Design Engineer
|  | M | Binder content | Prior to commencement | Lab Testing | Binder content should comply with the target values set out in Table 10.4 of section 10.8 of the contract specifications. | Mix design
4 | Plant and Equipment | H | All plant and equipment should comply with contract specifications 9.4, 10.14 and 10.16 unless changed in risk register. Hold point | Prior to commencement | submission, visual inspection | Prior to movement of any plant on to site of works, submission of daily plant inspection verification checklist. | Submissions and records of removal of holds
5 | Ashphalt Mix Design | H | Comencement of mix design - Witness point | Prior to mix design comencement | Document review | The mix design shall not commence before test results and compliance certificates for the virgin materials have been submitted and compliance of the virgin materials to the Specification has been confirmed.Notify the Principal’s Representative not less than 48 hours prior to commencement of mix designs | Confirmation that all virgin materials meet the specifiction
|  | H | Mix Design shall conform with sections 10.9 and 10.10 of the contract specifications and then be submitted to the principals reperesentative for approval. Unless ammended in risk register | Prior to commencement | Lab Testing | Written advice to Principal’s Representative of the proposed mix design for each nominal size mix including results of the mix design tests and other required information listed in section 10.10.5 of the design specification. | Mix Design | Site Engineer | Design Engineer
6 | Asphalt Production Trial and Testing | H | Testing should be undertaken during asphalt production as outlined in section 10.11 of the contract specifications. If Asphalt is not complying with the specifications this should be used as a hold point. | Prior to commencement | Lab Testing and measurements | NZTA M/10, NZTA M/10, ASTM D3203, ASTM D1188 | Asphalt Plant Certifications and results | Site Engineer
|  | H | Mixing Plant Calibration Charts - Hold Point | Prior to Production Mix Trial | Document review, Submission | Provide Mixing plant calibration charts to principals Representative | Principals Representative confirmation of acceptance
|  | W | Commencement of the Production Mix Trial Witness Point | Prior to Production Mix Trial | Submission | Notify the Principal’s Representative not less than 48 hours prior to commencement of Production Mix Trial | Evidence of notification
|  | H | In the Production Mix Trial, the Contractor shall manufacture each nominal mix size to the submitted mix design that was satisfactory to the Principal’s Representative and shall use the nominated mixing plant in order to confirm that the specified mix properties can be achieved in production. Witness Point | Following production mix trial | Submission of results | All test results on each nominal mix size produced in the Production Mix Trial, and Written advice to the Principal’s Representative of any adjustments to the mix which are necessary to achieve the properties of the submitted mix design. As outlined in section 10.12 of the contract specifications. | Evidence of notification
7 | Construction Trial | H | 10 or more days before asphalt paving is due to comence, a construction trial shall be undertaken. Sufficient asphalt shall be produced to give two paver runs at least 30 metres long, placed at specified thickness with at least one longitudinal joint. The construction trial shall demonstrate all construction techniques proposed in the methodology. -Hold Point | Prior to Construction trial | Notification | Notice to Principal’s Representative, 48 hours prior to commencement of Construction trial that all resources required for the trial are available and all arrangements required for the trial have been made. | Evidence of notification
|  | H | The construction trial shall not commence until acceptable plant calibration charts, as adjusted where necessary, following the plant mix trial are provided for inspection by the Principal’s Representative | Prior to Construction trial | Submission | Mixing Plant Calibration charts are submitted to pricipals representative. | Evidence of notification
|  | W | Testing of Asphalt - The Contractor shall sample and test the asphalt produced in the production trial | During Asphalt production | Lab Testing | In accordance with Section 10.18 of the contract specifications, except that the Contractor shall take and test not less than three representative samples of each nominal mix size taken at approximately the quarter points in the production trial and in accordance with M/10. | Testing results
|  | H | Placing, Compaction, Finishing and testing of Asphalt for Trial shall be in accordance with section 10.13.3 of the contract specifications. - Hold point | During and following construction trial | Lab testing | All test results on each nominal mix size produced, placed compacted and finished in the Construction trials, and, if required, Written advice to the Principal’s Representative of any alterations in procedures or adjustments to the plant and equipment as necessary to produce asphalt in accordance with this Specification. | Evidence of notification
8 | Final Job Mix Approval | H | Following completion of the construction trials Complete details of the ‘Job Mix’, the ‘Job Aggregate Particle Size Distribution’, the ‘Job Bitumen Content’ and the ‘Job Mix Temperature’ for each nominal mix size should be submitted to the princials representative | Following construction trial | Submission of results | At lest 2 days prior to the planned commencement of the works | Evidence of release of hold point
9 | Weather Limitations |  | Ensure there is a clear weather window when Prime coating is scheduled. | Prior to Prime Coating | Review | The prime coat shall be applied only when the surface temperature is at least 10°C and is expected to remain in excess of 10°C for the duration of the application of the prime coat. Spraying shall not proceed when rain has been forecast, or is likely to occur, and may cause damage to the prime coat. | Weather forecast
10 | Bituminous Prime Coat | M | Prime coat should be applied and maintained in accordance with sections 9.8 - 9.10 of the contract specifications. | During Construction | Visual Inspection | sections 9.8 - 9.10 of the contract specifications | Photos
|  | H | Spraying Records | During and Following prime coating | Submission | The record shall include: – The location and date of the spray run, – The temperature of the primer immediately before spraying, – The tank dipping before and after each spray run, – The surface temperature, – The calculated application rate of primer at the spraying temperature and – Any other pertinent information. | Spraying record
11 | Selection of Reference Area for Surface Finish | H | the Principal’s Representative and Contractor will select a Reference Area/s that have the surface finishes at joints and not at joints that both considers to be the standard that are compliant with the Specification and are to be achieved in the Works. | Prior to construction of surfacing Asphaltic Concrete | Visual Inspection | Written agreement by Contractor, including photographs of the Reference Areas for each nominal size mix. | Evidence of release of hold point
12 | Tack Coat | H | A tack coat of bitumen emulsion shall be applied to all existing surfaces on or against which asphalt is to be placed including the edges of all joints except hot joints. | Prior to placing Surfacing AC | Lab Testing and measurements | Tack coat should be applied in compliance with section 10.21 of the contract specifications or as modified in Risk Register. | Subcontractor QA Records | Site Engineer
13 | Construction of Surfacing Asphaltic Concrete | H | Site team QA Checks, Routine sampling and testing of asphalt for compliance with the specified test properties shall be carried out by the Contractor | During Construction | Site Measurements | The frequency of sampling and testing shall be not less than 1 test per 200 t or a minimum of two (2) tests per construction shift | QA Records and testing results | Site Engineer
|  | M | Delivery of Asphalt | During Construction | Review | Delivery of asphalt from the mixing plant to the site shall be in accordance with the requirements of M/10 and as specified in section 10.19 of the contract specifications | Planning Documents that show compliance
|  | M | Asphalt should be laid and rolled | During Construction | Review | in compiance with section 10.22, 10.23, 10.26, 10.27, 10.28 of the contract specifications | Photos and other evidence of compliance
14 | Layer checksheets | H | Each shift the Pavement Layers Checksheet FHIMS-CS-4055 is to be filled in and approved by the Quality Manager | At completion of each shift | Document and result review |  | FHIMS-CS-4055 | Site Engineer
15 | Surface Smoothness Testing | W | A Witness Point shall be designated at the completion of pneumatic tyred rolling and prior to surface smoothness testing and at the completion of smoothness testing. | Prior to Opening to Traffic | NAASRA Test | Testing should be undertaken as outlined in section 10.27.10 of the contract specification and meet the requirements set out in 10.27.9 | Surface Smoothness testing records | Site Engineer
16 | Density and ThicknessTesting | H | Cutting of cores and density testing should be undertaken in compliance with sections 10.24 and 10.25 of the project specifications unless ammended in Risk Register | Following Construction | Testing | Cores shall be cut from layers of compacted asphalt in accordance with the requirements of M/10 and as specified herein.
17 | Cleaning of Pavements Witness Point | W | Ensure Clean prior to handover | Following all construction and testing | Visual Inspection | The pavements shall be swept, and/or vacuumed clean by mechanical brooms, suction sweepers, hand brooming and/or other means, such that an acceptable standard of cleanliness is met before the pavement is opened for aircraft operations. | Approval documentation for witness point
18 | As-builts | H | All finished surface levels shall be surveyed by precise levelling to an accuracy of 2 mm with readings to 1 mm and the survey shall be undertaken under the control of a licensed surveyor. | At the completion of the Lot of work | Drawings | The survey results shall be submitted to the Engineer in a format agreed with the Engineer. | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date: