## Subbase Construction
[5 empty] | Process Control Plan |  | FHIMS-QA-6071 | Approved |  | Signature
[5 empty] | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
[5 empty] | Procedure: | Basecourse Construction |  | FH Quality Manager
Inspection & Test Plan / Checklist
| Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
| 1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | 3 | Survey Setout | H | Survey Model produced and benchmarks installed. Grader benching to be confirmed on a daily basis | Each shift | Measure, Survey | Random checks to be undertaken by survey to ensure grader control is working correctly | FHIMS-CS-4103 | Site Engineer
| 3 | Material Compliance | H | Aggregate material sample of Subbase | MIN 7 days prior to commencement | Sample | 20kg minimum | Sign ITP | Site Engineer | Design Engineer
|  |  |  | Source Grading | 1 test a MIN 7 days prior to commencement & 1 test per day of production thereafter | Lab testing | Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006) | Engineer approval
|  |  |  | Source Broken Faces | MIN 7 days prior to commencement and 1 test per day of production thereafter | Lab testing | Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006) | Engineer approval
|  |  |  | Source Flakiness Index | MIN 7 days prior to commencement | Lab testing | Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006) | Engineer approval
|  |  |  | Source Bearing strength (soaked CBR) | 1 test a MIN 7 days prior to commencement & 1 test per 1000m3 overall | Lab testing | Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006) | Engineer approval
|  |  |  | Source Crushing resistance | 1 test a MIN 7 days prior to commencement & 1 test per 1000m3 overall | Lab testing | Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006) | Engineer approval
|  |  |  | Source Weathering resistance | MIN 7 days prior to commencement | Lab testing | Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006) | Engineer approval
|  |  |  | Source clay Index | MIN 7 days prior to commencement & 1 test per 1000m3 thereafter | Lab testing | shall be less than 3, NZS4407 Test 3.5 | Engineer approval
|  |  |  | Source Plasticity Index | MIN 7 days prior to commencement & 1 test per 1000m3 thereafter | Lab testing | LL less than 25 & PI less than 6 | Engineer approval
| 4 | Basecourse Construction | H | Plant selection agreed upon that won't overstress pavement layers below | Prior to layer construction | review | engineers agreeance | Email | Site Engineer | Design Engineer
|  |  | H | Plateau Density Testing for Subbase Layer | Min. 1 initially | NDM Lab Testing | To establish roller pattern | Pavement Lab Testing Spreadsheet | Site Engineer
|  |  | W | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
|  |  | H | Degree of Compaction | 5 per 1000m2 max | NDM Lab Testing | Avg. >= 99% MDD and Min. >= 95% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
|  |  | H | Benkelman Beam Testing | Minimum 20 tests/1000m2 (5*5m grid) | Benkelman Beam Test | 90th percentile result less than 1.5mm | Pavement Lab Testing Spreadsheet | Site Engineer
|  |  | H | Finished surface shape check, submitted to engineer 1 working day prior to overlying layer | 5*5m grid survey, plotted with contours to scale 1:500 | Measurement | Engineers approval | Correspondance | Site Engineer
|  |  | H | Surface finish check | Prior to sealing | Visual inspection by Design Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping | FHMIS-CS-4060 | Site Engineer | Design Engineer
| 5 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for pavement testing as per Specifications | At completion of Lot | Document Review |  | Pavement Lab Testing Spreadsheet | Site Engineer | Design Engineer
| 6 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
| QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
| QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
| Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date:
Note on H14: Sheriff, Chris - FH Projects: Insert Frequency & Testing requirements
Note on H15: POWELL, Thomas: Amend all yellow to NZTA M/04 2006
Note on H18: POWELL, Thomas: spec table 8.3 asks for soaked CBR for bearing strength but 8.4.5 asks for this test instead
Note on H26: POWELL, Thomas: Is this the new NZTA M04 2024? If not I'd push back to 95min 98av, otherwise very tough
Note on F27: Sheriff, Chris - FH Projects: Insert Frequency
Note on H27: Sheriff, Chris - FH Projects: Insert Frequency