## Road Marking
|  |  |  | Process Control Plan |  | FHIMS-QA-6078 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
|  |  |  | Procedure: | Road Marking |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7078 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Survey Setout | H | The Contractor must set out the Pavement Markings as shown on the Drawings as soon as ashphalt works are completed. The setting out of the Pavement Marking must be undertaken by a competent the Engineering surveyor, having qualifications that meet the pre-requisites for becoming a licensed surveyor, and who is experienced in this type of survey work. | Prior to commencement | Survey | The precision of the survey for the new markings must be such that the finished markings are located to a horizontal accuracy of ± 25 mm. The lines to be painted shall be marked out by the Contractor with chalk and approved by the Principal’s Representative prior to painting. | Survey receipt | Site Engineer
|  | W | Survey work must include spotting of the pavement, as required, to locate and define the extent of the new markings in sufficient detail for the painting of the required markings to the tolerances specified. | Prior to commencement | Visual check of spots before painting the lines | Spots shall be at a spacing of 10m or less on curves. For new marking with respect to specified location: Transverse location -+20mm, Longitudinal location -+50mm. All lines shall appear by eye to be straight, or where designed as a curve, curve is smooth between each transition from straight to curve. | QA Records | Site Engineer
3 | Material Compliance | H | Paint | Prior to commencement | Visual inspection/ Document review | Comply with specifications set out in section 17.3 of the contract specifications, FHIMS-CS-4021- Line Marking Materials Checksheet. | Manufacturing certificates, delivery dockets and checksheet | Site Engineer
|  | H | Glass Beads | Prior to commencement | Visual inspection/ Document review | AS/NZS 2009: 2006 Glass Beads for Road-Marking Materials. | Manufacturing certificates, delivery dockets and checksheet | Site Engineer
4 | Removal of dirt and contaminants from pavement surfacing | H | The surface of the asphalt or concrete pavement in the areas to be painted must be thoroughly cleaned prior to the application of the pavement marking paint. | Prior to commencement | Visual Inspection | As outlined in Section 17.5.2 of the contract specifications. | Photographs and QA documentation | Site Engineer
5 | Removal of Redundant Pavement Markings | H | All redundant pavement markings shall be removed. The surface of existing painted markings must be thoroughly cleaned prior to repainting. All existing paint that is not strongly adhering to the pavement must be removed prior to re-painting. | Prior to marking | Visual Inspection | The shape of the old markings can not be distinguished. The final surface texture is similar to the surrounding pavement. "Blackout out" of pavement markings is not allowed in this contract. | Photographs and QA documentation | Site Engineer
6 | Quality Assurance Requirements | H | Evidence of an approved quality system shall be provided to the Principal prior to pavement marking activities commencing. | Daily | Collating information on a daily basis | An approved pavement marking quality system shall include one of the following options: Certification to Road markers Federation’s Quality Assurance Programme (QAP); or Certification to JAS-ANZ accredited certifying body to ISO 9002 including the criteria of the NZRF QAP Specification and Guidelines; or Certification by JAS-ANZ accredited certifying body to the criteria of the NZRF QAP Specification and Guidelines, with the certification policy to be approved by TNZ. | Subcontractor QA Records | Site Engineer
7 | Plant Records | H | Plant shall have current certificates of compliance. |  |  | in accordance with NZTA T/12 or NZTA T/8 as applicable | QA Records/ Certificates
8 | Paint Marking | W | Paint application should comply with sections 17.5.1 and 17.5.3 of the contract specifications. | During pavement marking | Visual inspection |  | Photographs and Subcontractor QA Records | Site Engineer
9 | Application Rates | H | The paint must be applied in two (2) even coats to give a minimum total dry film thickness of 120 microns. Film thickness is measured on steel plates | Min of 2 per day and after pressure or speed settings are changed | Test | TNZ P/12 Appendix A gives details of the plate test | Subcontractor QA Records | Site Engineer
10 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date: