## Network Drainage
|  |  |  | Process Control Plan |  | FHIMS-QA-6007 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
|  |  |  | Procedure: | Drainage |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: | [7 empty] | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Set out Inspection | W | Pinciple inspection after setting out of work where concrete operations will occur. | Prior to commencement | Visual inspection |  | Written confirmation from Principles Rep
3 | Foundation Scala Penetrometer Record | M | Record ' Scala Penetrometer' to be completed, | 1 per 20m of trench and 1 at structures | Submission | Confirm the undisturbed subgrade preperation has a greater than 50 kPa bearing strength. Test to 400mm depth minimum | Record Completed
4 | Materials | W | Granular Bedding Material | On ordering and on arrival at site | Visual, testing | All bedding material shall be approved by the Engineer and unless otherwise stated follow the specification set out in section 12.2.1.1 of the contract specification. | Dockets
|  | W | Aggregate Concrete Bedding | On ordering and on arrival at site | Visual, testing | All Aggregate concrete bedding should be in coompliance with section 12.2.1.2 of the contract specification. | Deliver dockets and testing
|  | W | Pipes, fittings and Joints | Prior to laying / placing | Visual inspection | All pipes, fittings and joints should comply with sections 12.2.2 and 12.2.3 of the contract specifications. | Supply Dockets and Photographs
|  | W | Unless otherwise stated, other drainage structures shall be constructed of reinforced concrete | Each Structure | Visual | NZS3109, NZS3124, Concrete Specification and the concrete shall have a minimum crushing strength of 17.5 Mpa at 28 days. Anchor blocks shall be constructed of reinforced concrete as per above. | Supply Dockets, testing and Photographs
|  | M | Precast manholes are to be used unless specified otherwise on the contract drawings. | Each Structure | Visual | Manholes and their components should comply with section 12.2.4 of the Contract specifications | Record Complete
|  | M | Cesspits, Unless otherwise stated all catchpits shall be precast reinforced concrete | Each Structure | Visual | NZS3109, contract drawings and Section 12.2.5 of the contract specifications | Supply Dockets and Photographs
|  | M | Materials for concrete, Cement and Aggregates | Every pour | Visual inspection | Cement shall be ordinary Portland cement conforming to NZS3122: 1977. Rapid hardening Portland cement shall only be used with the approval of the Engineer.Aggregates shall comply with NZS3121: 1980. Coarse aggregate shall be 20 mm maximum, except aggregate for concrete block filling, which shall be 13.2 mm maximum. | Deliver dockets and testing
|  | M | Supply of concrete shall be from A ready mixed concrete plant | Prior to commencement | Document Review | Plant must hold either a current High or Special Grading complying with NZS3104 and 3109. | Copies of certification
5 | Construction | H | All reticulation works, including laying of new lines and reinstatement of existing systems are to be carried out by, or under the supervision of a registered drainlayer to current trade certificate practices. | Before Comencement | Visual inspection | Unless otherwise specified all construction shall comply with NZS 4452,AS/NZS 3725, and AS/NZS 1260 | Copies of qualifications
|  | W | All bedding shall be placed and compacted to ensure the pipe is evenly supported over the entire length | Each structure and pipe | Initial Inspection and follow up photographic evidence. | All Concrete and granular bedding should comply with section 12.3.2 of the contract specifications. | FHIMS-CS-4025 Drainage Line Record
|  | W | All foundations require inspection by the Principal or Principals Representative during Concrete Operations | Prior to commencement of formwork and rienforcing | Visual inspection |  | Written confirmation from Principles Rep
|  | W | Laying and Jointing Pipes | Each structure and pipe | Initial Inspection and follow up photographic evidence. | Concrete pipes shall be installed to NZS/AS 3725, uPVC pipes shall be installed to AS/NZS 1260. All laying and Jointing of pipes should comply with section 12.3.2 of the contract specifications. | FHIMS-CS-4025 Drainage Line Record
|  | W | Drainage Structures. Manholes, inspection chambers or other drainage structures shall be constructed as per standard drawings. | Each structure and pipe | Initial Inspection and follow up photographic evidence. | Drainage structures shall be installed to section 12.3.4 of the contract specifications. | FHIMS-CS-4025 Drainage Line Record
|  | H | An ispection is required by the Principal or Principals Representative after completion of formwork prior to placement of reinforcing/concrete and after completion of reinforcing. | Before Each Pour | Site Inspection | Concrete Pre-Pour Checklist completed prior to concrete pour, also complete FHIMS-CS-4029 - concrete pump - permit to pump, if required. Form work should comply with NZS3109 | FHIMS-CS-4008 - Concrete Inspection Record, Written confirmation from Principles Rep
|  | H | An ispection is required by the Principal or Principals Representative after completion of concrete and installation of construction joints | Before Each Pour | Visual inspection | Engineer Approval | Written confirmation from Principles Rep at each stage
6 | Tolerances | M | Before backfilling comences a survey inspection should be undertaken to ensure Manholes and pipelines are withing allowed tollerances. | During construction | Measure | All manholes and pipelines should be within the horizontal and zvertical tollerances outlined in section 12.4.1 of the contract specifications. | Survey receipt
7 | Layer Depth | W |  | Layer depth as Required | Review | Placement of backfill must not exceed an uncompacted thickness of 200mm for AP20 and 200mm for AP65 | Onsite Inspections
8 | Backfill Testing Regime | W |  | Clegg test 1 per layer every 30m | Photographs to be supplied witnessing each layer lift. Photographs to be supplied witnessing each layer lift | Testing must be carried out on the first backfill layer with subsequent layers tested as required. Compacted layer depth no less than 2.5 times the maximum filling aggregate size | Record Complete
9 | Presure Testing | W | Complete low pressure Air testing and associated record | Each Line | Submission, test | Engineer/witness to be present when completing final acceptance pressure testing. Standard NZS 4452 | Completed FHIMS-CS-4074 - Low Pressure Air Test Record
10 | Pipeline Camera | W | CCTV Inspection Videos to be Reviewed | Each Line | Submission | Camera to run all pipelines (CCTV). Footage is to be reviewed and be of acceptable standard prior to beginning subbase construction. A final flushed line CCTV footage (prior to asphalting) is required for Engineer and Council records. | Record Completed
11 | As Builts | W | As Builts to be taken with GPS unit during comstruction and provided to engineer at the conclusion of the project | As Required | Record | Record as built | Record Completed
12 | Stage completion inspection | H | Inspecytion by engineer to confirm stage complies with specifications | At completion of stage and before next stage comences | Record | As per section 12.4.2 of the project specifications. | Email confirming approval has been given for stage completion.
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date: