## Subbase Construction
|  |  |  | Process Control Plan |  | FHIMS-QA-6071 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
|  |  |  | Procedure: | Subbase Construction |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Survey Setout | H | Survey Model produced and benchmarks installed. Grader benching to be confirmed on a daily basis | Each shift | Measure, Survey | Random checks to be undertaken by survey to ensure grader control is working correctly | FHIMS-CS-4103 | Site Engineer
3 | Material Compliance | H | Aggregate material sample of Subbase | MIN 7 days prior to commencement | Sample | 30kg minimum | Sign ITP | Site Engineer | Design Engineer
|  |  | Source Grading | 3 tests a MIN 7 days prior to commencement, 1/500m3 overall | Lab testing | Table 7.1 , 7.4.2 Project specification | Engineer approval
|  |  | Source Broken Faces | MIN 7 days prior to commencement and 1 test per 500m3 thereafter | Lab testing | 70% retained on <37mm sieves to have 2 or more broken | Engineer approval
|  |  | Source Bearing strength | 3 tests a MIN 7 days prior to commencement & 1 per 1000m3 overall | Lab testing | soaked CBR of min 35% (NZS 4407, Test 3.15) | Engineer approval
|  |  | Source Crushing resistance | 3 tests a MIN 7 days prior to commencement & 1 per 1000m3 overall | Lab testing | less than 10% passing 2.36mm sieve using 130kn load. NZS4407 3.10 | Engineer approval
|  |  | Source Plasticity Index | 3 tests a MIN 7 days prior to commencement, 1/500m3 overall | Lab testing | LL less than 25 & PI less than 6 | Engineer approval
4 | Subgrade separation layer | H | Placement of geotextile separation layer | During construction | review | Correct strength 'A34' used and minimum laps installed per NZTA F/7 | certificate of compliance | Site Engineer
|  |  | Placement of geogrid separation layer | During construction | review | Correct grade Cirtex Gridtex 40/40. Installed to manufacturers specs | photos, certificate of compliance | Site Engineer
5 | Subbase Construction | H | Plant selection agreed upon that won't overstress subgrade | Prior to layer construction | review | engineers agreeance | Email | Site Engineer | Design Engineer
|  | H | Engineer approval of geotextile layer | Prior to layer construction | Lab testing | Layer has been signed off | Correspondance | Site Engineer | Design Engineer
|  | H | Plateau Density Testing for Subbase Layer | Min. 1 initially | NDM Lab Testing | To establish roller pattern | Pavement Lab Testing Spreadsheet | Site Engineer
|  | W | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
|  | H | Degree of Compaction | 5 per 1000m2 max | NDM Lab Testing | Avg. >= 95% MDD and Min. >= 92% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
|  | H | Benkelman Beam Testing | Minimum 20 tests/1000m2 (5*5m grid) | Benkelman Beam Test | 90th percentile result less than 2.0mm | Pavement Lab Testing Spreadsheet | Site Engineer
|  | H | Finished surface shape check, submitted to engineer 1 working day prior to overlying layer | 5*5m grid survey, plotted with contours to scale 1:500 | Measurement | Engineer Approval | Correspondance, FHIMS-CS-4069 | Site Engineer
|  | H | Surface finish check | Prior to sealing | Visual inspection by Design Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping | FHMIS-CS-4060 | Site Engineer | Design Engineer
6 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for pavement testing as per Specifications | At completion of Lot | Document Review |  | Pavement Lab Testing Spreadsheet | Site Engineer | Design Engineer
7 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date:
Note on H14: Sheriff, Chris - FH Projects: Insert Frequency & Testing requirements
Note on F27: Sheriff, Chris - FH Projects: Insert Frequency
Note on H27: Sheriff, Chris - FH Projects: Insert Frequency