## Subgrade Construction
|  |  |  | Process Control Plan |  | FHIMS-QA-6069 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer
|  |  |  | Procedure: | Subgrade Construction |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7069 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | Drawings and documents are current | Sign ITP | Site Engineer
2 | Earthwork Methodology | H | Submit Earthworks Method including (proof rolling plan) | Min 3 weeks prior to commencement | Document Review | Engineers approval | Correspondence | Site Engineer | Design Engineer
3 | Cut to Waste | H | Earthworks cut to waste | Prior to Testing | Document Review | Unsuitable material removed | Photos / Sign ITP | Site Engineer
4 | Subgrade testing | H | Subgrade CBR testing | 20*20m grid | Scalar | Scala result above 4% or 8% depending on pavement area | Pavement Lab Testing Spreadsheet | Site Engineer
|  | H | Subgrade shear strength | 20*20m grid | Shear vane | >100kpa | Pavement Lab Testing Spreadsheet | Site Engineer
|  | W | Provide 1 working days notice to engineer ahead of proof roll | All instances | Submission | NTE | Correspondence | Site Engineer | Design Engineer
|  | H | Site Engineer and Design Engineer to undertake a Proof Roll test on the trimmed subgrade to the approved proof roll plan | 100% area | Visual Inspection | Written record | FHIMS-CS-4005 - Proof Roll Checksheet | Site Engineer | Design Engineer
|  | H | Any subgrade area that does not pass subgrade testing or proof rolling | Per occurance | Document Review | Notify engineer | Correspondence | Site Engineer | Design Engineer
|  | H | Carry out a Level Check on the trimmed subgrade | 10*10m grid | straightedge & total station | Tolerance = -20mm + 0mm | Survey record | Site Engineer
3 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for pavement testing as per Specifications | At completion of Lot | Document Review |  | Pavement Lab Testing Spreadsheet | Site Engineer | Design Engineer
4 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into M-Files | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
5 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date:
Note on H13: Sheriff, Chris - FH Projects: Insert Frequency & Testing requirements
Note on E15: Sheriff, Chris - FH Projects: Insert Frequency
Note on H15: Sheriff, Chris - FH Projects: Insert Frequency & Additional Specification call for
Note on E16: Sheriff, Chris - FH Projects: Insert Frequency
Note on H16: Sheriff, Chris - FH Projects: Insert Frequency & Additional Specification call for