## Topsoil Respread
|  |  |  | Process Control Plan |  | FHIMS-QA-6009 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
|  |  |  | Procedure: | Topsoil Re-spread, Grassing & Hydro seeding |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7009 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Confirm with Engineer the need to separate the topsiol, stripping method and stockpile locations. | Prior to commencement | Document Review |  | Written confirmation | Site Engineer
2 | Topsoil | W | Areas to be top soiled must be ripped to 150mm deep before spreading topsoil to allow mixing between layers | Daily | Visual inspection |  | Photos | Site Engineer
|  | W | Topsoil to be placed to a compacted depth of 150mm and track rolled/lightly compacted | Daily | Visual inspection | Design Engineer to randomly check depth of topsoil for compliance | Photos | Site Engineer | Design Engineer
3 | Survey As Built | H | Ensure cut/fill slopes comply with design after topsoil placement | After placing topsoil | Measurement |  | Survey receipt | Site Engineer
4 | Weed Removal |  | All areas to be covered in topsoil are to be thoroughly cleared of weeds using a combination of mechanical/clearance. The use of glyphosphate herbicide is to be approved by the Engineer. |  |  |  | Photos | Site Engineer
5 | Grassing | W | Grass seed shall be Avanex™ Bird deterrent endophytic grass or similarly approved by NAL. | Prior to commencement | Document Review |  | Written approval of product from NAL. | Site Engineer
|  | W | Areas to be grassed shall be sown with the specified grass seed at a rate of 1 kg to 30 square metre. Successful establishment shall be a 95% growth of a satisfactory sward. | Daily | Visual inspection | if necessary oversowing shall be carried out at the Contractors expense | Delivery Dockets | Site Engineer
6 | Hydro seeding | W | Hydro seeding or drill seeding shall be undertaken to sow the grass seed depending on the time of year, and based on the experience of the Principal and Contractor | Prior to commencement | Document Review |  | Photos | Site Engineer
|  | W | Hydro seed mix is applied by the sub-contractor to get an even coverage and the product produces grass | Daily | Visual inspection | Any areas that don’t take are to be redone at the sub-contractors expense | Delivery Dockets | Site Engineer
7 | Practical Completion | W | Practical completion of turf works shall not be granted until: Grassed areas have a healthy and vigorously growing grass sward | At completion of works | Visual inspection | Hold Point Released | Engineer approval | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date: