## ITS Installation
|  |  |  | Process Control Plan |  | FHIMS-QA-6095 | Approved |  | Signature
|  |  |  | Contract Name: | NAL Apron Upgrade |  | FH Engineer |  | Thomas Powell
|  |  |  | Procedure: | ITS Installation |  | FH Quality Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | (insert contract name suffix)-CS-7095 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Confirm with engineer if existing GPU's are to be retained, moved or removed and locations of New GPU's | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Survey Setout | H | Survey existing GPU's, mark out new GPU's and identify underground feeds. | Prior to commencement | Survey | Identify where new and existing services may clash | Survey receipt | Site Engineer
3 | Locate existing services | H | Ensure all services are marked with paint and/or pegs and use hydrovac to locate where not sure of depth. | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | As-built Drawings Doc. Review | Site Engineer
4 | Material Compliance |  | All new cable ducts shall be Electrical Heavy Duty type to AS 2053 coloured orange | Prior to supplying to site | Visual inspection/ Document review | AS/NZS 3000 | Delivery dockets
5 | Duct Installation | H | Complete checksheet for Duct installation | During Construction | Visual and measurement | Complete for each run between pull pit/jointing chamber | FHIMS-CS-4048 | Site Engineer
6 | Joint Chamber/Pull Pit Installation | H | Complete checksheet for chamber and pit installation | During Construction | Visual and measurement | Complete form for each Pull Pit or Jointing Chamber installed | FHIMS-CS-4072 | Site Engineer
7 | Survey As Built | H | Ensure all ducts are picked up every 10m before backfilling commences | During Construction | Measurement |  | Survey receipt | Site Engineer
8 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Principals Rep : |  |  |  |  | Signature: |  |  | Date: