## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Surfacing | itp |  |  |  |  | ITP - Surfacing
section | PCP - Asphalt - Surfacing
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Provide vendor’s certified test reports for all bituminous material proposed to be used on Site for approval by Engineer
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
checkpoint | 2 - Pre seal inspection
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Inspect surface before Prime coat to determine application rate and allow for inspection
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - The surface should have no free water, and the moisture content should not be less than 2% below the modified optimum moisture content as determined for the material.
label | RECORDS - Photos
checkpoint | 3 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bituminous primer
label | FREQUENCY - Prior to commencement
label | INSPECTION - submission
label | CONFORMANCE CRITERIA - CRS 60 emulsion product complying with NZTA M02 and base binder confirming with NZTA M/1 2020 unless otherwise approved by the Engineer.
label | RECORDS - Testing documentation, confirmation of acceptance by Engineer
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Aggregates, all aggregates used should comply with section 10.6 of the contract specifications, unless changed in Risk register.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - The Contractor shall supply test certificates for all aggregate fractions proposed for use in the Works. The test certificates shall cover all test properties specified in Table 10.1 and Table 10.2 for each aggregate fraction and shall not be more than one month old. The test certificates specified above shall be submitted to the Engineer not less than 5 working days prior to the commencement of mix design and this shall constitute a Hold Point.
label | RECORDS - Testing documentation, confirmation of acceptance by Engineer
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Bituminous Materials. As outlined in section 10.7 of contract specifications or amended in Risk register. Witness point
label | FREQUENCY - Prior to commencement
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - The source/s from which all bituminous materials are to be obtained, the details of the manufacturer/s and the manufacturing process/es and test results for each material indicating full compliance with this Specification shall be supplied to the Engineer 5 working days prior to the date on which the laboratory asphalt mix design is commenced.
label | RECORDS - Testing documentation, confirmation of acceptance by Engineer
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Binder content
label | FREQUENCY - Prior to commencement
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - Binder content should comply with the target values set out in Table 10.4 of section 10.8 of the contract specifications.
label | RECORDS - Mix design
checkpoint | 4 - Plant and Equipment
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All plant and equipment should comply with contract specifications 9.4, 10.14 and 10.16 unless changed in risk register. Hold point
label | FREQUENCY - Prior to commencement
label | INSPECTION - submission, visual inspection
label | CONFORMANCE CRITERIA - Prior to movement of any plant on to site of works, submission of daily plant inspection verification checklist.
label | RECORDS - Submissions and records of removal of holds
holdpoint | HOLD POINT
checkpoint | 5 - Ashphalt Mix Design (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Comencement of mix design - Witness point
label | FREQUENCY - Prior to mix design comencement
label | INSPECTION - Document review
label | CONFORMANCE CRITERIA - The mix design shall not commence before test results and compliance certificates for the virgin materials have been submitted and compliance of the virgin materials to the Specification has been confirmed.Notify the Principal’s Representative not less than 48 hours prior to commencement of mix designs
label | RECORDS - Confirmation that all virgin materials meet the specifiction
holdpoint | HOLD POINT
checkpoint | 5 - Ashphalt Mix Design (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Mix Design shall conform with sections 10.9 and 10.10 of the contract specifications and then be submitted to the principals reperesentative for approval. Unless ammended in risk register
label | FREQUENCY - Prior to commencement
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - Written advice to Principal’s Representative of the proposed mix design for each nominal size mix including results of the mix design tests and other required information listed in section 10.10.5 of the design specification.
label | RECORDS - Mix Design
holdpoint | HOLD POINT
checkpoint | 6 - Asphalt Production Trial and Testing (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Testing should be undertaken during asphalt production as outlined in section 10.11 of the contract specifications. If Asphalt is not complying with the specifications this should be used as a hold point.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Lab Testing and measurements
label | CONFORMANCE CRITERIA - NZTA M/10, NZTA M/10, ASTM D3203, ASTM D1188
label | RECORDS - Asphalt Plant Certifications and results
holdpoint | HOLD POINT
checkpoint | 6 - Asphalt Production Trial and Testing (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Mixing Plant Calibration Charts - Hold Point
label | FREQUENCY - Prior to Production Mix Trial
label | INSPECTION - Document review, Submission
label | CONFORMANCE CRITERIA - Provide Mixing plant calibration charts to principals Representative
label | RECORDS - Principals Representative confirmation of acceptance
holdpoint | HOLD POINT
checkpoint | 6 - Asphalt Production Trial and Testing (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Commencement of the Production Mix Trial Witness Point
label | FREQUENCY - Prior to Production Mix Trial
label | INSPECTION - Submission
label | CONFORMANCE CRITERIA - Notify the Principal’s Representative not less than 48 hours prior to commencement of Production Mix Trial
label | RECORDS - Evidence of notification
checkpoint | 6 - Asphalt Production Trial and Testing (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - In the Production Mix Trial, the Contractor shall manufacture each nominal mix size to the submitted mix design that was satisfactory to the Principal’s Representative and shall use the nominated mixing plant in order to confirm that the specified mix properties can be achieved in production. Witness Point
label | FREQUENCY - Following production mix trial
label | INSPECTION - Submission of results
label | CONFORMANCE CRITERIA - All test results on each nominal mix size produced in the Production Mix Trial, and Written advice to the Principal’s Representative of any adjustments to the mix which are necessary to achieve the properties of the submitted mix design. As outlined in section 10.12 of the contract specifications.
label | RECORDS - Evidence of notification
holdpoint | HOLD POINT
checkpoint | 7 - Construction Trial (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - 10 or more days before asphalt paving is due to comence, a construction trial shall be undertaken. Sufficient asphalt shall be produced to give two paver runs at least 30 metres long, placed at specified thickness with at least one longitudinal joint. The construction trial shall demonstrate all construction techniques proposed in the methodology. -Hold Point
label | FREQUENCY - Prior to Construction trial
label | INSPECTION - Notification
label | CONFORMANCE CRITERIA - Notice to Principal’s Representative, 48 hours prior to commencement of Construction trial that all resources required for the trial are available and all arrangements required for the trial have been made.
label | RECORDS - Evidence of notification
holdpoint | HOLD POINT
checkpoint | 7 - Construction Trial (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The construction trial shall not commence until acceptable plant calibration charts, as adjusted where necessary, following the plant mix trial are provided for inspection by the Principal’s Representative
label | FREQUENCY - Prior to Construction trial
label | INSPECTION - Submission
label | CONFORMANCE CRITERIA - Mixing Plant Calibration charts are submitted to pricipals representative.
label | RECORDS - Evidence of notification
holdpoint | HOLD POINT
checkpoint | 7 - Construction Trial (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Testing of Asphalt - The Contractor shall sample and test the asphalt produced in the production trial
label | FREQUENCY - During Asphalt production
label | INSPECTION - Lab Testing
label | CONFORMANCE CRITERIA - In accordance with Section 10.18 of the contract specifications, except that the Contractor shall take and test not less than three representative samples of each nominal mix size taken at approximately the quarter points in the production trial and in accordance with M/10.
label | RECORDS - Testing results
checkpoint | 7 - Construction Trial (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Placing, Compaction, Finishing and testing of Asphalt for Trial shall be in accordance with section 10.13.3 of the contract specifications. - Hold point
label | FREQUENCY - During and following construction trial
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - All test results on each nominal mix size produced, placed compacted and finished in the Construction trials, and, if required, Written advice to the Principal’s Representative of any alterations in procedures or adjustments to the plant and equipment as necessary to produce asphalt in accordance with this Specification.
label | RECORDS - Evidence of notification
holdpoint | HOLD POINT
checkpoint | 8 - Final Job Mix Approval
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Following completion of the construction trials Complete details of the ‘Job Mix’, the ‘Job Aggregate Particle Size Distribution’, the ‘Job Bitumen Content’ and the ‘Job Mix Temperature’ for each nominal mix size should be submitted to the princials representative
label | FREQUENCY - Following construction trial
label | INSPECTION - Submission of results
label | CONFORMANCE CRITERIA - At lest 2 days prior to the planned commencement of the works
label | RECORDS - Evidence of release of hold point
holdpoint | HOLD POINT
checkpoint | 9 - Weather Limitations
label | DETAIL - Ensure there is a clear weather window when Prime coating is scheduled.
label | FREQUENCY - Prior to Prime Coating
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - The prime coat shall be applied only when the surface temperature is at least 10°C and is expected to remain in excess of 10°C for the duration of the application of the prime coat. Spraying shall not proceed when rain has been forecast, or is likely to occur, and may cause damage to the prime coat.
label | RECORDS - Weather forecast
checkpoint | 10 - Bituminous Prime Coat (1)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Prime coat should be applied and maintained in accordance with sections 9.8 - 9.10 of the contract specifications.
label | FREQUENCY - During Construction
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - sections 9.8 - 9.10 of the contract specifications
label | RECORDS - Photos
checkpoint | 10 - Bituminous Prime Coat (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Spraying Records
label | FREQUENCY - During and Following prime coating
label | INSPECTION - Submission
label | CONFORMANCE CRITERIA - The record shall include:
label | – The location and date of the spray run,
label | – The temperature of the primer immediately before spraying,
label | – The tank dipping before and after each spray run,
label | – The surface temperature,
label | – The calculated application rate of primer at the spraying temperature and
label | – Any other pertinent information.
label | RECORDS - Spraying record
holdpoint | HOLD POINT
checkpoint | 11 - Selection of Reference Area for Surface Finish
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - the Principal’s Representative and Contractor will select a Reference Area/s that have the surface finishes at joints and not at joints that both considers to be the standard that are compliant with the Specification and are to be achieved in the Works.
label | FREQUENCY - Prior to construction of surfacing Asphaltic Concrete
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Written agreement by Contractor, including photographs of the Reference Areas for each nominal size mix.
label | RECORDS - Evidence of release of hold point
holdpoint | HOLD POINT
checkpoint | 12 - Tack Coat
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - A tack coat of bitumen emulsion shall be applied to all existing surfaces on or against which asphalt is to be placed including the edges of all joints except hot joints.
label | FREQUENCY - Prior to placing Surfacing AC
label | INSPECTION - Lab Testing and measurements
label | CONFORMANCE CRITERIA - Tack coat should be applied in compliance with section 10.21 of the contract specifications or as modified in Risk Register.
label | RECORDS - Subcontractor QA Records
holdpoint | HOLD POINT
checkpoint | 13 - Construction of Surfacing Asphaltic Concrete (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Site team QA Checks, Routine sampling and testing of asphalt for compliance with the specified test properties shall be carried out by the Contractor
label | FREQUENCY - During Construction
label | INSPECTION - Site Measurements
label | CONFORMANCE CRITERIA - The frequency of sampling and testing shall be not less than 1 test per 200 t or a minimum of two (2) tests per construction shift
label | RECORDS - QA Records and testing results
holdpoint | HOLD POINT
checkpoint | 13 - Construction of Surfacing Asphaltic Concrete (2)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Delivery of Asphalt
label | FREQUENCY - During Construction
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - Delivery of asphalt from the mixing plant to the site shall be in accordance with the requirements of M/10 and as specified in section 10.19 of the contract specifications
label | RECORDS - Planning Documents that show compliance
checkpoint | 13 - Construction of Surfacing Asphaltic Concrete (3)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Asphalt should be laid and rolled
label | FREQUENCY - During Construction
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - in compiance with section 10.22, 10.23, 10.26, 10.27, 10.28 of the contract specifications
label | RECORDS - Photos and other evidence of compliance
checkpoint | 14 - Layer checksheets
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Each shift the Pavement Layers Checksheet FHIMS-CS-4055 is to be filled in and approved by the Quality Manager
label | FREQUENCY - At completion of each shift
label | INSPECTION - Document and result review
label | RECORDS - FHIMS-CS-4055
holdpoint | HOLD POINT
checkpoint | 15 - Surface Smoothness Testing
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - A Witness Point shall be designated at the completion of pneumatic tyred rolling and prior to surface smoothness testing and at the completion of smoothness testing.
label | FREQUENCY - Prior to Opening to Traffic
label | INSPECTION - NAASRA Test
label | CONFORMANCE CRITERIA - Testing should be undertaken as outlined in section 10.27.10 of the contract specification and meet the requirements set out in 10.27.9
label | RECORDS - Surface Smoothness testing records
checkpoint | 16 - Density and ThicknessTesting
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Cutting of cores and density testing should be undertaken in compliance with sections 10.24 and 10.25 of the project specifications unless ammended in Risk Register
label | FREQUENCY - Following Construction
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - Cores shall be cut from layers of compacted asphalt in accordance with the requirements of M/10 and as specified herein.
holdpoint | HOLD POINT
checkpoint | 17 - Cleaning of Pavements Witness Point
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure Clean prior to handover
label | FREQUENCY - Following all construction and testing
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - The pavements shall be swept, and/or vacuumed clean by mechanical brooms, suction sweepers, hand brooming and/or other means, such that an acceptable standard of cleanliness is met before the pavement is opened for aircraft operations.
label | RECORDS - Approval documentation for witness point
checkpoint | 18 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All finished surface levels shall be surveyed by precise levelling to an accuracy of 2 mm with readings to 1 mm and the survey shall be undertaken under the control of a licensed surveyor.
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | CONFORMANCE CRITERIA - The survey results shall be submitted to the Engineer in a format agreed with the Engineer.
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Basecourse | itp |  |  |  |  | ITP - Basecourse
section | PCP - Basecourse Construction
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Survey Model produced and benchmarks installed. Grader benching to be confirmed on a daily basis
label | FREQUENCY - Each shift
label | INSPECTION - Measure, Survey
label | CONFORMANCE CRITERIA - Random checks to be undertaken by survey to ensure grader control is working correctly
label | RECORDS - FHIMS-CS-4103
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Aggregate material sample of Subbase
label | FREQUENCY - MIN 7 days prior to commencement
label | INSPECTION - Sample
label | CONFORMANCE CRITERIA - 20kg minimum
label | RECORDS - Sign ITP
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (2)
label | DETAIL - Source Grading
label | FREQUENCY - 1 test a MIN 7 days prior to commencement & 1 test per day of production thereafter
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (3)
label | DETAIL - Source Broken Faces
label | FREQUENCY - MIN 7 days prior to commencement and 1 test per day of production thereafter
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (4)
label | DETAIL - Source Flakiness Index
label | FREQUENCY - MIN 7 days prior to commencement
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (5)
label | DETAIL - Source Bearing strength (soaked CBR)
label | FREQUENCY - 1 test a MIN 7 days prior to commencement & 1 test per 1000m3 overall
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (6)
label | DETAIL - Source Crushing resistance
label | FREQUENCY - 1 test a MIN 7 days prior to commencement & 1 test per 1000m3 overall
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (7)
label | DETAIL - Source Weathering resistance
label | FREQUENCY - MIN 7 days prior to commencement
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 8.1 , 8.4.2 Project specification, NZTA M04 (2006)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (8)
label | DETAIL - Source clay Index
label | FREQUENCY - MIN 7 days prior to commencement & 1 test per 1000m3 thereafter
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - shall be less than 3, NZS4407 Test 3.5
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (9)
label | DETAIL - Source Plasticity Index
label | FREQUENCY - MIN 7 days prior to commencement & 1 test per 1000m3 thereafter
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - LL less than 25 & PI less than 6
label | RECORDS - Engineer approval
checkpoint | 4 - Basecourse Construction (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Plant selection agreed upon that won't overstress pavement layers below
label | FREQUENCY - Prior to layer construction
label | INSPECTION - review
label | CONFORMANCE CRITERIA - engineers agreeance
label | RECORDS - Email
holdpoint | HOLD POINT
checkpoint | 4 - Basecourse Construction (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Plateau Density Testing for Subbase Layer
label | FREQUENCY - Min. 1 initially
label | INSPECTION - NDM Lab Testing
label | CONFORMANCE CRITERIA - To establish roller pattern
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 4 - Basecourse Construction (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | FREQUENCY - During construction
label | INSPECTION - Visual Inspection
label | RECORDS - Photos
checkpoint | 4 - Basecourse Construction (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Degree of Compaction
label | FREQUENCY - 5 per 1000m2 max
label | INSPECTION - NDM Lab Testing
label | CONFORMANCE CRITERIA - Avg. >= 99% MDD and Min. >= 95% MDD
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 4 - Basecourse Construction (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Benkelman Beam Testing
label | FREQUENCY - Minimum 20 tests/1000m2 (5*5m grid)
label | INSPECTION - Benkelman Beam Test
label | CONFORMANCE CRITERIA - 90th percentile result less than 1.5mm
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 4 - Basecourse Construction (6)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Finished surface shape check, submitted to engineer 1 working day prior to overlying layer
label | FREQUENCY - 5*5m grid survey, plotted with contours to scale 1:500
label | INSPECTION - Measurement
label | CONFORMANCE CRITERIA - Engineers approval
label | RECORDS - Correspondance
holdpoint | HOLD POINT
checkpoint | 4 - Basecourse Construction (7)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Surface finish check
label | FREQUENCY - Prior to sealing
label | INSPECTION - Visual inspection by Design Engineer after site sweeping
label | CONFORMANCE CRITERIA - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | RECORDS - FHMIS-CS-4060
holdpoint | HOLD POINT
checkpoint | 5 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure correct no. of test sets performed for pavement testing as per Specifications
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 6 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Taxiway Lighting | itp |  |  |  |  | ITP - Taxiway Lighting
section | PCP - Ground Lighting
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Isolation Procedures
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure All AGL circuits entering the site are isolated and where possible pulled out of ducts that enter the work site.
label | ○ Provide insulation resistance test results for all existing AGL circuits that are to be retained at the completion of the works (including those unmodified by the project).
label | FREQUENCY - Prior to commencement and then monthly testing
label | INSPECTION - Visual Inspection and testing
label | CONFORMANCE CRITERIA - All CCRs are lockedout to prevent accidental reinstatement.
label | RECORDS - Insulation resistance test results, photos of isolated CCRs, Contract witness Point
checkpoint | 3 - Existing light Survey
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Prior to any pavement works, all lights, SITs and light bases affected by the reconstruction works shall be surveyed. Survey should include:
label | – Location;
label | – Orientation (deviation angle);
label | – Colour pattern;
label | – Circuit;
label | – Labelling; and
label | – Secondary cable route between the light and its associated SIT pit.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - The survey shall be undertaken using the coordinate system employed in the design drawings. Any discrepancy in the survey with the design set out information shall be brought to the attention of the Contract Administrator for resolution in accordance with clause 6.11 of the Conditions of Contract.
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 4 - Existing Light Removal
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Prior to any pavement works, all lights and SITs and light bases affected by the reconstruction works shall be removed and replaced with provided temporary red lights, adjacent to the red barriers as outlined on the drawings.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual Inspection
label | RECORDS - Photographs
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirm the location of all existing underground cables and services on site and mark them out with stakes.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | RECORDS - Survey record
holdpoint | HOLD POINT
checkpoint | 6 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Pipes to be encased in concrete as part of Duct Bank works shall be Class 12 PVC pipes.
label | FREQUENCY - Prior to supplying to site
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - Drawings,Pipes to AS/NZS 61386.1 or heavy-duty rigid conduit to AS/NZS 61386.1.
label | RECORDS - Delivery dockets
holdpoint | HOLD POINT
checkpoint | 6 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - All new cable ducts shall be Electrical Heavy Duty type to AS 2053 coloured orange
label | FREQUENCY - Prior to supplying to site
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - AS/NZS 3000
label | RECORDS - Delivery dockets
checkpoint | 6 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Concrete
label | FREQUENCY - Prior to supplying to site
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - Concrete for duct banks should comply with section 15.3.2 of the contract specification.
label | RECORDS - Manufacturers certificate, delivery dockets
checkpoint | 6 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Inspect any Cable sand Delivered to site to ensure it meets criteria. The sand shall be clean and free of organic matter or sharp stones.
label | FREQUENCY - On arrival at site
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - The bedding material shall be finely divided sand which contains at least 90% by mass passing a 2.37 mm sieve and not more than 15% by mass passing a 0.075 mm sieve.
label | RECORDS - Delivery dockets, Lab testing
checkpoint | 7 - Trenching in Under Ground Cables
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Where the new ducts are in the proximity of existing cables/duct, they should be seperated horizontaly by at least 1m. Excavations should be deep enough to provide a minimum cover of 750mm.
label | FREQUENCY - Across Each Trench
label | INSPECTION - Visual inspection, measurement
label | CONFORMANCE CRITERIA - Depth and distance measurements
label | RECORDS - Photographs
holdpoint | HOLD POINT
checkpoint | 8 - Bedding of services
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - If the excavated soil is not compatible material free of rocks, or will not pass through a 25 mm sieve then:
label | – The bottom of the trench shall comprise a bed of 50 mm of sand placed before the first enclosure or cable is laid, and,
label | – A layer of sand shall be placed to cover the conduit with 75 mm of sand before backfilling.
label | FREQUENCY - Across Each Trench
label | INSPECTION - Visual inspection, measurement
label | RECORDS - Lab testing, Photographs
holdpoint | HOLD POINT
checkpoint | 9 - Duct Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Inspect all ducts before concrete is poured to ensure they are clean and free from burrs. Installation of ducts should comply with Section 15.2.2 of the project specification.
label | CONFORMANCE CRITERIA - Witness point
label | RECORDS - Photographs
holdpoint | HOLD POINT
checkpoint | 10 - Laying cable, ducts, pits and installing light foundations (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - When crossing existing cables
label | FREQUENCY - Whenever crossing existing cables
label | INSPECTION - Testing
label | CONFORMANCE CRITERIA - New Cables/ ducts must be:
label | – Crossing below existing with a minimum vertical separation of 100mm
label | – Provide at least 50mm of new bedding material above and below the existing cables.
label | – The bedding material shall extend 100mm beyond the edge of the outside cables.
label | – IR test the affected direct buried circuits immediately after the backfill to ensure the existing cables were not damaged during excavation.
label | RECORDS - Test results and Photographs
holdpoint | HOLD POINT
checkpoint | 10 - Laying cable, ducts, pits and installing light foundations (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All pit installations and amendments should occur in compliance with section 15.5 of the specification.
label | FREQUENCY - During installation or amendment
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Section 15.5 of speciifications
label | RECORDS - Photographs, ITS Pit Intallation Checksheet
holdpoint | HOLD POINT
checkpoint | 10 - Laying cable, ducts, pits and installing light foundations (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - 150 mm wide PVC marker tape bearing the words "Caution - Buried Electric Cables Below" shall be laid above all new cable ducts for their entire length.
label | FREQUENCY - Across each trench
label | INSPECTION - Visual inspection
label | RECORDS - Photographs
holdpoint | HOLD POINT
checkpoint | 11 - Duct Installation
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Complete checksheet for Duct installation
label | FREQUENCY - During Construction
label | INSPECTION - Visual and measurement
label | CONFORMANCE CRITERIA - Complete for each run between pull pit/jointing chamber
label | RECORDS - FHIMS-CS-4048
holdpoint | HOLD POINT
checkpoint | 12 - Joint Chamber/Pull Pit Installation
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Complete checksheet for chamber and pit installation
label | FREQUENCY - During Construction
label | INSPECTION - Visual and measurement
label | CONFORMANCE CRITERIA - Complete form for each Pull Pit or Jointing Chamber installed
label | RECORDS - FHIMS-CS-4072
holdpoint | HOLD POINT
checkpoint | 13 - Backfilling cable trenches
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - When not under pavement Compaction testing should be undertaken at a rate of 1 test per 400m of conduit laid per 0.5m of backfill depth (minimum 3).
label | ○ Compaction Testing under pavements shall be carried out every 25m and every 0.5m lift.
label | FREQUENCY - Along Each Trench
label | INSPECTION - Clegg testing
label | CONFORMANCE CRITERIA - Where trenches are under constructed pavements and shoulders, or generally in dry conditions, the backfill shall be compacted to a relative dry density of not less than 95% of maximum dry density (test No. 5.1.1 of AS1289) in the case of cohesive material, or 75% Density Index (test No. E6.1 of AS1289) in the case of cohesionless material.
label | RECORDS - Clegg testing results form
holdpoint | HOLD POINT
checkpoint | 14 - Testing
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Testing to be carried out by Subcontractor and approved Test sheets to be completed. (min. 1 per supply box)
label | FREQUENCY - Upon completion of installing lights
label | INSPECTION - Test results
label | CONFORMANCE CRITERIA - Specification requirements
label | RECORDS - Subcontractor QA forms and certificate of compliance
holdpoint | HOLD POINT
checkpoint | 15 - Commissioning
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Demonstrating that specific Commissioning requirements details in the Specification have been complied with.
label | FREQUENCY - Upon completion of installing lights
label | INSPECTION - Document review / Testing
label | CONFORMANCE CRITERIA - Road lighting Specification Section 8
label | RECORDS - Subcontractor QA forms and certificate of compliance
holdpoint | HOLD POINT
checkpoint | 16 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Provide complete As-builts of both existing and Installed cables and ducts.
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Road Marking | itp |  |  |  |  | ITP - Road Marking
section | PCP - Road Marking
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Survey Setout (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The Contractor must set out the Pavement Markings as shown on the Drawings as soon as ashphalt works are completed. The setting out of the Pavement Marking must be undertaken by a competent the Engineering surveyor, having qualifications that meet the pre-requisites for becoming a licensed surveyor, and who is experienced in this type of survey work.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - The precision of the survey for the new markings must be such that the finished markings are located to a horizontal accuracy of ± 25 mm. The lines to be painted shall be marked out by the Contractor with chalk and approved by the Principal’s Representative prior to painting.
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 2 - Survey Setout (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Survey work must include spotting of the pavement, as required, to locate and define the extent of the new markings in sufficient detail for the painting of the required markings to the tolerances specified.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual check of spots before painting the lines
label | CONFORMANCE CRITERIA - Spots shall be at a spacing of 10m or less on curves. For new marking with respect to specified location: Transverse location -+20mm, Longitudinal location -+50mm. All lines shall appear by eye to be straight, or where designed as a curve, curve is smooth between each transition from straight to curve.
label | RECORDS - QA Records
checkpoint | 3 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Paint
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - Comply with specifications set out in section 17.3 of the contract specifications, FHIMS-CS-4021- Line Marking Materials Checksheet.
label | RECORDS - Manufacturing certificates, delivery dockets and checksheet
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Glass Beads
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - AS/NZS 2009: 2006 Glass Beads for Road-Marking Materials.
label | RECORDS - Manufacturing certificates, delivery dockets and checksheet
holdpoint | HOLD POINT
checkpoint | 4 - Removal of dirt and contaminants from pavement surfacing
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The surface of the asphalt or concrete pavement in the areas to be painted must be thoroughly cleaned prior to the application of the pavement marking paint.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - As outlined in Section 17.5.2 of the contract specifications.
label | RECORDS - Photographs and QA documentation
holdpoint | HOLD POINT
checkpoint | 5 - Removal of Redundant Pavement Markings
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All redundant pavement markings shall be removed. The surface of existing painted markings must be thoroughly cleaned prior to repainting. All existing paint that is not strongly adhering to the pavement must be removed prior to re-painting.
label | FREQUENCY - Prior to marking
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - The shape of the old markings can not be distinguished. The final surface texture is similar to the surrounding pavement. "Blackout out" of pavement markings is not allowed in this contract.
label | RECORDS - Photographs and QA documentation
holdpoint | HOLD POINT
checkpoint | 6 - Quality Assurance Requirements
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Evidence of an approved quality system shall be provided to the Principal prior to pavement marking activities commencing.
label | FREQUENCY - Daily
label | INSPECTION - Collating information on a daily basis
label | CONFORMANCE CRITERIA - An approved pavement marking quality system shall include one of the following options:
label | ○ Certification to Road markers Federation’s Quality Assurance Programme (QAP); or
label | ○ Certification to JAS-ANZ accredited certifying body to ISO 9002 including the criteria of the NZRF QAP Specification and Guidelines; or
label | ○ Certification by JAS-ANZ accredited certifying body to the criteria of the NZRF QAP Specification and Guidelines, with the certification policy to be approved by TNZ.
label | RECORDS - Subcontractor QA Records
holdpoint | HOLD POINT
checkpoint | 7 - Plant Records
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Plant shall have current certificates of compliance.
label | CONFORMANCE CRITERIA - in accordance with NZTA T/12 or NZTA T/8 as applicable
label | RECORDS - QA Records/ Certificates
holdpoint | HOLD POINT
checkpoint | 8 - Paint Marking
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Paint application should comply with sections 17.5.1 and 17.5.3 of the contract specifications.
label | FREQUENCY - During pavement marking
label | INSPECTION - Visual inspection
label | RECORDS - Photographs and Subcontractor QA Records
checkpoint | 9 - Application Rates
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - The paint must be applied in two (2) even coats to give a minimum total dry film thickness of 120 microns. Film thickness is measured on steel plates
label | FREQUENCY - Min of 2 per day and after pressure or speed settings are changed
label | INSPECTION - Test
label | CONFORMANCE CRITERIA - TNZ P/12 Appendix A gives details of the plate test
label | RECORDS - Subcontractor QA Records
holdpoint | HOLD POINT
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Drainage | itp |  |  |  |  | ITP - Drainage
section | PCP - Stormwater Drainage
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Set out Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Pinciple inspection after setting out of work where concrete operations will occur.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Visual inspection
label | RECORDS - Written confirmation from Principles Rep
checkpoint | 3 - Foundation Scala Penetrometer Record
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Record ' Scala Penetrometer' to be completed,
label | FREQUENCY - 1 per 20m of trench and 1 at structures
label | INSPECTION - Submission
label | CONFORMANCE CRITERIA - Confirm the undisturbed subgrade preperation has a greater than 50 kPa bearing strength. Test to 400mm depth minimum
label | RECORDS - Record Completed
checkpoint | 4 - Materials (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Granular Bedding Material
label | FREQUENCY - On ordering and on arrival at site
label | INSPECTION - Visual, testing
label | CONFORMANCE CRITERIA - All bedding material shall be approved by the Engineer and unless otherwise stated follow the specification set out in section 12.2.1.1 of the contract specification.
label | RECORDS - Dockets
checkpoint | 4 - Materials (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Aggregate Concrete Bedding
label | FREQUENCY - On ordering and on arrival at site
label | INSPECTION - Visual, testing
label | CONFORMANCE CRITERIA - All Aggregate concrete bedding should be in coompliance with section 12.2.1.2 of the contract specification.
label | RECORDS - Deliver dockets and testing
checkpoint | 4 - Materials (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Pipes, fittings and Joints
label | FREQUENCY - Prior to laying / placing
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - All pipes, fittings and joints should comply with sections 12.2.2 and 12.2.3 of the contract specifications.
label | RECORDS - Supply Dockets and Photographs
checkpoint | 4 - Materials (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Unless otherwise stated, other drainage structures shall be constructed of reinforced concrete
label | FREQUENCY - Each Structure
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - NZS3109, NZS3124, Concrete Specification and the concrete shall have a minimum crushing strength of 17.5 Mpa at 28 days. Anchor blocks shall be constructed of reinforced concrete as per above.
label | RECORDS - Supply Dockets, testing and Photographs
checkpoint | 4 - Materials (5)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Precast manholes are to be used unless specified otherwise on the contract drawings.
label | FREQUENCY - Each Structure
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - Manholes and their components should comply with section 12.2.4 of the Contract specifications
label | RECORDS - Record Complete
checkpoint | 4 - Materials (6)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Cesspits, Unless otherwise stated all catchpits shall be precast reinforced concrete
label | FREQUENCY - Each Structure
label | INSPECTION - Visual
label | CONFORMANCE CRITERIA - NZS3109, contract drawings and Section 12.2.5 of the contract specifications
label | RECORDS - Supply Dockets and Photographs
checkpoint | 4 - Materials (7)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Materials for concrete, Cement and Aggregates
label | FREQUENCY - Every pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Cement shall be ordinary Portland cement conforming to NZS3122: 1977. Rapid hardening Portland cement shall only be used with the approval of the Engineer.Aggregates shall comply with NZS3121: 1980. Coarse aggregate shall be 20 mm maximum, except aggregate for concrete block filling, which shall be 13.2 mm maximum.
label | RECORDS - Deliver dockets and testing
checkpoint | 4 - Materials (8)
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Supply of concrete shall be from A ready mixed concrete plant
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Plant must hold either a current High or Special Grading complying with NZS3104 and 3109.
label | RECORDS - Copies of certification
checkpoint | 5 - Construction (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - All reticulation works, including laying of new lines and reinstatement of existing systems are to be carried out by, or under the supervision of a registered drainlayer to current trade certificate practices.
label | FREQUENCY - Before Comencement
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Unless otherwise specified all construction shall comply with NZS 4452,AS/NZS 3725, and AS/NZS 1260
label | RECORDS - Copies of qualifications
holdpoint | HOLD POINT
checkpoint | 5 - Construction (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All bedding shall be placed and compacted to ensure the pipe is evenly supported over the entire length
label | FREQUENCY - Each structure and pipe
label | INSPECTION - Initial Inspection and follow up photographic evidence.
label | CONFORMANCE CRITERIA - All Concrete and granular bedding should comply with section 12.3.2 of the contract specifications.
label | RECORDS - FHIMS-CS-4025 Drainage Line Record
checkpoint | 5 - Construction (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - All foundations require inspection by the Principal or Principals Representative during Concrete Operations
label | FREQUENCY - Prior to commencement of formwork and rienforcing
label | INSPECTION - Visual inspection
label | RECORDS - Written confirmation from Principles Rep
checkpoint | 5 - Construction (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Laying and Jointing Pipes
label | FREQUENCY - Each structure and pipe
label | INSPECTION - Initial Inspection and follow up photographic evidence.
label | CONFORMANCE CRITERIA - Concrete pipes shall be installed to NZS/AS 3725, uPVC pipes shall be installed to AS/NZS 1260. All laying and Jointing of pipes should comply with section 12.3.2 of the contract specifications.
label | RECORDS - FHIMS-CS-4025 Drainage Line Record
checkpoint | 5 - Construction (5)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Drainage Structures. Manholes, inspection chambers or other drainage structures shall be constructed as per standard drawings.
label | FREQUENCY - Each structure and pipe
label | INSPECTION - Initial Inspection and follow up photographic evidence.
label | CONFORMANCE CRITERIA - Drainage structures shall be installed to section 12.3.4 of the contract specifications.
label | RECORDS - FHIMS-CS-4025 Drainage Line Record
checkpoint | 5 - Construction (6)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - An ispection is required by the Principal or Principals Representative after completion of formwork prior to placement of reinforcing/concrete and after completion of reinforcing.
label | FREQUENCY - Before Each Pour
label | INSPECTION - Site Inspection
label | CONFORMANCE CRITERIA - Concrete Pre-Pour Checklist completed prior to concrete pour, also complete FHIMS-CS-4029 - concrete pump - permit to pump, if required. Form work should comply with NZS3109
label | RECORDS - FHIMS-CS-4008 - Concrete Inspection Record, Written confirmation from Principles Rep
holdpoint | HOLD POINT
checkpoint | 5 - Construction (7)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - An ispection is required by the Principal or Principals Representative after completion of concrete and installation of construction joints
label | FREQUENCY - Before Each Pour
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Engineer Approval
label | RECORDS - Written confirmation from Principles Rep at each stage
holdpoint | HOLD POINT
checkpoint | 6 - Tolerances
label | ACTION (Hold, Monitor, Witness) - M
label | DETAIL - Before backfilling comences a survey inspection should be undertaken to ensure Manholes and pipelines are withing allowed tollerances.
label | FREQUENCY - During construction
label | INSPECTION - Measure
label | CONFORMANCE CRITERIA - All manholes and pipelines should be within the horizontal and zvertical tollerances outlined in section 12.4.1 of the contract specifications.
label | RECORDS - Survey receipt
checkpoint | 7 - Layer Depth
label | ACTION (Hold, Monitor, Witness) - W
label | FREQUENCY - Layer depth as Required
label | INSPECTION - Review
label | CONFORMANCE CRITERIA - Placement of backfill must not exceed an uncompacted thickness of 200mm for AP20 and 200mm for AP65
label | RECORDS - Onsite Inspections
checkpoint | 8 - Backfill Testing Regime
label | ACTION (Hold, Monitor, Witness) - W
label | FREQUENCY - Clegg test 1 per layer every 30m
label | INSPECTION - Photographs to be supplied witnessing each layer lift.
label | ○ Photographs to be supplied witnessing each layer lift
label | CONFORMANCE CRITERIA - Testing must be carried out on the first backfill layer with subsequent layers tested as required. Compacted layer depth no less than 2.5 times the maximum filling aggregate size
label | RECORDS - Record Complete
checkpoint | 9 - Presure Testing
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Complete low pressure Air testing and associated record
label | FREQUENCY - Each Line
label | INSPECTION - Submission, test
label | CONFORMANCE CRITERIA - Engineer/witness to be present when completing final acceptance pressure testing. Standard NZS 4452
label | RECORDS - Completed FHIMS-CS-4074 - Low Pressure Air Test Record
checkpoint | 10 - Pipeline Camera
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - CCTV Inspection Videos to be Reviewed
label | FREQUENCY - Each Line
label | INSPECTION - Submission
label | CONFORMANCE CRITERIA - Camera to run all pipelines (CCTV). Footage is to be reviewed and be of acceptable standard prior to beginning subbase construction. A final flushed line CCTV footage (prior to asphalting) is required for Engineer and Council records.
label | RECORDS - Record Completed
checkpoint | 11 - As Builts
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - As Builts to be taken with GPS unit during comstruction and provided to engineer at the conclusion of the project
label | FREQUENCY - As Required
label | INSPECTION - Record
label | CONFORMANCE CRITERIA - Record as built
label | RECORDS - Record Completed
checkpoint | 12 - Stage completion inspection
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Inspecytion by engineer to confirm stage complies with specifications
label | FREQUENCY - At completion of stage and before next stage comences
label | INSPECTION - Record
label | CONFORMANCE CRITERIA - As per section 12.4.2 of the project specifications.
label | RECORDS - Email confirming approval has been given for stage completion.
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Subbase | itp |  |  |  |  | ITP - Subbase
section | PCP - Subbase Construction
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Survey Model produced and benchmarks installed. Grader benching to be confirmed on a daily basis
label | FREQUENCY - Each shift
label | INSPECTION - Measure, Survey
label | CONFORMANCE CRITERIA - Random checks to be undertaken by survey to ensure grader control is working correctly
label | RECORDS - FHIMS-CS-4103
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Aggregate material sample of Subbase
label | FREQUENCY - MIN 7 days prior to commencement
label | INSPECTION - Sample
label | CONFORMANCE CRITERIA - 30kg minimum
label | RECORDS - Sign ITP
holdpoint | HOLD POINT
checkpoint | 3 - Material Compliance (2)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Source Grading
label | FREQUENCY - 3 tests a MIN 7 days prior to commencement, 1/500m3 overall
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Table 7.1 , 7.4.2 Project specification
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (3)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Source Broken Faces
label | FREQUENCY - MIN 7 days prior to commencement and 1 test per 500m3 thereafter
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - 70% retained on <37mm sieves to have 2 or more broken
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (4)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Source Bearing strength
label | FREQUENCY - 3 tests a MIN 7 days prior to commencement & 1 per 1000m3 overall
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - soaked CBR of min 35% (NZS 4407, Test 3.15)
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (5)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Source Crushing resistance
label | FREQUENCY - 3 tests a MIN 7 days prior to commencement & 1 per 1000m3 overall
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - less than 10% passing 2.36mm sieve using 130kn load. NZS4407 3.10
label | RECORDS - Engineer approval
checkpoint | 3 - Material Compliance (6)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Source Plasticity Index
label | FREQUENCY - 3 tests a MIN 7 days prior to commencement, 1/500m3 overall
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - LL less than 25 & PI less than 6
label | RECORDS - Engineer approval
checkpoint | 4 - Subgrade separation layer (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Placement of geotextile separation layer
label | FREQUENCY - During construction
label | INSPECTION - review
label | CONFORMANCE CRITERIA - Correct strength 'A34' used and minimum laps installed per NZTA F/7
label | RECORDS - certificate of compliance
holdpoint | HOLD POINT
checkpoint | 4 - Subgrade separation layer (2)
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - Placement of geogrid separation layer
label | FREQUENCY - During construction
label | INSPECTION - review
label | CONFORMANCE CRITERIA - Correct grade Cirtex Gridtex 40/40. Installed to manufacturers specs
label | RECORDS - photos, certificate of compliance
checkpoint | 5 - Subbase Construction (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Plant selection agreed upon that won't overstress subgrade
label | FREQUENCY - Prior to layer construction
label | INSPECTION - review
label | CONFORMANCE CRITERIA - engineers agreeance
label | RECORDS - Email
holdpoint | HOLD POINT
checkpoint | 5 - Subbase Construction (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Engineer approval of geotextile layer
label | FREQUENCY - Prior to layer construction
label | INSPECTION - Lab testing
label | CONFORMANCE CRITERIA - Layer has been signed off
label | RECORDS - Correspondance
holdpoint | HOLD POINT
checkpoint | 5 - Subbase Construction (3)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Plateau Density Testing for Subbase Layer
label | FREQUENCY - Min. 1 initially
label | INSPECTION - NDM Lab Testing
label | CONFORMANCE CRITERIA - To establish roller pattern
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 5 - Subbase Construction (4)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | FREQUENCY - During construction
label | INSPECTION - Visual Inspection
label | RECORDS - Photos
checkpoint | 5 - Subbase Construction (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Degree of Compaction
label | FREQUENCY - 5 per 1000m2 max
label | INSPECTION - NDM Lab Testing
label | CONFORMANCE CRITERIA - Avg. >= 95% MDD and Min. >= 92% MDD
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 5 - Subbase Construction (6)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Benkelman Beam Testing
label | FREQUENCY - Minimum 20 tests/1000m2 (5*5m grid)
label | INSPECTION - Benkelman Beam Test
label | CONFORMANCE CRITERIA - 90th percentile result less than 2.0mm
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 5 - Subbase Construction (7)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Finished surface shape check, submitted to engineer 1 working day prior to overlying layer
label | FREQUENCY - 5*5m grid survey, plotted with contours to scale 1:500
label | INSPECTION - Measurement
label | CONFORMANCE CRITERIA - Engineer Approval
label | RECORDS - Correspondance, FHIMS-CS-4069
holdpoint | HOLD POINT
checkpoint | 5 - Subbase Construction (8)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Surface finish check
label | FREQUENCY - Prior to sealing
label | INSPECTION - Visual inspection by Design Engineer after site sweeping
label | CONFORMANCE CRITERIA - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | RECORDS - FHMIS-CS-4060
holdpoint | HOLD POINT
checkpoint | 6 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure correct no. of test sets performed for pavement testing as per Specifications
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 7 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Subgrade | itp |  |  |  |  | ITP - Subgrade
section | PCP - Subgrade Construction
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Drawings and documents are current
label | RECORDS - Sign ITP
holdpoint | HOLD POINT
checkpoint | 2 - Earthwork Methodology
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Submit Earthworks Method including (proof rolling plan)
label | FREQUENCY - Min 3 weeks prior to commencement
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Engineers approval
label | RECORDS - Correspondence
holdpoint | HOLD POINT
checkpoint | 3 - Cut to Waste
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Earthworks cut to waste
label | FREQUENCY - Prior to Testing
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Unsuitable material removed
label | RECORDS - Photos / Sign ITP
holdpoint | HOLD POINT
checkpoint | 4 - Subgrade testing (1)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Subgrade CBR testing
label | FREQUENCY - 20*20m grid
label | INSPECTION - Scalar
label | CONFORMANCE CRITERIA - Scala result above 4% or 8% depending on pavement area
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 4 - Subgrade testing (2)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Subgrade shear strength
label | FREQUENCY - 20*20m grid
label | INSPECTION - Shear vane
label | CONFORMANCE CRITERIA - >100kpa
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 4 - Subgrade testing (3)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Provide 1 working days notice to engineer ahead of proof roll
label | FREQUENCY - All instances
label | INSPECTION - Submission
label | CONFORMANCE CRITERIA - NTE
label | RECORDS - Correspondence
holdpoint | WITNESS POINT
checkpoint | 4 - Subgrade testing (4)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Site Engineer and Design Engineer to undertake a Proof Roll test on the trimmed subgrade to the approved proof roll plan
label | FREQUENCY - 100% area
label | INSPECTION - Visual Inspection
label | CONFORMANCE CRITERIA - Written record
label | RECORDS - FHIMS-CS-4005 - Proof Roll Checksheet
holdpoint | HOLD POINT
checkpoint | 4 - Subgrade testing (5)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Any subgrade area that does not pass subgrade testing or proof rolling
label | FREQUENCY - Per occurance
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Notify engineer
label | RECORDS - Correspondence
holdpoint | HOLD POINT
checkpoint | 4 - Subgrade testing (6)
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Carry out a Level Check on the trimmed subgrade
label | FREQUENCY - 10*10m grid
label | INSPECTION - straightedge & total station
label | CONFORMANCE CRITERIA - Tolerance = -20mm + 0mm
label | RECORDS - Survey record
holdpoint | HOLD POINT
checkpoint | 3 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure correct no. of test sets performed for pavement testing as per Specifications
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | RECORDS - Pavement Lab Testing Spreadsheet
holdpoint | HOLD POINT
checkpoint | 4 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | FREQUENCY - At completion of Lot
label | INSPECTION - Document Review
label | CONFORMANCE CRITERIA - Ensure all QA is uploaded into M-Files
label | RECORDS - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 5 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Topsoil Re-spread, Grassing & Hydro seeding | itp |  |  |  |  | ITP - Topsoil Re-spread, Grassing & Hydro seeding
section | PCP - Topsoil Re-spread, Grassing & Hydroseeding (ID 67502)
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirm with Engineer the need to separate the topsiol, stripping method and stockpile locations.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Written confirmation
holdpoint | HOLD POINT
checkpoint | 2 - Topsoil (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Areas to be top soiled must be ripped to 150mm deep before spreading topsoil to allow mixing between layers
label | FREQUENCY - Daily
label | INSPECTION - Visual inspection
label | RECORDS - Photos
checkpoint | 2 - Topsoil (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Topsoil to be placed to a compacted depth of 150mm and track rolled/lightly compacted
label | FREQUENCY - Daily
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Design Engineer to randomly check depth of topsoil for compliance
label | RECORDS - Photos
holdpoint | WITNESS POINT
checkpoint | 3 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure cut/fill slopes comply with design after topsoil placement
label | FREQUENCY - After placing topsoil
label | INSPECTION - Measurement
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 4 - Weed Removal
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - All areas to be covered in topsoil are to be thoroughly cleared of weeds using a combination of mechanical/clearance. The use of glyphosphate herbicide is to be approved by the Engineer.
label | RECORDS - Photos
checkpoint | 5 - Grassing (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Grass seed shall be Avanex™ Bird deterrent endophytic grass or similarly approved by NAL.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Written approval of product from NAL.
checkpoint | 5 - Grassing (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Areas to be grassed shall be sown with the specified grass seed at a rate of 1 kg to 30 square metre. Successful establishment shall be a 95% growth of a satisfactory sward.
label | FREQUENCY - Daily
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - if necessary oversowing shall be carried out at the Contractors expense
label | RECORDS - Delivery Dockets
checkpoint | 6 - Hydro seeding (1)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Hydro seeding or drill seeding shall be undertaken to sow the grass seed depending on the time of year, and based on the experience of the Principal and Contractor
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Photos
checkpoint | 6 - Hydro seeding (2)
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Hydro seed mix is applied by the sub-contractor to get an even coverage and the product produces grass
label | FREQUENCY - Daily
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Any areas that don’t take are to be redone at the sub-contractors expense
label | RECORDS - Delivery Dockets
checkpoint | 7 - Practical Completion
label | ACTION (Hold, Monitor, Witness) - W
label | DETAIL - Practical completion of turf works shall not be granted until: Grassed areas have a healthy and vigorously growing grass sward
label | FREQUENCY - At completion of works
label | INSPECTION - Visual inspection
label | CONFORMANCE CRITERIA - Hold Point Released
label | RECORDS - Engineer approval
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP
checklist | ITP - Utilities | itp |  |  |  |  | ITP - Utilities
section | PCP - Utility Installation
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Confirm with engineer if existing GPU's are to be retained, moved or removed and locations of New GPU's
label | FREQUENCY - Prior to commencement
label | INSPECTION - Document Review
label | RECORDS - Check Drawing Register
holdpoint | HOLD POINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Survey existing GPU's, mark out new GPU's and identify underground feeds.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Survey
label | CONFORMANCE CRITERIA - Identify where new and existing services may clash
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 3 - Locate existing services
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all services are marked with paint and/or pegs and use hydrovac to locate where not sure of depth.
label | FREQUENCY - Prior to commencement
label | INSPECTION - Potholing
label | CONFORMANCE CRITERIA - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | RECORDS - As-built Drawings Doc. Review
holdpoint | HOLD POINT
checkpoint | 4 - Material Compliance
label | ACTION (Hold, Monitor, Witness) -
label | DETAIL - All new cable ducts shall be Electrical Heavy Duty type to AS 2053 coloured orange
label | FREQUENCY - Prior to supplying to site
label | INSPECTION - Visual inspection/ Document review
label | CONFORMANCE CRITERIA - AS/NZS 3000
label | RECORDS - Delivery dockets
checkpoint | 5 - Duct Installation
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Complete checksheet for Duct installation
label | FREQUENCY - During Construction
label | INSPECTION - Visual and measurement
label | CONFORMANCE CRITERIA - Complete for each run between pull pit/jointing chamber
label | RECORDS - FHIMS-CS-4048
holdpoint | HOLD POINT
checkpoint | 6 - Joint Chamber/Pull Pit Installation
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Complete checksheet for chamber and pit installation
label | FREQUENCY - During Construction
label | INSPECTION - Visual and measurement
label | CONFORMANCE CRITERIA - Complete form for each Pull Pit or Jointing Chamber installed
label | RECORDS - FHIMS-CS-4072
holdpoint | HOLD POINT
checkpoint | 7 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Ensure all ducts are picked up every 10m before backfilling commences
label | FREQUENCY - During Construction
label | INSPECTION - Measurement
label | RECORDS - Survey receipt
holdpoint | HOLD POINT
checkpoint | 8 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | DETAIL - Red pen mark up drawings to be included in QA file
label | FREQUENCY - At the completion of the Lot of work
label | INSPECTION - Drawings
label | RECORDS - Asbuilt Drawing
holdpoint | HOLD POINT
checkpoint | Final Inspection
textbox | QA Compiled By:
textbox | QA checked By Discipline Manager:
textbox | Accepted By Principals Rep:
date | Date:
holdpoint | Sign ITP