## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Cladding QA
section | Substrate inspection
checkpoint | Waterproofing done prior to installation
checkpoint | Locate all GL, RL, Setout Point, Window Finish Line, Seismic Joint Position, and Control/Movement Joint.
section | Cladding Titanium Gold Installation
checkpoint | Fixing Bracke to concrete with Hilti HUS-CR S/S Anchor screw
checkpoint | Apply Vapour bond sealant into all Penetrations
checkpoint | S/S Pin to be installed 25mm deep into Granite Stone
checkpoint | Min Edge Distance 45mm
checkpoint | Type A and Type B Requires addational L-Bracket and S/S Pin to be installed into centre top and centre bottom of the stone
checkpoint | Horizontal/vertical module spacing as in between tile to be 5mm with 2mm tolerance
checkpoint | Groove Line filled with Mapei LM Sealant
section | Granite Stone Cladding Installation with direct fix to steel door
checkpoint | Prime the substrate with Eco Prime Grip Plus
checkpoint | Apply Mapelastic Smart with Mapenet 150 over RAB Board /Cement Board.
checkpoint | Direct fix with Kerapoxy Adhesive
checkpoint | Grout stone joint with Mapei Ultracolor plus
checkpoint | Appling Anti -Graffiti shield after installation