## Sheet1
1.1 | Site Set Up | Enviornmental controls implemented as per DESCP | DESCP | Checksheet | Pre-Construction | Visual, hold point |  | Downer | 1.1 - Site Set Up | Inspection Point: Quality Control Activity - Enviornmental controls implemented as per DESCP | Acceptance Criteria - DESCP | Verifying Document - Checksheet | Frequency - Pre-Construction | Inspection Type (Visual, other) - Visual, hold point | Inspection: Key - | Inspection: By - Downer | 1.1 - Site Set Up
1.2 | Work Boundaries Confirmed | Engineer to confirm the boundaries of work. | Engineer Approval | Email Confirmation from engineer | Pre-Construction | Inspection, Hold point |  | Engineer | 1.2 - Work Boundaries Confirmed | Inspection Point: Quality Control Activity - Engineer to confirm the boundaries of work. | Acceptance Criteria - Engineer Approval | Verifying Document - Email Confirmation from engineer | Frequency - Pre-Construction | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Inspection Point: Quality Control Activity - Enviornmental controls implemented as per DESCP
1.3 | Vegetation Clearance | Removal of debris and vegetation using cut and stack method. Cleared with hand tools followed by an excavator. | Area cleared of vegetation and approval from ecologist | Email confirmation from Ecologist | Pre-Construction | Operation, Hold point |  | Ecologist | 1.3 - Vegetation Clearance | Inspection Point: Quality Control Activity - Removal of debris and vegetation using cut and stack method. Cleared with hand tools followed by an excavator. | Acceptance Criteria - Area cleared of vegetation and approval from ecologist | Verifying Document - Email confirmation from Ecologist | Frequency - Pre-Construction | Inspection Type (Visual, other) - Operation, Hold point | Inspection: Key - | Inspection: By - Ecologist | Acceptance Criteria - DESCP
1.4 | Services Located | Service Locations complete and stream banks walked, stormwater pipes cleared around and identified with bright wooden peg. | Services identified, approved controls are in place. Transpower sent info and approves continuation. | Service Location Report | Pre-Construction | Inspection, Hold point |  | Downer, Transpower | 1.4 - Services Located | Inspection Point: Quality Control Activity - Service Locations complete and stream banks walked, stormwater pipes cleared around and identified with bright wooden peg. | Acceptance Criteria - Services identified, approved controls are in place. Transpower sent info and approves continuation. | Verifying Document - Service Location Report | Frequency - Pre-Construction | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Downer, Transpower | Verifying Document - Checksheet
1.5 | Wingwall Installed | Sandbags laid on filter fabric in stream. Platform level and wingwall structure lowered into stream and braced with steel piles into stream bed. Sandbags wrapped in filter fabric at wings of wall and bypass pipe installed through sandbags. | Max water storage height 1m | Photos | Pre-Construction | Inspection, Hold point |  | Downer | 1.5 - Wingwall Installed | Inspection Point: Quality Control Activity - Sandbags laid on filter fabric in stream. Platform level and wingwall structure lowered into stream and braced with steel piles into stream bed. Sandbags wrapped in filter fabric at wings of wall and bypass pipe installed through sandbags. | Acceptance Criteria - Max water storage height 1m | Verifying Document - Photos | Frequency - Pre-Construction | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Downer | Frequency - Pre-Construction
1.6 | Fish Relocation | All fish relocated. | Confirmation from Project Ecologist. | Email confirmation from Project Ecologist. | Pre-Construction | Inspection, Hold point |  | Ecologist | 1.6 - Fish Relocation | Inspection Point: Quality Control Activity - All fish relocated. | Acceptance Criteria - Confirmation from Project Ecologist. | Verifying Document - Email confirmation from Project Ecologist. | Frequency - Pre-Construction | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Ecologist | Inspection Type (Visual, other) - Visual, hold point
2.1 | Material Approval | Rock and Geotextiles as specified | D50/700: 100% CHAR(LESS) 1000mm 50% CHAR(LESS) 700mm 15% CHAR(LESS) 300mm Geotextile: Class E | Quarry Certs / Photos | Prior to placement of Rip Rap | Visual |  | Downer | 2.1 - Material Approval | Inspection Point: Quality Control Activity - Rock and Geotextiles as specified | Acceptance Criteria - D50/700: 100% CHAR(LESS) 1000mm 50% CHAR(LESS) 700mm 15% CHAR(LESS) 300mm Geotextile: Class E | Verifying Document - Quarry Certs / Photos | Frequency - Prior to placement of Rip Rap | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Inspection: Key -
2.2 | Stream Bed Excavations | Stream bed excavated to typical section profiles. Cut matieral transferred to laydown area. | As per drawings C-03-01, C-03-02 | Email Confirmation from engineer | Every 50m of chainage | Inspection, Hold point |  | Engineer | 2.2 - Stream Bed Excavations | Inspection Point: Quality Control Activity - Stream bed excavated to typical section profiles. Cut matieral transferred to laydown area. | Acceptance Criteria - As per drawings C-03-01, C-03-02 | Verifying Document - Email Confirmation from engineer | Frequency - Every 50m of chainage | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Inspection: By - Downer
2.3 | Subgrade Inspection | Scala penetrometer test to assess subgrade strength | Engineer to assess subgrade strength | Email Confirmation from engineer | Every 50m of chainage | Inspection, Hold point |  | Engineer | 2.3 - Subgrade Inspection | Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength | Acceptance Criteria - Engineer to assess subgrade strength | Verifying Document - Email Confirmation from engineer | Frequency - Every 50m of chainage | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | 1.2 - Work Boundaries Confirmed
2.4 | Geotextile | Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications | As per drawings C-03-01, C-03-02 | Photos | Every 50m of cahinage | Visual |  | Downer | 2.4 - Geotextile | Inspection Point: Quality Control Activity - Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications | Acceptance Criteria - As per drawings C-03-01, C-03-02 | Verifying Document - Photos | Frequency - Every 50m of cahinage | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Inspection Point: Quality Control Activity - Engineer to confirm the boundaries of work.
2.5 | Stream Base Rock Channel | Rocks carried and placed in stream base as per new design profile. | As per drawings C-03-01, C-03-02 | Email Confirmation from engineer | Every 50m of chainage | Inspection, Hold point |  | Engineer | 2.5 - Stream Base Rock Channel | Inspection Point: Quality Control Activity - Rocks carried and placed in stream base as per new design profile. | Acceptance Criteria - As per drawings C-03-01, C-03-02 | Verifying Document - Email Confirmation from engineer | Frequency - Every 50m of chainage | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Acceptance Criteria - Engineer Approval
3.1 | Material Approval | Gabion basket, rock, and rip rap as specified | Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK | Photos / Material Certs | Prior to Gabion Construction | Visual |  | Downer | 3.1 - Material Approval | Inspection Point: Quality Control Activity - Gabion basket, rock, and rip rap as specified | Acceptance Criteria - Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK | Verifying Document - Photos / Material Certs | Frequency - Prior to Gabion Construction | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Verifying Document - Email Confirmation from engineer
3.2 | Cut Face Inspection | Inspect Cut face | As per drawing C-03-01 | Email Confirmation from engineer | Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face. | Inspection, Hold point |  | Engineer | 3.2 - Cut Face Inspection | Inspection Point: Quality Control Activity - Inspect Cut face | Acceptance Criteria - As per drawing C-03-01 | Verifying Document - Email Confirmation from engineer | Frequency - Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face. | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Frequency - Pre-Construction
3.3 | Subgrade Inspection | Scala penetrometer test to assess subgrade strength | Engineer to assess subgrade strength | Email Confirmation from engineer | Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth. | Inspection, Hold point |  | Engineer | 3.3 - Subgrade Inspection | Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength | Acceptance Criteria - Engineer to assess subgrade strength | Verifying Document - Email Confirmation from engineer | Frequency - Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth. | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Inspection Type (Visual, other) - Inspection, Hold point
3.4 | Concrete Foundation | Insitu poured gabion wall concrete foundation | Concrete mix as per design. 200mm thick | Concrete dockets | Prior to first layer of gabion basket installation | Inspection, Hold point |  | Downer, Engineer | 3.4 - Concrete Foundation | Inspection Point: Quality Control Activity - Insitu poured gabion wall concrete foundation | Acceptance Criteria - Concrete mix as per design. 200mm thick | Verifying Document - Concrete dockets | Frequency - Prior to first layer of gabion basket installation | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Downer, Engineer | Inspection: Key -
3.5 | Gabion Base Row Alignments | Gabion position marked out, inspection to confirm in correct location as per the specifications | Positioned so base extends minimum 0.5m each side of basket | Photos / Asbuilts | Prior to backfill of first gabion layer | Visual verification |  | Downer | 3.5 - Gabion Base Row Alignments | Inspection Point: Quality Control Activity - Gabion position marked out, inspection to confirm in correct location as per the specifications | Acceptance Criteria - Positioned so base extends minimum 0.5m each side of basket | Verifying Document - Photos / Asbuilts | Frequency - Prior to backfill of first gabion layer | Inspection Type (Visual, other) - Visual verification | Inspection: Key - | Inspection: By - Downer | Inspection: By - Engineer
3.6 | Drianage Inspection | ID04 DPM and drainage coil behind retaining wall | DN100 NOVACOIL placed at base of batter and heel of benches | Approval from Building Inspector | Prior to backfill of first gabion layer | Inspection, Hold point |  | NCC Building Inspector | 3.6 - Drianage Inspection | Inspection Point: Quality Control Activity - ID04 DPM and drainage coil behind retaining wall | Acceptance Criteria - DN100 NOVACOIL placed at base of batter and heel of benches | Verifying Document - Approval from Building Inspector | Frequency - Prior to backfill of first gabion layer | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - NCC Building Inspector | 1.3 - Vegetation Clearance
3.7 | Gabion Layer Inspections | Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications | Max 4 high gabion baskets on true right bank each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket. | Photos / Asbuilts | Each gabion layer, prior to backfill | Visual |  | Engineer | 3.7 - Gabion Layer Inspections | Inspection Point: Quality Control Activity - Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications | Acceptance Criteria - Max 4 high gabion baskets on true right bank each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket. | Verifying Document - Photos / Asbuilts | Frequency - Each gabion layer, prior to backfill | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Engineer | Inspection Point: Quality Control Activity - Removal of debris and vegetation using cut and stack method. Cleared with hand tools followed by an excavator.
3.8 | Gabion Row Backfill | NDM testing on backfill at 200mm lifts | 200mm lifts, 95% MDD | NDM Report | Every "x" Lineal m, Each 200mm life, Each Gabion Layer | Inspection, Hold point |  | Downer | 3.8 - Gabion Row Backfill | Inspection Point: Quality Control Activity - NDM testing on backfill at 200mm lifts | Acceptance Criteria - 200mm lifts, 95% MDD | Verifying Document - NDM Report | Frequency - Every "x" Lineal m, Each 200mm life, Each Gabion Layer | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Downer | Acceptance Criteria - Area cleared of vegetation and approval from ecologist
3.9 | Rock Armouring | Placement of riprap | Directed by Engineer on site | Email Confirmation from engineer | After completion of Gabion Wall | Visual |  | Engineer | 3.9 - Rock Armouring | Inspection Point: Quality Control Activity - Placement of riprap | Acceptance Criteria - Directed by Engineer on site | Verifying Document - Email Confirmation from engineer | Frequency - After completion of Gabion Wall | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Engineer | Verifying Document - Email confirmation from Ecologist
3.1 | Completion of Gabion Wall | Engineer to inspect completed gabion wall | Gabion wall constructed as per drawings | Email from Engineer as confirmation of Approval | After completion of Gabion Wall | Inspection, Hold point |  | Engineer | 3.1 - Completion of Gabion Wall | Inspection Point: Quality Control Activity - Engineer to inspect completed gabion wall | Acceptance Criteria - Gabion wall constructed as per drawings | Verifying Document - Email from Engineer as confirmation of Approval | Frequency - After completion of Gabion Wall | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Frequency - Pre-Construction
4.1 | Material Approval | Gabion basket, rock, and rip rap as specified | Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK | Photos / Material Certs | Prior to Gabion Construction | Visual |  | Downer | 4.1 - Material Approval | Inspection Point: Quality Control Activity - Gabion basket, rock, and rip rap as specified | Acceptance Criteria - Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK | Verifying Document - Photos / Material Certs | Frequency - Prior to Gabion Construction | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Inspection Type (Visual, other) - Operation, Hold point
4.2 | Cut Face Inspection | Inspect Cut face | As per drawing C-03-01 | Email Confirmation from engineer | Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face. | Inspection, Hold point |  | Engineer | 4.2 - Cut Face Inspection | Inspection Point: Quality Control Activity - Inspect Cut face | Acceptance Criteria - As per drawing C-03-01 | Verifying Document - Email Confirmation from engineer | Frequency - Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face. | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Inspection: Key -
4.3 | Subgrade Inspection | Scala penetrometer test to assess subgrade strength | Engineer to assess subgrade strength | Email Confirmation from engineer | Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth. | Inspection, Hold point |  | Engineer | 4.3 - Subgrade Inspection | Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength | Acceptance Criteria - Engineer to assess subgrade strength | Verifying Document - Email Confirmation from engineer | Frequency - Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth. | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Inspection: By - Ecologist
4.4 | AP65 Compaction Testing | NDM Testing done on AP65 base. CONCRETE? | 95% MDD approved by Engineer | NDM Report | Prior to first layer of gabion basket installation | Inspection, Hold point |  | Downer, Engineer | 4.4 - AP65 Compaction Testing | Inspection Point: Quality Control Activity - NDM Testing done on AP65 base. CONCRETE? | Acceptance Criteria - 95% MDD approved by Engineer | Verifying Document - NDM Report | Frequency - Prior to first layer of gabion basket installation | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Downer, Engineer | 1.4 - Services Located
4.5 | Gabion Base Row Alignments | Gabion position marked out, inspection to confirm in correct location as per the specifications | Bottom two layers to be two units wide with every third unit laid perpendicular. Positioned so base extends minimum 0.5m each side of basket. | Photos / Asbuilts | Prior to backfill of first gabion layer | Visual verification |  | Downer | 4.5 - Gabion Base Row Alignments | Inspection Point: Quality Control Activity - Gabion position marked out, inspection to confirm in correct location as per the specifications | Acceptance Criteria - Bottom two layers to be two units wide with every third unit laid perpendicular. Positioned so base extends minimum 0.5m each side of basket. | Verifying Document - Photos / Asbuilts | Frequency - Prior to backfill of first gabion layer | Inspection Type (Visual, other) - Visual verification | Inspection: Key - | Inspection: By - Downer | Inspection Point: Quality Control Activity - Service Locations complete and stream banks walked, stormwater pipes cleared around and identified with bright wooden peg.
4.6 | Drianage Inspection | ID04 DPM and drainage coil behind retaining wall | DN100 NOVACOIL placed at base of batter and heel of benches | Approval from Building Inspector | Prior to backfill of first gabion layer | Inspection, Hold point |  | NCC Building Inspector | 4.6 - Drianage Inspection | Inspection Point: Quality Control Activity - ID04 DPM and drainage coil behind retaining wall | Acceptance Criteria - DN100 NOVACOIL placed at base of batter and heel of benches | Verifying Document - Approval from Building Inspector | Frequency - Prior to backfill of first gabion layer | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - NCC Building Inspector | Acceptance Criteria - Services identified, approved controls are in place. Transpower sent info and approves continuation.
4.7 | Gabion Layer Inspections | Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications | Each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket. | Photos / Asbuilts | Each gabion layer, prior to backfill | Visual |  | Engineer | 4.7 - Gabion Layer Inspections | Inspection Point: Quality Control Activity - Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications | Acceptance Criteria - Each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket. | Verifying Document - Photos / Asbuilts | Frequency - Each gabion layer, prior to backfill | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Engineer | Verifying Document - Service Location Report
4.8 | Gabion Row Backfill | NDM testing on backfill at 200mm lifts | 200mm lifts, 95% MDD | NDM Report | Every "x" Lineal m, Each 200mm life, Each Gabion Layer | Inspection, Hold point |  | Downer | 4.8 - Gabion Row Backfill | Inspection Point: Quality Control Activity - NDM testing on backfill at 200mm lifts | Acceptance Criteria - 200mm lifts, 95% MDD | Verifying Document - NDM Report | Frequency - Every "x" Lineal m, Each 200mm life, Each Gabion Layer | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Downer | Frequency - Pre-Construction
4.9 | Rock Armouring | Placement of riprap | Directed by Engineer on site | Email Confirmation from engineer | After completion of Gabion Wall | Visual |  | Engineer | 4.9 - Rock Armouring | Inspection Point: Quality Control Activity - Placement of riprap | Acceptance Criteria - Directed by Engineer on site | Verifying Document - Email Confirmation from engineer | Frequency - After completion of Gabion Wall | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Engineer | Inspection Type (Visual, other) - Inspection, Hold point
4.1 | Completion of Gabion Wall | Engineer to inspect completed gabion wall | Gabion wall constructed as per drawings | Email from Engineer as confirmation of Approval | After completion of Gabion Wall | Inspection, Hold point |  | Engineer | 4.1 - Completion of Gabion Wall | Inspection Point: Quality Control Activity - Engineer to inspect completed gabion wall | Acceptance Criteria - Gabion wall constructed as per drawings | Verifying Document - Email from Engineer as confirmation of Approval | Frequency - After completion of Gabion Wall | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - Engineer | Inspection: Key -
4.11 | II06 Final - Residential | Residential final inspection. When all building consent requirements are complete. | Gabion Wall constructed as per design | II06 Report | After completion of Gabion Wall | Inspection, Hold point |  | NCC Building Inspector | 4.11 - II06 Final - Residential | Inspection Point: Quality Control Activity - Residential final inspection. When all building consent requirements are complete. | Acceptance Criteria - Gabion Wall constructed as per design | Verifying Document - II06 Report | Frequency - After completion of Gabion Wall | Inspection Type (Visual, other) - Inspection, Hold point | Inspection: Key - | Inspection: By - NCC Building Inspector | Inspection: By - Downer, Transpower
5.1 | Material Approval | Rip Rap and Geotextiles as specified | D50/700: 100% CHAR(LESS) 1000mm 50% CHAR(LESS) 700mm 15% CHAR(LESS) 300mm Geotextile: Class E | Quarry Certs / Photos | Prior to placement of Rip Rap | Visual |  | Downer | 5.1 - Material Approval | Inspection Point: Quality Control Activity - Rip Rap and Geotextiles as specified | Acceptance Criteria - D50/700: 100% CHAR(LESS) 1000mm 50% CHAR(LESS) 700mm 15% CHAR(LESS) 300mm Geotextile: Class E | Verifying Document - Quarry Certs / Photos | Frequency - Prior to placement of Rip Rap | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | 1.5 - Wingwall Installed
5.2 | Excavation profile | Excavated to typical section profiles. Cut matieral transferred to laydown area. | As per drawings C-03-01, C-03-02 | Photos / Asbuilts | Every 50m of cahinage | Visual |  | Downer | 5.2 - Excavation profile | Inspection Point: Quality Control Activity - Excavated to typical section profiles. Cut matieral transferred to laydown area. | Acceptance Criteria - As per drawings C-03-01, C-03-02 | Verifying Document - Photos / Asbuilts | Frequency - Every 50m of cahinage | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Inspection Point: Quality Control Activity - Sandbags laid on filter fabric in stream. Platform level and wingwall structure lowered into stream and braced with steel piles into stream bed. Sandbags wrapped in filter fabric at wings of wall and bypass pipe installed through sandbags.
5.3 | Geotextile | Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications | As per drawings C-03-01, C-03-02 | Photos | Every 50m of cahinage | Visual |  | Downer | 5.3 - Geotextile | Inspection Point: Quality Control Activity - Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications | Acceptance Criteria - As per drawings C-03-01, C-03-02 | Verifying Document - Photos | Frequency - Every 50m of cahinage | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Acceptance Criteria - Max water storage height 1m
5.4 | Placement of rock | Rocks carried and placed in stream base as per design profile. | As per drawings C-03-01, C-03-02 | Photos | Every 50m of cahinage | Visual |  | Downer | 5.4 - Placement of rock | Inspection Point: Quality Control Activity - Rocks carried and placed in stream base as per design profile. | Acceptance Criteria - As per drawings C-03-01, C-03-02 | Verifying Document - Photos | Frequency - Every 50m of cahinage | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Verifying Document - Photos
5.5 | Final Inspection | Inspection to confirm Revetment is correct depth, sufficient placement of infill material |  | Photos | Every 50m of cahinage | Visual |  | Downer | 5.5 - Final Inspection | Inspection Point: Quality Control Activity - Inspection to confirm Revetment is correct depth, sufficient placement of infill material | Acceptance Criteria - | Verifying Document - Photos | Frequency - Every 50m of cahinage | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Frequency - Pre-Construction
6.1 | New Sump CHAR(AMP) Pipe Outlet Installed | New sump CHAR(AMP) pipe outlet to stream installed and placed through gabion baskets at approx. CH116 | as per LDM | Photos / Asbuilts | After Installation | Visual |  | Downer | 6.1 - New Sump CHAR(AMP) Pipe Outlet Installed | Inspection Point: Quality Control Activity - New sump CHAR(AMP) pipe outlet to stream installed and placed through gabion baskets at approx. CH116 | Acceptance Criteria - as per LDM | Verifying Document - Photos / Asbuilts | Frequency - After Installation | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Inspection Type (Visual, other) - Inspection, Hold point
6.2 | New concrete surround CHAR(AMP) flapgate | New concrete surround CHAR(AMP) flapgate on existing SW pipe at CH195 | as per manufacturer's specs | Photos / Asbuilts | After Installation | Visual |  | Downer | 6.2 - New concrete surround CHAR(AMP) flapgate | Inspection Point: Quality Control Activity - New concrete surround CHAR(AMP) flapgate on existing SW pipe at CH195 | Acceptance Criteria - as per manufacturer's specs | Verifying Document - Photos / Asbuilts | Frequency - After Installation | Inspection Type (Visual, other) - Visual | Inspection: Key - | Inspection: By - Downer | Inspection: Key -
7.1 | Practical Completion Walkover | Walkover with Eng, Client and Contractor | Contract works agreed to be practically complete with construction defects noted. | Construction defects list, PC Cert | Upon Completion of Works | Inspection | PM,ENG, Client Rep. |  | 7.1 - Practical Completion Walkover | Inspection Point: Quality Control Activity - Walkover with Eng, Client and Contractor | Acceptance Criteria - Contract works agreed to be practically complete with construction defects noted. | Verifying Document - Construction defects list, PC Cert | Frequency - Upon Completion of Works | Inspection Type (Visual, other) - Inspection | Inspection: Key - PM,ENG, Client Rep. | Inspection: By - | Inspection: By - Downer
7.2 | As-built drainage plan | Registered drainlayer to provide a colour as-built drainage plan to Council, which includes a north point. | Conforms to design and engineer approvals | Surmmary as-built report and redline drawings | Upon Completion of Works | Action |  | Downer | 7.2 - As-built drainage plan | Inspection Point: Quality Control Activity - Registered drainlayer to provide a colour as-built drainage plan to Council, which includes a north point. | Acceptance Criteria - Conforms to design and engineer approvals | Verifying Document - Surmmary as-built report and redline drawings | Frequency - Upon Completion of Works | Inspection Type (Visual, other) - Action | Inspection: Key - | Inspection: By - Downer | 1.6 - Fish Relocation
Inspection Point: Quality Control Activity - All fish relocated.
Acceptance Criteria - Confirmation from Project Ecologist.
Verifying Document - Email confirmation from Project Ecologist.
Frequency - Pre-Construction
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Ecologist
2.1 - Material Approval
Inspection Point: Quality Control Activity - Rock and Geotextiles as specified
Acceptance Criteria - D50/700: 100% CHAR(LESS) 1000mm 50% CHAR(LESS) 700mm 15% CHAR(LESS) 300mm Geotextile: Class E
Verifying Document - Quarry Certs / Photos
Frequency - Prior to placement of Rip Rap
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
2.2 - Stream Bed Excavations
Inspection Point: Quality Control Activity - Stream bed excavated to typical section profiles. Cut matieral transferred to laydown area.
Acceptance Criteria - As per drawings C-03-01, C-03-02
Verifying Document - Email Confirmation from engineer
Frequency - Every 50m of chainage
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
2.3 - Subgrade Inspection
Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength
Acceptance Criteria - Engineer to assess subgrade strength
Verifying Document - Email Confirmation from engineer
Frequency - Every 50m of chainage
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
2.4 - Geotextile
Inspection Point: Quality Control Activity - Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications
Acceptance Criteria - As per drawings C-03-01, C-03-02
Verifying Document - Photos
Frequency - Every 50m of cahinage
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
2.5 - Stream Base Rock Channel
Inspection Point: Quality Control Activity - Rocks carried and placed in stream base as per new design profile.
Acceptance Criteria - As per drawings C-03-01, C-03-02
Verifying Document - Email Confirmation from engineer
Frequency - Every 50m of chainage
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
3.1 - Material Approval
Inspection Point: Quality Control Activity - Gabion basket, rock, and rip rap as specified
Acceptance Criteria - Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK
Verifying Document - Photos / Material Certs
Frequency - Prior to Gabion Construction
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
3.2 - Cut Face Inspection
Inspection Point: Quality Control Activity - Inspect Cut face
Acceptance Criteria - As per drawing C-03-01
Verifying Document - Email Confirmation from engineer
Frequency - Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face.
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
3.3 - Subgrade Inspection
Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength
Acceptance Criteria - Engineer to assess subgrade strength
Verifying Document - Email Confirmation from engineer
Frequency - Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth.
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
3.4 - Concrete Foundation
Inspection Point: Quality Control Activity - Insitu poured gabion wall concrete foundation
Acceptance Criteria - Concrete mix as per design. 200mm thick
Verifying Document - Concrete dockets
Frequency - Prior to first layer of gabion basket installation
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Downer, Engineer
3.5 - Gabion Base Row Alignments
Inspection Point: Quality Control Activity - Gabion position marked out, inspection to confirm in correct location as per the specifications
Acceptance Criteria - Positioned so base extends minimum 0.5m each side of basket
Verifying Document - Photos / Asbuilts
Frequency - Prior to backfill of first gabion layer
Inspection Type (Visual, other) - Visual verification
Inspection: Key -
Inspection: By - Downer
3.6 - Drianage Inspection
Inspection Point: Quality Control Activity - ID04 DPM and drainage coil behind retaining wall
Acceptance Criteria - DN100 NOVACOIL placed at base of batter and heel of benches
Verifying Document - Approval from Building Inspector
Frequency - Prior to backfill of first gabion layer
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - NCC Building Inspector
3.7 - Gabion Layer Inspections
Inspection Point: Quality Control Activity - Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications
Acceptance Criteria - Max 4 high gabion baskets on true right bank each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket.
Verifying Document - Photos / Asbuilts
Frequency - Each gabion layer, prior to backfill
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Engineer
3.8 - Gabion Row Backfill
Inspection Point: Quality Control Activity - NDM testing on backfill at 200mm lifts
Acceptance Criteria - 200mm lifts, 95% MDD
Verifying Document - NDM Report
Frequency - Every "x" Lineal m, Each 200mm life, Each Gabion Layer
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Downer
3.9 - Rock Armouring
Inspection Point: Quality Control Activity - Placement of riprap
Acceptance Criteria - Directed by Engineer on site
Verifying Document - Email Confirmation from engineer
Frequency - After completion of Gabion Wall
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Engineer
3.1 - Completion of Gabion Wall
Inspection Point: Quality Control Activity - Engineer to inspect completed gabion wall
Acceptance Criteria - Gabion wall constructed as per drawings
Verifying Document - Email from Engineer as confirmation of Approval
Frequency - After completion of Gabion Wall
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
4.1 - Material Approval
Inspection Point: Quality Control Activity - Gabion basket, rock, and rip rap as specified
Acceptance Criteria - Gabion Baskets: 2x1x1m PVC coated Gabion Rock: xxx Riprap: 700 ESD ROCK
Verifying Document - Photos / Material Certs
Frequency - Prior to Gabion Construction
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
4.2 - Cut Face Inspection
Inspection Point: Quality Control Activity - Inspect Cut face
Acceptance Criteria - As per drawing C-03-01
Verifying Document - Email Confirmation from engineer
Frequency - Once 2 (lineal) metres of excavation has been completed to assess stability of the cut face.
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
4.3 - Subgrade Inspection
Inspection Point: Quality Control Activity - Scala penetrometer test to assess subgrade strength
Acceptance Criteria - Engineer to assess subgrade strength
Verifying Document - Email Confirmation from engineer
Frequency - Once all topsoil, organic material, and/or soft top layer(s) have been removed to the design depth.
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
4.4 - AP65 Compaction Testing
Inspection Point: Quality Control Activity - NDM Testing done on AP65 base. CONCRETE?
Acceptance Criteria - 95% MDD approved by Engineer
Verifying Document - NDM Report
Frequency - Prior to first layer of gabion basket installation
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Downer, Engineer
4.5 - Gabion Base Row Alignments
Inspection Point: Quality Control Activity - Gabion position marked out, inspection to confirm in correct location as per the specifications
Acceptance Criteria - Bottom two layers to be two units wide with every third unit laid perpendicular. Positioned so base extends minimum 0.5m each side of basket.
Verifying Document - Photos / Asbuilts
Frequency - Prior to backfill of first gabion layer
Inspection Type (Visual, other) - Visual verification
Inspection: Key -
Inspection: By - Downer
4.6 - Drianage Inspection
Inspection Point: Quality Control Activity - ID04 DPM and drainage coil behind retaining wall
Acceptance Criteria - DN100 NOVACOIL placed at base of batter and heel of benches
Verifying Document - Approval from Building Inspector
Frequency - Prior to backfill of first gabion layer
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - NCC Building Inspector
4.7 - Gabion Layer Inspections
Inspection Point: Quality Control Activity - Inspection to confirm gabion layer offset, backslope, and geotextile as per specifications
Acceptance Criteria - Each layer offset by 0.5m from the layer below. 10% backslope on baskets. Class E geotextile behind basket.
Verifying Document - Photos / Asbuilts
Frequency - Each gabion layer, prior to backfill
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Engineer
4.8 - Gabion Row Backfill
Inspection Point: Quality Control Activity - NDM testing on backfill at 200mm lifts
Acceptance Criteria - 200mm lifts, 95% MDD
Verifying Document - NDM Report
Frequency - Every "x" Lineal m, Each 200mm life, Each Gabion Layer
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Downer
4.9 - Rock Armouring
Inspection Point: Quality Control Activity - Placement of riprap
Acceptance Criteria - Directed by Engineer on site
Verifying Document - Email Confirmation from engineer
Frequency - After completion of Gabion Wall
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Engineer
4.1 - Completion of Gabion Wall
Inspection Point: Quality Control Activity - Engineer to inspect completed gabion wall
Acceptance Criteria - Gabion wall constructed as per drawings
Verifying Document - Email from Engineer as confirmation of Approval
Frequency - After completion of Gabion Wall
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - Engineer
4.11 - II06 Final - Residential
Inspection Point: Quality Control Activity - Residential final inspection. When all building consent requirements are complete.
Acceptance Criteria - Gabion Wall constructed as per design
Verifying Document - II06 Report
Frequency - After completion of Gabion Wall
Inspection Type (Visual, other) - Inspection, Hold point
Inspection: Key -
Inspection: By - NCC Building Inspector
5.1 - Material Approval
Inspection Point: Quality Control Activity - Rip Rap and Geotextiles as specified
Acceptance Criteria - D50/700: 100% CHAR(LESS) 1000mm 50% CHAR(LESS) 700mm 15% CHAR(LESS) 300mm Geotextile: Class E
Verifying Document - Quarry Certs / Photos
Frequency - Prior to placement of Rip Rap
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
5.2 - Excavation profile
Inspection Point: Quality Control Activity - Excavated to typical section profiles. Cut matieral transferred to laydown area.
Acceptance Criteria - As per drawings C-03-01, C-03-02
Verifying Document - Photos / Asbuilts
Frequency - Every 50m of cahinage
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
5.3 - Geotextile
Inspection Point: Quality Control Activity - Geotextile coth laid as per design profile. Overlapped as per manufacturers specifications
Acceptance Criteria - As per drawings C-03-01, C-03-02
Verifying Document - Photos
Frequency - Every 50m of cahinage
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
5.4 - Placement of rock
Inspection Point: Quality Control Activity - Rocks carried and placed in stream base as per design profile.
Acceptance Criteria - As per drawings C-03-01, C-03-02
Verifying Document - Photos
Frequency - Every 50m of cahinage
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
5.5 - Final Inspection
Inspection Point: Quality Control Activity - Inspection to confirm Revetment is correct depth, sufficient placement of infill material
Acceptance Criteria -
Verifying Document - Photos
Frequency - Every 50m of cahinage
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
6.1 - New Sump CHAR(AMP) Pipe Outlet Installed
Inspection Point: Quality Control Activity - New sump CHAR(AMP) pipe outlet to stream installed and placed through gabion baskets at approx. CH116
Acceptance Criteria - as per LDM
Verifying Document - Photos / Asbuilts
Frequency - After Installation
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
6.2 - New concrete surround CHAR(AMP) flapgate
Inspection Point: Quality Control Activity - New concrete surround CHAR(AMP) flapgate on existing SW pipe at CH195
Acceptance Criteria - as per manufacturer's specs
Verifying Document - Photos / Asbuilts
Frequency - After Installation
Inspection Type (Visual, other) - Visual
Inspection: Key -
Inspection: By - Downer
7.1 - Practical Completion Walkover
Inspection Point: Quality Control Activity - Walkover with Eng, Client and Contractor
Acceptance Criteria - Contract works agreed to be practically complete with construction defects noted.
Verifying Document - Construction defects list, PC Cert
Frequency - Upon Completion of Works
Inspection Type (Visual, other) - Inspection
Inspection: Key - PM,ENG, Client Rep.
Inspection: By -
7.2 - As-built drainage plan
Inspection Point: Quality Control Activity - Registered drainlayer to provide a colour as-built drainage plan to Council, which includes a north point.
Acceptance Criteria - Conforms to design and engineer approvals
Verifying Document - Surmmary as-built report and redline drawings
Frequency - Upon Completion of Works
Inspection Type (Visual, other) - Action
Inspection: Key -
Inspection: By - Downer