## Sheet1
1 | Design | H | Confirm with engineer if existing GPU's are to be retained, moved or removed and locations of New GPU's | Prior to commencement | Document Review |  | Check Drawing Register | 1 - Design | ACTION (Hold, Monitor, Witness) - H | DETAIL - Confirm with engineer if existing GPU's are to be retained, moved or removed and locations of New GPU's | FREQUENCY - Prior to commencement | INSPECTION - Document Review | CONFORMANCE CRITERIA - | RECORDS - Check Drawing Register | 1 - Design
2 | Survey Setout | H | Survey existing GPU's, mark out new GPU's and identify underground feeds. | Prior to commencement | Survey | Identify where new and existing services may clash | Survey receipt | 2 - Survey Setout | ACTION (Hold, Monitor, Witness) - H | DETAIL - Survey existing GPU's, mark out new GPU's and identify underground feeds. | FREQUENCY - Prior to commencement | INSPECTION - Survey | CONFORMANCE CRITERIA - Identify where new and existing services may clash | RECORDS - Survey receipt | ACTION (Hold, Monitor, Witness) - H
3 | Locate existing services | H | Ensure all services are marked with paint and/or pegs and use hydrovac to locate where not sure of depth. | Prior to commencement | Potholing | All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | As-built Drawings Doc. Review | 3 - Locate existing services | ACTION (Hold, Monitor, Witness) - H | DETAIL - Ensure all services are marked with paint and/or pegs and use hydrovac to locate where not sure of depth. | FREQUENCY - Prior to commencement | INSPECTION - Potholing | CONFORMANCE CRITERIA - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services | RECORDS - As-built Drawings Doc. Review | DETAIL - Confirm with engineer if existing GPU's are to be retained, moved or removed and locations of New GPU's
4 | Material Compliance |  | All new cable ducts shall be Electrical Heavy Duty type to AS 2053 coloured orange | Prior to supplying to site | Visual inspection/ Document review | AS/NZS 3000 | Delivery dockets | 4 - Material Compliance | ACTION (Hold, Monitor, Witness) - | DETAIL - All new cable ducts shall be Electrical Heavy Duty type to AS 2053 coloured orange | FREQUENCY - Prior to supplying to site | INSPECTION - Visual inspection/ Document review | CONFORMANCE CRITERIA - AS/NZS 3000 | RECORDS - Delivery dockets | FREQUENCY - Prior to commencement
5 | Duct Installation | H | Complete checksheet for Duct installation | During Construction | Visual and measurement | Complete for each run between pull pit/jointing chamber | FHIMS-CS-4048 | 5 - Duct Installation | ACTION (Hold, Monitor, Witness) - H | DETAIL - Complete checksheet for Duct installation | FREQUENCY - During Construction | INSPECTION - Visual and measurement | CONFORMANCE CRITERIA - Complete for each run between pull pit/jointing chamber | RECORDS - FHIMS-CS-4048 | INSPECTION - Document Review
6 | Joint Chamber/Pull Pit Installation | H | Complete checksheet for chamber and pit installation | During Construction | Visual and measurement | Complete form for each Pull Pit or Jointing Chamber installed | FHIMS-CS-4072 | 6 - Joint Chamber/Pull Pit Installation | ACTION (Hold, Monitor, Witness) - H | DETAIL - Complete checksheet for chamber and pit installation | FREQUENCY - During Construction | INSPECTION - Visual and measurement | CONFORMANCE CRITERIA - Complete form for each Pull Pit or Jointing Chamber installed | RECORDS - FHIMS-CS-4072 | CONFORMANCE CRITERIA -
7 | Survey As Built | H | Ensure all ducts are picked up every 10m before backfilling commences | During Construction | Measurement |  | Survey receipt | 7 - Survey As Built | ACTION (Hold, Monitor, Witness) - H | DETAIL - Ensure all ducts are picked up every 10m before backfilling commences | FREQUENCY - During Construction | INSPECTION - Measurement | CONFORMANCE CRITERIA - | RECORDS - Survey receipt | RECORDS - Check Drawing Register
8 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | 8 - As-builts | ACTION (Hold, Monitor, Witness) - H | DETAIL - Red pen mark up drawings to be included in QA file | FREQUENCY - At the completion of the Lot of work | INSPECTION - Drawings | CONFORMANCE CRITERIA - | RECORDS - Asbuilt Drawing | 2 - Survey Setout
ACTION (Hold, Monitor, Witness) - H
DETAIL - Survey existing GPU's, mark out new GPU's and identify underground feeds.
FREQUENCY - Prior to commencement
INSPECTION - Survey
CONFORMANCE CRITERIA - Identify where new and existing services may clash
RECORDS - Survey receipt
3 - Locate existing services
ACTION (Hold, Monitor, Witness) - H
DETAIL - Ensure all services are marked with paint and/or pegs and use hydrovac to locate where not sure of depth.
FREQUENCY - Prior to commencement
INSPECTION - Potholing
CONFORMANCE CRITERIA - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
RECORDS - As-built Drawings Doc. Review
4 - Material Compliance
ACTION (Hold, Monitor, Witness) -
DETAIL - All new cable ducts shall be Electrical Heavy Duty type to AS 2053 coloured orange
FREQUENCY - Prior to supplying to site
INSPECTION - Visual inspection/ Document review
CONFORMANCE CRITERIA - AS/NZS 3000
RECORDS - Delivery dockets
5 - Duct Installation
ACTION (Hold, Monitor, Witness) - H
DETAIL - Complete checksheet for Duct installation
FREQUENCY - During Construction
INSPECTION - Visual and measurement
CONFORMANCE CRITERIA - Complete for each run between pull pit/jointing chamber
RECORDS - FHIMS-CS-4048
6 - Joint Chamber/Pull Pit Installation
ACTION (Hold, Monitor, Witness) - H
DETAIL - Complete checksheet for chamber and pit installation
FREQUENCY - During Construction
INSPECTION - Visual and measurement
CONFORMANCE CRITERIA - Complete form for each Pull Pit or Jointing Chamber installed
RECORDS - FHIMS-CS-4072
7 - Survey As Built
ACTION (Hold, Monitor, Witness) - H
DETAIL - Ensure all ducts are picked up every 10m before backfilling commences
FREQUENCY - During Construction
INSPECTION - Measurement
CONFORMANCE CRITERIA -
RECORDS - Survey receipt
8 - As-builts
ACTION (Hold, Monitor, Witness) - H
DETAIL - Red pen mark up drawings to be included in QA file
FREQUENCY - At the completion of the Lot of work
INSPECTION - Drawings
CONFORMANCE CRITERIA -
RECORDS - Asbuilt Drawing