## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
63f98180-0f34-48be-ae6b-c69411673df1 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.01 | Balcony
38b31077-4fa9-4cc7-ad7e-72f6ca4987a2 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.02 | Balcony
38435187-63aa-41ad-b3ab-321b4a4cb73b |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.03 | Balcony
10038531-555d-48a8-baa2-8511acaef6da |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.04 | Balcony
0f2c982f-2ded-481d-9df0-e05b670ad529 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.05 | Balcony
47281894-895e-46fb-894f-6022987dfb61 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.06 | Balcony
6095645a-972e-4918-bd0a-c43d78df0f2e |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.07 | Balcony
74f33264-a7f6-44b8-93da-d1a4fe710098 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.08 | Balcony
add08a32-267f-48cb-b419-df04e72ba9a7 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.09 | Balcony
83e1a251-9293-4f91-ab4e-4adf5afc5ba1 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.10 | Balcony
d6866b01-3582-4576-acbc-eab2c0c00f20 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.11 | Balcony
f9b9e8a5-1f3a-43a0-ba84-972dfa2969f3 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.12 | Balcony
a7f11e11-190b-4240-8312-a35bf7135e36 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block A - Terraces | A.13 | Balcony
c66d7171-a30c-4131-9e2b-dae6617d2dd6 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.01 | Balcony
18db8fef-8dab-4a9a-871d-c114140c02f9 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.02 | Balcony
9789859f-83a8-4ec1-8d60-9dbb91895b50 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.03 | Balcony
d41b7cb8-11cb-4240-9227-1dfaab36fc5c |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.04 | Balcony
3d1a7dd0-a8ae-4587-80da-54e95899be09 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.05 | Balcony
00897fe4-8216-4474-9086-c25d83dd2344 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.06 | Balcony
eaaab378-374a-4f37-8de0-370931ba366f |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.07 | Balcony
d76c627a-d4c6-48be-b21d-011a6c58de4d |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.G.08 | Balcony
a4eb6115-0364-4df2-b9a6-1cc1fb59eafc |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.01 | Balcony
b065ff46-bc28-44bf-b8e0-b53e4084895c |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.02 | Balcony
7d5373ec-7507-4b87-a2a1-76ac7c0d2146 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.03 | Balcony
4afcf659-6e45-4d9e-9e83-c055b103b7e0 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.04 | Balcony
da66c35a-f5c9-4b5b-bb6c-b45c4678893b |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.05 | Balcony
6aa7b04f-d83a-4401-a3b9-0fc551dea207 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.06 | Balcony
80469d1a-1f26-4d82-b838-228109cf8f70 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.07 | Balcony
a1b4d818-3d21-4c63-a6c6-dbc6447e64a4 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.1.08 | Balcony
bac7523d-432d-4f08-8149-8508bc2296d7 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.01 | Balcony
d3ef3d7d-6822-4db0-9eac-f90468c34a04 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.02 | Balcony
36b5bcd8-dc7a-46cc-ab54-53e71ce71bc8 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.03 | Balcony
40bff0d5-ac24-4b24-b325-99acd6a83190 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.04 | Balcony
eaf57353-489e-4310-afeb-21b858ad03f2 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.05 | Balcony
2d51fff9-30f5-4bac-a349-8687b0e9636e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.06 | Balcony
b48d66a9-6b34-431f-bec8-f0cf76345cb9 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.07 | Balcony
bf4cfbbd-b22a-4587-bb08-6f3e0c32aca0 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.2.08 | Balcony
12e9c3b4-9206-4d34-9ee4-722ff5ee4b55 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.01 | Balcony
df0609d4-aaf9-4e4b-9e5e-48d4eed07692 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.02 | Balcony
9a9fb305-11bc-4226-95ce-400aad314bab |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.03 | Balcony
c4079f2b-0a16-420b-a832-8f262f9b1cbe |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.04 | Balcony
5c903017-da43-4eb8-b13e-a2094862bcdc |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.05 | Balcony
59d0fe2c-1f1b-449f-800f-ddc91474c5ba |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.06 | Balcony
2c40757c-2aca-4396-b18a-2fa2668c861d |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.07 | Balcony
39038c33-52e1-46e2-b987-bca92c1c3a59 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.3.08 | Balcony
439e26ad-12c0-49a4-aa37-5e9b39a1804a |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.01 | Balcony
24966d92-408d-4410-8170-3dad1a1d0c73 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.02 | Balcony
641ce8e0-c663-4184-8c25-d70c019c6b8e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.03 | Balcony
58260016-7011-42aa-856b-c277ead53363 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.04 | Balcony
c7533375-215a-4221-af11-be7f59c386b7 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.05 | Balcony
f41dea9f-9240-4147-bd19-bede11f96670 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.06 | Balcony
f7b73639-8c07-4be2-841e-b35f918b86de |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.07 | Balcony
54ba4fee-c006-443c-8160-63ac9ddaa031 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.4.08 | Balcony
36c17dba-ff8c-497a-9060-f9cf3a99e4a0 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.5.01 | Balcony
eff23474-7d1d-407a-884f-5fa530911ad0 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.5.02 | Balcony
f9c09d89-7e22-4703-992b-6840cdf6ee5e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.5.03 | Balcony
1bdbf96d-43ac-4800-9fa3-b6dc9507d424 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block B - Apartments | B.5.04 | Balcony
590eae5f-01d4-48c6-bf51-99e43b42019e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.LG.01 | Balcony
4e5ba4af-be62-45ac-889c-58c02a658779 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.LG.02 | Balcony
3922688b-fa69-41cc-8e3c-c993585f98e7 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.LG.03 | Balcony
cced08b3-2120-412e-ae06-72995e8d5145 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.LG.04 | Balcony
9ccd81d3-319e-4d14-a7ef-48d88f0968f9 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.01 | Balcony
fa0c5c0b-9f96-4b04-9eb4-c5099768f69b |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.02 | Balcony
f375b516-9e78-40c8-a9c5-747000803765 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.03 | Balcony
cb2d7c4b-b6e2-48dd-82e4-debeaf5973c4 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.04 | Balcony
a133df1b-1efb-4567-abd5-7c980bca4ccc |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.05 | Balcony
5ce9ff29-873e-46c7-8207-da43fff2e1b1 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.06 | Balcony
5f88934d-7419-4785-9896-d1b2c3d1a253 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.07 | Balcony
90b40f95-7cf4-4f7e-a50b-ae54e118ebf5 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.08 | Balcony
2f8fa3fd-1922-4fd5-91d2-8c675074020a |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.09 | Balcony
43195d77-5f1f-45e3-8ccf-22e882ea962d |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.G.10 | Balcony
aacbbd2f-5dbe-4fde-83d6-5e05086b5ce2 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.1.01 | Balcony
ba51afb0-4cdf-4671-a648-2cb025f062b0 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.1.02 | Balcony
ec314966-e287-43e0-9864-017e162f9184 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.1.03 | Balcony
ca2e3043-87cc-49a7-9c19-8714f776416e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.1.04 | Balcony
3ec4e493-31fa-41cf-82b4-18b0e0646dab |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.01 | Balcony
74706fb1-1658-47e7-8f51-034827942730 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.02 | Balcony
c1d016be-8183-422b-8650-5967fa4fa519 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.03 | Balcony
103f807b-77fa-4999-afa0-331d4fb22b9a |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.04 | Balcony
172d8112-4c4f-4b31-b541-2a75f94a229c |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.05 | Balcony
7c1b4abf-df4c-46f0-b51f-57f35b3bb9b5 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.06 | Balcony
ac0dab21-a0e8-4d6d-8dbf-898e0476e748 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.07 | Balcony
b716a5e6-8eab-4ed2-a7b2-7663b1f66943 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.2.08 | Balcony
d93534a4-a35e-4ff7-bc9c-4b80f43ff37f |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.01 | Balcony
1108899e-d3d2-4856-9ed7-88bc39f73377 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.02 | Balcony
ce04f170-576e-43f8-ac08-a73cfb3621c5 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.03 | Balcony
2423df6d-3945-49d4-8797-dbadfadb0895 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.04 | Balcony
21b997f2-7928-4808-9e2b-59a38d9d40e8 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.05 | Balcony
fd25b3c8-d8c4-4a97-8ec7-c3a22e398d90 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.06 | Balcony
61a367a4-1275-4133-9b00-b1cde5d13e2e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.07 | Balcony
f95fa3ee-cd4a-4242-904d-1ef0024758cb |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.3.08 | Balcony
2d135cd3-db69-4cbd-9445-1c1a9936ad0e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.4.01 | Balcony
d3fb6145-3bed-430a-8b76-66ce84a102d9 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.4.02 | Balcony
9fd122fb-fa89-4555-b0e8-c2281dd57d8a |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block C - Apartments | C.4.03 | Balcony
feffd7aa-c832-4484-af1c-9cd7342c5eb1 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.01 | Balcony
37360a87-123c-4716-8057-cce09dbc04a9 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.02 | Balcony
ea3565d7-3c67-470d-906f-f06606601870 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.03 | Balcony
a1a7aaac-6ccf-4037-93a4-4ce3202102ee |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.04 | Balcony
c72c09b2-db98-45b3-93ae-33dcff0a8ae5 |  | pass | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.05 | Balcony
1d3f46af-1a6f-4536-b0a2-206f76c20519 |  | pass | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.06 | Balcony
8a7ba3c4-6f1b-456a-a21a-f2b35c2e0d37 |  | pass | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.07 | Balcony
3a3debc9-89b9-4dd9-8072-c048275f8b33 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.08 | Balcony
9f06f7d7-4f2f-48a7-b4f7-477a411006e1 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.09 | Balcony
666c1507-4177-4e66-b037-4e35d5837af2 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.10 | Balcony
073edfe7-a5c3-4552-9457-ac112f99259a |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.11 | Balcony
df4dc406-2bf4-4629-958d-0f707807eb05 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.12 | Balcony
3e53e3f3-23e5-4e20-831f-59aaf7a89eb7 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.13 | Balcony
d0a93128-20c9-4724-a0f4-acb7eac02b8e |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.14 | Balcony
6543fc99-21d2-441e-9192-83d1daea024a |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.15 | Balcony
ca77cf05-5508-4f57-a1fc-bab5ffea6fb6 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.16 | Balcony
b7cfac3a-38c8-4568-bb35-5910e68bf484 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.17 | Balcony
aec506b2-aa27-4258-9685-9d213934b1bb |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.18 | Balcony
f7e799c3-00f8-4e6f-ab0f-45f5eb3476c1 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.19 | Balcony
ffbd9472-47d5-4f93-aea7-35e17bc6cf09 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.20 | Balcony
ea4ba7bf-c6ef-4cbb-9698-f36f083ff3ab |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block D - Terraces | D.21 | Balcony
37f488c7-91a7-4d6a-b7eb-a7113cf01daf |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.01 | Balcony
824ce89e-eb73-417a-bb0b-455cd43dfcf9 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.02 | Balcony
4ca55775-e290-4068-a938-be6e219cc14e |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.03 | Balcony
e3196903-8826-4585-8a32-0b8706887ce8 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.04 | Balcony
5597360d-9ee4-4354-be21-776a3c9db600 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.05 | Balcony
662f7544-08e3-4143-bd69-7ee498c9f959 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.06 | Balcony
6b209e25-d796-4267-b70a-8b680466bdcf |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.07 | Balcony
601b2a86-8503-4ab5-9d7b-36dd4511ce6d |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.08 | Balcony
2450e3eb-1cca-4950-94b6-1f03fc0cc6f5 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.09 | Balcony
dbcda12f-05e4-4a5f-9ced-8c3ce4303af2 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.10 | Balcony
bb3c1929-5930-41c6-bfae-323a93eb25a4 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.11 | Balcony
f602ce18-12ee-4c40-9d2e-699bb9daf2c0 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.12 | Balcony
27a83947-851c-4a92-89f4-dee126f8c864 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.13 | Balcony
df89a4fc-97a7-43dc-abbe-939cf0ed89d7 |  | work-in-progress | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.14 | Balcony
48f08079-b103-4ae4-9c84-3407b7ae3af6 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.15 | Balcony
7ee06e3b-c384-404f-a02b-0887de5e2406 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.16 | Balcony
e6c97a8a-9304-4bc3-8dfb-c111f9ffe309 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.17 | Balcony
cdc28d6f-5499-4701-a729-52390e23c837 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.18 | Balcony
80c7f62f-f690-44aa-8e19-bcfb7f9115fe |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.19 | Balcony
4f555210-d382-4884-aad9-59ae8a6929e9 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.20 | Balcony
61a11cfb-c4e6-4d7f-91a7-87810200075c |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.21 | Balcony
c4592e30-7f41-4f37-a7ff-9bf2ebff48d7 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.22 | Balcony
6de3e829-534e-4ed2-a1c2-d064341e5b2f |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.23 | Balcony
0fe2d065-4aac-4689-8586-fab5dddefb58 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.24 | Balcony
c6f33e91-3bb4-491f-96ad-214ce9cf4997 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.25 | Balcony
9f98bd64-2ebf-487b-9242-f092d0afcaa6 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.26 - PH | Balcony
1918b1fd-329f-4881-8261-907be7f8a998 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.27 - PH | Balcony
f3927fe5-5315-4f77-addd-0e8d16e557d6 |  | not-started | Balcony Waterproofing | checklist | FALSE | FALSE | Site QA | Block E - Terraces | E.28 - PH | Balcony