## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
00b18f1d-1d67-55da-8c2d-f9f0db6d099d | checklist | Balcony Waterproofing |  | Balcony
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
480da7f6-ee06-5806-bfed-93751fefa9ba | checkpoint | Area barricaded off to allow no access to balconies with signs posted/ visible to include date of application, "No access waterproofing work in progress"
8f30ca43-cdc2-526b-94f4-d5b563a69aba | note | Attach relevant photos
1037d7d9-36a0-5ecd-8cf8-040891af90fd | checkpoint | WP details listed at architectural drawings for clarifications are followed.
0211ebc7-0c19-5501-972e-fbc69d62d70d | tickbox | Membrane system & methodology checked off against MN Builders standard waterproofing details & MSDS
70c9fcdb-b295-50cd-8c7d-bb08336e7b8e | tickbox | Substrate clean, structurally sound & ready to receive membrane as per application guidelines of specified waterproofing system.
ae273fda-b0cc-511b-b9bd-821095f0464f | tickbox | Ensure no high points or crevices are in the substrate
e5f38f69-6812-58ff-ab85-96b40dbe8105 | tickbox | HOLDPOINT - Do not proceed if above has not been signed off
97199724-5e31-54d7-82e5-d1a1b52fd9b6 | checkpoint | Apply Polybit PVC primer to all PVC drains and pipes - Apply selected primer at a rate of 100ml/m2 as per datasheet & application guidelines
d96cf244-03fc-5e76-8c59-8fff102a4956 | note | Attach relevant photos
ca33e51d-8cb5-58b2-beae-342846d0c072 | checkpoint | Prime substrate with Polybit Hydrapoxy or PU primer - Apply selected primer at a rate of 150-200 gr/m2 as per datasheet & application guidelines
7b104534-8083-5323-af76-463a645058c5 | note | Attach relevant photos
e28d8a9c-3937-5121-a204-ee64f7a1d260 | checkpoint | Seal all corners, joints, gaps, cracks and penetrations with Polybit HydraFlex polurethane sealant - Apply selected sealant as per datasheet & application guidelines
458e573e-c9de-556d-b1b9-3c48f09763f9 | note | Attach relevant photos
42631763-42b2-5349-ae5a-507a38da7760 | checkpoint | Balustrade base i.e shoe base or angle base installed & grouted with structural grout (as required)
97686a27-8c67-5352-a50c-9908766b3cc8 | note | Joint between bttom of base & substrate to be no greater than 10mm with continuous bead of caulking
3d20910c-5e97-5f23-96cb-f76c95a03dc6 | checkpoint | Overflow at the ends of balustrades in place
4ae24b8a-5d65-5df7-b3ab-41c180858761 | note | Approximate width of over floor to be 50mm
0e1fc875-2be0-521a-9cae-7b3dfe52ca90 | note | Height of overflow must be lower than the bttom of subsill
dec58cca-c7d4-5906-bf9b-96e8eb91add8 | note | Angle to be installed between end of base & wall with top of angle to be at FFL
3418a08f-da4f-5600-b9aa-0decbe414895 | checkpoint | Apply 1st coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
eeb6cc04-214d-5c1d-bdf3-09a76fba5f22 | checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
0e4d9cd3-5e30-55bc-b546-79b8075a41a1 | note | Attach relevant photos
556989f0-e78f-51c5-bfe3-2214783f13ef | checkpoint | Apply 2nd coat of Polybit Hydraguard PU on floors with a turnup of 100mm on walls - Apply selected membrane at a rate of 1.5kg/m2 as per datasheet & application guidelines
d8098c93-d375-4c22-90ef-f55b3f85349e | checkpoint | The WPM must be terminated at the specified height outlined in the wind classification report, also the WPM must be employ at the water stop angles for doors and wondow (if Applicable)
e9a960db-2f10-5451-9e84-d05b22cfb486 | note | Attach relevant photos
a8823488-8dfb-5880-b1c9-8e4be7bf6311 | checkpoint | Dry day for second coat (if required).
c735c198-2846-50df-b8f0-08c7ffd8d3a1 | checkpoint | Carry out dry film thickness test using positector coating thickness inspection instruction. - Review result against datatsheet & application guidelines
85d40d9f-b50d-56b1-a809-6cb0b8ca38c8 | note | Attach relevant photos
| checkpoint | Apply polyguard protective UV topcoat as per data sheet and application guidelines
7cdb4e45-6738-5f3f-bfd3-e32726cbaf6a | checkpoint | If required - Rectification of defective works for failure of flood test/thickness test & all works completed.
eb212c15-9b93-5fa4-8058-7227436a7511 | note | Attach relevant photos
53a39f63-d0fa-5f68-b041-8758ce990b68 | checkpoint | Final sign off - All general waterproofing work completed as per the above ITP
435c1fba-39cb-5a36-ac5c-321e0ffe018c | note | HOLDPOINT - Once all above items have been signed off work may proceed