## Master List Templates
Id | Type | Name | Values | Prompting Name
4c5a5194-4539-436c-9b33-84544af0dc32 | checklist | Add Item Install QA Checklist |  | Item Install QA
c12fa712-88ed-4430-90b9-34a4f039d2c6 | section | Prestart
dc9c8f75-afe6-4697-8c39-a9df5be8fe49 | checkpoint | Opening correct, rebates, drip grooves
7c0d042f-790b-4134-bb09-4dffc55c5353 | checkpoint | Area clear, tidy and accessible
9f7e991a-8fac-4cf3-8717-78e950edebfe | checkpoint | Building wrap correctly installed
b80f3dbb-391f-42a1-b7fa-87743197a00d | checkpoint | Flashing tape correctly installed
b5e1766f-1fe2-458f-9fed-ca1a7d9ebdbd | section | Install QA
3c723d06-15e8-4651-8c0f-01cf5e657cd6 | checkpoint | Correct packings and sufficient at fixings
254c6d1c-e06c-4ef8-9c20-7b06fdb6f778 | checkpoint | Reveal material correct size (TWT) and undamaged
c8728484-743b-4916-9c6a-08f2ce092207 | checkpoint | Reveal grooves correct size and location for linings
95b8c2b4-e910-4c6b-88df-e62e9010ede7 | checkpoint | Frame installed correctly
db7076fd-263d-4949-a98c-9752fe1b0d4a | checkpoint | Head flashing installed
e7fea739-febd-4cd7-82e1-19e2b8ec21c0 | checkpoint | Openings correct and operational
c9a520de-761e-41ea-932c-fc5f35b0adfa | checkpoint | Sealants and air seals installed correctly with Perf rod
c51b863d-ee2a-4207-8641-025eb4e80f65 | checkpoint | Hardware installed and operational
3857b6b2-1f2b-48ac-86a5-0130983e2776 | checkpoint | Manifestation installed
21da88c2-b982-4308-8362-3bc49c7d90cb | checkpoint | Glazing completed correct to specification including wedging
03a7f334-23ef-4135-992e-ce3111be826b | section | Handover / Signoff
6a848c84-177e-492d-8933-b25e66e07882 | checkpoint | Item inspected and damage free
98dc0bbf-5629-4fd0-827f-d04545b6db5c | checkpoint | Area and item left clean and tidy
878d987d-fbe5-44fd-beb7-27df5801737d | checkpoint | Protection tapes and films installed
0c292d0b-2172-4519-9ea1-d121950c8b5a | checkpoint | Item inspected, all elements checked, correct, functioning and approved
f9d3db23-eb5b-4495-a7b4-a898a8c95651 | checkpoint | Windows left clean
b0c1ee99-2e2c-40b1-9dbc-24a6a7e5c20a | checkpoint | Window openers, etc commmissioned
bb9eea3e-a049-4b11-8c09-10382d42dbd5 | checkpoint | Remidial list completed
b046f659-4486-4ac4-9535-6dda7610201b | checkpoint | Handover keys
48aca3aa-5247-434d-893e-701fba333550 | signoff | Request approval
532ad8da-d0ff-41e7-b474-7ff851c00f89 | checklist | Add Variation |  | Variation Details -
3817f27e-322e-4ea9-aaa6-03b1ab58549a | checkpoint | Variation Details Approved
0d17dc3b-72da-5688-a5ad-4bf8f7b3bf81 | textbox | Reference/Drawing/Instruction Number
8496d6fa-8887-5058-96c5-0addf1e0cb3d | textbox | Variation Area
ab8351a7-afc2-5eb0-8ef3-12918c54ad87 | textbox | Materials & labour breakdown
cb1afb71-679b-45d7-a96d-52dfe7a46ed2 | signoff | Request Variation Acknowledgement
954c5ca0-e11b-47e5-a158-b133c3b7a5cf | checkpoint | Variation Completed
a5da6ffe-75f4-440c-aabf-96ae256241db | signoff | Request Variation Signoff
131e30a7-d03d-40e6-b402-889ccc21fd59 | checklist | Add Weekly H&S Checklist |  | H&S Week Starting:
1565a351-da34-469f-9714-2401bf64ff93 | checkpoint | Task Analysis/JSA
0669ea63-d6c8-4e3d-a556-be77ea240321 | checkpoint | Toolbox Minutes
8957937b-828d-4be2-817b-ae17cfed9e82 | checkpoint | Hot Works Permits/Confined Spaces/Working at heights
cd179878-93f3-45d7-ac33-973e6b42f7f1 | checkpoint | Site Safety Inspection Checklists
264dffe1-7567-4b7c-ab14-48a0c55bc978 | checkpoint | Hazard ID
b89174ee-0ee4-4749-81cd-79dd28b0c647 | checkpoint | Accident/Incident/Near Miss Investigation Report
d8a6d3c3-c9e2-44ad-a201-eb8ae122fbac | checkpoint | Notice/Record of Serious Harm Accident
835929b5-9e26-4542-b48d-908934c10aca | checkpoint | Additional Heath & Safety Documentation
86c1a839-ad53-4d01-895b-f7d384781229 | checklist | Centrafix: Bifold Doors and Bifold Windows |  | Centrafix: Bifold Doors and Bifold Windows
547e3b7a-8b71-446e-865b-4415c6a0de15 | checkpoint | Item is correct colour
5fd1d701-8d59-4a07-8714-555f88acc36a | checkpoint | WGANZ labels applied
5fea5373-2655-41a7-aaf7-2aa53e62c7a2 | checkpoint | Surface finish is compliant to standards
460d3c1a-3e11-41cf-9b30-ff7e6a71aa1c | checkpoint | Small joint and backsealing correct
741d01e4-430c-4b8a-89ec-057b1cda112c | checkpoint | Glass inspection items
6e3703b8-16fa-4b26-86a5-672128da2061 | checkpoint | Obscure in correct items
ed31c027-960b-4b59-b1a1-b068c153ab33 | checkpoint | Toughened where required
54f8380b-1a12-4d85-b67f-e2e621cd745c | checkpoint | Free of blemishes to NZ standards
49a9ef72-72c6-4828-9e51-0eb52fc43a05 | checkpoint | Correct edge cover
5087b42e-93ec-4f59-a59f-a5fd62734cdc | checkpoint | Hardware is correct and correctly fitted
b5447eaa-38fc-471f-9101-e82a37f077eb | checkpoint | Liner sizes and timber type are correct
bee7348f-67f5-46bd-b81c-9541172a0c6a | checkpoint | Liners grooved/plain as required
a4c337ac-5b69-41e3-ba17-70a8f3bef4ee | checkpoint | Item is identifiable i.e., labelled
8adb5cf3-954e-46fc-9923-b8c87d596c7c | checkpoint | Sizes are correct against job sheets
47ef11ed-bf79-4cde-90c4-265adbde6fc1 | checkpoint | Drainage correct as per APL manufacturing pack
cbaaae79-1ef0-4c6f-a21c-6044dcc66332 | checkpoint | Doors are square and operating/sealing correctly
2d4caa23-3f42-4eff-89e3-859358a519ee | checkpoint | Strikers are engaging correctly on loose leaves
38b7b7f0-7e06-49af-ae21-e8c286a0663e | checkpoint | Flushbolts/twinbolts are engaging correctly
adc28cf5-1e0a-4456-bc16-36791a788cf5 | checkpoint | Track fitted correctly
ec86ac5a-a7ba-4ae3-b833-fe0fac639e4c | checkpoint | Correct beads supplied for site glazing
8b6c7928-0c8f-4434-a5a2-ae9de723e5e4 | checkpoint | Sillsafe is applied correctly
26648048-c98e-49f5-a300-8f716eae7da0 | checkpoint | Soakers correctly fitted over Sillsafe ends
12ed189c-d37b-4048-846f-c65c0aa9b7c0 | checkpoint | Foam Tape fitted to sill fixing leg
d49c1686-b8f5-441a-adc3-3997c7031ea8 | checklist | Centrafix: Fixed/Awning/Casement Windows |  | Centrafix: Fixed/Awning/Casement Windows
36b735a5-104c-4f0b-ae65-906ec02ef29a | checkpoint | Item is correct colour
02fb647f-e093-45bc-8efe-01e33850838f | checkpoint | WGANZ labels applied
e116af28-9cd9-4dd3-bf90-1ced75561e17 | checkpoint | Surface finish is compliant to standards
c7f8aff0-2913-4c88-8d83-bfc67370032f | checkpoint | Small joint and backsealing correct
1dbfac29-355b-41a6-b281-902374ac3b9a | checkpoint | Glass inspection items
baf3f00d-7b03-4129-82fa-53d8d76c8cda | checkpoint | Obscure in correct items
6a5cf9d1-e3a7-4d45-84a4-2313f3514121 | checkpoint | Toughened to inside or where required
9c244847-2699-46cc-988d-f5f3e0ba1094 | checkpoint | Free of blemishes to NZ standards
e75b60bf-ec6b-43cb-90d1-77fc86ebd302 | checkpoint | Correct edge cover
babb5cf3-5067-447a-a705-70f3d6179e90 | checkpoint | Hardware is correct and correctly fitted
88c6f796-902f-4466-b8ce-b82d26b025bb | checkpoint | Liner sizes and timber type are correct
dca93678-e13a-4ade-8ec1-40f5bb070279 | checkpoint | Liners grooved/plain as required
b3570f48-554e-4867-8c11-e7dacfb60fd4 | checkpoint | Item is identifiable i.e.. labelled
5bb3cce5-65bb-48f0-96f4-91da0956b12c | checkpoint | Drainage correct as per APL manufacturing pack
17ac2c81-a72e-44a4-84e8-5369e3d7b731 | checkpoint | Sizes are correct against job sheets
521ceebc-4cca-4f82-8b7f-7cf56d08cbb7 | checkpoint | Sashes are fitted square and operating correctly
a16979ce-a0eb-4e3a-8e2b-8ea8d67e110d | checkpoint | Restrictor stays fitted where required
237b59c7-e9e3-4a60-b1e9-60a5494f7234 | checkpoint | Correct beads supplied for site glazing
9e1cb929-6eb8-43f4-9ab6-765933d248cc | checkpoint | Sillsafe is applied correctly
0dcca117-32e8-4907-9f3b-520bf43b9c3a | checkpoint | Soakers correctly fitted over Sillsafe ends
2e03dbc9-fa03-4037-b5f4-046c9cf70b7e | checkpoint | Foam Tape fitted to sill fixing leg
67263a2b-3f7f-47ac-bfef-4e195d754a3c | checkpoint | Joinery unit is clean and ready for delivery
7e8f145f-4680-4e8d-b315-b8aaa3c8e7eb | checklist | Centrafix: Hinged & French Doors |  | Centrafix: Hinged & French Doors
4afd6e7d-dd3f-4cc0-a82a-04c806abbcaf | checkpoint | Is item the correct colour
abb0676e-0079-49eb-bc72-8e211fd13100 | checkpoint | WGANZ Labels applied
32a3539d-6f40-4213-811e-2125141bde29 | checkpoint | Surface finish is compliant to standards
f4f1517c-a815-4677-8339-8fe5722b8163 | checkpoint | Small joint and backsealing correct
40f63d76-cf37-42d2-a110-19739d14612b | checkpoint | Glass inspection items
6dc432dd-0129-44fc-8a18-3ca891b4c936 | checkpoint | Obscure in correct items
acdc7c6c-4c9d-40ba-bbde-e5cc4a358ea4 | checkpoint | Toughened where required
7ce71086-bd97-4a5c-a4b2-e78f257c6b6b | checkpoint | Free of blemishes to NZ standards
092883cd-0748-4f13-a959-b5521e28d7a8 | checkpoint | Correct edge cover
fd0efd41-af0f-40a0-9f20-fb8f11236d6b | checkpoint | Hardware is correct and correctly fitted
6b0bd76b-2019-4ea7-8290-3f7c86008b37 | checkpoint | Liner sizes and timber type are correct
1bcce1b9-e547-4c85-8aa6-5067524f5211 | checkpoint | Liners grooved/plain as required
de984496-88b3-474c-97f5-778584a1711f | checkpoint | Iten is identafiable ie labelled
d25c1248-58e4-42bb-a7f8-6657c8014f68 | checkpoint | Sizes and orientation are correct against job sheets
b21c6945-8eee-4831-8743-ce2bb81612a6 | checkpoint | Drainage correct as per APL manufacturing pack
ea396561-4265-4668-92c5-18e47d47e52a | checkpoint | The sill is drained through pre-punched holes in the frame and track
63e86cd0-f6a1-4296-b376-a992c1952897 | checkpoint | 6mm holes located at the base of the face near the mitres
d82014eb-8d57-4cee-a4ea-8e4dc8974e29 | checkpoint | Punched drainage slot by the mitre blocks (this area on the sill should not be sealed)
8134cbfd-72d2-42c7-9538-2135fd04e6b6 | checkpoint | Doors are square and operating/sealing correctly
ca5c8e24-89e0-48e6-a777-5f3b086d9f7e | checkpoint | Strikers are engaging correctly
9f8a9e5c-52a1-4b94-967f-ba8b43cf5625 | checkpoint | Flushbolts/twinbolts are engaging correctly
9d165972-c0a8-46a0-9063-af3b8fd29b30 | checkpoint | Correct beads supplied for site glazing
7ff9b5ac-5c01-4eb0-93ba-ba6cfb6800e6 | checkpoint | Sillsafe is applied correctly
987eabb7-026a-4db0-90d3-ca71491c80bf | checkpoint | Soakers correctly fitted over Sillsafe ends
6b78c960-c5b0-4aff-8467-f20aa3b0da85 | checkpoint | Foam Tape fitted to sill fixing leg
8e6b0d49-1afc-45cd-b703-664219d1c822 | checklist | Centrafix: Sliding Doors & Sliding Windows |  | Centrafix: Sliding Doors & Sliding Windows
67fff268-0668-47ec-9630-444752923561 | checkpoint | Item is correct colour
ee8c8ee5-5620-4bc0-879e-a07f93f3fe90 | checkpoint | WANZ labels applied
e4865bbf-94fa-4173-bf28-6a61759878f9 | checkpoint | Surface finish is compliant to standards
376804ff-4722-42f8-8c73-8f591d1588c2 | checkpoint | Small joint and backsealing correct
54eb17a4-00ce-431a-ace7-0f7c27ef3129 | checkpoint | Glass inspection items
0813397b-eaf0-4c6d-9b71-ad49827917dc | checkpoint | Obscure in correct items
ef10802d-3707-4418-9bda-3ba0b30452c0 | checkpoint | Toughened where required
5f51cca3-3c31-4607-b30f-bc8995ab2410 | checkpoint | Free of blemishes to NZ standards
bcaa90e9-bd3d-4936-a10b-67b43fc8bc63 | checkpoint | Correct edge cover
fdb9d9d2-45fd-49ea-aad7-4b78f6590098 | checkpoint | Hardware is correct and correctly fitted
3f78225b-2dd1-4415-9300-d2525d63bff5 | checkpoint | Liner sizes and timber type are correct
072d301f-86dc-4e9a-9375-71f2b1a83711 | checkpoint | Liners grooved/plain as required
41e2a922-bfd1-44ae-9f4d-fb9d4118e96d | checkpoint | Item is identifiable i.e., labelled
507b09d1-c8a6-41c9-8bd4-a8e626417344 | checkpoint | Sizes are correct against job sheets
5159e11c-a401-4ac0-b974-ab47a74ce9d8 | checkpoint | Drainage correct as per APL manufacturing pack
50659570-6c1e-41d6-8b8f-c22f17b24ffc | checkpoint | Panels are sliding freely
df1f2a74-6cb4-467a-8698-55a8d6e67ddd | checkpoint | Correct weight rollers fitted
fcd04201-43bf-4466-a2f5-ecfcbcea7407 | checkpoint | Stops and end caps fitted correctly
3c800690-0ea8-452e-82c5-26b5d10207fe | checkpoint | Infills are correct either installed or with the door
f6d24d01-18c0-4394-ac72-c8099e46d6c0 | checkpoint | Sill Safe is applied correctly
83572acd-c244-4a08-abdd-95b4284e9c35 | checkpoint | Soakers correctly fitted over Sill Safe ends
62154e66-ab9d-414c-95f6-fca1d1d9e4a4 | checkpoint | Foam Tape fitted to sill fixing leg
caea2f79-bc7d-4c8e-aeaf-aab371054833 | checkpoint | Joinery is clean and ready for delivery
64f65ea6-078a-4b7b-bd96-ef12f5e2f8a3 | checklist | Woods - Grafton Install QA Checklist |  | W
f3d408dc-948d-4085-8da1-8bda54114f32 | section | Pre-start
c8d05fe5-ec28-4917-a50c-dc5d29705f63 | checkpoint | Openings Correct
f694bbf0-240e-4525-801e-ca7adfc9543f | checkpoint | Area Tidy
830d9bad-0da1-4034-887d-61a9819c91a4 | checkpoint | Water Proofing / Flashing Tape installed
4348e6f5-f408-4da7-bb77-68c84d39d7e9 | section | Install
0b04e9f9-78f4-4545-9832-bbb255a84c28 | checkpoint | Correct Packing
30f79605-263d-49c6-a230-82dd292cee5f | checkpoint | Frame Installed Correctly / As per SD’s
a65e1a50-d426-43da-a49c-8cc81b5bf503 | checkpoint | Fixings as per SD's / Overseal Complete
4ccdd101-6023-4e02-aefd-d658e437fbc1 | checkpoint | Seals and PEF Rod Completed
8b67c5b2-bd60-4387-a7e1-0ecab2be67cb | checkpoint | Seal between 6mm & 20mm Wide
94db30c8-c893-40c8-9bf6-65338510fe37 | checkpoint | Sub Sill End Dams sealed correctly
c391fd9c-3fe8-4b4f-8f28-dbf1103cec9f | checkpoint | Head & External Flashings Installed
1490a0f7-bcfc-4d9b-9295-3eae13eb55d5 | checkpoint | Hardware Installed and Operational
e1e7ff09-c332-4ae1-9f9f-0fd933544db1 | checkpoint | Manifestation Strips N/A
e8ddd385-d4a6-4f66-b2dd-fd3ecbedf49e | section | Glazing
a43f9681-f631-4b03-9709-035386defaad | checkpoint | Glass Defect Free
fd68c266-b2c6-4b5a-94f6-caaaf8e550f7 | checkpoint | Back Pan - Clean Cavitiy - Backpan QA if installed on site
33f7ae68-33b2-47e3-9cb8-ae2266af2b1a | checkpoint | Glass Type - Installed Correctly
df6ac5c2-9823-41f1-8cb6-c73e65a15a77 | checkpoint | Glass Installed - Correct Orientation
2237d2e8-bc28-473a-bf46-f1f4513dbe72 | checkpoint | Wedge - Complete
cb2b6054-e193-4fb0-80ab-0fef1d493792 | section | Handover
5239a585-5194-48f6-9d7b-8dfb7af75262 | checkpoint | Defects List Completed
46ee65b3-d52b-44ba-b064-ab8716fc81f3 | checkpoint | Area Clean and Tidy
04757274-f54d-4178-8908-48c61d8d3e9b | checkpoint | Window opening Functional
7e0bb2b9-37d5-4fe2-a983-4e3ccc0dc41c | checkpoint | Doors Operational
6b57082a-a4f0-4b99-96b3-aed32c15b224 | checkpoint | Handover Keys
187be866-5472-4c7a-96f3-c76dfc0c9336 | checkpoint | Please find pictures attached
f11636d2-5fc8-46d5-ac72-326c48829803 | section | Client Signoff
192cded3-8b7b-4c4f-9aca-7b85fc510fef | checkpoint | SIGNED