## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
2223e847-6c61-4feb-8be1-1693f7a97ad0 | checklist | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ | itp | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ
b69c460b-73a7-424b-bdb4-0b4deadbae15 | section | Details
293c3191-5b74-4587-b7cd-8da022cd719d | checkpoint | Maximum Lot Size - 1 Culvert
d2bef293-d61c-50be-ad49-f4679a6064b3 | note | Acceptance Criteria and Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
38b62273-d7f9-543f-8f6d-5e877d927f40 | note | Check Item - Check Item
33f20396-a47d-54f3-bf5d-c47b386459b9 | note | Reference - MRTS04 Table A.2
91a0479f-cf2f-418f-8335-7ae9b2787cdb | checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
ca121c07-a963-5583-b7f5-e218066d2a0b | note | Acceptance Criteria and Frequency (Project Specific) - Administrator Approval - Per Project
c3038458-88a9-5db5-b42a-f7a1499891d9 | note | Check Item - Hold Point 2
f8bf377f-efa9-5b4c-9cba-71b85b6b12fc | note | Reference - MRTS03 Cl 11.3.1
43f345e5-766e-4d10-83f1-c1835c443ebc | signoff | Hold Point
96d8da73-2bc2-46d5-874b-865a883268ac | section | Excavation
4efb6554-969c-436e-aecc-7ee97a6d05c6 | checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
a493ec26-0d4c-53e7-be6c-0f9b607bfbb0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
89d358c5-3920-5645-a564-e94638c3b56a | note | Check Item - Check Item
922b95a6-62a7-523d-86d2-a733614ed741 | note | Reference - MRTS03 Cl 12.3.1
fa3852f0-2f29-459e-8ec1-ec1d215683e4 | checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
47ed0c94-1f5c-5f71-bb23-f3901f8d6d48 | textbox | Reference Unsuitable Lot No. :
d644e436-f0f1-5d74-9e54-df5cdbf86334 | note | Acceptance Criteria and Frequency (Project Specific) - Visual - Per lot
b7cade95-54f0-5283-9830-4a479f52d44b | note | Check Item - Hold Point 4
822efda0-1279-534a-a409-166de5b3c9d1 | note | Reference - MRTS04 Cl 9.4
bdb0ac6f-921b-47d1-929c-c24c4a4efee9 | signoff | Hold Point
f5e34e3f-a662-44a3-8315-d1da72ea5607 | checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation - AS 1289.5.4.1 or AS1289.5.7.1
98fe33f6-55b5-5f00-9016-79d9e226d3b8 | note | Acceptance Criteria and Frequency (Project Specific) - Cl 15, Table 15.3(b)
a7d7100b-0fb6-5320-b304-2eaf746c45d5 | note | ○ CV 95% minimum (1 tests / 50m2 - min 2 / lot)
3aca3eca-12a0-5f14-8557-f6f6e63dad12 | note | Check Item - Test results
c892eb99-8509-5312-b92a-30b3abf461e4 | note | Reference - MRTS04 Table A.2
e226b779-8c58-47fb-b4e3-943985c18cb0 | section | Installation
3c622348-aff6-4788-80cc-9a86cd4c92d5 | checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 & MRTS71
a478407c-3fb0-54b8-aacc-4cff309ba6e6 | note | Acceptance Criteria and Frequency (Project Specific) - MRTS03
c493e606-6d66-551d-9b8f-be4dfb9965f5 | note | ○ Cl.15: End Structures
7f9fd1f3-e5ca-5fea-90a6-e3aa64e89cda | note | ○ Cl.21: Gullies
35a88e25-babb-5d11-8aad-c80d4809a770 | note | ○ Cl.21: Access Chambers
884900f0-bac2-50c2-8d06-0810ae782d5c | note | Check Item - Check Item
eb9e1f91-903f-5406-b380-c8e677e25856 | note | Reference - MRTS03 Cl.6.1
65be6c1b-ef3e-44cc-a98c-547778026b13 | checkpoint | Precast: Installed in accordance with MRTS03 - Components shall be laid on a foundation bedding which provides continuous even support to the structures.
cca5c89b-71e7-51f7-a1d9-67b6daf4d521 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b393fa4-983f-5de2-a3e6-1f2d898ecc16 | note | ○ Cl.19: Precast End Structures
f90a2d33-525f-57e5-96cf-9fff5ff5a36d | note | ○ Cl.21: Precast Gullies
cdc6ae48-8d15-502a-be99-16e8d72f93cf | note | ○ Cl.21.5.1 Precast Access Chamber
61c89b62-043c-58e2-8492-2ada9ca96c8c | note | Check Item - Check Item
89edf5a1-a0ab-5e45-b560-e41f7b2e06c5 | note | Reference - MRTS03
cf50c872-288f-5c31-bb9f-0ea4e001f864 | note | ○ Cl. 16
1b23088b-6c47-5d67-8393-7172671f3407 | note | ○ Cl. 21
80979e20-4f38-51a4-b5d8-a872f3b403e7 | note | ○ Cl. 21.5.1
b567fb59-f323-448c-badf-511f1f75627c | checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
3430cb37-83ef-5afc-a8a5-8cc076bc9977 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
800cac85-4224-5ce8-a66d-aaf8bc3181f4 | note | Check Item - Check Item
6e9eef64-8289-5a89-aa20-1049b28eb3f6 | note | Reference - MRTS03 Cl. 21.3
dfaa4058-eef2-4cad-9aa6-219d62764428 | section | Tolerances
7d3c0253-be18-4095-85d8-d5adbb323067 | checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
8a850430-d178-5dc8-b1d2-34f61f26aefd | note | Acceptance Criteria and Frequency (Project Specific) - ±50mm (All points specified on drawings)
c940c91f-7bdb-58f6-aca8-e529eef468aa | note | Check Item - Survey Results
04b13825-791e-549f-a170-c1ad4c3d3a70 | note | Reference - MRTS03 Cl.21.4.2
fb4854d8-5c50-4a8c-90b7-ed8e112e216e | checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
5673cc54-89f1-58d0-832d-1c1dbfbd0d54 | note | Acceptance Criteria and Frequency (Project Specific) - ±10mm (All points specified on drawings)
ef81275d-babf-51fa-bc40-87b3d7c56478 | note | Check Item - Survey Results
1aee99e6-2f32-5107-853d-ad44122a3d0a | note | Reference - MRTS03 Cl.21.4.2
9115132c-3b4f-4f41-afec-19902eaa5051 | checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
2db82d9d-dde8-5096-8f59-b33775849d3e | note | Acceptance Criteria and Frequency (Project Specific) - Gullies:
7ae75b0d-7505-5b7e-9723-9063b4b2b25f | note | ○ ±100mm in road direction
c9e6fd66-4687-5a46-97cb-bc4e6252c9bd | note | ○ ±50mm perpendicular to road
88a8f2f1-f02d-5d85-a726-4dc76c79a67f | note | Access Chambers:
390c1a0f-273e-5c31-aca0-492a632de92a | note | ○ ±100mm (All points specified on drawings)
1bdc3cd0-1021-5a1e-9102-ef548406d75c | note | Check Item - Survey Results
72f6fadb-2318-52c0-aea4-0f98cceecdb5 | note | Reference - MRTS03 Cl.21.4.1
9d693f3f-d3c4-4fd1-a6bb-737ed667b88c | checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
dc6788a0-ea2a-56bd-96f3-544c6054c45c | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f25cdfff-adf4-54ee-87f0-5d194d4ae2ab | note | Check Item - Check Item
4331d280-bfbf-5112-90d3-bcb1c6b2bf6c | note | Reference - MRTS03 Cl.21.4.2
290096fa-3e1b-4ab3-86c4-96049e7f73c5 | checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
75aa627b-f4b8-5699-b5c0-4fca1393344f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
c7f26026-aad1-5168-ad65-c39cf9e408a6 | note | Check Item - Hold Point 5, Hold Point 6
c0bc4a07-0017-5766-8b99-0d37b5fd6d7d | note | Reference - MRTS03 Cl.21.3
348b4aaa-c002-4271-afbd-c6c7a53918ab | signoff | Hold Point
69b077da-cec1-4694-b801-2d50154c4278 | section | Backfill
bfe0fdcf-84c6-49a9-8063-44d766789912 | checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
49eed5f1-7da9-50f7-adeb-e9bfe9dd9ad3 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
94c43eb6-139a-5585-8bb1-a4e86c829833 | note | Check Item - Hold Point 4
1763df09-c45c-582d-a468-cdb8081259a7 | note | Reference - MRTS03 11.3.10
ded6a73a-69f8-4847-aa78-02c52d717758 | signoff | Hold Point
2f04afa9-7d07-4af9-8ab1-084f4702c399 | checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
b53f375e-0a39-5ebb-ae2a-2e53eb3658df | note | Acceptance Criteria and Frequency (Project Specific) - Quarry Material Test Results
96ca09a7-7967-50f9-8056-ce30e5c9247f | note | Check Item - Hold Point 8
d2e4cd7c-15a6-5c98-a5c2-2382ac83d3a7 | note | Reference - MRTS04 Cl. 14.2.1
164953e1-9ccb-4583-b3b8-49f80a14bb0d | signoff | Hold Point
e7c0e0e2-470d-42e2-8d21-929bc2a19dc1 | checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
d48953a5-91f4-577f-a7eb-40a680de2f60 | note | Acceptance Criteria and Frequency (Project Specific) - Test Results
d96d4662-f470-596c-bb76-22fbd58d8d0d | note | Check Item - Witness Point 5
4f8f5256-d4a3-5f45-9fea-a47011b265be | note | Reference - MRTS04 Cl. 19.3.1
7a735ad0-c8ad-4eb2-85be-3570de831167 | checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, and so on have been completed and inspected, and any specified curing periods have elapsed.
1b4f136e-9b2c-5b63-a010-4120a0e55e33 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
5f02f401-aeb9-5f83-a1f6-0e82eda2b7c6 | note | Check Item - Hold Point 14
6bd1bb4c-1d9f-5734-a033-033b8770df51 | note | Reference - MRTS04 Cl.19.3.3
0c58fc12-37ee-4530-ba08-df0c718b67c6 | signoff | Hold Point
a0fcdd7c-e045-410c-98ad-fbe22f99e1fd | checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
de31f19f-5085-51d3-bee4-6154bb49c1f4 | note | Acceptance Criteria and Frequency (Project Specific) - Class A: WPI < 1200, PI > 7,
1455db66-97c0-5110-a3e5-fbb3c72b259e | note | ○ % passing 0.075mm: 15 - 30
8d1fe649-8075-5952-bc30-196838771572 | note | ○ Class B: 1200 < WPI < 2200
c69cccb6-03bb-5f24-a0ac-9ef484de5f6f | note | ○ Class A/B: 100% passing 25mm
91ccad1b-5219-56bd-af8f-7e56fecfacc7 | note | Check Item - Witness Point
f9d581ac-77df-57a6-97fa-6d23e31828f5 | note | Reference - MRTS04 19.3.1, 19.2.2
13bbc4b3-3ec7-484d-8d46-2eff75dc81b8 | checkpoint | Compaction - Q142A, Q141B
6a489e98-a59e-54dd-a581-79c7316e24da | note | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
28bd9d0e-cbe8-5317-a1ac-a1c8fe522a55 | note | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
190e1975-86b3-54ab-a9ad-0e2b2950d5fc | note | Check Item - Test results
3663444b-b184-5d64-9fa0-c64d9d1446d3 | note | Reference - MRTS04 Table 15.3(b), MRTS03.1 Cl.1
3c50dfa6-906e-48d6-a9b4-41106e5a4541 | checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
ce7fef80-1fce-51f7-bfff-4ce790f67a5f | note | Acceptance Criteria and Frequency (Project Specific) - Class A: 70-100%
c1824456-4340-56a9-86c3-235d545c1df4 | note | ○ Class B: 80-110%
f6a2a2dd-fe82-5bf3-9191-ba846def8e33 | note | Check Item - Test results
ea4f1610-1c96-5464-8ce1-4b4923fb210b | note | Reference - MRTS04 Table 15.3(c)
d121b8f7-538d-4f24-a8c1-c31e95b44a60 | section | Completion
f3d98613-d6ca-4a01-9467-f04f51aadebf | checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
ed054509-1eb8-5046-bfe8-e95715185799 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3e03187a-ce38-5110-9742-3060c21e9751 | note | Check Item - Witness Point
58ea9517-912a-5653-8eea-1b4adde567c1 | note | Reference - MRTS03 Cl. 21.6.2
c269161c-7971-4d7b-94df-14405d96cde5 | checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
d842c967-9805-5ab0-903e-6dab97121806 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
0230c03c-d4ec-574c-9758-097910f3e93b | note | Check Item - Hold Point 3
b8973046-7cec-5d65-ac95-16e28f599fec | note | Reference - MRTS03 Cl11.3.5
f30be7b9-9278-4568-b3d0-8e1fa7d96e8b | signoff | Hold Point
481afc67-4987-4dc2-8b3d-77b4d7e3a1bf | checkpoint | Final Verification
83e1286a-be19-55ea-bc08-f74795c7d55d | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
9fd0b727-b765-529d-9b83-02ad6b05d2fa | textbox | Print Name:
8a3fd2d4-2399-57c4-9cf9-e1fa66720640 | date | Date:
68b74ba5-e1de-57dc-b456-ad42a0271a63 | note | Project Manager Verify that the Above has been Constructed according to Specification
2fb4d60a-aea4-5248-aa83-a9af7a4d691b | textbox | Print Name:
ec9e5a53-e7e8-5110-8c33-a0e47b833ab3 | date | Date:
0a3379cf-587c-4f6e-b30f-6de25eb362d2 | signoff | Signature
c7ed0b22-a887-46d1-a4c4-f0195248c8d0 | section | Final Sign Offs (to be completed at closure of Lot)
8196b64b-863a-450c-8942-a8e679bf12be | checkpoint | Agreed Quantities
b73ab12d-b0ef-404c-bc21-8953863418d2 | signoff | Agreed Quantities Sign Off
b930208a-7075-4dae-b084-eecf932376de | checkpoint | Closure of Lot
21c230a8-9074-41e5-9358-e2261ad1eb57 | signoff | Closure of Lot Sign Off