## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Material Testing | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Material Testing Rev B
section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Crushing Resistance
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4407:3.10
label | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Weathering Quality Index
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4407:3.11
label | Acceptance Criteria - AA, AB, AC, BA, BB, CA
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 10,000 m3
label | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
label | Acceptance Criteria - Compacted using NZ Vibe Hammer
label | ○ 4-day soaked CBR ≥ 80%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
label | Acceptance Criteria - PI ≤ 5
label | ○ CI ≤ 3
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - NZTA M04: 2024
label | ○ AP40 - Class 2
label | ○ PI and CI applies
label | Designer - A
label | Eng. Rep - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Broken Faces Content
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.14
label | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
label | Designer - A
label | Eng. Rep - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
label | Notes:
label | H = Hold point up to approval of Optimisation Testing
label | M = Monitor during production
label | Detail of Activity / Test - Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - NZTA M04:2024-Class 2
label | ○ Class 2 in Table 12 for PSD
label | ○ Table 13 for shape control
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Designer - A
label | Eng. Rep - I
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Blend Particle Size Distribution
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 per 1,000 m3
label | Inspection / Test method - NZS4407:3.8.1
label | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
label | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
label | Designer - R
label | Eng. Rep - A
label | Contractor - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Indirect Tensile Strength, ITS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 Optimisation test per aggregate type
label | Inspection / Test method - NZTA T/19: 2020
label | Acceptance Criteria - Testing at 1mm/min:
label | ○ BSM Dry ITS: 175 kPa to 400 kPa
label | ○ BSM Soaked ITS: 150 kPa to 350 kPa
label | Testing at 50.8mm/min:
label | ○ BSM Dry ITS: 210 kPa to 480 kPa
label | ○ BSM Soaked ITS: 180 kPa to 450 kPa
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Designer to advise on binder content(s)
label | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
label | Designer - R
label | Eng. Rep - A
label | Contractor - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Unconfined Compressive Strength, UCS
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 Optimisation test per aggregate type
label | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
label | Acceptance Criteria - UCS limits set by the design engineeer
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Designer to advise on binder content(s)
label | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
label | Designer - R
label | Eng. Rep - A
label | Contractor - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
label | Detail of Activity / Test - Modified Maximum Dry Density
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Single Point DD vs WC during optimisation test
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - To determine target density
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Designer
label | Project Specific Notes / Instructions - Required before Stabilisation comences
label | Designer - R
label | Eng. Rep - A
label | Contractor - I
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Pre Construction Works Rev B
section | 2.0. BEFORE BITUMEN STABILISATION STARTS
checkpoint | 2.01 - Setout section
label | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
label | ○ Refer to Project Specific Notes
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Document existing furniture
label | Record documents (QCP - Quality Control Portal) - Electronic survey files
label | Responsibility - Contractor & Stabilising Contractor
label | Project Specific Notes / Instructions - Note that the two transition ends of the site will require a digout as per the digout table on DWG#T2W-802-007.
label | ○ Extent of these as follows:
label | – RP 4235 to RP 4270
label | – RP 7580 to RP 7640
label | Designer -
label | Eng. Rep -
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Pre-hoe entire area, then shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Use grader's machine control and inspect shape
label | Record documents (QCP - Quality Control Portal) - N/A
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
label | Designer -
label | Eng. Rep -
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Pre-hoe entire area, then shape and proof roll
label | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site specific methodology statement and/or IFC drawings and proof roll while compacting
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Visual check or Vibratory Roller's response meter
label | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
label | Designer -
label | Eng. Rep -
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.04 - Spreading of Cement (for modified subbase) (2.24t/m3 x 0.19m x 1.5% = 6.4 kg/m2)
label | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - every 400 m2
label | ○ every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 0.5kg/m2 of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep -
label | Contractor - R
checkpoint | 2.05 - Spreading of Cement (for modified subbase) (2.24t/m3 x 0.19m x 1.5% = 6.4 kg/m2)
label | Detail of Activity / Test - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep -
label | Contractor - R
checkpoint | 2.06 - Compaction of Modified Subbase
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If MDD can't be achieved then the PDT- MDD must be approved by the ER
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Compaction of Modified Subbase
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | 2.08 - Compaction of Modified Subbase
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 95%
label | ○ Minimum DoC ≥ 92%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Overlay and check levels
label | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Prior to stabilisation per section
label | Inspection / Test method - Survey
label | Acceptance Criteria - Subbase + 15 / - 5
label | Record documents (QCP - Quality Control Portal) - Surveyor
label | Responsibility - Stabilising Contractor with Main Contractor
label | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
label | – overlay aggregate quality / consistency
label | – moisture content
label | – any concerns with shape and tie in
label | – etc.
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Production Plan
label | Detail of Activity / Test - Plan showing cut lines and sequencing of works
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to each section
label | Inspection / Test method - Daily Report
label | Acceptance Criteria - Points covered in NZTA B/5
label | Record documents (QCP - Quality Control Portal) - Daily Production Plan
label | Responsibility - Stabilising Contractor
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - FBS | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - FBS Rev B
section | 3.0. BITUMEN STABILISATION OPERATION
checkpoint | 3.01 - Stabilising Agents
label | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Per Batch
label | Inspection / Test method - TNZ M/15
label | Acceptance Criteria - Conform to Specification
label | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.02 - Stabilising Agents
label | Detail of Activity / Test - Cement, GP
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Per Batch
label | Inspection / Test method - NZS 3122
label | Acceptance Criteria - Conform to Specification
label | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.03 - Stabilising Agents
label | Detail of Activity / Test - Bitumen (130/150)
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Per Batch
label | Inspection / Test method - M/1
label | Acceptance Criteria - Conform to Specification
label | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.04 - Weather conditions
label | Detail of Activity / Test - Material behind stabiliser
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading
label | Inspection / Test method - Measurement
label | Acceptance Criteria - Material after stabilisation:
label | ○ BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.05 - Weather conditions
label | Detail of Activity / Test - Wind
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - Wind speed < 25 km/hr
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.06 - Weather conditions
label | Detail of Activity / Test - Rain
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Prior to spreading cement or lime
label | Inspection / Test method - Local weather stations
label | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilsing Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.07 - Spreading of powdered stabilising agent (Cement / Lime)
label | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - every 400 m2
label | ○ every 150m for a 2.4m width
label | Inspection / Test method - Weigh mat or tray
label | Acceptance Criteria - ± 0.5kg/m2 of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.08 - Spreading of powdered stabilising agent (Cement / Lime)
label | Detail of Activity / Test - Compare area spread with weight used for each spreader load
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going measurement by computer/load cells
label | Inspection / Test method - Measurement each run
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.09 - Injection of bituminous stabilising agent (FBS or BE)
label | Detail of Activity / Test - Flow meter and operator's display readings
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
label | Inspection / Test method - Visual display reading
label | Acceptance Criteria - ± 5% of specified rate
label | Record documents (QCP - Quality Control Portal) - N/A
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.10 - Injection of bituminous stabilising agent (FBS or BE)
label | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Record usage from PCU at the end of each run
label | Inspection / Test method - Record readings at the end of each run
label | Acceptance Criteria - ± 3% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.11 - Injection of bituminous stabilising agent (FBS or BE)
label | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - For each bitumen tanker load
label | Inspection / Test method - Dip bitumen tanker before and after
label | Acceptance Criteria - ± 2.5% of specified rate
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.12 - Injection & Mixing of Water
label | Detail of Activity / Test - In-situ Stabilisation process
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On-going visual assessment
label | Inspection / Test method - Visual and hand squeeze test
label | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.13 - Depth of stabilisation
label | Detail of Activity / Test - Depth of stabilisation
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - Every 200m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - +15mm / -5mm from specified depth
label | Record documents (QCP - Quality Control Portal) - Daily work Log
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - I
label | Contractor - R
checkpoint | 3.14 - FBS material
label | Detail of Activity / Test - Stabilised material strength - ITS
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
label | Inspection / Test method - NZTA T/19N: 2020
label | Acceptance Criteria - Testing at 1mm/min:
label | ○ BSM Dry ITS: 150 kPa to 400 kPa
label | ○ BSM Soaked ITS: 120 kPa to 350 kPa
label | Testing at 50.8mm/min:
label | ○ BSM Dry ITS: 180 kPa to 450 kPa
label | ○ BSM Soaked ITS: 150 kPa to 420 kPa
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | 3.15 - Compaction
label | Detail of Activity / Test - Plateau Density Test
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
label | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
label | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
label | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess.
label | ○ IANZ report when processed
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.16 - Compaction
label | Detail of Activity / Test - Maximum Dry Density
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
label | Inspection / Test method - NZS 4402.4.1.3
label | Acceptance Criteria - For analysis of DoC
label | ○ To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes
label | ○ Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | 3.17 - Compaction
label | Detail of Activity / Test - Degree of Compaction (DoC)
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1,000m2
label | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
label | Acceptance Criteria - Average DoC ≥ 98%
label | ○ Minimum DoC ≥ 95%
label | Record documents (QCP - Quality Control Portal) - IANZ Report
label | Responsibility - Stabilising Contractor
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.18 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
label | Detail of Activity / Test - Clegg Impact Value
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 5 per 1000m2
label | Acceptance Criteria - CIV ≥ 50
label | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
label | Responsibility - Stabilising Contractor
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.19 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
label | Detail of Activity / Test - Degree of Saturation, DOS
label | Action (Hold, Monitor, Witness) - M
label | Minimum Test Frequency - 5 per 1000m2
label | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
label | Acceptance Criteria - aim for DOS ≤ 80%
label | Record documents (QCP - Quality Control Portal) - IANZ report
label | Responsibility - Contractor
label | Project Specific Notes / Instructions - Report only
label | Designer - I
label | Eng. Rep - A
label | Contractor - R
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Post Construction | itp |  |  |  |  | ITP - Foam Bitumen Stabilisation Zone 8 - 802 Puketerata Hill - Post Construction Rev B
section | 4.0. Testing and Sgnoff
checkpoint | 4.01 - Finished Pavement
label | Detail of Activity / Test - Crossfall
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - ± 0.5% of specified crossfall measure
label | ○ 2m apart
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - Finished Pavement
label | Detail of Activity / Test - Stabilised width
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - 1 every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - -20mm, +100mm
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Finished Pavement
label | Detail of Activity / Test - Surface Shape
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - < 10mm using 3m straight edge
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
label | Designer -
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Finished Pavement
label | Detail of Activity / Test - Surface Levels
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - every 20m
label | Inspection / Test method - Measurement
label | Acceptance Criteria - -5mm, +15mm
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Designer -
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.05 - Finished Pavement
label | Detail of Activity / Test - Surface Finish
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Per Lot
label | Inspection / Test method - Visual
label | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
label | 2. Smaller aggregate held in place by fine material
label | 3. matrix does not displace under normal trafficking and/or sweeping
label | Record documents (QCP - Quality Control Portal) - Survey
label | Responsibility - Stabilising Contractor
label | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
label | Designer -
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.06 - Finished Pavement
label | Detail of Activity / Test - Roughness
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Before Sealing
label | Inspection / Test method - TNZ TM 7003 v1
label | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
label | Record documents (QCP - Quality Control Portal) - Test Certificate
label | Responsibility - Contractor
label | Designer -
label | Eng. Rep - A
label | Contractor - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.07 - Pavement Layer Signoff
label | Detail of Activity / Test - Assessment of all test results for conformity
label | Action (Hold, Monitor, Witness) - H
label | Minimum Test Frequency - Each Lot
label | Inspection / Test method - Site Inspection
label | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
label | Record documents (QCP - Quality Control Portal) - NCR
label | Responsibility - Engineers Representative
label | Designer -
label | Eng. Rep -
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature