## ITP Cover Page - Footpath
Northern Access road & carpark Footpath/ Shared path Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-006-004 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | SP2-006-004
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Northern access road & carpark Footpath/ Shared path |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 27.4.5 Footpath
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2025-08-01 |  | Cordelia Girdler-Brown/Nick Adams |  | Draft for Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Approved | 13/01/2025 |  | Cordelia Girdler-Brown |  | Changes made as per comments from DN1210-WSP-GCO-0100 |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS |  |  | #VALUE! |  | 15/01/2025 | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 15/01/2025 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Footpath
Kerb & Channel Inspection and Test Plan
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-006-004 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: 13/01/2025 | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS | [11 empty] | General Comments: 1. Item numbers are untidy and confusing (I.e. not in standard order). 2. Standard / Specification references are unclear. It is good that test methods are referenced, however, there should also be a reference for the acceptance criteria. Additionally, many references just say "Standard" - this is not an acceptable reference. | The necessary changes have been made.
3.1 | SUBGRADE IMPROVEMENT LAYER - AP65-2 SOURCE MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 100kN | NZS4407:2015 Test 3.10 TCC-IDC-IT-4.3.1-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | ≥60% | NZS4402 Test 6.1.1 TCC-IDC-IT-4.3.1-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, CA or CB | NZS4407 Test 3.11 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.2 | SUBGRADE IMPROVEMENT LAYER AP65-2 PRODUCTION MATERIAL TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.2.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 63.0mm 100% passing 37.5mm 68-90% passing 19.0mm 42-76% passing 9.5mm 26-58% passing 4.75mm 16-44% passing 2.36mm 10-33% passing 1.18mm 6-24% passing 0.425mm 3-14% passing 0.075mm 1-6% passing | NZS4407 Test 3.8.1 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.2 | Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 34-50% 19.0 – 4.75 18-40% 9.5 – 2.36 12-32% 4.75 – 1.18 6-24% 2.36 – 0.6 2-20% 1.18 – 0.3 0-15% 0.6 – 0.15 0-12% | TCC-IDC IT-4.7.2 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.2.3 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4407 Clause 4.3 TCC-IDC-IT-4.7.1 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.2.4 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | ≤ 8 | NZS4407:2015 Test 3.4 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.2.5 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent Washing method | ≥25 | NZS4407 Test 3.6 TCC-IDC-IT-4.7.2 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.2.6 | Accelerated Weathering | NZTA T/20 Ethylene Glycol Accelerated Weathering Test | ≤ 30% increase in fines | TCC-IDC IT-4.7.2 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.3 | Basecourse Layer TCC-AP40-1 - PRODUCTION PROPERTY TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.3.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of 130kN | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.3.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | ≥ 80% | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.3.3 | Accelerated Weathering | NZTA T/20 Ethylene Glycol Accelerated Weathering Test | ≤ 30% increase in fines | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.3.4 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | PS 20.9 TCC-IDC IT-4.8 table 4.6 | IANZ Accredited Report | 1 Test Per Material, Per Source every 10,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.4 | Basecourse Layer TCC-AP40-1 - PRODUCTION PROPERTY TESTING - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
3.4.1 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 37.5mm 100% passing 19.0mm 60-75% passing 9.5mm 37-50% passing 4.75mm 20-35% passing 2.36mm 12-28% passing 1.18mm 9-20% passing 0.600mm 7-12% passing 0.300mm 3-10% passing 0.150mm 0-5% passing 0.075mm 0-5% passing | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.4.2 | Shape Control | Tolerance allowed from approved grading curve (%) | Sieve Size % Tolerance 37.5 – 9.5 28-48% 19.0 – 4.75 14-34% 9.5 – 2.36 7-27% 4.75 – 1.18 6-22% 2.36 – 0.6 2-20% 1.18 – 0.3 5-19% 0.6 – 0.15 2-14% | PS 20.9 TCC-IDC IT-4..8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.4.3 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | ≥ 40 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.4.4 | Cone Penetrometer Limit | NZS4407:2015, Test 3.2 Cone Penetration | Cone Penetrometer ≤ 30 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.4.5 | Plasticity Index | NZS4407:2015, Test 3.4 Plasticity Index | Plasticity Index ≤ 8 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.4.6 | Clay Index NZS 4407 Test 3.5 | Clay Index NZS 4407 Test 3.5 | ≤ 5 | PS 20.9 TCC-IDC IT-4.8 table 4.7 | IANZ Accredited Report | Number of Tests Required Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
SECTION 4 - CONSTRUCTION - PREP FOOTPATH
4.1 | SUBGRADE
4.1.1 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa CBR: <3 Single Test Min SU: >50kPa | 232735.02-WSP-DR-UDL 0405 PS:27.4.2 | Shear Vane Report | 1 test per 100M2 | H | SE
4.1.2 | Cut Subgrade Testing - Granular Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 2 blows per 100mm penetration or <3 CBR | 232735.02-WSP-DR-UDL 0405 PS:27.4.2 | Scala Report | 4 test per 400M2 | H | SE |  |  |  | 2 blows / 100mm is fine as long as the CBR value is met.
4.1.3 | Proof Roll Subgrade | Visual Inspection of Proof Roll | Visual Inspection | Appendix XVIII | Visual Site Record | Across Finished Area | H | SE
4.2 | SUBBASE (only if CBR is <3)
4.2.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface 225mm Below From Finish Height | +0mm/ -30mm | TNZ B/02: 2005 5.1 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | H | SE
4.2.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | H | SE
4.2.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Appendix XVIII | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | H | SE
4.2.4 | Hold point | Subbase signoff | Conqa signoff |  | Conqa signoff | Each area | HP | ENG
4.3 | BASECOURSE
4.3.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface 125mm Below From Finish Height | +15mm/ -5 | TNZ B/02: 2005 5.1 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.3.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
4.3.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Appendix XVIII | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
4.3.4 | Hold point | Basecourse signoff | Conqa signoff |  | Conqa signoff | Each area | HP | ENG
4.4 | FORMWORK
4.4.1 | Surveyor check | Equivalent to check the position of the formwork | +100mm/ -20mm of design | TNZ B/02: 2005 5.1 PS:27.4.5 viii | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | HP | ENG
4.4.2 | Surveyor check | Equivalent to check finished height of framework | +\- 10mm of design | NZS 3109:1997 PS:27.4.5 viii | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | H | SE
4.5 | REINFORCING MESH
4.5.1 | Reinforcing Mesh Check | Ensure the right mesh | 665 Reinforcing mesh | Project Specifications 27.4.2 | Dockets | Measurements | C | SE
4.5.2 | Reinforcing Mesh Check | Ensure that overlap and clearince from edges | 50mm top cover, 300mm overlap | NZS 3109:1997 5.3.2 | photos | Measurements | H | SE
4.6 | CONCRETE
4.6.1 | Concrete | 20.0 MPA concrete. 4kg/m3 black oxide (2.5%) | 28 days concrete strength test of 20MPA | 232735.02-WSP-DR-UDL 0405 PS:27.4.5 | Concrete Delivery dockets | During construction | H | SE
4.6.2 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | 232735.02-WSP-DR-UDL 0405 | Post Pour Checksheet | After pour | H | SE |  |  | This superseeds 27.4.5 (d) in the project specification
4.6.3 | Final Finish | Finish to be either: - Brushed finish | U5 Finish | 232735.02-WSP-DR-UDL 0405 PS:27.4.5 | Post Pour Checksheet | After pour | H | SE
SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | Final Inspection | Final inspection of all concrete work. | All works meet project specifications and standards. | NZTA P39: 2013 | Final inspection report | 100% of works | HP | ENG
5.2 | As-Builts | Final inspection of all concrete work. Red Pen Mark up | All works meet project specifications and standards. | PS 16.7.6 | Red Pen Markup | All completed works | D | SV