## Hinge Extender
|  |  |  | Construction Process: | Start RP |  | INSPECTION AND TEST PLAN - VERSION CONTROL |  |  | 0 | 1 | 2 | 3
[5 empty] | Finish RP |  | Prepared by Project Engineer: |  | PE name | dd/mm/yy
|  |  |  | Project Name: Tirau to Waiouru Rehabilitation Acceleration Programe (TWRAP) Works |  |  | Reviewed by Construction Manager: |  | PM name | dd/mm/yy
[7 empty] | Reviewed by Surf./ Pavmt Manager: |  | Surfacing or Pavement Manager | dd/mm/yy
Client's Rep. : Engineers Rep Name |  | Contractor's Rep. : Contractor's Rep Name |  | Specifications: NZTA M04 Description: Batter Hinge Extender |  |  | Approved Quality Manager.: |  | Hansel Feliciano | 2025-01-17
[7 empty] | Approved Pavements SME.: |  | Responsible Group SME | dd/mm/yy
[7 empty] | Issued by: Project Manager: |  | Chris Dunphy | 2025-01-17
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents (QCP - Quality Control Portal | Responsibility | Project Specific Notes / Instructions | Checked by R = Responsible, I, Informed, A = Approve
|  | Detail of Activity / Test | Action (Hold, Monitor, Witness) | Minimum Test Frequency | Inspection / Test method |  |  |  |  | QA / Site Engineer | Eng. Rep / NZTA | Contractor | Date
1.0. Aggregate Acceptance Testing
1.01 | NZTA M04 | Crushing Resistance | H | 1 Test per material per source | NZS4407:2.4.7 | > 130KN | IANZ report | Contractor |  | A | I | R | dd/mm/yy
1.02 |  | Particle size distribution | H | 1 Test per material per source | NZS4407:2.4.7 | As per NZTA M04 Specfication | IANZ report | Contractor |  | A | I | R | dd/mm/yy
2.0 Construction
2.01 | Mark out earthwork extents | Set out and approve extent of earthworks | M | Prior to earthworks | Visual / Photo | QA/Site Engineers Approval | Checksheet | Contractor |  | A | I | R | dd/mm/yy
2.02 | Earthworks | Excavate to a depth required in the design drawing | M | For each site where hinge extender is required | Visual / Photo | QA/Site Engineers Approval | Photo | Contractor |  | A | I | R | dd/mm/yy
2.03 | Post Installation | EZY-Guard LDS Z-Post 2000mm long at 1.0m C/C spacing or NU-Guard High Tensile Posts 1900mm at 1.0m C/C spacing | M | For each site where hinge extender is required | Visual / Photo | As Per Design Drawing | Photo | Contractor |  | A | I | R | dd/mm/yy
2.04 | Timber Board Installation | Install 2 to 3 No. 250mm X 50mm H5 Timber Boards fixed with galvanised M12 bolt and square washers | H | For each site where shoulder support is required | Visual / Photo | As Per Design Drawing | Photo | Contractor | To Ensure a minimum of 150mm of the bottom timber board buried in the embankment | A | I | R | dd/mm/yy
2.05 | AP40 Placement | Backfill and compact using M4 AP40 | H | Test Every 10m | Clegg | Clegg Results >30 | Checksheet/Photo | Contractor |  | A | I | R | dd/mm/yy
Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance. | [6 empty] | H | Hold Point | Work Shall not proceed past the HP until released by the Eng. Rep.
Contractor's Rep Name:_____________________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | W | Witness Point | An Inspection which must be witnessed by the Eng. Rep.
Engineer's Rep. Name:____________________________________ |  |  | Signature:____________________________________ |  |  | Date: _____________________________ | M | Monitor Point | Intermittent monitoring of any stage of the work in progress by the Eng. Rep.